## Read Me
Column Heading | Description of the data
Project Name | If the project is in the CAISO queue, the project name should reflect similar to the posted Queue Report, but may not match exactly.
Queue Number: | If the queue number is an CAISO project it will be: ##, or, if two queues have combined then the queue number will reflect ##,##. A ####CONV is a two-to-three party contract conversion or is a converstion project repowering with new generation. A ####PREC, that is an existing two-party generating facility that has yet to complete a contract conversion.
If the queue number includes "W", "WDT", "WD", "GFID", "RD" or "Rule 21" then the project is connecting on the Participating TO's distribution system.
Projects that are dynamic or pseudo-ties, are projects in a balancing authority area other than the CAISO but are treated as Participating Generators under the CAISO Tariff.
Res_ID | The resource ID for the project or the portion of the project that is interconnecting.
Hybrid | If the resource ID is hybrid, then Y = Yes and N = No
Co-located | If the resource ID is co-located, then Y = Yes and N = No
Status | Active - The resource ID has begun the new resource implementation process.
Sync OK - The resource ID has synchronized to the grid.
COMX - The resource ID has achieved commercial operation for markets which means it is no longer testing and is bidding into the market .
COD - The resource ID has achieved its commercial operation date.
Nameplate | The MW quantity of the resource ID.
Generation by fuel type | The subsequent columns list the various fuel types and the MW associated with each fuel type.
Active_Date | The date that the resource ID began the new resource implementation process.
Sync_Date | The date that the resource ID synchronized to the grid.
COMX_Date | The date that the resource ID achieved commercial operation for markets.
MF_COD | The date that the resource ID achieves commercial operation.
IC_COD | The date that the Interconnection Customer believes this resource ID will achieve its commercial operation date.

## May 19, 2024
PROJECT_NAME | QUEUE_NUMBER | RES_ID | HYBRID_YN | CO_LOCATED_YN | STATUS | NAMEPLATE_MW | SOLAR_MWS | WIND_MWS | BATT_MWS | GEO_MWS | HYDRO_MWS | NG_MWS | OTHER_MWS | ACTIVE_DATE | SYNC_DATE | COMX_DATE | MF_COD | IC_COD
Alamitos Energy Storage 2 | 0002CONV | ALAMIT_2_AESBT2 | N | N | Active | 82 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 2022-05-09 |  |  |  | 2024-09-11
Tulare Dac Solar | 2614-WD | ALPAUG_1_TUDSR1 | N | N | Active | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-03-07 |  |  |  | 2024-07-15
Bear Canyon Energy Storage | 1097 | BERCYN_2_BCEBT1 | N | N | Sync OK | 13 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 2021-02-27 | 2024-04-26 |  |  | 2024-05-17
Big Rock Solar Farm | 1166 | BGROCK_2_BRFBX2 | N | Y | Active | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 2022-01-14 |  |  |  | 2025-04-30
HAT CREEK BIOENERGY | 3126 RD | BURNEY_6_HCCTG1 | N | N | Active | 2.88 | 0 | 0 | 0 | 0 | 0 | 0 | 2.88 | 2023-11-04 |  |  |  | 2024-08-28
Caballero Storage | 1470 | CABLRO_2_CBSBT1 | N | N | Active | 99.7 | 0 | 0 | 106.2 | 0 | 0 | 0 | 0 | 2023-07-24 |  |  |  | 2024-11-09
RuAnn Dairy Digester BioMAT | 1864-WD | CAMDEN_6_RDDBM1 | N | N | COD | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 2019-12-11 | 2023-12-13 |  | 2024-04-24 | 2024-04-24
Buckman Springs BESS | WDT179 | CAMERN_6_BSPBT1 | N | N | Active | 0.46 | 0 | 0 | 0.46 | 0 | 0 | 0 | 0 | 2023-03-03 |  |  |  | 2024-11-24
Buckman Springs PV | W178 | CAMERN_6_BSPSR1 | N | N | COD | 0.845 | 0.845 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-11-17 | 2023-04-20 |  | 2024-01-29 | 2024-01-29
Casa Diablo 4 | WDT315 | CASADB_1_CD4GT1 | N | N | COD | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 2021-07-06 | 2022-05-18 | 2022-07-14 | 2024-04-16 | 2024-04-16
Casa Diablo 4 | WDT315 | CASADB_1_CD4GT1 | N | N | COD | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 2021-07-06 | 2022-05-18 | 2022-12-28 | 2024-04-16 | 2024-04-16
Chalan Solar Storage | 1495 | CHALAN_2_CHABT1 | N | Y | Active | 25 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 2023-08-08 |  |  |  | 2025-02-01
Chalan Solar | 1495 | CHALAN_2_CHASR1 | N | Y | Active | 64.9 | 64.9 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-28 |  |  |  | 2025-02-01
Avenue 26 Solar Phase I | 2915-WD | CHWCHL_1_AVSSR1 | N | N | Active | 2.56 | 2.56 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-04 |  |  |  | 2024-06-27
Avenue 26 Solar Phase II | 3037-WD | CHWCHL_1_AVSSR2 | N | N | Active | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-04 |  |  |  | 2024-06-27
SEPV Barbara 3 | 1642-WD,2041-WD | CUYAMA_6_SB3SB1 | Y | N | COD | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 2022-08-15 | 2023-11-30 |  | 2024-01-02 | 2024-01-02
Dos Palos Clean Power | 2649-WD | DOSPAL_1_DPSSR1 | N | N | Active | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-28 |  |  |  | 2024-07-31
Desert Sunlight PV II Storage 2 | 146,147 | DSRTSN_2_DS2BX2 | N | Y | COD | 230 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 2023-01-04 | 2024-01-31 |  | 2024-04-09 | 2024-04-09
Beaumont Energy Storage I | WDT1648 | DYLAN_2_BMTBT1 | N | N | Sync OK | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 2023-03-10 | 2024-04-19 |  |  | 2024-07-02
San Jacinto Grid | SCE WDT1558 | ECASCO_2_SJGBT1 | N | N | Active | 65 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 2022-06-13 |  |  |  | 2024-06-27
East Cleveland Road Solar | 2799-WD | ELNIDO_1_ECRSR1 | N | N | Active | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-04 |  |  |  | 2024-06-15
Carris Storage 1 | SCE WDT1646 | ESNHWR_2_CS1BT3 | N | N | Active | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2022-08-16 |  |  |  | 2024-06-27
Hecate Energy Desert Storage 1 | SCE WDT1551 | ESNHWR_2_HDSBT2 | N | N | Active | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2022-10-07 |  |  |  | 2024-06-27
Separator | 1641 | ETIWND_2_SEPBT1 | N | N | Sync OK | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 2023-02-03 | 2023-10-12 |  |  | 2024-04-29
Inland Empire Energy Storage | 1669S | ETIWND_6_INEBT1 | N | N | Active | 70 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-09-10
Quartzite Solar 8 BESS | 1198,1526 | FILIPPI_2_QZSBTX | N | Y | Active | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 2022-01-13 |  |  |  | 2024-12-01
Quartzite Solar 8 | 1198,1526 | FILIPPI_2_QZSSRX | N | Y | Active | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-16 |  |  |  | 2024-12-01
Goleta Energy Storage and Goleta Energy Storage 2 | WDAT1454 and WDT1454EXP | GOLETA_2_GE2BT3 | N | N | COD | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 2022-06-02 | 2023-11-28 |  | 2024-01-06 | 2024-01-06
PAINTER BESS | WDT1539 | GOLETA_2_PAIBT2 | N | N | Active | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2024-05-04 |  |  |  | 2024-09-30
EnerSmart El Cajon | W159 | GRNITE_6_ESCBT1 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-06-29 |  |  |  | 2024-12-15
Hanford Peaker Plant | 0071CONV | GWFPWR_1_HPPBT1 | N | Y | Active | 99.4 | 0 | 0 | 99.4 | 0 | 0 | 0 | 0 | 2023-12-11 |  |  |  | 2024-09-01
Lead | 1713 | GWFPWR_1_LEDBT1 | N | N | Active | 32 | 0 | 0 | 32.7 | 0 | 0 | 0 | 0 | 2023-10-02 |  |  |  | 2024-09-01
Baldy Mesa Hybrid | 1413,1519 | HAMLIN_1_BLDSB1 | Y | N | COD | 150 | 150 | 0 | 75 | 0 | 0 | 0 | 0 | 2023-03-07 | 2023-08-04 |  | 2024-04-30 | 2024-04-30
Baldy Mesa SP | 1413,1519 | HAMLIN_1_BMSBT2 | Y | N | Sync OK | 50 | 50 | 0 | 25 | 0 | 0 | 0 | 0 | 2023-03-09 | 2024-02-12 |  |  | 2024-05-01
Avenal Cutoff Dac Spring Solar | 2796-WD | HENRTA_6_ACDSR3 | N | N | Active | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-03-07 |  |  |  | 2024-05-01
Electrolyte | 0062CONV | HENRTA_6_ELCBX2 | N | Y | Active | 99.4 | 0 | 0 | 99.4 | 0 | 0 | 0 | 0 | 2023-10-23 |  |  |  | 2024-09-01
Wilmington 2 Carson | WDT1818 | HINSON_2_W2CSR2 | N | N | Active | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-06-23 |  |  |  | 2024-08-26
Wilmington 1 | WDT1815 | HINSON_2_WI1SR1 | N | N | Active | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-06-23 |  |  |  | 2025-03-25
Hummingbird Energy Storage | 1454 | HUMBRD_1_HMBBT1 | N | N | Active | 75 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 2022-11-28 |  |  |  | 2024-12-01
Inyokern Solar 1203 | WDT1203 | INYOKN_1_IKSSR1 | N | N | Active | 19.9 | 19.9 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-10-23 |  |  |  | 2024-08-13
Inyokern Solar 1281 | WDT1281 | INYOKN_1_IKSSR2 | N | N | Active | 11.9 | 11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-10-23 |  |  |  | 2024-11-01
Titanium 1 BESS | WDT1428 | JOHANN_2_T1BBT1 | N | N | Active | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 2018-04-26 |  |  |  | 2024-06-01
Kettle Solar One | 1532 | JVREPK_1_KSOSB1 | Y | N | Active | 90 | 90 | 0 | 70 | 0 | 0 | 0 | 0 | 2021-04-21 |  |  |  | 2026-10-31
Fresno Community Solar | 2392-WD | KERNEY_6_FCSSR1 | N | N | Active | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-02-03 |  |  |  | 2024-02-25
El Segundo Hawthorne | WDT1814 | LAFRES_2_ESHSR1 | N | N | Active | 0.64 | 0.64 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-06-23 |  |  |  | 2025-06-19
Cald BESS Phase 1 | WDT1641,WDT1736 | LAGBEL_2_CBPBT1 | N | N | Sync OK | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 2023-02-24 | 2024-04-25 |  |  | 2024-05-18
AFTW Storage | WDAT3197 | LAKEVW_6_AFTBT1 | N | N | Active | 1.14 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 2023-09-27 |  |  |  | 2024-09-30
Los Esteros Critical Energy Facility Expansion BESS | 378 | LECEF_1_BATTRY | N | N | Active | 3.3 | 0 | 0 | 3.3 | 0 | 0 | 0 | 0 | 2018-04-26 |  |  |  | 2024-09-01
LeConte Energy Storage | 1175 | LECONT_2_LESBT1 | N | N | COMX | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 2021-05-23 | 2022-05-12 | 2022-07-15 |  | 2024-06-01
LeConte Energy Storage | 1175 | LECONT_2_LESBT1 | N | N | COMX | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 2021-05-23 | 2022-05-12 | 2022-09-01 |  | 2024-06-01
Dominguez Carson | WDT1817 | LGHTHP_2_DOCSR1 | N | N | Active | 0.96 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-06-23 |  |  |  | 2024-08-26
Enchanted Rock Lodi | LODI No. 7851 | LODI25_6_ERKNG1 | N | N | Sync OK | 47.97 | 0 | 0 | 0 | 0 | 0 | 47.97 | 0 | 2023-01-25 | 2024-04-01 |  |  | 2024-05-24
West Tambo Clean Power II | 2864-WD | LVNGST_1_WTASR1 | N | N | Active | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-04-26 |  |  |  | 2024-06-01
Acid | 0063CONV | MALAGA_1_ACDBX2 | N | Y | Active | 97 | 0 | 0 | 97 | 0 | 0 | 0 | 0 | 2023-10-19 |  |  |  | 2024-09-01
Marvel 2 | 1295 | MARVEL_2_MARBT3 | N | N | COD | 75 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 2022-05-25 | 2023-06-08 | 2023-07-24 | 2024-04-25 | 2024-04-25
Marvel | 1295 | MARVEL_2_MARBX2 | N | N | COD | 325 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 2022-02-17 | 2023-06-08 | 2023-07-18 | 2024-04-25 | 2024-04-25
McFarland Solar B Hybrid | 1171 | MCFLND_5_MFSSB1 | Y | N | Active | 300 | 300 | 0 | 150 | 0 | 0 | 0 | 0 | 2024-03-28 |  |  |  | 2024-09-30
Cadillac 1 BESS | WDT1504 | MESAS_2_CADBT1 | N | N | Active | 3.5 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 2019-04-19 |  |  |  | 2024-08-01
Workman Mill Whittier | WDT1819 | MESAS_2_WMWSR1 | N | N | Active | 1.92 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-06-23 |  |  |  | 2024-08-26
Yorktown 1 BESS | WDT1514 | MESAS_2_YORBT1 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2019-10-11 |  |  |  | 2024-08-01
Mesquite Solar 4 BESS | 1291 | MSOLAR_2_MS4BT1 | N | Y | COD | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2022-10-26 | 2023-10-31 |  | 2024-01-26 | 2024-01-26
Mesquite Solar 4 | 1291 | MSOLAR_2_MS4SR4 | N | Y | COD | 52.5 | 52.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-10-25 | 2023-09-05 |  | 2024-01-18 | 2024-01-18
EnerSmart Murray 1 | W187 | MURRAY_6_ESMBT1 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-10-11 |  |  |  | 2025-11-20
EnerSmart Murray 2 | W183 | MURRAY_6_ESMBT2 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-10-11 |  |  |  | 2025-11-20
EnerSmart Murray 3 | W186 | MURRAY_6_ESMBT3 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-10-11 |  |  |  | 2025-11-20
EnerSmart Murray 4 | W184 | MURRAY_6_ESMBT4 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-10-11 |  |  |  | 2025-11-20
EnerSmart Murray 5 | W227 | MURRAY_6_ESMBT5 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-10-11 |  |  |  | 2025-11-20
EnerSmart Murray 6 | W229 | MURRAY_6_ESMBT6 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-10-11 |  |  |  | 2025-11-20
EnerSmart Murray 7 | W166 | MURRAY_6_ESMBT7 | N | N | Active | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-10-11 |  |  |  | 2025-11-20
Northern Orchard Solar | 1259,946 | NORORC_2_NOSBX2 | Y | N | Active | 150 | 150 | 0 | 92 | 0 | 0 | 0 | 0 | 2023-10-10 |  |  |  | 2024-12-01
Arrache 4006 I | 5517 | OASIS_6_AR4SR1 | N | N | COD | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-02-17 | 2023-06-01 |  | 2024-05-20 | 2024-05-20
Arrache 8083 III | 5447 | OASIS_6_AR8SR3 | N | N | Sync OK | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-06 | 2023-04-20 |  |  | 2024-04-29
Ma 4035 | 5330 | OASIS_6_MA4SR1 | N | N | COD | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-04-21 | 2023-08-02 |  | 2024-05-20 | 2024-05-20
Lara Solar 2 Hybrid | 2142-WD | ORTGA_6_LSLSB1 | Y | N | Active | 0.925 | 0.925 | 0 | 0.925 | 0 | 0 | 0 | 0 | 2023-12-28 |  |  |  | 2024-06-01
Chula Vista Energy Center 2 BESS | 1045 | OTAY_6_CVEBT3 | N | Y | Active | 49.7 | 0 | 0 | 49.7 | 0 | 0 | 0 | 0 | 2022-12-09 |  |  |  | 2025-09-15
EnerSmart Chula Vista 1 | W190 | OTAY_6_ECVBT1 | N | N | Sync OK | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-06-29 | 2024-01-12 |  |  | 2024-02-09
EnerSmart Chula Vista 2 | W191 | OTAY_6_ECVBT2 | N | N | Sync OK | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2021-06-29 | 2024-01-12 |  |  | 2024-02-09
Paulsell Solar Energy Center BESS | 1350 | PALSEL_6_PLSBT1 | N | Y | Sync OK | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 2023-08-23 | 2024-04-10 |  |  | 2024-05-04
Paulsell Solar Energy Center PV | 1350 | PALSEL_6_PLSSR1 | N | Y | Sync OK | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-08-23 | 2024-04-10 |  |  | 2024-05-04
Mesa Wind Project | WDT400 | PANERO_2_MWPWD1 | N | N | Sync OK | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 2021-04-13 | 2024-04-04 |  |  | 2024-04-30
Peregrine Storage | 1670 | PERGRN_2_PRSBT1 | N | N | Active | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 2022-06-12 |  |  |  | 2024-12-01
CES Electron Farm | 2226-WD | PNOCHE_2_CEFSR1 | N | N | Active | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-08-29 |  |  |  | 2025-02-01
Antelope Solar 2 Raceway BESS | 1208 | POLRIS_2_ASRBT1 | N | Y | COD | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 2023-02-28 | 2023-10-31 |  | 2024-03-27 | 2024-03-27
Antelope Solar 2 Raceway | 1208 | POLRIS_2_ASRSR1 | N | Y | COD | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-10-19 | 2023-10-06 |  | 2024-03-27 | 2024-03-27
Pome BESS | 1669 | POMRDO_6_POMBT1 | N | N | Active | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 2023-09-27 |  |  |  | 2024-09-21
Silver State South Solar Project Storage | 467,502 | PRIMM_2_SSSBT1 | N | Y | Active | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 2023-02-17 |  |  |  | 2024-10-30
Proxima Solar | 1244 | PROXSR_2_PROSR1 | N | Y | Sync OK | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-07-28 | 2024-03-05 |  |  | 2024-03-01
Proxima Solar BESS 1A | 1244 | PROXSR_2_PS1BT1 | N | Y | COD | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 2022-08-03 | 2024-01-11 |  | 2024-04-08 | 2024-04-08
Proxima Solar BESS 1B | 1244 | PROXSR_2_PS1BT2 | N | Y | COD | 32 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 2022-08-30 | 2024-01-11 |  | 2024-05-07 | 2024-05-07
Proxima Solar 1B | 1244 | PROXSR_2_PS1SR2 | N | Y | COD | 69.74 | 69.74 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-08-30 | 2024-03-05 |  | 2024-05-07 | 2024-05-07
Proxima Solar BESS 2 | 1244 | PROXSR_2_PS2BT3 | N | Y | COD | 90 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 2022-08-30 | 2024-01-11 |  | 2024-04-11 | 2024-04-11
Willy 9 Antelope Valley Complex | 1215,1319 | RATSKE_2_WAVBT1 | N | N | Active | 126 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 2023-06-04 |  |  |  | 2024-09-01
Watts II | 5421 | RDWAY_1_WA2SR3 | N | N | COD | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-09-28 |  | 2024-01-15 | 2024-01-15
Watts I | 5350 | RDWAY_1_WAISR2 | N | N | Sync OK | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-09-28 |  |  | 2024-05-28
Visalia CSG | 1732-WD | RECTOR_2_VISSR1 | N | N | COD | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-03-07 | 2023-11-22 |  | 2024-04-03 | 2024-04-03
Rexford Solar Farm BESS | 1516 | REXFRD_2_RSFBX2 | N | Y | Active | 240 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 2023-05-22 |  |  |  | 2024-12-20
Rexford Solar Farm | 1516 | REXFRD_2_RSFSX2 | N | Y | Active | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-07-14 |  |  |  | 2024-12-20
Hazel B | WDT1295 | RNDSBG_1_HZBSR2 | N | N | Active | 2.99 | 2.99 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-04-26 |  |  |  | 2024-12-20
Menifee Power Bank | 1645 | ROMOLA_5_MPBBT1 | N | N | COMX | 230 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 2023-05-18 | 2024-03-18 | 2024-05-17 |  | 2024-05-17
Menifee Power Bank 2 | 1645 | ROMOLA_5_MPBBT2 | N | N | Sync OK | 230 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 2023-05-24 | 2024-03-21 |  |  | 2024-05-17
Menifee Power Bank 3 | 1645 | ROMOLA_5_MPBBT3 | N | N | Sync OK | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 2023-05-24 | 2024-04-18 |  |  | 2024-07-03
Menifee Power Bank 4 | 1645 | ROMOLA_5_MPBBT4 | N | N | Active | 110 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 2023-10-09 |  |  |  | 2024-08-01
Rosamond West Solar Central BESS A1 | 506 | RTEDDY_2_RWSBT1 | N | Y | COD | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 2023-02-14 | 2024-01-09 |  | 2024-05-02 | 2024-05-02
Rosamond West Solar Central BESS A2 | 506 | RTEDDY_2_RWSBT2 | N | Y | COD | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 2023-02-14 | 2024-01-09 |  | 2024-05-02 | 2024-05-02
Rosamond West Solar Central BESS A3 | 506 | RTEDDY_2_RWSBT3 | N | Y | COD | 45 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 2023-02-14 | 2024-01-09 |  | 2024-05-09 | 2024-05-09
Rosamond West Solar Central BESS B | 506 | RTEDDY_2_RWSBT4 | N | Y | COD | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 2023-02-14 | 2024-01-09 |  | 2024-05-02 | 2024-05-02
Rosamond West Solar Central BESS C | 506 | RTEDDY_2_RWSBT5 | N | Y | COD | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 2023-02-14 | 2024-01-09 |  | 2024-05-03 | 2024-05-03
Solano Renewables 1 | 108,1463,PREC0527 | RUSSELL_2_SOLANO1 | N | N | COD | 230 | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 2023-03-15 | 2023-10-05 |  | 2024-02-06 | 2024-02-06
Sandrini Sol 1 | 1397 | SANDRN_2_SS1SR1 | N | N | Active | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-06-17 |  |  |  | 2024-10-22
Sandrini Sol 2 | 1398 | SANDRN_2_SS2SR2 | N | N | Active | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-06-17 |  |  |  | 2024-07-20
Santa Paula Energy Storage | WDT1532 | SAUGUS_2_SPESBT1 | N | N | COD | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 2022-03-10 | 2023-12-04 |  | 2024-03-16 | 2024-03-16
Scarlet Solar 2 BESS | 1135 | SCARLT_2_SS2BT1 | N | Y | Active | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 2022-12-21 |  |  |  | 2024-06-20
Scarlet Solar 2 PV | 1135 | SCARLT_2_SS2SR1 | N | Y | Active | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-12-21 |  |  |  | 2024-06-20
Scarlet Solar CA 1A | 1135 | SCARLT_2_SSABT1 | N | Y | COD | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2021-10-12 | 2024-01-05 |  | 2024-05-03 | 2024-05-03
Scarlet Solar CA 1A PV | 1135 | SCARLT_2_SSASR1 | N | Y | COD | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-04-12 | 2023-12-19 |  | 2024-05-03 | 2024-05-03
Scarlet Solar CA 1B | 1135 | SCARLT_2_SSBBT1 | N | Y | COD | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 2021-10-12 | 2024-01-05 |  | 2024-05-03 | 2024-05-03
Scarlet Solar CA 1B PV | 1135 | SCARLT_2_SSBSR1 | N | Y | COD | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-04-12 | 2023-12-20 |  | 2024-05-02 | 2024-05-02
Alta Mesa Wind | WDT1444 | SEAWND_2_AMWWD1 | N | N | Active | 27 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 2021-03-12 |  |  |  | 2024-06-01
Rutan I | 5816 | SHUTLE_6_RUISR1 | N | N | COD | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-10-12 |  | 2024-04-29 | 2024-04-29
Rutan II | 5817 | SHUTLE_6_RUISR2 | N | N | COD | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-10-12 |  | 2024-04-29 | 2024-04-29
Rutan III | 5818 | SHUTLE_6_RUISR3 | N | N | COD | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-09-29 |  | 2024-04-29 | 2024-04-29
North Fork Community Power | 2007-RD | SJOAQN_6_NFCBM1 | N | N | Active | 2.344 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2021-06-08 |  |  |  | 2024-07-16
Tule Hydropower Plant | WDT1794 | SPRGVL_2_TULE | N | N | Active | 6.4 | 0 | 0 | 0 | 0 | 6.4 | 0 | 0 | 2021-12-01 |  |  | 1914-01-01 | 2024-10-15
Apparent First Hybrid | 653F | SPVUSA_1_SPVSB1 | N | N | Active | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-04-26 |  |  |  | 2024-11-30
Tahoe 1 | 1339 | TAHOE_2_THOBT1 | N | Y | Active | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 2023-09-28 |  |  |  | 2024-08-01
Tahoe 2 | 1339 | TAHOE_2_THOBT2 | N | Y | Active | 109 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 2023-09-25 |  |  |  | 2024-08-01
Tahoe 3 | 1339 | TAHOE_2_THOBT3 | N | Y | Active | 110 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 2023-09-25 |  |  |  | 2024-08-01
Tracy Desalination Plant | 2187-RD | TRACY_1_BIOTG1 | N | N | Active | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2022-11-29 |  |  |  | 2024-09-16
Willow Springs Solar 3 | 1076 | TUMBWD_2_WISBT3 | N | N | Sync OK | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 2020-11-11 | 2024-04-02 |  |  | 2024-06-01
Willow Springs Solar 4 | 1217 | TUMBWD_2_WISBT4 | N | N | Sync OK | 75 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 2020-12-27 | 2024-04-02 |  |  | 2024-06-01
Ultrapower Chinese Station BESS | 1116 | ULTPCH_1_UCSBT1 | N | N | Active | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2020-02-12 |  |  |  | 2024-06-30
Ortega Grid | SCE WDT1636 | VALLEY_5_ORTBT1 | N | N | Active | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 2022-07-01 |  |  |  | 2024-06-14
Pechanga CHP | Rule 21 GFID 2738 WDAT 976 | VALLEY_5_PENCT1 | N | N | Active | 4.6 | 0 | 0 | 0 | 0 | 0 | 4.6 | 0 | 2021-12-09 |  |  |  | 2024-08-08
Bottleneck Energy Storage | WDT1639 | VESTAL_2_BTNBT1 | N | N | Sync OK | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 2023-01-26 | 2024-03-13 |  |  | 2024-05-30
Sloth BESS | 421 | VICPAS_2_SLOBT1 | N | Y | COD | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 2023-02-15 | 2023-10-27 |  | 2024-03-26 | 2024-03-26
Sloth | 421 | VICPAS_2_SLOSR1 | N | Y | COD | 49.5 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-01-04 | 2023-10-27 |  | 2024-03-26 | 2024-03-26
Sol Catcher BESS 1 | 1302 | VICPAS_2_SOCBT1 | N | Y | COD | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 2023-02-15 | 2023-10-26 | 2024-02-13 | 2024-03-26 | 2024-03-26
Sol Catcher BESS 2 | 1302 | VICPAS_2_SOCBT2 | N | Y | COD | 71 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 2023-02-15 | 2023-10-26 |  | 2024-03-26 | 2024-03-26
Sol Catcher BESS PV1 | 1302 | VICPAS_2_SOCSR1 | N | Y | COD | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-14 | 2023-10-25 | 2024-03-11 | 2024-03-26 | 2024-03-26
Sol Catcher BESS PV2 | 1302 | VICPAS_2_SOCSR2 | N | Y | COD | 93.5 | 93.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-15 | 2023-10-31 | 2024-04-02 | 2024-04-02 | 2024-04-02
Sol Catcher BESS PV2 | 1302 | VICPAS_2_SOCSR2 | N | Y | COD | 93.5 | 93.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-15 | 2023-10-31 | 2024-04-02 | 2024-04-02 | 2024-04-02
Sol Catcher BESS PV3 | 1302 | VICPAS_2_SOCSR3 | N | Y | COD | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-15 | 2023-10-18 |  | 2024-03-26 | 2024-03-26
Victory Pass Solar BESS | 1200 | VICPAS_2_VPSBT1 | N | Y | COD | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 2023-02-15 | 2023-10-18 |  | 2024-03-27 | 2024-03-27
Victory Pass Solar | 1200 | VICPAS_2_VPSSR1 | N | Y | COD | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-01-04 | 2023-10-31 |  | 2024-03-26 | 2024-03-26
Landpro Madelyn | 5692 | VICTOR_1_LMASR1 | N | N | Sync OK | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-11-08 |  |  | 2024-04-29
Landpro Mitchell | 5694 | VICTOR_1_LMISR2 | N | N | Sync OK | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-10-12 |  |  | 2024-05-28
Landpro Rudy | 5693 | VICTOR_1_LRUSR3 | N | N | Sync OK | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-10-12 |  |  | 2024-04-29
Nunn | 5345 | VICTOR_1_NUNSR4 | N | N | Sync OK | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2023-10-12 |  |  | 2024-04-29
Vikings Co-located BESS |  | VIKING_2_VCBBT1 | N | N | Active | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 2023-12-21 |  |  |  | 2024-07-01
Vikings Co-located PV |  | VIKING_2_VCSSR1 | N | N | Active | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-21 |  |  |  | 2024-06-01
Vikings Solar BESS Hybrid Project | GIA-2021-64 | VIKING_2_VSHSB1 | Y | N | Sync OK | 150 | 132.108 | 0 | 150 | 0 | 0 | 0 | 0 | 2023-06-02 | 2024-01-11 |  |  | 2024-04-08
West Ford Flat Energy Storage | 1367 | WDFRDF_2_WFFBT1 | N | N | Sync OK | 25 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 2023-01-28 | 2024-04-26 |  |  | 2024-05-22
BATERIA DEL SUR 2A | 1531 | WESCAN_2_BDSBT2 | N | N | Active | 119 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 2024-02-01 |  |  |  | 2024-10-15
White Wing Ranch Solar | 1062 | WHITEW_5_WWRSR1 | N | N | Active | 179 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-09-28 |  |  |  | 2024-07-15
Sagebrush Solar 2 ESS 40 | 1325 | WSTWND_2_SBSBT2 | N | Y | Sync OK | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 2023-07-20 | 2024-02-22 |  |  | 2024-06-01
Sagebrush Solar 2 ESS 59 | 1325 | WSTWND_2_SBSBT3 | N | Y | Sync OK | 59 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 2023-07-20 | 2024-02-22 |  |  | 2024-06-01
Yellow Pine 2 A BESS | 1341 | YELPIN_2_YP2BT2 | N | Y | Sync OK | 53 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 2023-04-19 | 2024-03-21 |  |  | 2024-04-01
Yellow Pine 2 B BESS | 1341 | YELPIN_2_YP2BT3 | N | Y | Sync OK | 32 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 2023-08-25 | 2024-03-21 |  |  | 2024-04-01
Yellow Pine 2 A PV | 1341 | YELPIN_2_YP2SR2 | N | Y | Sync OK | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-08-25 | 2024-03-21 |  |  | 2024-04-01
Yellow Pine 2 B PV | 1341 | YELPIN_2_YP2SR3 | N | Y | Sync OK | 65 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-08-25 | 2024-03-21 |  |  | 2024-04-01
Harq |  |  | N | N | Active | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-11 |  |  |  | 2025-01-31
South Bay Pseudo Gen | 275 |  | N | N | Active | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-07 |  |  |  | 2024-09-15
Menifee Power Bank 5 | 1645 |  | N | N | Active | 55 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 2024-01-08 |  |  |  | 2025-10-01
ATLAS SOLAR | 1402 |  | N | N | Active | 3200 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 2022-06-30 |  |  |  | 2027-02-28
Deer Creek Solar 1 PV | WDT1384 |  | N | Y | Active | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-09-14 |  |  |  | 2024-11-01
Azalea | 1493 |  | N | N | Active | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-04-30 |  |  |  | 2025-03-09
Pelicans Jaw Hybrid Solar | 1593 |  | N | N | Active | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 2022-09-26 |  |  |  | 2025-12-01
Bellefield Solar Farm | 1510 |  | N | Y | Active | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-07-14 |  |  |  | 2025-06-01
Pomegranate | 1243 |  | N | N | Active | 249.7 | 249.7 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-11-25 |  |  |  | 2024-03-08
Starlight Solar | 1432 |  | N | Y | Active | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-07-30 |  |  |  | 2025-04-30
Aratina Solar Center 1 | 1204 |  | N | Y | Active | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-06-12 |  |  |  | 2024-12-30
Chiquito Grid | SCE WDT1635 |  | N | N | Active | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 2022-06-13 |  |  |  | 2026-02-28
Humidor Storage 1 | 1629 |  | N | N | Active | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 2022-08-17 |  |  |  | 2026-03-31
Mulqueeney Ranch Wind | 1277,1459 |  | N | N | Active | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 2019-08-30 |  |  |  | 2024-10-01
Sand Hill C | 1363 |  | N | N | Active | 80.8 | 0 | 80.8 | 0 | 0 | 0 | 0 | 0 | 2019-10-31 |  |  |  | 2024-12-17
Angela | 1443 |  | N | N | Active | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-29 |  |  |  | 2024-12-30
Camino Solar | 1419 |  | N | Y | Active | 54.28 | 54.28 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-13 |  |  |  | 2024-12-31
North Johnson Energy Center | 1047 |  | N | N | Active | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 2021-07-12 |  |  |  | 2025-06-01
Las Camas 1 | 1382 |  | N | N | Active | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-13 |  |  |  | 2024-11-30
Sonoma School District Microgrid | 2606-WD |  | N | N | Active | 0.12 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 2021-02-05 |  |  |  | 2024-08-14
Lake Alpaugh Battery Storage | 1143 |  | N | N | Active | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2021-03-24 |  |  |  | 2024-10-15
Ares Nevada | 1064 |  | N | N | Active | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 2020-01-29 |  |  |  | 2027-01-08
Eagle Creek 2 | 1620-WD |  | Y | N | Active | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 2020-05-28 |  |  |  | 2024-06-01
Pastoria Solar | 1335 |  | N | Y | Active | 105.2 | 105.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-11-13 |  |  |  | 2025-06-15
Daggett Solar 1 | 1312 |  | N | N | Active | 144 | 148.96 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-01 |  |  |  | 2024-12-15
Rosamond South East | 1211 |  | N | Y | Active | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-13 |  |  |  | 2024-11-01
Lithium | 0124CONV |  | N | Y | Active | 52 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 2023-11-02 |  |  |  | 2024-12-31
Camino Solar BESS | 1419 |  | N | Y | Active | 10.28 | 0 | 0 | 10.28 | 0 | 0 | 0 | 0 | 2023-11-03 |  |  |  | 2027-12-31
Aratina Solar Center 1 b PV | 1204 |  | N | Y | Active | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-07-13 |  |  |  | 2025-05-01
Aratina Solar Center 1 b BESS | 1204 |  | N | Y | Active | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 2023-07-13 |  |  |  | 2025-05-01
Intermountain; Unit 4 AHNM Share; IPP Renewed |  |  | N | N | Active | 55.55 | 0 | 0 | 0 | 0 | 0 | 55.55 | 0 | 2024-05-08 |  |  |  | 2025-03-01
Sun Pond Solar 2 |  |  | N | Y | Active | 42.5 | 42.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-07 |  |  |  | 2026-02-01
Seal Beach PV | WDAT1644 |  | N | Y | Active | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-12 |  |  |  | 2024-08-23
Cyclone Solar | 1327 |  | N | Y | Active | 30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-13 |  |  |  | 2025-03-31
Sun Pond Solar 1 |  |  | N | Y | Active | 42.5 | 42.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-07 |  |  |  | 2026-02-01
Noosa Energy Storage | 1557 |  | N | N | Active | 99 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 2024-05-09 |  |  |  | 2025-09-30
Intermountain; Unit 3 RVS Share; IPP Renewed |  |  | N | N | Active | 31.99 | 0 | 0 | 0 | 0 | 0 | 31.99 | 0 | 2024-05-08 |  |  |  | 2025-03-01
Intermountain; Unit 4 RVS Share; IPP Renewed |  |  | N | N | Active | 31.99 | 0 | 0 | 0 | 0 | 0 | 31.99 | 0 | 2024-05-08 |  |  |  | 2025-03-01
Sun Pond Storage 1 |  |  | N | Y | Active | 42.5 | 0 | 0 | 42.5 | 0 | 0 | 0 | 0 | 2024-03-07 |  |  |  | 2026-02-01
Sun Pond Storage 2 |  |  | N | Y | Active | 42.5 | 0 | 0 | 42.5 | 0 | 0 | 0 | 0 | 2024-03-07 |  |  |  | 2026-02-01
Cyclone Solar Rosamond South I BESS 1 | 1327 |  | N | Y | Active | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 2024-03-15 |  |  |  | 2025-03-31
Cyclone Solar Rosamond South I BESS 3 | 1327 |  | N | Y | Active | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2024-03-15 |  |  |  | 2025-03-31
Sequoia 1 Farmersville 2 | GFID#5863 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-11-22 |  |  |  | 2024-10-15
BTF Storage DIDF | 3318-WD |  | N | N | Active | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2024-01-03 |  |  |  | 2024-11-15
Janus | 1455 |  | N | Y | Active | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 2023-08-13 |  |  |  | 2024-02-01
Santee BESS | W131 |  | N | N | Active | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2024-01-18 |  |  |  | 2024-09-15
Bellefield Solar Farm BESS | 1510 |  | N | Y | Active | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 2024-01-23 |  |  |  | 2025-06-01
Dark Sky Energy Center | W260 |  | N | N | Active | 7.33 | 0 | 0 | 7.33 | 0 | 0 | 0 | 0 | 2024-01-24 |  |  |  | 2024-10-10
Sequoia 3 Porterville 7 | GFID#5861 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-10-15
Sequoia 1 Tulare 1 | GFID#5769 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-10-15
Sequoia 1 Tulare 2 | GFID#5770 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-10-15
Avocet Storage | 1608 |  | N | N | Active | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 2024-01-29 |  |  |  | 2024-09-01
Lithium Unit 1 | PREC0049 |  | N | Y | Active | 60.5 | 0 | 0 | 0 | 0 | 0 | 55.3 | 0 | 2023-09-19 |  |  |  | 2024-12-31
Intermountain; Unit 3 AHNM Share; IPP Renewed |  |  | N | N | Active | 55.55 | 0 | 0 | 0 | 0 | 0 | 55.55 | 0 | 2024-05-08 |  |  |  | 2025-03-01
Sequoia 3 Porterville 6 | GFID#5860 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-10-15
Fish Lake Geothermal |  |  | N | N | Active | 19.8 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 2023-06-01 |  |  |  | 2024-09-30
Seal Beach BESS | WDAT1644 |  | N | Y | Active | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2024-03-12 |  |  |  | 2024-08-23
Rosamond South East BESS 2 | 1211 |  | N | Y | Active | 92 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 2024-03-15 |  |  |  | 2025-03-31
Ventasso Energy Storage | 1662 |  | N | N | Active | 50 | 0 | 0 | 50.774 | 0 | 0 | 0 | 0 | 2023-10-20 |  |  |  | 2025-03-15
Holtville Peaker | GI-2022-161 |  | N | N | Active | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 2024-01-19 |  |  |  | 2025-04-01
Sequoia 1 Farmersville 3 | GFID#5864 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-10-15
Sequoia 2 Hanford 2 | GFID#5807 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-10-15
Bellefield 2 Solar Farm | 1631 |  | N | N | Active | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 2023-10-09 |  |  |  | 2025-07-15
Sequoia 2 Hanford 1 | GFID#5806 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-10-15
Aratina Solar Center 1 a BESS | 1204 |  | N | Y | Active | 75 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 2023-07-13 |  |  |  | 2025-05-01
Sequoia 1 Farmersville 1 | GFID#5862 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-02 |  |  |  | 2024-10-15
Nighthawk Storage | 1673 |  | N | N | Active | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 2024-03-28 |  |  |  | 2025-01-01
Rio Vista Solar | 2967-WD |  | N | N | Active | 2.73 | 2.73 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-28 |  |  |  | 2024-09-30
Pittsburg RV Boat Solar | 3187-RD |  | N | N | Active | 2.9 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-28 |  |  |  | 2024-07-31
Foster Clean Power A | 2622-WD |  | Y | N | Active | 3 | 3 | 0 | 1.25 | 0 | 0 | 0 | 0 | 2024-03-29 |  |  |  | 2024-07-31
Cal Portland Cement Wind Mojave | WDT1371 |  | N | N | Active | 23.52 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 2023-10-12 |  |  |  | 2024-09-20
North Brawley Solar |  |  | Y | N | Active | 35 | 42 | 0 | 35 | 0 | 0 | 0 | 0 | 2023-10-14 |  |  |  | 2024-11-01
Snowline Duncan Road North | SCE GFID 5601 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-04 |  |  |  | 2024-11-01
Snowline Duncan Road South | SCE GFID 5641 |  | N | N | Active | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-04 |  |  |  | 2024-11-01
Snowline White Road Central | SCE GFID 5643 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-04 |  |  |  | 2024-11-01
Snowline White Road North | SCE GFID 5599 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-04 |  |  |  | 2024-11-01
Snowline White Road South | SCE GFID 5644 |  | N | N | Active | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-04 |  |  |  | 2024-11-01