## PGaE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013 | 2025 |  | Q1-2021 | Q1-2021 | Q1-2021 | Q1-2021 | In-Service | N/A | Q4-2018 | (blank)
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2022 | Q3-2022 | Q3-2021 | Q3-2021 | Q3-2021 | Q3-2021 | In-Service | N/A | Q3-2021 | Q1-2023: no date changes at this time.
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 |  | 2023 |  | Q2-2022 | Q2-2022 | Q2-2022 | Q2-2022 | In-Service | N/A | Q3-2021 | Q1-2023: no date changes at this time.
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023 | 2026 | Q3-2022 | Q3-2022 | Q3-2022 | Q3-2022 | Q3-2022 | In-Service | N/A | Q3-2021 | Q1-2023: no date changes at this time.
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015 | 2022 | Q4-2022 | Q1-2023 | Q4-2022 | Q4-2022 | Q4-2022 | In-Service | PTC: A.17-12-010 | Q3-2022 | Q1-2023: no date changes at this time.
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019 | 2023 | Q1-2023 | Q1-2023 | Q4-2022 | Q4-2022 | Q4-2022 | In-Service | PTC: A.17-12-010 | Q3-2022 | Q1-2023: no date changes at this time.
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E | 2018-2019 | 2023 | 2023 | Q4-2023 | Q2-2023 | Q1-2023 | Q2-2023 | Q2-2023 | In-Flight | N/A | Q2-2022 | Q1-2023: schedule/construction sequencing date adjustments.
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015 | 2022 | Q4-2022 | Q1-2023 | Q2-2023 | Q2-2023 | Q4-2023 | In-Flight | NOC: AL 5872E | Q2-2021 | Q1: Delay due to reprioritization
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018 | 2022 | Q4-2022 | Q4-2022 | Q4-2022 | Q4-2023 | Q4-2023 | In Flight | N/A | Q2-2020 | Q1-2023: no date changes at this time.
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 |  | 2023 | Q1-2023 | Q2-2023 | Q3-2023 | Q4-2023 | Q4-2023 | In-Flight | N/A | Q4-2021 | Q1-2023: schedule/construction sequencing date adjustments.
Tesla 230 kV Bus Series Reactor project | PG&E | 2018-2019 | 2023 | 2023 | Q4-2023 | Q4-2023 | Q3-2023 | Q4-2023 | Q4-2023 | In-Flight | N/A | Q2-2022 | Q1-2023: schedule/construction sequencing date adjustments.
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA_230KV BUS REACTORS C – D | PG&E | 2018-2019 | 2023 | 2023 | Q4-2023 | Q4-2023 | Q3-2023 | Q4-2023 | Q4-2023 | In-Flight | N/A | Q2-2023 | Q1-2023: schedule/construction sequencing date adjustments.
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020 | 2022 | Q1-2022 | Q4-2022 | Q4-2022 | Q1-2024 | Q4-2023 | In-Flight | NOC: AL 5293-E | Q1-2021 | Q1-2023: The line reconductoring is complete, the bus work at LeGrand SS, ISD December 2023. The project was deferred but recently has been funded for 2023, team curently scheduling resources.
Giffen Line Reconductoring Project | PG&E | 2018-2019 |  | 2023 | Q1-2023 | Q1-2023 | Q1-2023 | Q1-2024 | Q1-2024 | In Flight | NOC: AL 6600-E | Q4-2023 | Q1-2023: no date changes at this time.
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013 | 2025 | Q3-2023 | Q4-2023 | Q1-2024 | Q1-2024 | Q2-2024 | In-Flight | TBD | Q2-2024 | Q1: Delay due to reprioritization
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021 | 2023 | Q1-2023 | Q1-2023 | Q1-2023 | Q4-2022 | Q2-2024 | In-Flight | NOC: AL 5390-E | Q1-2022 | Q1: Delay due to reprioritization
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | 2024 | Q2-2024 | Q3-2024 | Q3-2024 | Q2-2024 | Q2-2024 | In-Flight | NOC - TBD on Filing Date | Q1-2023 | Q1-2023: schedule/construction sequencing date adjustments.
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017 | 2024 | Q4-2024 | Q2-2024 | Q2-2024 | Q2-2024 | Q2-2024 | In-Flight | NOC: AL 6047-E | Q2-2022 | Q1-2023: no date changes at this time.
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025 | 2025 | Q1-2025 | Q2-2024 | Q2-2024 | Q2-2024 | Q3-2024 | In-Flight | N/A | Q1-2023 | Q1-2023: schedule/construction sequencing date adjustments.
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014 | 2023 | Q4-2023 | Q4-2024 | Q4-2024 | Q4-2024 | Q4-2024 | In-Flight | N/A | Q3-2019 | Q1-2023: no date changes at this time.
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019 | 2022 | Q4-2022 | Q2-2023 | Q4-2024 | Q4-2024 | Q4-2024 | Initiating | TBD | Q1-2024 | Q1-2023: no date changes at this time.
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023 | 2023 |  | Q4-2024 | Q4-2024 | Q4-2024 | Q4-2024 | Initiating | TBD | Q4-2023 | Q1-2023: no date changes at this time.
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024 | 2027 | Q2-2027 | Q1-2026 | Q2-2026 | Q4-2026 | Q1-2025 | In-Flight | TBD | Q4-2024 | Q1: Improvement due to reprioritization
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011 | 2025 | Q1-2025 | Q1-2025 | Q1-2025 | Q1-2025 | Q1-2025 | In-Flight | N/A | Q2-2024 | Q1-2023: no date changes at this time.
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025 | 2025 | Q4-2025 | Q4-2025 | Q3-2025 | Q1-2025 | Q2-2025 | In-Flight | TBD | Q4-2023 | Q1: Reason for delay due to error. Feb 2025 ISD was draft date. May 2025 was supposed to be ISD in Q4 2022 TDF
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013 | 2025 | Q2-2025 | Q2-2025 | Q2-2025 | Q2-2025 | Q2-2025 | In-Flight | N/A | Q2-2021 | Q1-2023: no date changes at this time.
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016 | 2024 | Q4-2024 | Q4-2024 | Q3-2024 | Q4-2024 | Q2-2025 | In-Flight | N/A | Q1-2024 | Q1-2023: no date changes at this time.
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025 | 2025 |  | Q2-2025 | Q2-2025 | Q2-2025 | Q2-2025 | Initiating | TBD | Q4-2024 | Q1-2023: no date changes at this time.
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019 | 2024 | Q4-2024 | Q1-2025 | Q1-2025 | Q2-2025 | Q3-2025 | In-Flight | N/A | Q1-2025 | Q1-2023: schedule/construction sequencing date adjustments.
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016 | 2024 | Q3-2024 | Q3-2024 | Q2-2024 | Q3-2025 | Q3-2025 | In-Flight | N/A | Q2-2018 | Q1-2023: no date changes at this time.
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014 | 2025 | Q2-2025 | Q1-2027 | Q3-2025 | Q3-2025 | Q3-2025 | In-Flight | PTC: A.18-06-004 | Q4-2023 | Q1-2023: no date changes at this time.
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024 | 2026 | Q4-2026 | Q4-2026 | Q4-2025 | Q4-2025 | Q4-2025 | Initiating | TBD | Q4-2024 | Q1-2023: no date changes at this time.
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021 | 2024 | Q2-2024 | Q2-2024 | Q2-2024 | Q4-2025 | Q4-2025 | In-Flight | CPCN: A.17-12-021 | Q1-2024 | Q1-2023: no date changes at this time.
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019 | 2024 | Q4-2024 | Q4-2024 | Q4-2025 | Q4-2025 | Q4-2025 | Initiating | TBD | Q4-2025 | Q1-2023: no date changes at this time.
Reedley 70 kV Reinforcement (Renamed to Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017 | 2025 | Q4-2025 | Q3-2025 | Q4-2025 | Q4-2025 | Q4-2025 | In Flight | N/A | Q1-2024 | Q1-2023: no date changes at this time.
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009 | 2024 | Q2-2024 | Q2-2024 | Q2-2024 | Q2-2025 | Q4-2025 | In-Flight | N/A | Q3-2022 | Q1-2023: schedule/construction sequencing date adjustments. Partial 2023 funding reinstated
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023 | 2026 | Q4-2026 | Q4-2026 | Q4-2025 | Q4-2025 | Q4-2025 | Initiating | TBD | Q4-2024 | Q1-2023: no date changes at this time.
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023 | 2026 | Q3-2026 | Q3-2026 | Q3-2025 | Q4-2025 | Q4-2025 | In-Flight | PTC - TBD on Filing Date | Q3-2025 | Q1-2023: no date changes at this time.
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022 | 2025 | Q4-2025 | Q1-2025 | Q4-2024 | Q1-2026 | Q1-2026 | In-Flight | N/A | Q4-2025 | Q1-2023: no date changes at this time.
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026 | 2026 |  | Q1-2026 | Q2-2026 | Q2-2026 | Q2-2026 | Initiating | TBD | Q1-2025 | Q1-2023: no date changes at this time.
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028 | 2028 |  | Q2-2028 | Q2-2026 | Q2-2026 | Q2-2026 | Initiating | TBD | Q2-2025 | Q1-2023: no date changes at this time.
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022 | 2026 | Q4-2026 | Q4-2026 | Q2-2026 | Q2-2026 | Q2-2026 | Initiating | TBD | Q4-2025 | Q1-2023: no date changes at this time.
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019 | 2027 | Q2-2027 | Q4-2025 | Q4-2025 | Q4-2025 | Q2-2026 | In Flight | N/A | Q1-2025 | Q1: Delay due to reprioritization
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027 | 2027 |  | Q2-2027 | Q2-2026 | Q2-2026 | Q2-2026 | Initiating | TBD | Q2-2025 | Q1-2023: no date changes at this time.
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026 | 2026 |  | Q1-2026 | Q4-2026 | Q4-2026 | Q4-2026 | Initiating | TBD | Q2-2026 | Q1-2023: no date changes at this time.
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021 | 2026 | Q4-2026 | Q4-2026 | Q4-2026 | Q4-2026 | Q4-2026 | In-Flight | NOC - TBD on Filing Date | Q3-2025 | Q1-2023: no date changes at this time.
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022 | 2026 | Q2-2026 | Q2-2026 | Q4-2026 | Q4-2026 | Q4-2026 | Initiating | TBD | Q4-2024 | Q1-2023: no date changes at this time.
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2027 | Q2-2027 | Q4-2025 | Q2-2026 | Q3-2026 | Q4-2026 | In-Flight | TBD | Q3-2026 | Q1-2023: schedule/construction sequencing date adjustments.
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026 | 2026 |  | Q1-2026 | Q4-2026 | Q4-2026 | Q4-2026 | Initiating | TBD | Q2-2025 | Q1-2023: no date changes at this time.
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024 | 2026 | Q4-2026 | Q4-2026 | Q4-2026 | Q4-2026 | Q4-2026 | Initiating | TBD | Q4-2025 | Q1-2023: no date changes at this time.
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | Q4-2026 | Q3-2026 | Q4-2026 | Q4-2026 | Q4-2026 | In Flight | NOC - May 2024 | Q1-2026 | Q1-2023: no date changes at this time.
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024 | 2025 | Q4-2025 | Q4-2025 | Q4-2026 | Q4-2026 | Q4-2026 | Initiating | TBD | Q4-2025 | Q1-2023: no date changes at this time.
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020 | 2026 | Q4-2026 | Q4-2026 | Q4-2026 | Q4-2026 | Q4-2026 | In-Flight | N/A | Q4-2023 | Q1-2023: no date changes at this time.
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027 | 2027 |  | Q2-2027 | Q2-2027 | Q2-2027 | Q2-2027 | Initiating | TBD | Q4-2025 | Q1-2023: no date changes at this time.
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019 | 2024 | Q2-2024 | Q3-2025 | Q2-2026 | Q2-2026 | Q2-2027 | In Flight | NOC: AL 5026-E | Q4-2018 | Q1: Project relies on the Midway 230kV Section D Bus Upgrade project (T.0001650) to be in-serviced to provide a new terminal position for the new 230kV line. Due to the Midway 230kV Section D Bus Upgrade project being deferred due to 2023 budget constraints, this will push the Midway-Kern project out to April 2027.
South of Mesa Upgrade | PG&E | 2018-2019 | 2023 | 2026 | Q3-2026 | Q2-2026 | Q2-2026 | Q2-2027 | Q2-2027 | In Flight | NOC - Feb 2024 | Q4-2025 | Q1-2023: no date changes at this time.
South of San Mateo Capacity Increase | PG&E | 2007 | 2009 | 2027 | Q1-2027 | Q1-2027 | Q2-2027 | Q2-2027 | Q2-2027 | Initiating | TBD | Q1-2026 | Q1-2023: no date changes at this time.
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016 | 2027 | Q3-2027 | Q3-2027 | Q3-2027 | Q3-2027 | Q3-2027 | In Flight | NOC - TBD on Filing Date | Q1-2025 | Q1-2023: no date changes at this time.
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021 | 2026 | Q2-2026 | Q2-2026 | Q2-2026 | Q2-2026 | Q3-2027 | In-Flight | NOC: AL 5200-E | Q3-2025 | Q1: Delay due to reprioritization.
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025 | 2027 | Q4-2027 | Q4-2027 | Q4-2027 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | Q1-2023: no date changes at this time.
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027 | 2027 |  | Q2-2027 | Q4-2027 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | Q1-2023: no date changes at this time.
Maple Creek Reactive Support | PG&E | 2009 | 2011 | 2026 | Q3-2026 | Q3-2026 | Q4-2027 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | Q1-2023: no date changes at this time.
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008 | 2029 | Q2-2029 | Q2-2029 | Q4-2027 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | Q1-2023: no date changes at this time.
Mosher Transmission Project | PG&E | 2013-2014 | 2017 | 2027 | Q4-2027 | Q4-2027 | Q4-2027 | Q4-2027 | Q4-2027 | In Flight | NOC - April 2026 | Q1-2027 | Q1-2023: no date changes at this time.
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027 | 2027 |  | Q1-2027 | Q4-2027 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2025 | Q1-2023: no date changes at this time.
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022 | 2027 | Q4-2027 | Q1-2028 | Q1-2028 | Q1-2028 | Q1-2028 | In-Flight | N/A | Q2-2026 | Q1-2023: no date changes at this time.
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | Q3-2026 | Q3-2027 | Q3-2027 | Q1-2028 | Q1-2028 | In Flight | N/A | Q2-2025 | Q1-2023: no date changes at this time.
Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019 | 2024 | Q2-2024 | Q2-2027 | Q3-2027 | Q4-2027 | Q1-2028 | In Flight | NOC: AL 5924-E | Q4-2024 | Q1-2023: schedule/construction sequencing date adjustments.
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022 | 2028 | Q4-2028 | Q4-2028 | Q2-2028 | Q2-2028 | Q2-2028 | Initiating | TBD | Q1-2025 | Q1-2023: no date changes at this time.
Estrella Substation Project | PG&E | 2013-2014 | 2019 | 2026 | Q2-2026 | Q3-2026 | Q3-2026 | Q1-2027 | Q2-2028 | In-Flight | PTC: A.17-01-023 | Q2-2024 | Q1: The delay in getting the PTC will push the FISD (new) to May 2028
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022 | 2028 | Q2-2028 | Q2-2028 | Q2-2028 | Q2-2028 | Q2-2028 | In-Flight | TBD | Q1-2027 | Q1-2023: no date changes at this time.
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012 | 2027 | Q1-2027 | Q1-2027 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q1-2023: no date changes at this time.
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023 | 2027 | Q4-2027 | Q4-2027 | Q4-2027 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2026 | Q1-2023: no date changes at this time.
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021 | 2027 | Q4-2027 | Q4-2027 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q1-2023: no date changes at this time.
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018 | 2027 | Q4-2027 | Q1-2028 | Q2-2028 | Q3-2028 | Q4-2028 | In Flight | NOC - April 2026 | Q3-2026 | Q1-2023: schedule/construction sequencing date adjustments.
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024 | 2027 | Q4-2027 | Q4-2027 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q1-2023: no date changes at this time.
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | Q1-2028 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q2-2026 | Q1-2023: no date changes at this time.
New Manning 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | Q1-2028 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q1-2027 | Q1-2023: no date changes at this time.
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028 | 2028 |  | Q1-2028 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q1-2023: no date changes at this time.
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028 | 2028 |  | Q1-2028 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q1-2023: no date changes at this time.
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028 | 2028 |  | Q1-2028 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q1-2026 | Q1-2023: no date changes at this time.
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026 | 2026 | Q2-2026 | Q2-2026 | Q4-2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q1-2023: no date changes at this time.
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017 | 2027 | Q2-2027 | Q4-2028 | Q1-2029 | Q1-2029 | Q1-2029 | In-Flight | CPCN Expected Q1 2023 | Q1-2027 | Q1-2023: no date changes at this time.
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022 | 2029 | Q2-2029 | Q2-2029 | Q2-2029 | Q2-2029 | Q2-2029 | In Flight | N/A | Q3-2027 | Q1-2023: no date changes at this time.
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019 |  |  | Q4-2029 | Q4-2029 | Q4-2029 | Q3-2029 | On-Hold (CAISO) | CPCN - TBD on Filing Date | Q1-2024 | Q1: The current changes in milestone dates reflect a recalibration due to a systemwide changes to PG&E’s scheduling software and not changes to the project schedule. This project is under reassessment by CAISO and is currently on-hold. Once project is restarted, the in-service dates will be adjusted.
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028 | 2028 |  | Q1-2028 | Q4-2029 | Q4-2029 | Q4-2029 | Initiating | TBD | Q4-2028 | Q1-2023: no date changes at this time.
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015 | 2030 | Q4-2030 | Q4-2030 | Q4-2030 | Q1-2030 | Q1-2030 | Initiating | TBD | Q1-2028 | Q1-2023: no date changes at this time.
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021 | 2025 | Q4-2025 | Q3-2026 | Q3-2026 | Q2-2030 | Q4-2031 | In-Flight | NOC - TBD on Filing Date | Q2-2027 | Q1: Delay due to reprioritization.
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020 |  |  | Q2-2029 | Q2-2029 | Q2-2029 | Q4-2032 | On-Hold (CAISO) | CPCN - TBD on Filing Date | Q1-2030 | Q1: The current changes in milestone dates reflect a recalibration due to a systemwide changes to PG&E’s scheduling software and not changes to the project schedule. This project is under reassessment by CAISO and is currently on-hold. Once project is restarted, the in-service dates will be adjusted.
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023 | [6 empty] | On-Hold (CAISO) | TBD |  | (blank)

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Laguna Bell Corridor Upgrade | SCE | 2015 | 2020-12-31 | 2022-03-01 | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-05-01 |  | In-Service | N/A | N/A | Currently in-service; completed as a portion of Mesa 500 kV Substation Loop-In
Moorpark-Pardee No. 4 230 kV Circuit | SCE | 2018 | 2020-12-31 | 2021-06-01 | 2022-03-01 | 2022-05-31 | 2022-05-31 | 2022-05-31 |  | In-Service | N/A | N/A | In-service January 2022
Mesa 500 kV Substation Loop-In | SCE | 2014 | 2020-12-01 | 2022-03-01 | 2022-05-01 | 2022-05-31 | 2022-05-22 | 2022-05-22 |  | In-Service | N/A | N/A | In-service May 2022
Lugo-Mohave series capacitor upgrade | SCE | 2013 | 2016 | 2022-06-01 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | Construction | 2018-05-01 | 2020-12-01 | Most of the project expected in-service by June 2023 with full compensation by December 2023
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2013 | 2016 | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | Construction | 2018-05-01 | 2020-12-01 | Most of the project expected in-service by June 2023 with full compensation by December 2023
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | Design | Exempt | 2024-10-01
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2017 | 2018-12-31 | 2023-06-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | Construction | Exempt | Construction started | Joint SCE/LADWP project. SCE completed raising its towers and LADWP's are in progress. Substation upgrades (breakers and terminal equipment) require synchronizing outages with LADWP.
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | Permitting | 2009-09-01 | 2026-06-01 | Alberhill dates contingent on licensing
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | Design | 2015-04-01 | 2023-05-01 | Project resuming after a 6-month hold
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2020 | 2023-06-01 | 2023-05-01 | June-23 * | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | Design | Exempt | 2022-10-22 | Joint SCE/LADWP project. ISD for SCE’s portion of the project remains June 2024. Expected ISD of June 2025 includes LADWP's portion of the project.
Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 2021-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | Construction | N/A | Construction started | The in-service dates range from September 2022 to December 2025
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 |  | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | Design | Pending | 2023-11-01 | Project delayed due to equipment lead times
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 |  | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | Planning | N/A | 2024-04-01
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 |  | New | Pending | Pending | 2025-06-30 | 2025-06-01 | Design | N/A | 2024-03-01
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 |  | New | Pending | Pending | Pending | 2025-04-01 | Initiation | N/A | 2024-06-01
Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 |  |  |  |  | New | Pending | Initiation | N/A | Pending
Mira Loma 500 kV CB Upgrade Project | SCE | 2022-2023 | 2026 |  |  |  |  | New | Pending | Initiation | N/A | Pending

## SDGaE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-12-01 | 2023-05-01 | 2021-11-01 | 2021-10-22 | 2021-11-01 |  | Close-out | Exempt | 2021-05-17
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-06-01 | 2022-06-01 | 2022-12-14 | 2022-12-13 | 2022-12-02 | Completed | Construction | 2016-08-17 | 2020-06-10 | Energized in December 2022
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2022-11-01 | 2023-06-27 | 2023-08-25 | 2023-10-24 | 2023-10-24 | Completed | Construction | Exempt | 2021-07-26
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-04-01 | 2022-05-02 | 2022-05-31 | 2022-05-15 | 2022-05-15 | 2022-05-15 | Construction | Exempt | 2022-02-04
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2021-10-01 | 2022-12-01 | 2022-12-09 | 2022-12-27 | 2022-10-20 | 2022-11-18 | Construction | 2017-06-28 | 2021-01-19 | Completed and energized in Novemeber 2022
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-05-01 | 2022-09-01 | 2022-12-14 | 2022-12-27 | 2022-11-18 | 2023-02-08 | Construction | 2017-11-15 | 2022-01-03
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2023-05-01 | 2023-12-01 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-11-05 | Construction | 2012-05-18 | 2018-06-29
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2027-06-01 | 2024-05-02 | 2024-12-23 | 2024-12-23 | 2024-10-21 | 2024-06-25 | Design | 2023-08-22 | 2024-08-19
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 2022-06-01 |  |  |  | 2022-08-24 | 2024-10-21 | 2024-12-17 | Design | TBD | TBD
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 1905-07-08 | 2023-04-01 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2025-08-28 | 2023-02-13 | Design | 2016-04-25 | 2024-08-09
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-04-16 | 2026-06-08 | Design | 2023-09-01 | 2024-03-01
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2027-03-12 | 2026-11-10 | Design | Exempt | 2025-03-20
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-10-14 | 2027-11-14 | Planning | 2026-07-24 | 2027-04-12
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 2022-06-01 |  |  |  | 2024-08-15 | 2029-06-04 | 2029-02-27 | Planning | TBD | 2024-07-19

## VEA_GLW
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 2021 | 2021-09-01 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service |  | In service | N/A | 2021 | The GridLiance 230kV Ring Bus and associated 230kV Transmission Line loop-in were placed in service Nov-2021. The VEA 138kV Station upgrades were placed in service Dec-2021. The 230/138kV Transformer was delivered to site and mounted on the foundation Oct-2021. The Transformer failed testing at-site and was required to be shipped back to the factory for repair. Expected in-service date for the Transformer is Q2-2022.
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 | 2022-12-20 | 2023-06-23 | In Flight | N/A | Sept-21
GLW/VEA area upgrades | VEA/GLW | 2021-2022 | TBD |  | N/A | TBD |  | TBD | TBD | Permitting, engineering and design | N/A | TBD

## DCRT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | Inflight | Inflight | Approved

## LSPower
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-12-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2023-06-24 | In-Flight | Q4-2020 | 2023-10-22
Round Mountain 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2023-12-24 | In-Flight | 2023-04-22 | 2023-04-23

## CitizensEnergy
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | In-Flight |  | 2023-07-21