## Revision_History
FNM Scope for FNM DB23M3
(Production 3/15/2023)
Revision History
Effective Date | Version | Description
2023-01-05 | 1 | Final scope by due date. The scope is considered finalized without any addendum attached.
2023-03-13 | 2 | Add additional information
California ISO – Public

## NRI
I. NRI Projects
No | PTO | Resource ID | Project Name / Description | Project Key | Capacity (MW) | POD | Additional Information
1 | PGAE | SOLBLU_2_WSBSX2 | Westlands Solar Blue | 15AS884809 | 250 | GATES 230KV BUS | New Aggregate Solar resource; child resources: SOLBLU_2_WSBSR1: 125 MW SOLBLU_2_WSBSR2: 125 MW
2 | PGAE | SANDRN_2_SS2SR2 | Sandrini Sol 2 | 17AS1795 | 200 | WHEELER RIGDE 230KV Bus | New Solar resource
3 | PGAE | SANDRN_2_SS1SR1 | Sandrini Sol 1 | 17AS1796 | 100 | WHEELER RIGDE 230KV Bus | New Solar resource
4 | PGAE | KERNEY_6_FCSSR1 | Fresno Community Solar | 22GEN21087 | 10 | KEARNEY 70KV BUS | New Solar resource
5 | PGAE | CHESTN_2_CHWSX2 | Chestnut Westside PV | 22GEN24024 | 150 | GATES 230KV BUS | New Aggregate Solar resource; child resources: CHESTN_2_CHWSR1: 75 MW CHESTN_2_CHWSR2: 75 MW
6 | PGAE | VISTRA_5_PLABT4 | Plano Storage 4 | 22NGR22252 | 74.6 | MOSS LANDING 500 Kv BUS | New Storage resource
7 | PGAE | CUYAMA_6_SB3SB1 | SEPV Barbara 3 | 22NGR23728 | 3 | Cuyama 70kV Bus | New Non-Generation resource
8 | PGAE | CHESTN_2_CHWBX2 | Chestnut Westside BESS | 22NGR23984 | 135 | GATES 230KV BUS | New Aggregate Non-Generation resource; child resources: CHESTN_2_CHWBT1: 67.5 MW CHESTN_2_CHWBT2: 67.5 MW
9 | PGAE | SOLBLU_2_WSBBX2 | Westlands Solar Blue BESS | 22NGR23985 | 225 | GATES 230KV BUS | New Aggregate Non-Generation resource; child resources: SOLBLU_2_WSBBT1: 112.5 MW SOLBLU_2_WSBBT2: 112.5 MW
10 | SCE | LCKHT1_2_LH1SR2 | Lockhart Solar 2 | 19AS9101 | 75 | Kramer 230kV Bus | New Solar resource
11 | SCE | VICTOR_1_LMASR1 | Landpro Madelyn | 22GEN21517 | 1 | VICTOR 115KV BUS | New Solar resource
12 | SCE | VICTOR_1_LMISR2 | Landpro Mitchell | 22GEN21518 | 1.5 | VICTOR 115KV BUS | New Solar resource
13 | SCE | VICTOR_1_LRUSR3 | Landpro Rudy | 22GEN21519 | 1.5 | VICTOR 115KV BUS | New Solar resource
14 | SCE | VICTOR_1_NUNSR4 | Nunn | 22GEN21521 | 1 | VICTOR 115KV BUS | New Solar resource
15 | SCE | SHUTLE_6_RUISR1 | Rutan I | 22GEN21522 | 1.5 | ANTELOPE 66KV BUS | New Solar resource
16 | SCE | SHUTLE_6_RUISR2 | Rutan II | 22GEN21523 | 1.5 | ANTELOPE 66KV BUS | New Solar resource
17 | SCE | SHUTLE_6_RUISR3 | Rutan III | 22GEN21524 | 1 | ANTELOPE 66KV BUS | New Solar resource
18 | SCE | RDWAY_1_WAISR2 | Watts I | 22GEN21526 | 1.5 | KRAMER 115KV BUS | New Solar resource
19 | SCE | LCKHT1_2_LH1SR1 | Lockhart Solar 1 PV PMAX | 22GEN25500 | 20 |  | Existing Solar resource; EMS pmax increase from 65 MW to 85 MW
20 | SCE | WHTHIL_3_WHAWD1 | White Hills Wind A | 22PSEUDO23753 | 50 | ELDORADO BUS 230 KV BUS | New Pseudo resource
21 | SCE | WHTHIL_3_WHBWD2 | White Hills Wind B | 22PSEUDO23754 | 300 | ELDORADO BUS 230 KV BUS | New Pseudo resource
22 | SDGE | MSOLAR_2_MS4SR4 | Mesquite Solar 4 | 22NGR24445 | 52.5 | MESQUITE 230KV BUS | New Solar resource
23 | SDGE | MSOLAR_2_MS4BT1 | Mesquite Solar 4 BESS | 22NGR24456 | 10 | MESQUITE 230KV BUS | New Non-Generation resource
24 | SDGE | OTAY_6_CVEBT3 | Chula Vista Energy Center 2 BESS | 22NGR24837 | 49.7 | OTAY 69KV BUS | New Non-Generation resource
25 | SCE |  | CONTRL_1_CASAD2 | 22RIG24042 | 10.5 |  | RIG Reconfiguration
26 |  |  | Glass House Camarillo | 22RIG22841 | 13.2 |  | RIG Reconfiguration
27 |  |  | Kingbird A | 22RIG22895 | 20 |  | RIG Reconfiguration
28 |  |  | Kingbird B | 22RIG22896 | 20 |  | RIG Reconfiguration
29 |  |  | Summer_Wheat | 22RIG23115 | 19.8 |  | RIG Reconfiguration
30 |  |  | Mount Signal 3 | 22RIG23116 | 250 |  | RIG Reconfiguration
31 |  |  | Terminus | 22RIG23178 | 20 |  | RIG Reconfiguration
32 |  |  | Algonquin Power Sanger | 22RIG23348 | 55.4 |  | RIG Reconfiguration
33 |  |  | Garnet Wind-ANIRA Upgrade | 22RIG23594 | 6.5 |  | RIG Reconfiguration
34 |  |  | GSD M | 22RIG23705 | 1.75 |  | RIG Reconfiguration
35 |  |  | GSD L | 22RIG23706 | 1.25 |  | RIG Reconfiguration
36 |  |  | GSD H | 22RIG23707 | 1.5 |  | RIG Reconfiguration
37 |  |  | GSD G | 22RIG23708 | 1.25 |  | RIG Reconfiguration
38 |  |  | GSD F1 | 22RIG23709 | 1.33 |  | RIG Reconfiguration
39 |  |  | GSD D | 22RIG23710 | 1.25 |  | RIG Reconfiguration
40 |  |  | GSD C1 | 22RIG23711 | 1.16 |  | RIG Reconfiguration
41 |  |  | FREEWAY | 22RIG23712 | 2 |  | RIG Reconfiguration
42 |  |  | NorthStar_NERCB003 | 22RIG23916 | 61.6 |  | RIG Reconfiguration
43 |  |  | CONTRL_1_CASAD3 | 22RIG24043 | 14 |  | RIG Reconfiguration
44 |  |  | High Desert Power Project; RIG recertification 2022 | 22RIG24074 | 830 |  | RIG Reconfiguration
45 |  |  | Woodland Biomass; Unit 1; IDG070GovBlockUpdate | 22RIG24460 | 25 |  | RIG Reconfiguration
46 |  |  | Mammoth G1- CONTRL_1_CASAD1 | 22RIG24522 | 7.5 |  | RIG Reconfiguration
47 |  |  | High 5 Solar RIG Reconfiguration - HSL | 22RIG24559 | 100 |  | RIG Reconfiguration
48 |  |  | 2021 SVP GIA RIG - Device ID IDG005 | 22RIG24566 | 25 |  | RIG Reconfiguration
49 |  |  | Arlington Solar 2a RIG Reconfiguration | 22RIG24575 | 100 |  | RIG Reconfiguration
50 |  |  | SVP GIA RIG Replacement | 22RIG24734 | 25 |  | RIG Reconfiguration
51 |  |  | Slate RIG Reconfiguration -Hybrid Phase 2B | 22RIG24753 | 249.5 |  | RIG Reconfiguration
52 |  |  | SILVERSTRAND ENERGY STORAGE | 22RIG24764 | 20 |  | RIG Reconfiguration
53 |  |  | Crockett Cogen RIG Reconfig | 22RIG24865 | 240 |  | RIG Reconfiguration
54 |  |  | Tropico Solar RIG Reconfig | 23RIG25719 | 70 |  | RIG Reconfiguration
55 |  |  | Tropico Solar Big Beau RIG Reconfig | 23RIG25720 | 58 |  | RIG Reconfiguration
56 |  |  | EdSan 2 Edwards 1A RIG | 23RIG25819 | 166 |  | RIG Reconfiguration
57 |  |  | EdSan 2 Edwards 3 RIG | 23RIG25820 | 24 |  | RIG Reconfiguration
58 |  |  | Sanborn Solar 2 Edwards Sanborn S4 RIG | 23RIG25824 | 36 |  | RIG Reconfiguration
59 |  |  | Edsan 2 Edwards Sanborn E1B RIG | 23RIG25825 | 130 |  | RIG Reconfiguration
60 |  |  | EdSan 2 Sanborn 3 RIG | 23RIG25826 | 42 |  | RIG Reconfiguration
61 |  |  | EdSan 1 Sanborn 1 RIG | 23RIG25827 | 40 |  | RIG Reconfiguration
62 |  |  | EdSan 2 RIG | 23RIG25835 | 151 |  | RIG Reconfiguration
63 |  |  | SEPV Sierra BESS MW | 23RIG25956 | 8.25 |  | RIG Reconfiguration

## TRAN
II. Transmission Projects
No | PTO | RIMS ID | Project Name | Project Key
1 | PGAE | 20TRANS13706 | Palermo Substation: Install 115 kV Bus Tie Circuit Breaker & Second Breaker | ET4455
2 | PGAE | 20TRANS13706 | Palermo Substation: Install 115 kV Bus Tie Circuit Breaker & Second Breaker | ET4464
3 | PGAE | 21TRANS15396 | Eastshore 230kV Interconnection AWS Project | ET4575
4 | PGAE | 21TRANS15396 | Eastshore 230kV Interconnection AWS Project | ET4576
5 | PGAE | 21TRANS15396 | Eastshore 230kV Interconnection AWS Project | ET4577
6 | PGAE | 21TRANS15808 | Brighton-Grand Island #1 & #2 115kV NERC | ET4588
7 | PGAE | 21TRANS15844 | Palermo: Emergency Bank 1 Project | ET4589
8 | PGAE | 22TRANS20886 | Dunnigan Bank 1 Replacement | ET5106
9 | PGAE | 22TRANS24765 | COLUMBUS SUB: BK 1 FAILURE | ET5156
10 | SCE | 15TRANS874077 | Upgrade Eldorado-Lugo-Mohave 500 kV T/L Series Cap and Terminal Equipment (Multiple Locations) | ET3187
11 | SCE | 15TRANS874077 | Upgrade Eldorado-Lugo-Mohave 500 kV T/L Series Cap and Terminal Equipment (Multiple Locations) | ET4660
12 | SCE | 21TRANS19091 | Bishop RAS - Lyster Generation Addition | ET4709
13 | SDGE | 17TRANS6478 | TL639 Elliott to Sycamore Canyon Wood to Steel | ET3303
14 | SDGE | 19TRANS9146 | Q1532 KETTLE SOLAR ONE Generation Interconnection Loop in TL13844 | ET4122

## EIM_RC
III. EIM/ RC Projects
No | Entity | Project Name | Project Key
1 | AVA_BA | - ICCP mapping to AVA CIM model | 22EMS24914
2 | AVA_BA | - Note: the ratings in this submittal are SPRING = High1/High2, and WINTER = High3/High4 | 22EMS24915
3 | AZPS_BA | Transmission Line - Removed 230KV line PV-FDM Removed 230KV line PV-RUN Removed 69KV line PV-TTH Removed 69KV line PVTTHSAR Removed 69KV line TTH-STS Added 12KV line CVS-CVSB (zero impedance) Added 12KV line RDR-RDRB (zero impedance) Added 18KV line SPTSPTb (zero impedance) | 22EMS24933
4 | AZPS_BA | Substation\Load - Added the 12KV battery station | 22EMS24934
5 | AZPS_BA | Generator - Added 18KV generators naCTB A, naCTG A, & naSTG A | 22EMS24935
6 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added 18KV switching fields naCTB, naCTG, & naSTG (unit connect statuses) | 22EMS24936
7 | AZPS_BA | Generator - Removed 69KV boundary generator CVS EQG | 22EMS24937
8 | AZPS_BA | Substation\Load - Added the 12KV & 69KV voltage levels, between GK & BESSCVS | 22EMS24938
9 | AZPS_BA | Substation\Load - Added the 12KV battery station | 22EMS24939
10 | AZPS_BA | Transmission Line - Added 69KV series device VEX SD for the proper mapping of the measurements to VEX | 22EMS24940
11 | AZPS_BA | Substation\Load - Added the 34.5KV & 345KV voltage levels | 22EMS24941
12 | AZPS_BA | Substation\Load - Removed 345KV load AES EQ L | 22EMS24942
13 | AZPS_BA | Breaker(s)\ Disconnect(s) - added 12KV switching fields 1544F & 2144F | 22EMS24943
14 | AZPS_BA | Transformer - Updated the ratings and impedances for transformers XFMR12 A & XFMR9 A | 22EMS24944
15 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added 69KV switching fields 1461, 761, 961, PV L2, & SAR | 22EMS24945
16 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added 12KV switching field FDR0 | 22EMS24946
17 | AZPS_BA | Breaker(s)\ Disconnect(s) - Reconfigured 69KV switching field PBX-PRX, replaced the MOD with a LSD | 22EMS24947
18 | AZPS_BA | Breaker(s)\ Disconnect(s) - Removed 12KV switching field FDR2 | 22EMS24948
19 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added 230KV switching field WBUS-LP Reconfigured 230KV switching field LP from a MOD to a DISC | 22EMS24949
20 | AZPS_BA | Breaker(s)\ Disconnect(s) - Removed 69KV switching field K6657 | 22EMS24950
21 | AZPS_BA | Transformer - Changed the representation of transformer XFMR10 A from 2 winding to 3 winding | 22EMS24951
22 | AZPS_BA | Shoofly Install\ Removal - Added shoofly JS-FP TA | 22EMS24952
23 | AZPS_BA | Substation\Load - Renamed from ENTMP | 22EMS24953
24 | BANC_BA | Generator - Increase max operating capacity of logical unit by 5 MW. | 22EMS24979
25 | BANC_BA | Shunt Cap\Reactor\ SVD¿s - Addition/Update of cap banks. | 22EMS24980
26 | BANC_BA | Breaker(s)\ Disconnect(s) - Addition of new breakers for new cap bank. | 22EMS24981
27 | BANC_BA | Transmission Line - Removal of all Transmission lines, analogs on the terminals, and pseudo disconnects on outlying stations due to removal of STA. Topology modifications at STD, STE, and STG. | 22EMS24982
28 | BANC_BA | Substation\Load - Removal of STA due to substation being decomissioned. | 22EMS24983
29 | BCHA_RC | Transformer - Delete transformer | 22EMS24954
30 | BCHA_RC | Transformer - Add transformer | 22EMS24955
31 | BCHA_RC | Substation\Load - Add new substation | 22EMS24956
32 | BCHA_RC | Substation\Load - Add new substation | 22EMS24957
33 | BCHA_RC | Equipment Type - Updated ICCP | 22EMS24958
34 | BPA | CAPTJAC MOBT CB UCON updates | 22MRKT25337
35 | BPAT_BA | - Moved shunt cup form aux bus to main bus. | 22EMS24658
36 | BPAT_BA | Breaker(s)\ Disconnect(s) - Added a shoo-fly and two jumpers. | 22EMS24659
37 | BPAT_BA | Breaker(s)\ Disconnect(s) - Changed node 904à929 for MODs 5242 & 5243. | 22EMS24686
38 | BPAT_BA | Breaker(s)\ Disconnect(s) - Added a SECOND shoo-fly and two jumpers. | 22EMS24690
39 | BPAT_BA | Contingency Definition - Redisign Continency report process for RC West to match Template 1.4 requireonments. | 22EMS24899
40 | BPAT_BA | Substation\Load - Added new disconnects for a new solar gen. | 22EMS24925
41 | BPAT_BA | Breaker(s)\ Disconnect(s) - Added a shoofly disconnects from Snohomish PUD. | 22EMS24926
42 | BPAT_BA | Breaker(s)\ Disconnect(s) - Added a future normally open disconnect DSC 376. | 22EMS24927
43 | BPAT_BA | Transmission Line - New tie line "RAPD_COLU_1230 between BPA COLUMBIA and RAPIDS | 22EMS24928
44 | BPAT_BA | RAS - | 22EMS24929
45 | BPAT_BA | Generator - BPA Dynamic generator model mapping | 22EMS24930
46 | BPAT_BA | Contingency Definition - BPA Contingency List | 22EMS24931
47 | BPAT_TOP | Transmission Line - Update Item Number 6.23 | 22EMS24656
48 | BPAT_TOP | Changing CELILO DC POLE DSC_DC_POLE_3, DSC_DC_POLE_4 From NO TO NC | 22EMS24918
49 | BPAT_TOP | Transmission Line - Update Item Number 6.23 | 22EMS24984
50 | CHPD_BA | Generator - Updating generator turbine ratings for Rock Island units B4, B5, B6 and B7 | 22EMS24600
51 | CHPD_BA | - | 22EMS24774
52 | CHPD_BA | - | 22EMS24775
53 | CHPD_BA | - | 22EMS24776
54 | CHPD_BA | Breaker(s)\ Disconnect(s) - | 22EMS24777
55 | CHPD_BA | Transmission Line - ADDITION - Transmission Line from Rocky Reach - Ohme Substation. This line was seperated into two sections Rocky Reach - Olds Station and Olds Station - Ohme Substation need to remove the old sections and add new the routing of the line remains the same. | 22EMS24778
56 | CHPD_BA | Substation\Load - REMOVAL - Olds Station Substation decommissing leads to removal of Olds Station bus, substation, transformer, switches, and transmission line sections | 22EMS24779
57 | CHPD_BA | Substation\Load - When RC added Hawley Street 12/4/2020, the load was modeled incorrectly (should be split between 2 transformers) and the ICCPs were not mapped to the station elements because they were not available at the time. This submittal updates the ICCPs for this station. | 22EMS25378
58 | EPEC | EPE Incremental Updates | 23EMS26131
59 | GCPD_TOP | Breaker(s)\ Disconnect(s) - The status of Breaker GC1906 is changing and will now be identified as a NORMAL CLOSED. | 22EMS24462
60 | IID_TOP | S-Line Rating update on entitlement right | 22EMS24959
61 | IPCO_BA | Transmission Line - Addition of FILR-FIJN line segment | 22EMS25268
62 | IPCO_BA | Transmission Line - Addition of DBMS-BMBS line segment | 22EMS25269
63 | IPCO_BA | Transmission Line - Addition of BMSU-DBMS line segment | 22EMS25270
64 | IPCO_BA | Substation\Load - Addition of FILR | 22EMS25271
65 | IPCO_BA | Substation\Load - Addition of BMBS | 22EMS25272
66 | IPCO_BA | Substation\Load - Addition of DBMS | 22EMS25273
67 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 015Z | 22EMS25274
68 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 041A, 042A, 043A, 044A, 045A, 046A, 047Z | 22EMS25275
69 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 013Z | 22EMS25276
70 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 133Z | 22EMS25277
71 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 011A, 011Z, 012A, 013A, 014A | 22EMS25278
72 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 051A | 22EMS25279
73 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 101A, 102A | 22EMS25280
74 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 011A, 011Z, 012A, 013A, 014A | 22EMS25281
75 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 41A, 042A | 22EMS25282
76 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 041A, 042A, 043A | 22EMS25283
77 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 101A | 22EMS25284
78 | IPCO_BA | Breaker(s)\ Disconnect(s) - Update - 52A to 52H1 | 22EMS25285
79 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of 52F1, 52F2, 52T1 | 22EMS25286
80 | IPCO_BA | Generator - Update - | 22EMS25287
81 | IPCO_BA | Generator - Addition - New battery storage/generation WESR_1_BSP1 | 22EMS25288
82 | IPCO_BA | Generator - Addition - New battery storage/generation FILR_7_BSP1 | 22EMS25289
83 | IPCO_BA | Generator - Addition - New battery storage/generation MLBA_6_BSP1 | 22EMS25290
84 | IPCO_BA | Generator - Addition - New battery storage/generation BMBS_1_BMBS | 22EMS25291
85 | IPCO_BA | Generator - Addition - New battery storage/generation DBMS_1_DBMS | 22EMS25292
86 | IPCO_BA | - All ICCP Object IDs for IPCO_BA FNM. | 22EMS25293
87 | IPCO_BA | - CIM export of IPCO_BA FNM. | 22EMS25294
88 | LANL | RC Termination for LANL | 22EMS24898
89 | NEVP_BA | Update limits with higher normal than emergency | 23EMS26423
90 | NEVP_TOP | RAS - Updated EMS RAS details to match field | 22EMS24960
91 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Replaced RTU, SCADA telemetry updated | 22EMS24961
92 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Replaced RTU, SCADA telemetry updated | 22EMS24962
93 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding EIM switches for bus reconfiguration | 22EMS24963
94 | NEVP_TOP | Substation\Load - Adding new TCY-G bus for Tracy 120 kV reconfiguration | 22EMS24964
95 | NEVP_TOP | Transmission Line - Adding new branches for future lines and line re-terminations | 22EMS24965
96 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding ICCP object names for new Chukar cap banks | 22EMS24966
97 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding ICCP object names for new 171 breaker | 22EMS24967
98 | NEVP_TOP | Transmission Line - Adding new branches for future lines to WTY | 22EMS24968
99 | NEVP_TOP | Transmission Line - Adding EIM switches for line re-termination from TCY to WTY | 22EMS24969
100 | NEVP_TOP | Transmission Line - Adding new line and EIM switches for future line | 22EMS24970
101 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding switching equipment for new load on bus | 22EMS24971
102 | NEVP_TOP | Substation\Load - Adding new Switch #2 load on 120 kV bus | 22EMS24972
103 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding ICCP object names for remaining 120 kV bus equipment | 22EMS24973
104 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding breaker/switch equipment for future gen resource | 22EMS24974
105 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding bank #3 at sub | 22EMS24975
106 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding bank #4 at sub | 22EMS24976
107 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding breaker on 230 kV bus | 22EMS24977
108 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Adding breakers on 230 kV bus | 22EMS24978
109 | NEVP_TOP | Removal of 2 Switches in Humboldt | 23EMS26006
110 | NVE | HUMBOLDT (SPPC-13) switch HBT-RGS EIM default switch position updated | 23EMS25961
111 | NWMT | Please add a pseudobreaker at TRID_PLT to allow for switching at the load. | 22EMS24752
112 | NWMT | correct the modeling topology at Alkali generation. | 23EMS25792
113 | NWMT_TOP | Transmission Line - Updated some line and bank ratings; added and removed some switches | 22EMS24836
114 | PACE | Update PACE Bus Limits in database | 22EMS24742
115 | PAC_TOP | Transmission Line - Remove From MVA key for GOSHENI_BASALT_161 | 22EMS24601
116 | PAC_TOP | Transmission Line - Add 1 XFMR, 1 Sbus, 3 breakers, 9 SWs and tieline to MTCELTP$ (TSGT). Update normal state for CB 363 and 383 to CLOSED | 22EMS24602
117 | PAC_TOP | Breaker(s)\ Disconnect(s) - Remove AS JP1 | 22EMS24603
118 | PAC_TOP | Substation\Load - Update measurement direction for LD T3 | 22EMS24604
119 | PAC_TOP | Transformer - Remap T8 measurements to low side of Transformer | 22EMS24605
120 | PAC_TOP | Transmission Line - Update MVAR SCADA mapping for AEOLUS_ANTICLIN_500 MVAR branch | 22EMS24606
121 | PAC_TOP | Substation\Load - Added SCADA measurements for two loads (AUX 1 and AUX 2) | 22EMS24607
122 | PAC_TOP | Substation\Load - Clean up double modelling of Jim Bridger. Remove transformer T2 and rempove JP1, JP2, JP3. Update termination of JIMBRIDG_POINTOFR_230 branch | 22EMS24608
123 | PAC_TOP | Breaker(s)\ Disconnect(s) - Updates to 69kV topology | 22EMS25360
124 | PAC_TOP | Breaker(s)\ Disconnect(s) - Remove JP2 | 22EMS25361
125 | PAC_TOP | Transmission Line - Remove JP1 and CAMPWILL_LONEPEAK branch. Remap SCADA measurements to CAMPWILL_LEHINOTP branch | 22EMS25362
126 | PAC_TOP | Substation\Load - Delete and recreate 69 LD to generate new RDFID | 22EMS25363
127 | PAC_TOP | Substation\Load - Delete and recreate 138 LD1 to generate new RDFID | 22EMS25364
128 | PAC_TOP | Substation\Load - Delete and recreate XFMR2 LD to generate new RDFID | 22EMS25365
129 | PAC_TOP | Substation\Load - Add new Lower Valley substation between FREEDOM$ and DRYCRK$ | 22EMS25366
130 | PAC_TOP | Breaker(s)\ Disconnect(s) - Update normal state for FD724 to Open | 22EMS25367
131 | PAC_TOP | Breaker(s)\ Disconnect(s) - Remove JIMBRIDG MVAR cap curves and rename JIMBRIDE cap curves to JIMBRIDG. Change device type for 10H601, 2, 3, and 4 to Breaker type (MOABs) | 22EMS25368
132 | PAC_TOP | Breaker(s)\ Disconnect(s) - Add AS 2H976 | 22EMS25369
133 | PAC_TOP | Transmission Line - Add MOABs 2H831 and 2H833. Add line to Chalk Butte | 22EMS25370
134 | PGE_BA | Substation\Load - Cut off the Curtis-Northern Points on Curtis W64 bus | 22EMS24886
135 | PGE_BA | Breaker(s)\ Disconnect(s) - Remove SW_11696 and double modeling for Norther-Rivergate #1 line | 22EMS24887
136 | PGE_BA | Breaker(s)\ Disconnect(s) - Remove RVGT_STJN_V1532 double modeling | 22EMS24888
137 | PGE_BA | Substation\Load - Remap to RTU2 keys | 22EMS24889
138 | PGE_BA | Substation\Load - Update Canemah line measurements to RTU2, add mobile XFMR, and update SBUS config | 22EMS24890
139 | PGE_BA | Transmission Line - Add a line to ROSEWAY and reconfig SBUS | 22EMS24891
140 | PGE_BA | - CA defination update | 22EMS24892
141 | PGE_BA | - List of ICCP points mapping | 22EMS24893
142 | PGE_BA | - Model Difference report | 22EMS24894
143 | PGE_BA | - Model Updates for PGE: CIMxml model file | 22EMS24895
144 | PNM_BA | - Updated ICCP SCADA Mapping File | 22EMS24660
145 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed ICCP object nameW075$Persn_46_51941_B1_60M_Xf_Ds | 22EMS24866
146 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed ICCP object name W075$Persn_46_51943_B1_60M_Xf_Ds | 22EMS24867
147 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed ICCP object name W075$Person46kv_51942_60M_ST | 22EMS24868
148 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed ICCP object name W075$Persn_46_52043_B2_60M_Xf_Ds | 22EMS24869
149 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed ICCP object name W075$Persn_46_52041_B2_60M_Xf_Ds | 22EMS24870
150 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed ICCP object name W075$Person46kv_52042_60M_ST | 22EMS24871
151 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed SW 51941 from PNM model | 22EMS24872
152 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed SW 51943 from PNM model | 22EMS24873
153 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed BRK 51942 from PNM model | 22EMS24874
154 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed SW 52043 from PNM model | 22EMS24875
155 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed SW 52041 from PNM model | 22EMS24876
156 | PNM_BA | Breaker(s)\ Disconnect(s) - Removed BRK 52042 from PNM model | 22EMS24877
157 | PSEI_BA | Transmission Line - Line Segment with wrong name in WebOMS | 22EMS24657
158 | PSEI_BA | Substation\Load - New Substation and two new transmission lines, 2023 tentative energization. | 22EMS25311
159 | SNPD_TOP | Shoofly Install\ Removal - Installing a shoo-fly to bypass Three Lakes | 22EMS24773
160 | SPP_RC | Add WINDTALK Generation Substaion | 22EMS25437
161 | SRP_BA | SRP Mesquite RAS update | 22EMS23161
162 | SRP_BA | Transformer - Updated Transformer impedance of tranformers 1-12 | 22EMS25296
163 | SRP_BA | Transformer - Updated Transformer impedance of transformers 1A, 1B, 4 and 5 | 22EMS25297
164 | SRP_BA | Transmission Line - Updated impedance of compensators PLVRD2HAA500R2R and PLVRD2HAA500R3R | 22EMS25298
165 | SRP_BA | Transmission Line - Updated impedance of PRS_PPR_69_1 | 22EMS25299
166 | SRP_BA | Transmission Line - Updated impedance of HOD_PPR_69_1 | 22EMS25300
167 | SRP_BA | Transmission Line - Updated impedance of ROH__SYY___69_1 | 22EMS25301
168 | SRP_BA | Transmission Line - Updated impedance of HOR__IN____69_1 and CEM__HOR___69_1 | 22EMS25302
169 | SRP_BA | Transmission Line - Updated impedance of HAA__RDHK_500_1, HAA__RDHK_500_2, HAA__AVSE_500_1, and HAA__PL___500_3 | 22EMS25303
170 | SRP_BA | Transmission Line - Updated impedance of PCL__DBN__230_1 | 22EMS25304
171 | SRP_BA | Transmission Line - Updated impedance of HOS__SYY___69_2 and HOS__SK____69_1 | 22EMS25305
172 | SRP_BA | Breaker(s)\ Disconnect(s) - Updated naming of disconnects 921 and 931 | 22EMS25306
173 | SRP_BA | Shoofly Install\ Removal - Added temp switches TMP 6, TMP7, TMP8 | 22EMS25307
174 | SRP_BA | Breaker(s)\ Disconnect(s) - Added breakers and disconnects at Randolph substation (Breakers 618, 615, 612) and (Dsconnects 613, 614, 616, 617, 619, TMP1, TMP2, TMP3, TMP4, TMP5) | 22EMS25308
175 | SRP_BA | Substation\Load - Added Sidewinder substation | 22EMS25309
176 | SRP_BA | Substation\Load - Changed the name of SQUAWPK substation to YAZZIE substation. Updated the name of all equipment within the subsation (busses, branches, transformers, energy consumers). | 22EMS25310
177 | SRP_BA | Breaker(s)\ Disconnect(s) - Added disconnect OJ 17 and 18 | 22EMS25503
178 | SRP_BA | Breaker(s)\ Disconnect(s) - Added disconnect OJ 16 | 22EMS25504
179 | SRP_BA | Breaker(s)\ Disconnect(s) - Added new temp switches 10 and 11 and removed TMP 38, 39, and 40 | 22EMS25505
180 | SRP_BA | Breaker(s)\ Disconnect(s) - Added new breaker/disconnect at Halo to support connnection to FLATLAND | 22EMS25506
181 | SRP_BA | Substation\Load - Added new CREOSOTE Substation for new Solar Generation | 22EMS25507
182 | SRP_BA | Substation\Load - Added new FLATLAND Substation for new Solar Generation | 22EMS25508
183 | SRP_BA | Substation\Load - Added new Storey Substation for new Solar Generation | 22EMS25509
184 | SRP_BA | Transformer - Updated Transformer impedance of tranformers 1-12 | 22EMS25510
185 | SRP_BA | Transformer - Updated Transformer impedance of transformers 1A, 1B, 4 and 5 | 22EMS25511
186 | SRP_BA | Transmission Line - Updated impedance of compensators PLVRD2HAA500R1R, PLVRD2HAA500R2R and PLVRD2HAA500R3R | 22EMS25512
187 | SRP_BA | Transmission Line - Updated impedance of PRS_PPR_69_1 | 22EMS25513
188 | SRP_BA | Transmission Line - Updated impedance of HOD_PPR_69_1 | 22EMS25514
189 | SRP_BA | Transmission Line - Updated impedance of ROH__SYY___69_1 | 22EMS25515
190 | SRP_BA | Transmission Line - Updated impedance of HOR__IN____69_1 and CEM__HOR___69_1 | 22EMS25516
191 | SRP_BA | Transmission Line - Updated impedance of HAA__RDHK_500_1, HAA__RDHK_500_2, HAA__AVSE_500_1, and HAA__PL___500_3 | 22EMS25517
192 | SRP_BA | Transmission Line - Updated impedance of PCL__DBN__230_1 | 22EMS25518
193 | SRP_BA | Transmission Line - Updated impedance of HOS__SYY___69_2 and HOS__SK____69_1 | 22EMS25519
194 | SRP_BA | Breaker(s)\ Disconnect(s) - Updated naming of disconnects 921 and 931 | 22EMS25520
195 | SRP_BA | Shoofly Install\ Removal - Added temp switches TMP 6, TMP7, TMP8 | 22EMS25521
196 | SRP_BA | Breaker(s)\ Disconnect(s) - Added breakers and disconnects at Randolph substation (Breakers 618, 615, 612) and (Dsconnects 613, 614, 616, 617, 619, TMP12) | 22EMS25522
197 | SRP_BA | Substation\Load - Added Sidewinder substation | 22EMS25523
198 | SRP_BA | Substation\Load - Changed the name of SQUAWPK substation to YAZZIE substation. Updated the name of all equipment within the subsation (busses, branches, transformers, energy consumers). | 22EMS25524
199 | TEPC_TOP | Generator - Increase in MW high limit for generators 2A, 2B, 2C | 22EMS24878
200 | TEPC_TOP | Transmission Line - Correction of Springerville ties to PNM and SRP as PNM owns 100% of Gen3 and SRP owns 100% of Gen4 | 22EMS24879
201 | TEPC_TOP | Breaker(s)\ Disconnect(s) - New breakers and disconnects in West Wing | 22EMS24880
202 | TEPC_TOP | Shunt Cap\Reactor\ SVD¿s - Shunt Mvar limits updated in several substations to corrected values | 22EMS24881
203 | TEPC_TOP | Transmission Line - Removal of line 125 as no longer TEP owned | 22EMS24882
204 | TEPC_TOP | Substation\Load - Removal of DMP expansion yard and relocation of DMPGT generator | 22EMS24883
205 | TEPC_TOP | Substation\Load - Included 46kv and 14kv bus and line to South station, this needed to prevent isolation of Fort_Hua station due to Vail side disconnect as occurred in October | 22EMS24884
206 | TEPC_TOP | Generator - Increase in MW high limit for generators 2A, 2B, 2C | 22EMS25371
207 | TEPC_TOP | Transmission Line - Correction of Springerville ties to PNM and SRP as PNM owns 100% of Gen3 and SRP owns 100% of Gen4 | 22EMS25372
208 | TEPC_TOP | Breaker(s)\ Disconnect(s) - New breakers and disconnects in West Wing | 22EMS25373
209 | TEPC_TOP | Shunt Cap\Reactor\ SVD¿s - Shunt Mvar limits updated in several substations to corrected values | 22EMS25374
210 | TEPC_TOP | Transmission Line - Removal of line 125 as no longer TEP owned | 22EMS25375
211 | TEPC_TOP | Substation\Load - Removal of DMP expansion yard and relocation of DMPGT generator | 22EMS25376
212 | TEPC_TOP | Substation\Load - Included 46kv and 14kv bus and line to South station, this needed to prevent isolation of Fort_Hua station due to Vail side disconnect as occurred in October | 22EMS25377
213 | TPWR_BA | Breaker(s)\ Disconnect(s) - Map new ICCP IDs for the 10_432 and 10_433 disconnects | 22EMS24687
214 | TPWR_BA | Breaker(s)\ Disconnect(s) - Map new ICCP IDs for the 10_301 and 10_303 breakers | 22EMS24688
215 | TPWR_BA | Breaker(s)\ Disconnect(s) - Map new ICCP IDs for the 10_31 breaker | 22EMS24689
216 | WALC | WALC Incremental Updates | 23EMS25805
217 | WALC | DAVIS | 23EMS26345