## Implementation Milestones
Calendar | Release / Implementation (Updated Monthly) | Deployment | Market Simulation Start - End |  | Activation | Project Manager
Independent 2020 | Nodal Pricing Model – Advisory Service for PacifiCorp | Dec 2020 | 2020-10-05 | 2020-11-13 | 2021-01-01 | Mohan Koya
| Hybrid Resources Phase 1 | TBD | TBD | TBD | TBD | Wayne Magon
| Aliso Canyon Phase 5 - Dynamic Competitive Path Assessment | 2020-10-01 | 2020-09-30 | 2020-10-14 | 2020-11-20 | John Williams
| Intertie Deviation Settlement | 2020-12-01 | 2020-10-05 | 2020-11-13 | 2021-01-01 | David Luk
Fall 2020 | Commitment Cost Enhancement Tariff Clarifications | 2020-10-01 | 2020-07-27 | 2020-09-04 | 2020-07-20 | Brenda Smith
| Commitment Costs and Default Energy Bid Enhancements Phase 1 | 2020-03-26 | 2020-07-27 | 2020-09-04 | 2020-10-01 | Raymond Riley
| Energy Storage and Aggregated Distributed Energy Resource, Phase 3B | 2020-10-01 | 2020-07-27 | 2020-09-04 | 2020-10-01 | Mohan Koya
| EIM Enhancements 2020 | 2020-10-01 | 2020-07-27 | 2020-09-04 | 2020-10-03 | David Luk
| FERC Order 841 - FERC Requested Adjustments | 2020-10-01 | 2020-07-27 | 2020-09-04 | 2020-10-01 | Brenda Smith
| FRP Improvements - Buffer and Min | 2020-10-01 | 2020-07-27 | 2020-09-04 | 2020-10-01 | Brenda Smith
| ADS User Interface Replacement | 2020-10-01 | 2020-07-27 | 2020-09-04 | 2020-10-01 | John Williams
| Dispatch Operating Target Tariff Clarifications | 2020-10-01 | 2020-07-27 | 2020-09-04 | 2020-10-01 | John Williams
| Excess Behind the Meter Production | 2020-10-01 | 2020-07-27 | 2020-09-18 | 2021-01-01 | Ray Riley
| Market Settlement Timeline Transformation | 2020-10-01 | 2020-07-27 | 2020-09-18 | 2021-01-01 | David Luk
Spring 2021 | EIM - Public Service Company of New Mexico | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | Ayman Fattah
| EIM - Northwestern Energy | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | Kenneth Swain
| EIM - LADWP | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | Joanne Alai
| EIM - Turlock Irrigation District | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | David Luk
| EIM - BANC Ph2/WAPA | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | Ayman Fattah
2021 | System Market Power Mitigation | TBD | TBD | TBD | TBD | Adrian Chiosea
| Variable Operations and Maintenance Cost Review | TBD | TBD | TBD | TBD | Raymond Riley
Fall 2021 | Resource Adequacy Enhancements | 2021-10-01 | 2021-07-26 | 2021-09-03 | 2021-10-01 | Deann MacDougall
| Energy Storage and Aggregated Distributed Energy Resource Phase 4 | 2021-10-01 | 2021-07-26 | 2021-09-03 | 2021-10-01 | Adrian Chiosea
| Import Bidding and Market Parameters | 2021-10-01 | 2021-07-26 | 2021-09-03 | 2021-10-01 | Raymond Riley
| FRP Improvements - Deliverability | 2021-10-01 | 2021-07-26 | 2021-09-03 | 2021-10-01 | Adrian Chiosea
| Contingency Modeling Enhancements - Transmission | 2021-10-01 | 2021-07-26 | 2021-09-03 | 2021-10-01 | Mohan Koya
Spring 2022 | EIM - Avista | 2022-04-01 | 2021-12-01 | 2022-01-31 | 2022-04-01 | Kenneth Swain
| EIM - Tucson Electric Power | 2022-04-01 | 2021-12-01 | 2022-01-31 | 2022-04-01 | Adrian Chiosea
| EIM - Tacoma Power | 2022-04-01 | 2021-12-01 | 2022-01-31 | 2022-04-01 | Kenneth Swain
| EIM - Bonneville Power Administration | 2022-04-01 | 2021-12-01 | 2022-01-31 | 2022-04-01 | Joanne Alai
| EIM - Xcel Energy - Colorado | 2022-04-01 | 2021-12-01 | 2022-01-31 | 2022-04-01 | Adrian Chiosea
TBD | Day Ahead Market Enhancements | TBD | TBD | TBD | TBD | Adrian Chiosea
| Commitment Costs and Default Energy Bid Enhancements Phase 2 | 2022-10-01 | 2022-07-25 | 2022-09-02 | 2022-10-01 | Raymond Riley
| Extend Day-Ahead Market Enhancements to EIM Entities | 2022-10-01 | 2022-07-25 | 2022-09-02 | 2022-10-01 | Adrian Chiosea