## Implementation Milestones
Calendar | Release / Implementation (Updated Monthly) | Deployment | Market Simulation Start - End |  | Activation
Summer 2024 | Transmission Service & Market Scheduling Priorities Phase 2 | Summer 2024 | 2024 | 2024 | Summer 2024
| Transmission Exchange Agreement | Summer 2024 | 2024 | 2024 | Summer 2024
2024 | WEIM Resource Sufficiency Evaluation Enhancements Phase 2 Track 2 | 2024-02-21 | January 2024 | January 2024 | 2024-02-21
| Hybrid Resources Phase 2C - RIMS | Q3 2024 | Q2 2024 | Q2 2024 | Q3 2024
| Congestion Revenue Rights System Upgrade | 2024-07-23 | May 2024 | June 2024 | July 2024
| FERC 881 - Managing Transmission Line Ratings Track 1 | Q3 2024 | 2024 | 2024 | Q3 2024
| FERC 881 - Managing Transmission Line Ratings Track 2 | Q4 2024 | 2024 | 2024 | Q4 2024
Spring 2026 | Day-Ahead Market Enhancements | 2025-10-01 | 2025-06-02 | 2025-08-22 | 2026-05-01
| Extended Day-Ahead Market | 2025-10-01 | 2025-09-01 | 2026-01-16 | 2026-05-01
| EDAM ISO BAA Participation Rules Track A | Spring 2026 | 2025 |  | Spring 2026
| Extended Day-Ahead Market On-Boarding - Pacificorp | Spring 2026 | 2025 |  | Spring 2026
| WEIM - Berkshire Hathaway Energy Montana | Spring 2026 | December 2025 | January 2026 | Spring 2026