## PGaE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013 | 2025 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | In-Service | N/A | 2018-10-16 | In-Service
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2022 | 2022-07-06 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | In-Service | N/A | 2021-07-01 | In-Service
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 |  | 2023 |  | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | In-Service | N/A | 2021-08-03 | In-Service
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023 | 2026 | 2022-08-31 | 2022-07-29 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-11 | In-Service | N/A | 2021-07-26 | In-Service
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015 | 2022 | 2022-11-01 | 2023-03-15 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 | 2022-09-22 | In-Service
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019 | 2023 | 2023-01-13 | 2023-01-16 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 | 2022-09-22 | In-Service
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E | 2018-2019 | 2023 | 2023 | 2023-10-31 | 2023-04-05 | 2023-03-28 | 2023-05-01 | 2023-06-13 | 2023-07-27 | In-Flight | N/A | 2022-04-19 | Q2 2023: In construction. On track to planned In-service date.
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018 | 2022 | 2022-12-21 | 2022-12-12 | 2022-10-19 | 2023-10-31 | 2023-10-31 | 2023-10-31 | In Flight | N/A | 2020-04-30 | Q2-2023: No date changes at this time.
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2027 | 2027-06-28 | 2025-11-12 | 2026-04-09 | 2026-08-07 | 2026-10-02 | 2023-11-22 | In-Flight | TBD | 2023-08-16 | Q2: Improved ISD
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020 | 2022 | 2022-03-01 | 2022-12-14 | 2022-12-14 | 2024-02-23 | 2023-12-19 | 2023-11-27 | In-Flight | NOC: AL 5293-E | 2021-01-05 | Q2-2023: schedule/construction sequencing date adjustments.
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015 | 2022 | 2022-12-23 | 2023-03-10 | 2023-05-31 | 2023-05-31 | 2023-12-29 | 2023-12-29 | In-Flight | NOC: AL 5872E | 2021-06-01 | Q2-2023: No date changes at this time.
Giffen Line Reconductoring Project | PG&E | 2018-2019 |  | 2023 | 2023-01-13 | 2023-01-19 | 2023-01-11 | 2024-01-17 | 2024-01-17 | 2024-01-17 | In Flight | NOC: AL 6600-E | 2023-11-02 | Q2-2023: No date changes at this time.
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021 | 2023 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2022-12-30 | 2024-05-31 | 2024-03-27 | In-Flight | NOC: AL 5390-E | 2022-01-17 | Q2-2023: No date changes at this time.
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA_230KV BUS REACTORS C – D | PG&E | 2018-2019 | 2023 | 2023 | 2023-10-31 | 2023-10-27 | 2023-09-28 | 2023-11-29 | 2023-12-19 | 2024-03-29 | In-Flight | N/A | 2023-06-13 | Q2 2023: In construction. Schedule/construction sequencing date adjustments. On track to planned In-service date.
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017 | 2024 | 2024-12-27 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | In-Flight | NOC: AL 6047-E | 2022-06-01 | Q2-2023: No date changes at this time.
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025 | 2025 | 2025-03-28 | 2024-06-03 | 2024-04-30 | 2024-04-30 | 2024-07-12 | 2024-08-30 | In-Flight | N/A | 2023-04-10 | Q2-2023: schedule/construction sequencing date adjustments.
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | 2024 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | In-Flight | NOC - TBD on Filing Date | 2023-06-12 | Q2-2023: schedule/construction sequencing date adjustments.
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013 | 2025 | 2023-09-22 | 2023-11-06 | 2024-03-07 | 2024-03-20 | 2024-06-20 | 2024-10-25 | In-Flight | TBD | 2024-08-09 | Q2-2023: This project has been delayed due to 2023 funding limitations. Work is planned to resume in 2024.
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019 | 2022 | 2022-11-01 | 2023-04-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | Initiating | TBD | 2024-01-30 | Q2-2023: No date changes at this time.
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023 | 2023 |  | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | Initiating | TBD | 2023-10-01 | Q2-2023: No date changes at this time.
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014 | 2023 | 2023-12-29 | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-13 | 2024-12-13 | In-Flight | N/A | 2019-07-09 | Q2-2023: No date changes at this time.
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024 | 2027 | 2027-06-28 | 2026-01-14 | 2026-06-19 | 2026-10-19 | 2025-01-15 | 2025-01-31 | In-Flight | TBD | 2024-11-19 | Q2-2023: No date changes at this time.
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 |  | 2023 | 2023-03-04 | 2023-05-19 | 2023-07-18 | 2023-11-21 | 2023-10-30 | 2025-04-01 | In-Flight | N/A | 2021-11-16 | Q2-2023: Moraga 115 kV Bus Upgrade delayed due to 2023 funding limitations. Work is planned to resume in 2024. Moraga Bank 3 SW replacement operational 6/30/22
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025 | 2025 |  | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | Initiating | TBD | 2024-10-01 | Q2-2023: No date changes at this time.
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014 | 2025 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | In-Flight | PTC: A.18-06-004 | 2024-01-02 | Q2: Improved ISD
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025 | 2025 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | In-Flight | TBD | 2024-02-07 | Q2-2023: T-line Scoping being reviewed for approval. Procurements underway. Long Lead material estimates in preparation for ordering. Substation scoping approved. Civil design under way. Breakers ordered - 80-week lead time. CCVTs ordered - 60-week lead time. Switches 28-30-week lead time in process of ordering. Scope has increased due to triggering new control building, telecommunications pathways and equipment. CPUC permitting, Environmental, Biological, and Cultural requirements being evaluated.
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013 | 2025 | 2025-05-01 | 2025-05-01 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | In-Flight | N/A | 2021-04-07 | Q2-2023: No date changes at this time.
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016 | 2024 | 2024-10-11 | 2024-10-31 | 2024-08-26 | 2024-12-09 | 2025-05-30 | 2025-06-04 | In-Flight | N/A | 2024-08-15 | Q2-2023: schedule/construction sequencing date adjustments.
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016 | 2024 | 2024-08-06 | 2024-07-17 | 2024-05-08 | 2025-07-04 | 2025-07-04 | 2025-07-04 | In-Flight | N/A | 2018-06-18 | Q2-2023: No date changes at this time.
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019 | 2024 | 2024-10-02 | 2025-03-31 | 2025-02-14 | 2025-05-15 | 2025-08-11 | 2025-07-18 | In-Flight | N/A | 2025-03-03 | Q2-2023: No date changes at this time.
Reedley 70 kV Reinforcement (Renamed to Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017 | 2025 | 2025-12-25 | 2025-08-14 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | In Flight | N/A | 2024-02-28 | Q2-2023: Rescoped to Dinuba 70 kV Energy Storage
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019 | 2027 | 2027-04-01 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-05-08 | 2025-10-20 | In Flight | N/A | 2025-03-28 | Q2: Improved ISD
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021 | 2024 | 2024-05-24 | 2024-05-10 | 2024-05-24 | 2025-11-14 | 2025-11-13 | 2025-11-13 | In-Flight | CPCN: A.17-12-021 | 2024-02-07 | Q2-2023: No date changes at this time.
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-31 | 2026-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Initiating | TBD | 2024-12-01 | Q2-2023: No date changes at this time.
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019 | 2024 | 2024-12-01 | 2024-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Initiating | TBD | 2025-10-01 | Q2-2023: No date changes at this time.
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023 | 2026 | 2026-12-31 | 2026-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Initiating | TBD | 2024-12-01 | Q2-2023: No date changes at this time.
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009 | 2024 | 2024-04-30 | 2024-06-30 | 2024-04-30 | 2025-04-17 | 2025-12-31 | 2025-12-12 | In-Flight | N/A | 2022-07-05 | Q2-2023: No date changes at this time.
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023 | 2026 | 2026-07-10 | 2026-08-21 | 2025-08-18 | 2025-12-25 | 2025-12-30 | 2026-02-06 | In-Flight | PTC - TBD on Filing Date | 2025-09-22 | Q2-2023: schedule/construction sequencing date adjustments.
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022 | 2025 | 2025-10-02 | 2025-03-31 | 2024-12-24 | 2026-02-26 | 2026-02-26 | 2026-03-25 | In-Flight | N/A | 2025-11-10 | Q2-2023: This project has been delayed due to 2023 funding limitations. Work is planned to resume in 2024.
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | Initiating | TBD | 2025-02-01 | Q2-2023: No date changes at this time.
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | Initiating | TBD | 2025-05-01 | Q2-2023: No date changes at this time.
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022 | 2026 | 2026-12-01 | 2026-12-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | Initiating | TBD | 2025-10-01 | Q2-2023: No date changes at this time.
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | Initiating | TBD | 2025-05-01 | Q2-2023: No date changes at this time.
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011 | 2025 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2026-06-17 | In-Flight | N/A | 2025-04-08 | Q2-2023: Delay due to Prioritization.
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2026-06-01 | Q2-2023: No date changes at this time.
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022 | 2026 | 2026-05-01 | 2026-05-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2024-10-01 | Q2-2023: No date changes at this time.
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2025-06-01 | Q2-2023: No date changes at this time.
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024 | 2025 | 2025-12-31 | 2025-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2025-12-01 | Q2-2023: No date changes at this time.
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-01 | 2026-12-01 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | Initiating | TBD | 2025-12-01 | Q2-2023: No date changes at this time.
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | In Flight | NOC - May 2024 | 2026-01-23 | Q2-2023: No date changes at this time.
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021 | 2026 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | In Flight | NOC - TBD on Filing Date | 2025-07-24 | Q2-2023: No date changes at this time.
South of Mesa Upgrade | PG&E | 2018-2019 | 2023 | 2026 | 2026-09-03 | 2026-05-26 | 2026-05-26 | 2027-04-01 | 2027-04-01 | 2027-04-01 | In Flight | NOC - Feb 2024 | 2025-10-03 | Q2-2023: No date changes at this time.
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019 | 2024 | 2024-06-06 | 2025-07-03 | 2026-06-23 | 2026-06-23 | 2027-04-07 | 2027-04-07 | In Flight | NOC: AL 5026-E | 2018-11-01 | Q2-2023: This project relies on the Midway 230kV Section D Bus Upgrade project (T.0001650) to be in-serviced to provide a new terminal position for the new 230kV line.
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | Initiating | TBD | 2025-10-01 | Q2-2023: No date changes at this time.
South of San Mateo Capacity Increase | PG&E | 2007 | 2009 | 2027 | 2027-03-01 | 2027-03-01 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | Initiating | TBD | 2026-03-01 | Q2-2023: No date changes at this time.
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016 | 2027 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | In Flight | NOC - TBD on Filing Date | 2025-01-06 | Q2-2023: No date changes at this time.
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020 | 2026 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-16 | In-Flight | N/A | 2022-06-30 | Q2-2023: Delay due to Prioritization. Program consists of 9 individually managed projects
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021 | 2026 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2027-09-29 | 2027-09-29 | In Flight | NOC: AL 5200-E | 2025-07-29 | Q2-2023: No date changes at this time.
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025 | 2027 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-12-01 | Q2-2023: No date changes at this time.
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-12-01 | Q2-2023: No date changes at this time.
Maple Creek Reactive Support | PG&E | 2009 | 2011 | 2026 | 2026-07-01 | 2026-07-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-12-01 | Q2-2023: No date changes at this time.
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008 | 2029 | 2029-04-01 | 2029-04-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-12-01 | Q2-2023: No date changes at this time.
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-01-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2025-10-01 | Q2-2023: No date changes at this time.
Mosher Transmission Project | PG&E | 2013-2014 | 2017 | 2027 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | In Flight | NOC - April 2026 | 2027-01-20 | Q2-2023: No date changes at this time.
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022 | 2027 | 2027-11-10 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | In-Flight | N/A | 2026-05-13 | Q2-2023: No date changes at this time.
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | In Flight | N/A | 2025-05-12 | Q2-2023: No date changes at this time.
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022 | 2028 | 2028-12-01 | 2028-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | Initiating | TBD | 2025-01-31 | Q2-2023: No date changes at this time.
Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019 | 2024 | 2024-06-06 | 2027-06-03 | 2027-09-01 | 2027-11-30 | 2028-02-25 | 2028-05-23 | In Flight | NOC: AL 5924-E | 2024-11-01 | Q2-2023: This project has been delayed due to 2023 funding limitations.
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022 | 2028 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | In-Flight | TBD | 2027-02-15 | Q2-2023: No date changes at this time.
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012 | 2027 | 2027-02-01 | 2027-02-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q2-2023: No date changes at this time.
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023 | 2027 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2026-12-01 | Q2-2023: No date changes at this time.
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021 | 2027 | 2027-12-31 | 2027-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q2-2023: No date changes at this time.
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024 | 2027 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q2-2023: No date changes at this time.
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2026-06-01 | Q2-2023: No date changes at this time.
New Manning 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-02-01 | Q2-2023: Project Initiation in development subject to funding available to kick-off in 2023.
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q2-2023: No date changes at this time.
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-10-01 | Q2-2023: No date changes at this time.
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2026-03-01 | Q2-2023: No date changes at this time.
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026 | 2026 | 2026-05-01 | 2026-05-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q2-2023: No date changes at this time.
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017 | 2027 | 2027-06-21 | 2028-12-29 | 2029-01-01 | 2029-01-01 | 2029-01-01 | 2029-01-11 | In-Flight | CPCN Expected Q2 2023 | 2027-02-03 | Q2-2023: No date changes at this time.
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018 | 2027 | 2027-10-20 | 2028-02-16 | 2028-05-16 | 2028-08-14 | 2028-11-09 | 2029-02-05 | In Flight | NOC - April 2026 | 2026-07-22 | Q2-2023: This project has been delayed due to 2023 funding limitations.
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021 | 2025 | 2025-11-19 | 2026-08-18 | 2026-08-18 | 2030-05-23 | 2031-11-19 | 2029-03-30 | In-Flight | NOC - TBD on Filing Date | 2025-07-07 | Q2: Improved ISD
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022 | 2029 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-26 | In Flight | N/A | 2027-07-30 | Q2-2023: No date changes at this time.
Estrella Substation Project | PG&E | 2013-2014 | 2019 | 2026 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | In-Flight | PTC: A.17-01-023 | 2024-10-24 | Q2-2023: The delay in getting the PTC will push the FISD. Delay is also due to prioritization.
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | Initiating | TBD | 2028-12-01 | Q2-2023: No date changes at this time.
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015 | 2030 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-01-31 | 2030-01-31 | 2030-01-31 | Initiating | TBD | 2028-01-01 | Q2-2023: No date changes at this time.
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019 |  |  | 2029-12-04 | 2029-12-04 | 2029-12-04 | 2029-08-28 | 2032-10-21 | Cancelled | CPCN - TBD on Filing Date | 2026-07-15 | Q2-2023: Cancelled per CAISO 2023 TPP
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020 |  |  | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | In Flight | CPCN - TBD on Filing Date | 2030-03-25 | Q2-2023: Updated ISD reflects approval in CAISO 2023 TPP and current prioritization
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023 |  |  |  | TBD | TBD | TBD | TBD | On-Hold (CAISO) | TBD | TBD | Q2-2023: Project on CAISO Hold

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Laguna Bell Corridor Upgrade | SCE | 2015 | 44196 | 44621 | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-05-01 |  |  | In-Service | N/A | N/A | Currently in-service; completed as a portion of Mesa 500 kV Substation Loop-In
Moorpark-Pardee No. 4 230 kV Circuit | SCE | 2018 | 44196 | 44348 | 2022-03-01 | 2022-05-31 | 2022-05-31 | 2022-05-31 |  |  | In-Service | N/A | N/A | In-service January 2022
Mesa 500 kV Substation Loop-In | SCE | 2014 | 44166 | 44621 | 2022-05-01 | 2022-05-31 | 2022-05-22 | 2022-05-22 |  |  | In-Service | N/A | N/A | In-service May 2022
Lugo-Mohave series capacitor upgrade | SCE | 2013 | 2016 | 44713 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | Construction | 43221 | 2020-12-01 | Most of the project expected in-service by June 2023 with full compensation by December 2023
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2013 | 2016 | 44713 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | Construction | 43221 | 2020-12-01 | Most of the project expected in-service by June 2023 with full compensation by December 2023
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 40878 | 45627 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | Design | Exempt | 2024-10-01
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2017 | 43465 | 45078 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | 2025-01-01 | Construction | Exempt | Construction started | Joint SCE/LADWP project. SCE completed raising its towers and LADWP's are in progress. Substation upgrades (breakers and terminal equipment) require synchronizing outages with LADWP.
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | 2029-06-01 | Licensing | 2009-09-01 | 2026-06-01 | Alberhill dates contingent on licensing
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 46296 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | 2028-12-01 | Design | 2015-04-01 | 2024-05-24 | Project continues on hold
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2020 | 45078 | 45047 | June-23 * | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | Construction | Exempt | 2022-10-22 | Joint SCE/LADWP project. ISD for SCE’s portion of the project remains June 2024. Expected ISD of June 2025 includes LADWP's portion of the project.
Tie line Phasor Measurement Units | SCE | 2017-2018 | 44166 | 44531 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2024-02-28 | Construction | N/A | Construction started | The in-service dates range from September 2022 to February 2024
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 |  | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | 2024-05-31 | Design | Pending | 2023-11-01
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 |  | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | Engineering | N/A | 2024-04-01
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 |  | New | Pending | Pending | 2025-06-30 | 2025-06-01 | 2025-06-01 | Design | N/A | 2024-03-01 | Phased in-service date.
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 |  | New | Pending | Pending | Pending | 2025-04-01 | 2025-04-01 | Design | N/A | 2024-06-01
Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 |  |  |  |  | New | Pending | 2026-06-01 | Design | N/A | 2025-05-29
Mira Loma 500 kV CB Upgrade Project | SCE | 2022-2023 | 2026 |  |  |  |  | New | Pending | Pending | Initiation | N/A | Pending

## SDGaE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 44362 | 44531 | 2023-05-01 | 2021-11-01 | 2021-10-22 |  |  |  | Close-out | Exempt | 2021-05-17
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 42522 | 44713 | 2022-06-01 | 2022-12-14 | 2022-12-13 | Completed | Completed | Energized | Close-out | 42599 | 2020-06-10
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 43252 | 44866 | 2023-06-27 | 2023-08-25 | 2023-10-24 | Completed | Completed | Energized | Close-out | Exempt | 2021-07-26
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 41426 | 44652 | 2022-05-02 | 2022-05-31 | 2022-05-15 | 2022-05-15 | 2022-05-15 | Energized | Close-out | Exempt | 2022-02-04
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 44362 | 44470 | 2022-12-01 | 2022-12-09 | 2022-12-27 | 2022-11-18 | 2022-11-18 | Energized | Close-out | 42914 | 2021-01-19
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 42156 | 44682 | 2022-09-01 | 2022-12-14 | 2022-12-27 | 2023-02-08 | 2023-02-08 | Energized | Close-out | 43054 | 2022-01-03
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 42156 | 45047 | 2023-12-01 | 2024-05-28 | 2024-05-28 | 2024-11-05 | 2024-11-05 | 2025-08-07 | Construction | 41047 | 2018-06-29
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 43252 | 46539 | 2024-05-02 | 2024-12-23 | 2024-12-23 | 2024-06-25 | 2024-06-25 | 2024-06-25 | Design | 2023-08-22 | 2024-08-19
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 44713 |  |  |  | 2022-08-24 | 2024-12-17 | 2024-12-17 | 2024-10-18 | Design | TBD | TBD
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 2016 | 45017 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2023-02-13 | 2023-02-13 | 2026-02-24 | Design | 42485 | 2024-08-09
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 44362 | 45627 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-06-08 | 2026-06-08 | 2026-07-29 | Design | 45170 | 2024-03-01
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 42156 | 46419 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2026-11-10 | 2026-11-10 | 2026-12-09 | Design | Exempt | 2025-03-20
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 44364 | 46722 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-11-14 | 2027-11-14 | 2027-11-14 | Planning | 46227 | 2027-04-12
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 44713 |  |  |  | 2024-08-15 | 2029-02-27 | 2029-02-27 | 2029-04-30 | Planning | TBD | 2024-07-19

## VEA_GLW
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 1905-07-13 | 2021-09-01 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service |  |  | N/A | 2021 | The GridLiance 230kV Ring Bus and associated 230kV Transmission Line loop-in were placed in service Nov-2021. The VEA 138kV Station upgrades were placed in service Dec-2021. The 230/138kV Transformer was delivered to site and mounted on the foundation Oct-2021. The Transformer failed testing at-site and was required to be shipped back to the factory for repair. Expected in-service date for the Transformer is Q2-2022.
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 |  | 2023-06-23 | 2023-09-23 | In Flight | N/A | Sept-21
GLW/VEA area upgrades | VEA/GLW | 2021-2022 | TBD |  | N/A | TBD | TBD | TBD | TBD |  | Permitting, engineering and design | N/A | TBD

## DCRT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | Inflight | Approved

## LSPower
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-12-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-24 | 2024-06-01 | In-Flight | 2021-02-01 | 2023-02-01
Round Mountain 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-24 | 2024-12-01 | In-Flight | 2022-04-01 | 2023-08-01
Manning Substation | LS Power | 2021-2022 | 2028 | [5 empty] | 2027-12-01
Collinsville Substation | LS Power | 2021-2022 | 2028 | [5 empty] | 2027-12-01
San Jose Area HVDC 230 kV Line (Newark - NRS) | LS Power | 2021-2022 | 2028 | [5 empty] | 2028-04-01
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | LS Power | 2021-2022 | 2028 | [5 empty] | 2028-05-01

## CitizensEnergy
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | In-Flight |  | 2023-07-21