## PGaE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date (2020-2021 Transmission Plan) | Current Expected In-service date (12/20 BWP) | Project Status | Notes
San Bernard – Tejon 70 kV Line Reconductor | PG&E | 2013-2014 | 2018-05-01 | 2020-12-01 | 2020-01-23 | Operational
Gregg-Herndon #2 230 kV Line Circuit Breaker Upgrade | PG&E | 2012-2013 | 2015-03-01 | 2020-01-01 | 2020-01-24 | Operational
Fulton-Hopland 60 kV Line Project | PG&E | 2017-2018 | 2019-06-01 | 2020-03-01 | 2020-03-30 | Operational | Original project was the "Fulton-Fitch Mountain 60 kV Line Conductor"approved in 2009 Transmission Plan. The project was rescoped and renamed in the 2017-2018 Transmission Plan.
West Point – Valley Springs 60 kV Line | PG&E | 2007 | 2009-05-01 | 2020-07-01 | 2020-05-05 | Operational
Pease 115/60 kV Transformer Addition and Bus Upgrade | PG&E | 2012-2013 | 2016-05-01 | 2020-03-01 | 2020-12-10 | Operational
South of Palermo 115 kV Reinforcement Project | PG&E | 2010-2011 | 2014-05-01 | 2021-11-01 | 2021-01-14 | Operational
Los Esteros 230 kV Substation Shunt Reactor | PG&E | 2015-2016 | 2020-12-01 | 2021-05-01 | 2021-03-18 | Operational
Kern PP 230 kV Area Reinforcement | PG&E | 2011-2012 | 2016-03-01 | 2021-03-01 | 2021-03-29 | Operational
Semitropic – Midway 115 kV Line Reconductor | PG&E | 2012-2013 | 2016-05-01 | 2021-03-01 | 2021-03-29 | Operational
Wilson 115 kV SVC | PG&E | 2015-2016 | 2020-12-01 | 2021-04-01 | 2021-05-10 | Operational
Wheeler Ridge Voltage Support | PG&E | 2011-2012 | 2016-05-01 | 2021-04-01 | 2021-07-02 | Operational
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020 | 2021-04-01 | 2022-03-01 | Construction | 12/6/21 Reconductoring is Operational. Sub work ISD 3/22
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2023 | 2022-07-06 | Construction
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018-03-01 | 2021-12-01 | 2022-12-21 | Construction
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015-03-01 | 2022-04-01 | 2022-12-23 | Construction
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019-02-01 | 2022-02-01 | 2023-01-13 | Engineering
Oakland Clean Energy Initiative | PG&E | 2017-2018 | TBD | 2022-08-01 | 2023-03-04 | Construction
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021-05-01 | 2023-04-01 | 2023-03-30 | Engineering
Tesla 230 kV Bus Series Reactor project | PG&E | 2018-2019 | 2023 | 2023-12-01 | 2023-08-17 | Engineering
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014-03-01 | 2025-01-01 | 2023-12-29 | Construction
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009-05-01 | 2024-06-01 | 2024-04-30 | Engineering
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | 2024-12-01 | 2024-05-06 | Engineering
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021-12-01 | 2024-01-01 | 2024-05-24 | Engineering
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019-05-01 | 2024-05-01 | 2024-06-06 | Construction
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016-05-01 | 2023-03-01 | 2024-08-06 | Construction
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019-11-01 | 2023-11-01 | 2024-10-02 | Engineering | Original project was the "Cottonwood 115 kV substation shunt reactor" approved in 2015-2016 Transmission Plan. The project was rescoped and renamed in 2017-2018 Transmission Plan.
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016-05-01 | 2024-09-01 | 2024-10-11 | Engineering
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019 | 2024-06-01 | 2024-12-01 | Planning
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017 | 2024-04-01 | 2024-12-27 | Engineering
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011-05-01 | 2026-01-01 | 2025-01-29 | Planning
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | 2024-12-01 | 2025-03-28 | Engineering
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase | PG&E | 2010-2011 | 2013-05-01 | 2021-05-01 | 2025-05-01 | Construction | Scope of work being done in Kern PP 230 kV Area Reinforcement Project (in-service March 2021) and Midway 230kV Bus Section D Upgrade Project (in-service April 2025)
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014-05-01 | 2026-01-01 | 2025-06-23 | Engineering
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022 | 2027-12-01 | 2025-10-02 | Engineering
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2023-05-01 | 2025-11-19 | Planning | Original project was the "Cottonwood-Red Bluff No2 60 kV Line Project and Red Bluff Area 230/60 kV Substation Project" approved in 2010-2011 Transmission Plan. The project was rescoped and renamed in 2017-2018 Transmission Plan.
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013-05-01 | 2025-03-01 | 2025-12-22 | Engineering
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021-12-01 | 2026-07-01 | 2026-04-27 | Engineering
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026 | 2026 | 2026-05-01 | Planning
Estrella Substation Project | NEET West / PGaE | 2013-2014 | 2019-05-01 | 2026-11-01 | 2026-05-27 | Engineering
Maple Creek Reactive Support | PG&E | 2009 | 2011-03-01 | 2026-07-01 | 2026-07-01 | Planning | Rescoped to Willow Creek 60 kV Substation
Vaca Dixon Area Reinforcement | PG&E | 2017-2018 | 2023-12-01 | 2025-02-01 | 2026-07-10 | Construction | Original project was the "Vaca – Davis Voltage Conversion Project" approved in 2010-2011 Transmission Plan. The project was rescoped and renamed in 2017-2018 Transmission Plan. Portion w/ Vaca Dixon Bk 5 replacement FISD in Aug 2022; Plainfield project is in Engineering, rest are on hold due to incomplete project scope
South of Mesa Upgrade | PG&E | 2018-2019 | 2023 | 2027-12-01 | 2026-09-03 | Engineering
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2028-05-01 | 2026-09-29 | Engineering
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-01 | Planning
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020-12-01 | 2021-12-01 | 2026-12-01 | Planning
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022 | 2024-12-01 | 2026-12-01 | Planning
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024 | 2024 | 2026-12-01 | Planning
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2025-04-01 | 2026-12-16 | Engineering
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021-01-01 | 2024-01-01 | 2026-12-31 | Engineering
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012-03-01 | 2027-02-01 | 2027-02-01 | Planning
South of San Mateo Capacity Increase | PG&E | 2007 | 2009-05-01 | 2027-03-01 | 2027-03-01 | Planning
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017-03-01 | 2026-07-01 | 2027-06-21 | Engineering
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024 | 2024 | 2027-06-28 | Planning
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2023 | 2027-06-28 | Planning
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016-03-01 | 2027-12-01 | 2027-08-09 | Engineering
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018-05-01 | 2027-12-01 | 2027-10-20 | Engineering
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022 | 2027-12-01 | 2027-11-10 | Planning
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024 | 2024 | 2027-12-01 | Planning
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023-12-01 | 2027-12-01 | 2027-12-01 | Planning | Original project was the "Ignacio-Alto Voltage Conversion Project" approved in 2011-2012 Transmisison Plan. The project was rescoped and renamed in the 2017-2018 Transmission Plan.
Mosher Transmission Project | PG&E | 2013-2014 | 2017-12-01 | 2022-03-01 | 2027-12-15 | Engineering
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2021-12-01 | 2027-12-31 | Planning
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022 | 2028-12-01 | 2028-06-26 | Planning
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022 | 2028-12-01 | 2028-12-01 | Planning
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008 | 2029-04-01 | 2029-04-01 | Planning
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022-05-01 | 2029-09-01 | 2029-06-21 | Engineering
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015-05-01 | 2030-12-01 | 2030-12-01 | Planning
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020-05-01 | On hold | On Hold | On Hold
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019-12-01 | On hold | On Hold | On Hold
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023 | On hold | On Hold | On Hold
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019-06-01 | 2022-11-01 | 2022-11-22 | Planning
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015-12-01 | 2022-11-01 | 2022-11-01 | Planning
Giffen Line Reconductoring Project | PG&E | 2018-2019 | TBD | 2024-04-01 | 2023-01-01 | Engineering
Reedley 70 kV Reinforcement (Renamed to Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017-05-01 | 2023-05-01 | 2025-12-01 | Engineering | Rescoped to Dinuba 70 kV Energy Storage
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019-10-01 | 2027-04-01 | 2027-04-01 | Engineering
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022 | 2026-05-01 | 2026-05-01 | Planning
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023 | 2026 | 2026 | Planning
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024 | 2024 | 2025 | Planning
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025-07-17 | 2027 | 1905-07-19 | Planning
Contra Costa 230 kV Line Terminals Reconfiguration | PG&E | 2021-2022 |  | 2025-05-01 | 2025-05-01

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date (2020-2021 Transmission Plan) | Current Expected In-service date | Notes
Laguna Bell Corridor Upgrade | SCE | 2015 | 2020-12-31 | 2022-03-01 | 2020-05-01 | Currently in-service; completed as a portion of Mesa 500 kV Substation Loop-In
Moorpark-Pardee No. 4 230 kV Circuit | SCE | 2018 | 2020-12-31 | 2021-06-01 | 2022-03-01
Mesa 500 kV Substation Loop-In | SCE | 2014 | 2020-12-01 | 2022-03-01 | 2022-05-01
Lugo-Mohave series capacitor upgrade | SCE | 2013 | 2016 | 2022-06-01 | 2023-04-01
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2013 | 2016 | 2022-06-01 | 2023-06-01
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2017 | 2018-12-31 | 2023-06-01 | 2025-01-01
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2020 | 2023-06-01 | 2023-05-01 | June-23 *
Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 2021-12-01 | TBD
* Joint SCE/LADWP project. Date indicated only includes SCE scope

## SDGaE
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date (2020-2021 Transmission Plan) | Current Expected In-service date | Notes
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-05-01 | 2022-09-01
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-06-01 | 2022-06-01
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2027-06-01 | 2024-05-02
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-12-01 | 2023-05-01
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2022-11-01 | 2023-06-27
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2023-05-01 | 2023-12-01
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-06-01 | ISD currently under evaluation
TL13834 Trabuco-Capistrano 138 kV Line Upgrade | SDG&E | 2013-2014 | 2018-06-01 | 2021-12-01 | 2023-12-01
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2028-06-01 | ISD currently under evaluation
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-04-01 | 2022-05-02
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2021-10-01 | 2022-12-01
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-06-01
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 1905-07-08 | 2023-04-01 | 2024-06-12

## VEA_GLW
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date (2020-2021 Transmission Plan) | Current Expected In-service date | Notes
Bob-Mead 230 kV Reconductoring | GLW | 2017-2018 | 2020-12-01 | 2021-01-01 | 2020-12-20 | In-service
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 2021 | 2021-09-01 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | The GridLiance 230kV Ring Bus and associated 230kV Transmission Line loop-in were placed in service Nov-2021. The VEA 138kV Station upgrades were placed in service Dec-2021. The 230/138kV Transformer was delivered to site and mounted on the foundation Oct-2021. The Transformer failed testing at-site and was required to be shipped back to the factory for repair. Expected in-service date for the Transformer is Q2-2022.

## DCRT
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date (2020-2021 Transmission Plan) | Current Expected In-service date | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2021-12-01 | 2024-04-01

## LSPower
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date (2020-2021 Transmission Plan) | Current Expected In-service date | Notes
Gates 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-12-01 | 2024-06-01
Round Mountain 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-12-01 | 2024-12-01

## CitizensEnergy
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date (2020-2021 Transmission Plan) | Current Expected In-service date | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023