## Sheet1 (hidden)
Submission Date
Project Name
Queue Position
[Interconnection Customer] provides the following status updates on the progress of the Project:
Permitting Complete | 1 | Environmental or Land Use Permit Status What permits are required for the project (examples: CUP, CEQUA, SF299, Cost Recovery Account, EIR, EIS)? Which permits are approved? Which are still outstanding? What is the estimated approval date for the outstanding permits?
Third Posting | 2 | Financing Status Please provide a summary of the recent financing activities for the project and proof that financial security has been posted per the terms of the Interconnection Agreement.
| 3 | PPA Information Please provide the following PPA information, if applicable: 1. Point of Interconnection (POI) 2. MW capacity (allowing differences in utility defined project size before transformation and line losses) 3. Fuel type and technology 4. Site location
| 4 | Land Acquisition Please provide land acquisition status or proof that site exclusivity is current.
Written Notice to Proceed | 5 | Written notice to proceed Have you provided the notification to the Participating Transmission Owner (PTO) to design, procure, and construct transmission upgrades? If not, when is it due?
| 6 | Equipment Ordered Have you ordered equipment to construct your project?
| 7 | Project Modification Have any of the project facts changed since the facilities study or phase 2 results were published?
| 7.1 | If yes, have these changes been reviewed through the material modification review process?
| 8 | Affected System Are there any Identified Affected Systems for this project?
| 8.1 | If yes, which Affected Systems have you contacted and what were the responses?
| 9 | Metering and Telemetry Have you completed the design for your metering and telemetry?
Submittal of Initial Specs | 9.1 | If yes, have you contacted NewResourceImplementation@caiso.com?
| 9.2 | If not, what is the estimated completion date for metering and telemetry design?
UDC Milestone | 10 | Station Power Please describe the project’s plan for receiving station power. Has the project made arrangements for station power with the local retail service provider?
| 11 | In-service Date What is the in-service date specified in the Interconnection Agreement?
In-Service | 11.1 | Is the project still on track to meet this in-service date? If not, please provide the projected in-service date with an explanation here and submit a request for a material modification assessment to queuemanagement@caiso.com with an explanation of the cause of the delay.
| 11.2 | Is the project within nine (9) months of its in-service date?
| 11.3 | If yes, have you contacted NewResourceImplementation@caiso.com to begin the implementation process? Are you in an upcoming Full Network Model data base build?
| 11.4 | List the Full Network Model Build number, if applicable.
| 12 | Initial Synchronization What is the initial synchronization date specified in the Interconnection Agreement?
Initial Synchronization | 12.1 | Is the project still on track to meet this initial synchronization date? If not, please provide the projected initial synchronization date and an explanation here with the cause of the delay.
| 13 | ISO Program Participation
| 13.1 | Multi-stage generator?
| 13.1a | If yes, are you on track to meet the program’s requirements?
| 13.2 | QF – qualifying facility?
| 13.2a | If yes, are you on track to meet the program’s requirements?
| 13.3 | RA – resource adequacy?
| 13.3a | If yes, are you on track to meet the program’s requirements?
| 13.4 | ISO Station Power Program?
| 13.4a | If yes, are you on track to meet the program’s requirements?
| 13.5 | Use-limited resource?
| 13.5a | If yes, are you on track to meet the program’s requirements?
BAA Notification | 14 | BAA Is the current date within three (3) months of the Initial Synchronization Date outlined in the contract or the actual Initial Synchronization Date?
| 14.1 | If yes, has the IC provided the CAISO and PTO with Balancing Authority Area notice?
NU/ IFs Construction Start | 15 | Construction Status for the Project Please provide a description of construction status. Has the project broken ground? Has construction started on interconnection facilities and stand alone network upgrades (if any)?
| 15.1 | Is the construction schedule for the project and interconnection facilities on time? Please provide photos if practical.
| 16 | Testing Status Has your project started putting test energy on the grid?
| 16.1 | If yes, what percent complete is the testing? Have any major issues come up? Is there any risk to the contract milestone dates?
| 17 | Commercial Operation for Markets Is the project planning to declare Commercial Operation for Markets in advance of declaring Commercial Operation as specified in the Interconnection Agreement?
| 17.1 | If yes, please describe the current plan for the block implementation schedule. Has the project executed an Implementation Plan with the CAISO?
COD | 18 | Commercial Operation Date Is the project still on track to meet the Commercial Operation Date (COD) specified in the Interconnection Agreement?
| 18.1 | If not, please provide an explanation here and submit a request for material modification review to queuemanagement@caiso.com with an achievable date and an explanation of the cause of the delay.
| 19 | Point Of Contact/ Ownership Has the primary point of contact, Interconnection Customer of Record, or upstream ownership changed for the project? Who should CAISO Queue Management reach out to with questions?

## Status Report
| This Project Status Report is required to be submitted on a quarterly OR monthly if the project's construction has commenced. Please complete and return to the Queue Management project manager or queuemanagement@caiso.com. NOTE: If the Project is approaching or within 6 months of its Initial Synchronization Date, and is not expected to be delayed, please also complete the "Prior to Synch" tab. | [5 empty] | Last Updated: 6/1/2023
Status Report Submission Date
Project Name
Queue Number (####)
Interconnection Customer (Entity)
| Primary Customer Contact Name |  | The contact name must be reflected in RIMS or the primary or secondary contact on the Interconnection Customer Delegation of Authority form. If updates are required, please contact the ISO project manager.
| Interconnection Customer to include GIA milestone due dates (Column E) and the status of each milestone below, including notes as applicable. |  | GIA Milestone Date: (LGIA Appendix B or SGIA Attachment 4) | Completed?: Goal = Yes to all | Date Completed: | Comments or Notes:
NU/ IFs Construction Start | 1 | Construction Status for the Project Has the Project broken ground and started construction? If yes, please note that these Status Reports are required monthly once Construction has begun. |  | No
| 2 | Proof of Insurance Has the Project submitted proof of Insurance Coverage to the CAISO? If not, describe in the Notes the expected timeline for providing. |  | No
Permitting Complete | 3 | Environmental or Land Use Permit Have all of the required Permits for the Project been acquired? In the Notes, list all required permits and their current status. |  | No |  |  | If this project has executed multiple PPAs, please type the sum of the total MW capacity procured under all PPAs in item #2. below.
| 4 | Interconnection Financial Security Postings Has the Project submitted its third Interconnection Financial Security posting? |  | No |  |  | 1. PPA POI | 2. PPA MW Capacity | 3. PPA Fuel Type / Technology
| 5 | Power Purchase Agreements (PPA) Has the Project executed a PPA? If yes, describe the PPA(s) in the notes, and define the POI, MW capacity, and fuel type/technology of the PPAs. |  | No
| 6 | Land Acquisition Is the Site Exclusivity documentation current? In the Notes, please provide land acquisition status, including the type of land acquisition and/or term of lease. |  | No | N/A
Written Notice to Proceed | 7 | Written notice to proceed Has the Project provided the notification to the Participating Transmission Owner (PTO) to design, procure, and construct transmission upgrades? If due date is not achievable, describe in the notes the status of the required modification. |  | No
| 8 | Project Modification Requests Has the project completed all modification requests necessary for the proejct to achieve synchronization or commercial operation? If no, describe in the notes what is changing, and the status of any modification requests. |  | No | N/A
| 9 | Affected System Have all Identified Affected Systems provided approval for the Project? In the Notes, list all Affected Systems and their current statuses. NOTE: Documentation showing resolution for Identified Affected Systems must be submitted to Queue Management six months prior to Synchronization of the Project. |  | No
| 10 | Metering and Telemetry Has the Project completed the design for your metering and telemetry? If not, describe in the Notes the estimated completion date for metering and telemetry design. |  | No
UDC Milestone | 11 | Station Power Has the Project made arrangements for station power with the local retail service provider? In the Notes, describe the Project’s plan for receiving station power. |  | No
| 12 | Initial Specifications Has the Project submitted its Initial specification information, including Participating TO’s Transmission System information necessary to allow the Interconnection Customer to select equipment? If not, provide an expected timeline for completion in the Notes. |  | No
| 13 | Final Specifications Has the Project submitted its Final specification information for the Interconnection Customer’s Interconnection Facilities and Project, including System Protection Facilities, to the Participating TO and the CAISO? If not, provide an expected timeline for completion in the Notes. |  | No
| 14 | Interconnection Facilities Have all interconnection facilities and stand alone network upgrades (if any) identified in the Interconnection Agreement been completed? Please identify the list of interconnection facility upgrades and the status of each in the notes. |  | No
| 15 | New Resource Implementation (NRI) Process Has the Project (or blocks of the project) commenced the NRI process? If yes, describe in the Notes the status of the NRI Project in MPAI. |  | No
| 16 | Resource IDs How many Resource IDs does the Project intend to implement? Include # in note cell.
BAA Notification | 17 | In-service Date Is the Project in Service? If date is not achievable, describe in the notes the status of the required modification. |  | No
| 18 | Initial Synchronization Date Has the Project achieved its Initial Synchronization? If no, insert the current Initial Synchronization Date in the Notes. |  | No
| 19 | Commercial Operation for Markets (COM) Is the Project planning to declare Commercial Operation for Markets in advance of achieving COD as specified in the Interconnection Agreement? If yes, please describe the intended COM plan/schedule. |  | No | N/A
| 20 | Commercial Operation Date (COD) Is the Project on track to meet the COD specified in the Interconnection Agreement? If not, please describe in the Notes the status of the required modification request. |  | No | N/A
Reminders for Other Programs
| 21 | BAA Has the Project provided the CAISO and PTO with the Balancing Authority Area notice? |  | No | N/A
| 23 | Resource Adequacy If the Project intends to participate in Resource Adequacy, has it completed its registration into that Program? |  | No | N/A
COD | 24 | Use-limited Resource If the Project will be a Use-limited Resource, has it completed the Program requirements? |  | No | N/A

## Prior to Synch
If the Project is within 6 months of its Initial Synchronization Date and does not expect to be delayed, please complete this tab. All items on both this tab and the Status Report tab must be completed (or not applicable to the Project) in order for Queue Management to approve Initial Synchronization. FYI... This form/tab, including some data on the Status Report Tab, replaces the previously known Transmission Check Sheet.
|  | Completed?: Goal = Yes to all | Date Completed: (If Applicable) | Comments or Notes:
Inverter Confirmation
1 | Project Inverters Do the inverters that were installed match the most recently approved study or modification results? In the Notes, detail what inverters have been installed. Provide the manufacturer, model/type, MW rating of each. | No
Appendix H / Attachment 7 Confirmation
2 | Step Up Transformer Does the step up transformer, have a duration equal to the lesser of the normal three-phase fault clearing time (4-9 cycles) or one-hundred fifty (150) milliseconds, plus any subsequent post-fault voltage recovery to the final steady-state post-fault voltage unless clearing the fault effectively disconnects the generator from the system? | No
3 | Disturbance Response Will the Generating Facility remain online for any voltage disturbance caused by a single-phase fault on the transmission grid, or within the Project between the Point of Interconnection and the high voltage terminals of the Project’s step up transformer, with delayed clearing, plus any subsequent post-fault voltage recovery to the final steady-state post-fault voltage unless clearing the fault effectively disconnects the generator from the system? | No
4 | Momentary Cessation Does the Project meet the momentary cessation requirements? | No
5 | Off Nominal Frequency Does the Project comply with the off nominal frequency requirements set forth in the WECC Under Frequency Load Shedding Relay Application Guide or successor requirements as they may be amended from time to time? | No
6 | Power Factor Does the Project operate within a power factor range of 0.95 leading to 0.95 lagging, measured at the Point of Interconnection as defined in the LGIA in order to maintain a specified voltage schedule? | No
7 | Monitor and Record Data For LGIA only, does the project meet the monitor and record data requirements for all frequency ride-through events, transient low voltage disturbances that initiated reactive current injection, reactive current injection or momentary cessation for transient high voltage disturbances, and inverter trips? Including that the data must be time synchronized, using a GPS clock or similar device, to a one millisecond level of resolution; all data except phase angle measuring unit data must be sampled at least every 10 milliseconds; each recording will include as a minimum 150 milliseconds of data prior to the triggering event, and 1000 milliseconds of data after the event trigger; and the Project must store this data for a minimum of 30 days. | No
8 | Phase Angle Measuring For LGIA Only, has a phase angle measuring unit or functional equivalent been installed at the entrance to the facility or at the Generating Facility’s main substation transformer? Including that the phase angle measuring unit must have a resolution of at least 30 samples per second and this data will be stored for a minimum of 30 days. | No
Compliance: For NERC PRC-012 Compliance -- NERC PRC-012 - https://www.nerc.com/pa/Stand/Reliability%20Standards/PRC-012-2.pdf
9 | Limiting Mechanism Has the limiting mechanism as described in the GIA or response to MMA been installed? If so, please provide details about the mechanism by which the Project will limit its output to the approved MW at POI. | No
10 | PRC-012 Compliance Does the generating facility require compliance with compliance standard PRC-012? If so, does the Project meet the PRC-012 Criteria? | No
11 | WECC Compliance If the project is over 200 MW, has the Project complied with WECC Progress Report Policies and Procedures? And, has a report has been filed and approved by WECC? | No
12 | Reliability Coordinator Has the IC provided the Reliability Coordinator (RC West) notification and received approval for the limiting scheme RAS for compliance standard PRC-012? | No
Other confirmations:
13 | PMAX Is the PMAX value the same in the PGA, GIA, the App & Study RIMS project, and the NRI RIMS Project? | No
14 | Hybrid/Co-located Is the Project Co-located or Hybrid consistent with the PGA, GIA, the App & Study RIMS project, and the NRI RIMS Project? | No
15 | Financial Deficiencies Has the Project cured all financial deficiencies? -- Confirm no study cost invoices are in default. -- Confirm Project has fulfilled all financial obligations for CAISO studies (Study, Repower, MMAs, LOS, etc.) | No

## PM Tracker
This tab of for ISO Internal use only for project management purposes. DO NOT EDIT DATA HERE
Q# | Started Construction? | Proof of Insurance | Environmental or Land Use Permit | 3rd IFS Posting GIA Milestone: | 3rd IFS Postings | Power Purchase Agreements (PPA) | PPA POI | PPA MW | PPA Fuel Type/Technology | Land Acquisition Complete | Notice to Proceed GIA Milestone: | Written notice to proceed to PTO? | Project Modification Active? | Affected System Mitigation Complete? | Metering and Telemetry completed? | Station Power arrangements complete? | Initial Specifications submitted to PTO? | Final Specifications submitted to PTO? | Interconnection Facilities construction started? | NRI Process Started? | #Resource IDs Expected: | ISD GIA Milestone: | In-service Date Achieved? | Sync GIA Milestone: | Initial Synchronization Date Achieved? | Commercial Operation for Markets Achieved? | COD GIA Milestone: | Commercial Operation Date Achieved?
| No | No | No |  | No | No | n/a | n/a | n/a | No |  | No | No | No | No | No | No | No | No | No | 0 |  | No |  | No | No |  | No
[10 empty] | Y/N Only |  |  | Y/N Only | [12 empty] | Y/N Only |  | Y/N Only

## Dropdown (hidden)
Yes
No
N/A