## Roadmap Summary
Status | Open
Count of Topic | Column Labels
Initiative | API | Automation of workflow | Business process | Export/ Import, New columns | Policy | Unification | Usability | Grand Total
TBD | 7 |  | 6 | 1 | 2 | 1 | 2 | 19
Future |  |  | 6 | 1 | 2 |  | 2 | 11
Ops Enhancements | 7 |  |  |  |  | 1 |  | 8
Fall 2018 |  | 1 | [5 empty] | 1
Ops Enhancements |  | 1 | [5 empty] | 1
Summer 2018 |  |  | 1 |  |  |  |  | 1
Ops Enhancements |  |  | 1 |  |  |  |  | 1
Grand Total | 7 | 1 | 7 | 1 | 2 | 1 | 2 | 21

## Roadmap
Theme | Category | Topic | Sub Topics | Status | Target Initiative | Target Period | B2B API Impact | Comments
Additional functionality | Business process | Substitution | Not able to create RT Subs from Next Day onward | Completed | RSI 1B | 2018-04-01 |  | ALM 40824 postponed
Additional functionality | Error handling | Error messages during uploads | Detailed error/warning codes on RA/Supply Plan uploads (resource not in matching plan is not sufficient to coordinate) | Completed | RSI 1B | 2018-04-01 |  | Need information from stakeholder
Additional functionality | Notification | Notification to SC of any Outage replacement approval request |  | Completed | RSI 1B | 2018-04-01 |  | POSO implementation
Additional functionality | Reporting | Public posting of CSP Offers |  | Completed | RSI 1B | 2018-04-01 |  | Will be posted to OASIS
Additional functionality | Reporting | Ability to download/export non-RA capacity data |  | Completed | RSI 1B | 2018-04-01
Performance | Business process | Frequent runs of validation | More timely validation runs. SCs do not have to wait until next day or late afternoon to see immediate results. Stakeholder requested every 30 mins if there are changes to Plans. | Completed | RSI 1B | 2018-04-01 |  | ISO will schedule two additonal runs. One at noon and one at 3 PM.
Additional functionality | Business process | More frequent processing of EFC requests |  | Open | Future | TBD
Additional functionality | Business process | Coordination of supply plans | Improved ability to coordinate supply plans with counterparties and better facilitate sales and re-sales | Open | Future | TBD |  | Need information from stakeholder
Additional functionality | Business process | CPM | CIDI-00181232: ability to cancel an ED once it has been declined We can put a warning "This action will result in supplemental revenue for the next 30 days. Do you wish to continue?“ CIDI-00181230: After search, the monthly/intra-monthly/annually and start and end dates should be available so that users shouldn't have to reload the screen to re-query the results. CIDI-00181223: CPM Type should be more descriptive | Open | Future | TBD |  | ALM 43448 postponed
Additional functionality | Business process | CSP offers | CIDI-00181431 -Allow users to load offers from Monthly and copy into Intra-monthly offers. | Open | Future | TBD |  | ALM 41007 postponed
Additional functionality | Business process | CSP offers | Make the CSP Offers window variable size. The search for available resources window is able to be variable size but the CSP offers window is not. It would be easier if the window can be made longer to let users see the entire list of offers. | Open | Future | TBD |  | ALM 41008 postponed
Additional functionality | API | API Functionality for Replacements |  | No longer needed |  |  | Y - will likely not be needed with replacements being phased out with RSI - 1B | Descoped from RSI-1B. However, given the importance to MPs, this is under assessment if it can be delivered earlier.
Additional functionality | Business process | Substitution | Single substitution screen for POSO and forced substitution. | Open | Future | TBD |  | No eta but cannot accommodate for RSI 2017 timelines.
Additional functionality | Export/ Import, New columns | Export substitutions, import/export CSP offers, new columns in review substitution screen | a. Request to provide Export Functionality in Review Substituions Screen. b. Import/export buttons in CSP offer screen. c. Import/export buttons in Review Substitution screen. d. Add two additional columns in Review Substitution screen with Gen & Flex substitution MW amount to be import/export easily & effectively. | Open | Future | TBD |  | CIDI-00187965; ALM 44850
Additional functionality | Policy | Ability to nominate and receive Import Allocations Steps 8-11 |  | Open | Future | TBD
Additional functionality | Policy | Adopt the CPUC MCC buckets construct fully. | This will allow firm imports to count across the entire month instead of only on peak days. | Open | Future | TBD
Additional functionality | Usability | Populate queue number to be automatically on submission of a request | The queue number is for new NQC request from RIMS | Open | Future | TBD
Additional functionality | Notification | Requesting CPM Mw on CPM Email |  | Closed |  |  |  | CIDI 00186412; NA - Info sec did not approve sending MW and price in an email, so request is being closed.
Additional functionality | Usability | Pre-population of compliance month on filters | Ability to not have to select the compliance month for every filter (validation, TAC obligation, Peak obligation, outage replacement, outage impact) | Open | Future | TBD
Additional functionality | Usability | Supply and RA plans | System must have the ability for ISO users to download multiple RA/Supply Plans (excel files) across SCs for a given trade year and trade month. Note: ISO users must be able to select multiple RA/Supply Plans and then download them all at once. It will not be acceptable to download each RA/Supply Plan individually. | Completed | Future | TBD |  | Impacts ISO efficiency
Additional functionality | API | API to upload RA/Supply Plans | API Functionality supporting plan submittal, LSE/Supplier communication and daily RA commitments | Open | Ops Enhancements | TBD | Y - priority 3 | Descoped from RSI-1B
Additional functionality | API | API to submit CSP Offers |  | Open | Ops Enhancements | TBD | Y - priority 2 | Descoped from RSI-1B
Additional functionality | API | API to submit submit/retreive substitutions | Either an API solution or a bulk upload solution is being requested. | Open | Ops Enhancements | TBD | Y - priority 1 | Per CIDI:00190716 SC is requesting a bulk upload option to submit Planned Outage substitutions. For SC's that manage larger number of resources, a bulk upload option would assist in fufilling POS obligations.
Additional functionality | API | API to retrieve POSO assignments |  | Open | Ops Enhancements | TBD | Y - priority 1
Additional functionality | API | API to retrieve RA Data | to include all data elements on the RA tracker in the MOO flag payload | Open | Ops Enhancements | TBD | Y - priority 4
Additional functionality | Reporting | RA data, Outage data, Replacement data, Substitution data | CIDI 00185139 - Request for addition of operational RA data to the MPPF meetings, specifically: 1. Total RA Local/System/Flex requirements for the past, current and next month 2. Total RA Local/System/Flex resources provided to ISO daily 3. Total Planned Outage MWs that impacted the RA available MWs by day 4. Total Forced Outage MWs that impacted teh RA available MWs by day 5. Total MWs of replacement capacity provided for planned outages by day 6. Total MWs of substitute capacity provided for forced outages by day | Closed |  |  |  | SDG's request is with the Data Release Committee for consideration. Gautham to provide an update on May 17th, 2017 7/20 Gautham: Data was released for 2016, so this can be closed.
Additional functionality | API | API to retrieve NQC & EFC data |  | Open | Ops Enhancements | TBD | Y - priority 4 | RF - 00565594, CIDI - 00204908
Additional functionality | API | API to retrieve RAAIM pre-calculation run details |  | Open | Ops Enhancements | TBD | Y - priority 4
Additional functionality | Automation of workflow | Acquired contracts |  | Open | Ops Enhancements | Fall 2018
Additional functionality | Automation of workflow | LRA role build-out & configuration |  | In progress | Ops Enhancements | Summer 2018 |  | The LRA read role has been built and notifications are sent to the LRA when LSEs are deficient. The LRA write role is being developed to upload LSE credits.
Additional functionality | Automation of workflow | CPM Cost Allocation |  | In progress | Ops Enhancements | Fall 2018 |  | Will be completed by 2nd quarter of 2019
Additional functionality | Automation of workflow | Import Allocation Enhancements |  | In progress | Ops Enhancements | TBD
Additional functionality | Business process | Credits application | Order of application of credits | In progress | Ops Enhancements | Fall 2018
Additional functionality | Business process | LSE ID sourcing from MF | Unification of LSE IDs and process improvement | Open | Ops Enhancements | Summer 2018
Additional functionality | Reporting | NQC Enhancements | Comments from SC, bulk upload by ISO, posting of NQC to OASIS | In progress | Ops Enhancements | Summer 2018 |  | Posting to OASIS is pending. Rest has been completed
Additional functionality | Unification | Resource to area mapping | Controlling the entry points to where updates to this information can be made in CIRA. | Open | Ops Enhancements | TBD |  | Impacts ISO's controls and error handling.

## Summary Defect Backlog
Open versus Closed Defect Counts
Issue Counts by Status
Count of Issue # | Issue Status
Issue Status / Detected Year | Closed | Open | Evaluated | New | Postponed | Grand Total
2018 | 57 | 7 |  | 29 |  | 93
2017 | 52 | 8 | 1 | 8 |  | 69
2016 | 105 | 1 |  | 8 | 18 | 132
Grand Total | 214 | 16 | 1 | 45 | 18 | 294
Root Cause | (All)
Status | Closed
Issues resolved by deployment year and month
Count of Issues | Deployment Month & Year
Severity | 2-Very High | 3-High | 4-Medium | 5-Low | 6-Enhancement | Grand Total
2016 | 5 | 57 | 14 | 3 | 3 | 82
2017 | 1 | 40 | 12 |  | 6 | 59
2018 | 1 | 30 | 15 | 1 | 11 | 58
Grand Total | 7 | 127 | 41 | 4 | 20 | 199
For closures, # reported via CIDI
Status | Closed
Root Cause | (Multiple Items)
Severity | # of s/w fixes | # reported through CIDI
2016
2-Very High | 5 | 2
3-High | 57 | 19
4-Medium | 14 | 2
5-Low | 3 | 1
6-Enhancement | 3 | 2
2017
2-Very High | 1 | 1
3-High | 40 | 10
4-Medium | 12 | 4
6-Enhancement | 6 | 2
2018
2-Very High | 1
3-High | 30 | 4
4-Medium | 15
5-Low | 1 | 1
6-Enhancement | 10
Grand Total | 198 | 48
Status | Closed
Severity | (Multiple Items)
Root Cause | (Multiple Items)
Deployed with a Project? | (All)
Seasonal? | (All)
Deployment / Closure Year | Deployment/ Closure Month | Average of Turnaround days | Count of Issue #
2016 | 1 | 8 | 2
| 2 | 6.5 | 2
| 4 | 51.5 | 2
| 5 | 13.625 | 8
| 6 | 21.3333 | 3
| 7 | 26.6 | 5
| 8 | 30 | 7
| 9 | 31.5 | 4
| 10 | 5.3333 | 3
| 11 | 5.8571 | 7
| 12 | 9.25 | 16
2016 Total |  | 16.5932 | 59
2017 | 1 | 13.7778 | 9
| 2 | 13 | 7
| 3 | 8 | 1
| 4 | 12 | 3
| 5 | 12 | 1
| 6 | 16.3333 | 6
| 7 | 14 | 1
| 8 | 6 | 1
| 11 | 8.5 | 2
| 12 | 78.3333 | 3
2017 Total |  | 18.8529 | 34
2018 | 1 | 508 | 1
| 2 | 8 | 1
| 3 | 184.5 | 4
| 4 | 0 | 1
2018 Total |  | 179.1429 | 7
Grand Total |  | 28.74 | 100

## Defect Backlog
Issue # | System | Short Description | CIDI | Severity | Root Cause | Status | Detected on Date | Closing Date | Deployment date | ETA | Deployed with a Project? | Seasonal? | Detected Year | Deployment/ Closure Month | Deployment / Closure Year | Turnaround days | Turnaround <=5 days | Turnaround 6-10 days | Turnaround 11-20 days | Turnaround 21-30 days | Turnaround 31-45 days | Turnaround 46-60 days | Turnaround >60 days
39242 | CIRA | SC Transfer Job not transferring all resources to the new SC |  | 3-High | Software | Closed | 2016-01-06 | 2016-01-10 |  |  |  |  | 2016 | 1 | 2016 | 8 |  | Y
39258 | CIRA | SC Transfer Job does not transfer the Flex RA to the New Supplier when resource ownership is changed |  | 3-High | Software | Closed | 2016-01-06 | 2016-01-10 |  |  |  |  | 2016 | 1 | 2016 | 8 |  | Y
39287 | CIRA | CIRA RSI_Phase 1A: As an ISO user Unable to reject approved NQC records |  | 6-Enhancement | Requirement Gap | Postponed | 2016-01-09 | [5 empty] | 2016 |  |  | FALSE
39654 | CIRA | RSI_Phase1a_Search Substitution Requests_Substitutions are showing up when there is no substitution in compliance month |  | 4-Medium | Functionality | Closed | 2016-01-29 | 2016-12-22 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 347 | [6 empty] | Y
39918 | CIRA | CIRA Should round down the RA numbers to the lower integers for down-stream systems if the original RA capacity is a fractional number |  | 3-High | Enhancement | Closed | 2016-02-16 | 2016-04-04 |  |  |  |  | 2016 | 4 | 2016 | 52 | [5 empty] | Y
39962 | CIRA | CIRA: Cleaning unnecessary information from CIRA_MSTR. CIRA_DB_PROCESS_LOG table |  | 6-Enhancement | Enhancement | Postponed | 2016-02-18 | [5 empty] | 2016 |  |  | FALSE
39974 | CIRA | CIRA_RSI Phase 1A_BSC ids are populating in SC in Substitute Resource Selection section. |  | 5-Low | Software | New | 2016-02-18 | [5 empty] | 2016 |  |  | FALSE
40014 | CIRA | RAAM: Missing SCP_AVAIL payload for TD 2/21/16 |  | 3-High | Software | Closed | 2016-02-22 | 2016-02-25 |  |  |  |  | 2016 | 2 | 2016 | 7 |  | Y
40045 | CIRA | SCP Availability Calc Publish is erroring out for Trade Date 02-22-2016 |  | 3-High | Software | Closed | 2016-02-23 | 2016-02-25 |  |  |  |  | 2016 | 2 | 2016 | 6 |  | Y
40183 | CIRA | CIRA-RSI-Phase 1A: Unauthorized user is able view & Download Outage Impact Report for both outage view T45 and OTD |  | 3-High | Software | Closed | 2016-03-03 | 2016-04-20 |  |  |  |  | 2016 | 4 | 2016 | 52 | [5 empty] | Y
40203 | CIRA | CIRA_RSI Phase 1A Menu bar is incorrectly rendered on user access exception |  | 3-High | Software | Closed | 2016-03-04 | 2016-04-20 |  |  |  |  | 2016 | 4 | 2016 | 51 | [5 empty] | Y
40207 | CIRA | Enhancements to CSP offer submission | 179737 | 6-Enhancement | Enhancement | Postponed | 2016-03-04 | [5 empty] | 2016 |  |  | FALSE
40213 | CIRA | CIRA-RSI-Phase 1A: Not Published RAAIM Pre-Calcs are visible to External SCs (No data disclosure) |  | 4-Medium | Software | Closed | 2016-03-04 | 2017-07-05 |  |  |  |  | 2016 | 7 | 2017 | 492 | [6 empty] | Y
40270 | CIRA | CIRA-RSI-Phase 1A; Performance Requirement Details Missing from SRS |  | 4-Medium | Software | Closed | 2016-03-10 | 2017-07-20 |  |  |  |  | 2016 | 7 | 2017 | 501 | [6 empty] | Y
40313 | CIRA | CIRA-RSI-Phase 1A: Timestamp of SC Request Date does not update properly for Proxy details on OM Screen |  | 6-Enhancement | Software | Closed | 2016-03-14 | 2018-03-05 | NA |  |  |  | 2016 |  |  | #VALUE!
40414 | CIRA | CIRA Enhancement CIDI 00180350: CIRA Notifications should show the environment name | 180350 | 6-Enhancement | Enhancement | Postponed | 2016-03-23 | [5 empty] | 2016 |  |  | FALSE
40575 | CIRA | CIRA_RSI_Phase 1A: Flexible RA does not reflect all the hours it has been committed |  | 6-Enhancement | Requirement Gap | Postponed | 2016-04-07 | [5 empty] | 2016 |  |  | FALSE
40788 | CIRA | TAC Results Report errors out in Prod | 181052 | 3-High | Software | Closed | 2016-04-25 | 2016-06-10 |  |  |  |  | 2016 | 6 | 2016 | 50 | [5 empty] | Y
40798 | CIRA | CIRS-RSI-Phase 1A: CIRA should not show ISO price for CPM to MPs in Data Maintenance Search screen as well as it should not send to settlement/MQS |  | 6-Enhancement | Enhancement | Postponed | 2016-04-26 | [5 empty] | 2016 |  |  | FALSE
40805 | CIRA | CIRA-RSI-Phase 1A: MKT SIM -CPM CSP Email Notification | 180944 | 6-Enhancement | Enhancement | Postponed | 2016-04-26 | [5 empty] | 2016 |  |  | FALSE
40824 | CIRA | CIRA-RSI-Phase 1A: MKT SIM- Not able to create RT Subs from Next Day onward |  | 6-Enhancement | Enhancement | Postponed | 2016-04-27 | [5 empty] | 2016 |  |  | FALSE
40848 | CIRA | CIRA-RSI-Phase 1A: Show warning if resources are missing in resubmital plan were involved in any Substitution, Replacements and CPMs |  | 6-Enhancement | Enhancement | Postponed | 2016-04-28 | [5 empty] | 2016 |  |  | FALSE
40851 | CIRA | Peak results screen error in Prod | 181047 | 3-High | Software | Closed | 2016-04-29 | 2016-05-11 |  |  |  |  | 2016 | 5 | 2016 | 16 |  |  | Y
40854 | CIRA | RAAM Prod error - Availability calculation fails when there are multiple substitutions in a request and calculation invoked specific to the substituted resources. |  | 3-High | Software | Closed | 2016-04-29 | 2016-05-17 |  |  |  |  | 2016 | 5 | 2016 | 22 |  |  |  | Y
40856 | RAAM | Error when trying to load valid MW for Substitutions | 181256 | 2-Very High | Software | Closed | 2016-04-29 | 2016-05-13 |  |  |  |  | 2016 | 5 | 2016 | 18 |  |  | Y
40994 | CIRA | Outage Availability Report - Unavailable | 177387 | 3-High | Software | Closed | 2016-05-03 | 2016-05-19 |  |  |  |  | 2016 | 5 | 2016 | 20 |  |  | Y
40995 | CIRA | CIRA: MF to CIRA refresh failure due to LSE SCIDs length more than defined constraint |  | 3-High | Software | Closed | 2016-05-11 | 2016-05-17 |  |  |  |  | 2016 | 5 | 2016 | 10 |  | Y
40998 | CIRA | Need data fix for July Supply plan as the system is enforcing the SCID Import allocation check incorrectly | 181472 | 3-High | Software | Closed | 2016-05-11 | 2016-05-11 |  |  |  |  | 2016 | 5 | 2016 | 4 | Y
40999 | CIRA | CIRA needs to round down fractional MW values on Interties to the integer level | 179200 | 3-High | Requirement Gap | Closed | 2016-05-11 | 2016-05-18 |  |  |  |  | 2016 | 5 | 2016 | 11 |  |  | Y
41007 | CIRA | CIRA-RSI-Phase 1A: MKT SIM -Load CSP Offers Enhancement | 181431 | 6-Enhancement | Enhancement | Postponed | 2016-05-11 | [5 empty] | 2016 |  |  | FALSE
41008 | CIRA | CIRA-RSI-Phase 1A: MKT SIM -CSP Offer Screen - Enhancement | 181434 | 6-Enhancement | Enhancement | Postponed | 2016-05-11 | [5 empty] | 2016 |  |  | FALSE
41073 | CIRA | CIRA TAC Results report performance does not meet specified requirements |  | 4-Medium | Documentation | Postponed | 2016-05-18 | 2016-05-26 |  |  |  |  | 2016 |  |  | FALSE
41075 | CIRA | CIRA - Monthly Obligation report and Peak Results report are incorrect |  | 3-High | Software | Closed | 2016-05-18 | 2016-05-24 |  |  |  |  | 2016 | 5 | 2016 | 10 |  | Y
41082 | CIRA | CIRA: Annual Obligation report shows incorrect data |  | 3-High | Software | Closed | 2016-05-18 | 2016-07-11 |  |  |  |  | 2016 | 7 | 2016 | 58 | [5 empty] | Y
41091 | CIRA | CIRA: Outage Availability report performance does not meet specified requirements |  | 4-Medium | Requirement Gap | Closed | 2016-05-19 | 2018-03-05 |  |  |  |  | 2016 |  |  | 655 | [6 empty] | Y
41102 | CIRA | Error in the NQC Submission - CIRA shows the resource is not valid | 181717 | 3-High | Software | Closed | 2016-05-20 | 2016-05-25 |  |  |  |  | 2016 | 5 | 2016 | 9 |  | Y
41140 | CIRA | CIRA-Total RA calculation during RA Plan reupload is incorrect |  | 4-Medium | Software | Closed | 2016-05-24 | 2016-06-16 |  |  |  |  | 2016 | 6 | 2016 | 27 |  |  |  | Y
41141 | CIRA | CIRA-Yearly CV shows no records |  | 4-Medium | Software | Closed | 2016-05-24 | 2016-06-14 |  |  |  |  | 2016 | 6 | 2016 | 25 |  |  |  | Y
41229 | CIRA | Prod Issue: bulk update all records in the SCP_GF_RES table to include the timestamp 23:59:59 for EFF_END_DTS |  | 3-High | Software | Closed | 2016-06-02 | 2016-06-07 |  |  |  |  | 2016 | 6 | 2016 | 9 |  | Y
41333 | RAAM | Resource ID Drop-Down list does not populate the resources for newly created SCs. | 181822 | 3-High | Software | Closed | 2016-06-09 | 2016-06-10 |  |  |  |  | 2016 | 6 | 2016 | 5 | Y
41339 | CIRA | CIRA - TAC Results are showing incorrect data |  | 3-High | Software | Closed | 2016-06-09 | 2016-07-07 |  |  |  |  | 2016 | 7 | 2016 | 32 |  |  |  |  | Y
41486 | RAAM | RAAM not allowing users to submit Subs | 182460, 182420, 182456 | 2-Very High | Software | Closed | 2016-06-23 | 2016-07-07 |  |  |  |  | 2016 | 7 | 2016 | 18 |  |  | Y
41557 | CIRA | Market participants are unable to submit replacements in CIRA |  | 3-High | Performance | Closed | 2016-06-29 | 2016-08-09 | 2016-08-25 |  |  |  | 2016 | 8 | 2016 | 57 | [5 empty] | Y
41694 | CIRA | CIRA - some resources not in 'Saved NQC request' Excel export |  | 3-High | Software | Closed | 2016-07-07 | 2016-07-20 |  |  |  |  | 2016 | 7 | 2016 | 17 |  |  | Y
41697 | CIRA | update the correct mw volumes for NOB_BG Import for the September showing | 182745 | 3-High | Data | Closed | 2016-07-07 | 2016-08-01 |  |  |  |  | 2016 | 8 | 2016 | 29 |  |  |  | Y
41698 | RAAM | RAAM not showing the updated NQC values that are approved in CIRA | 182626 | 3-High | Software | Closed | 2016-07-07 | 2016-07-11 |  |  |  |  | 2016 | 7 | 2016 | 8 |  | Y
41754 | RAAM | Dispute #181646 SCP calculation run is not picking up Substitute resource in some cases |  | 3-High | Functionality | Closed | 2016-07-13 | 2016-07-15 | 2016-08-25 |  |  |  | 2016 | 8 | 2016 | 43 |  |  |  |  | Y
41877 | CIRA | CIRA Application was down and up frequently in Production |  | 3-High |  | Closed | 2016-07-19 | 2016-08-12 | 2016-08-25 |  |  |  | 2016 | 8 | 2016 | 37 |  |  |  |  | Y
42018 | CIRA | RA Plan versioning is incorrect which impacts the validation run. |  | 3-High | Functionality | Closed | 2016-07-25 | 2016-09-12 | 2016-08-25 |  |  |  | 2016 | 8 | 2016 | 31 |  |  |  |  | Y
42138 | CIRA | RSI-Phase 1A: MKT SIM Jul16 Obligation Rpts Peak Demand Showing Not Reflecting Subset of Days Resource |  | 2-Very High | Functionality | Closed | 2016-07-26 | 2016-09-15 | 2016-09-21 |  |  |  | 2016 | 9 | 2016 | 57 | [5 empty] | Y
42180 | CIRA | Export screen data from NQC results not matching the filter results on the screen |  | 3-High | Functionality | Closed | 2016-07-27 | 2016-08-09 | 2016-09-21 |  |  |  | 2016 | 9 | 2016 | 56 | [5 empty] | Y
42655 | CIRA | CIRA - RAAM tool hanging when new SCP calculation was run |  | 3-High | Software | Closed | 2016-08-11 | 2016-08-11 |  |  |  |  | 2016 | 8 | 2016 | 4 | Y
42735 | CIRA | CIRA- Review and make consistent jobs accross environments based on dependencies and business requirements |  | 6-Enhancement | Config / Install | New | 2016-08-15 | [5 empty] | 2016 |  |  | FALSE
42807 | CIRA | CIRA is keeping the comments from Old CV instead of updating per new CV |  | 4-Medium | Software | Closed | 2016-08-18 | 2016-08-18 |  |  |  |  | 2016 | 8 | 2016 | 4 | Y
42858 | CIRA | CIRA: Updating RA data in RR_RA table for SMUD Supporting Resources |  | 2-Very High | Data | Closed | 2016-08-19 | 2016-08-24 |  |  |  |  | 2016 | 8 | 2016 | 9 |  | Y
42899 | CIRA | CIRA- RT Substitution for Flex RA |  | 6-Enhancement | Requirement Gap | Postponed | 2016-08-23 | [5 empty] | 2016 |  |  | FALSE
42910 | CIRA | CIRA: HTTP Status 404 error is displayed when user tries the URL manipulation when expected text is User Access Denied. |  | 4-Medium | Software | Closed | 2016-08-22 | 2016-08-29 |  |  |  |  | 2016 | 8 | 2016 | 11 |  |  | Y
43201 | CIRA | SDGE requests the addition of CPM Capacity MWs for Generic/Flexible capacity on the API and RA Tracker | 184495 | 6-Enhancement | Enhancement | Postponed | 2016-09-06 | [5 empty] | 2016 |  |  | FALSE
43444 | CIRA | CIRA PROD: Record count is increased when user sorts by a resource on OM Replacements screen. |  | 3-High | Software | Closed | 2016-09-16 | 2016-09-21 |  |  |  |  | 2016 | 9 | 2016 | 9 |  | Y
43448 | CIRA | RSI-1A - CIRA screen enhancements from CIDI for CPM Designation UI | 00181230, 00181232, 00181223 | 6-Enhancement | Enhancement | Postponed | 2016-09-21 | [5 empty] | 2016 |  |  | FALSE
43467 | CIRA | CIRA- OM Replacements screen shows additional pages after sort is applied on resource ID column |  | 5-Low | Software | Closed | 2016-09-21 | 2016-12-06 |  |  |  |  | 2016 | 12 | 2016 | 80 | [6 empty] | Y
43491 | CIRA | CIRA-RSI-Phase 1A: New SC and/or ISO user is not able to submit the bid on behalf of new SC when resource ownership changes mid of the month. |  | 4-Medium | Software | Postponed | 2016-09-22 | [5 empty] | 2016 |  |  | FALSE
43555 | CIRA | Settlements not receiving Exempt_quantity from SCP Availability Calculations |  | 3-High | Functionality | Closed | 2016-09-26 | 2016-09-29 | 2016-09-30 |  |  |  | 2016 | 9 | 2016 | 4 | Y
43563 | CIRA | RSI-1A: Search not working as expected on CPM Designation screen (CIDI 00184091) | 184091 | 4-Medium | Functionality | Closed | 2016-09-27 | 2016-12-27 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 105 | [6 empty] | Y
43610 | CIRA | CV errors our Supply/RA resources with incorrect Import allocation check |  | 3-High |  | Closed | 2016-09-29 | 2016-10-04 | 2016-10-05 |  |  |  | 2016 | 10 | 2016 | 6 |  | Y
43675 | CIRA | CIRA - Resource Adequacy Showing line is incorrectly being calculated |  | 3-High | Data | Closed | 2016-10-03 | 2016-10-04 |  |  |  |  | 2016 | 10 | 2016 | 5 | Y
43685 | CIRA | CIRA-RSI-1A - Annual CPM miscellaneous issues |  | 4-Medium | Software | New | 2016-10-03 | [5 empty] | 2016 |  |  | FALSE
43773 | CIRA | ResourceAdequacyCapacity payload has a 7 hour offset | 185410 | 3-High | Software | Closed | 2016-10-10 | 2016-10-11 |  |  |  |  | 2016 | 10 | 2016 | 5 | Y
43788 | CIRA | Import Allocation Bilateral Trade not taking into account the start and end dates on the screen | 185544 | 4-Medium | Software | Closed | 2016-10-10 | 2016-11-10 |  |  |  |  | 2016 | 11 | 2016 | 35 |  |  |  |  | Y
43824 | CIRA | RSI-1A - CIRA - UAT - Two substitution requests submitted 2 seconds apart on the same unit because of which RA exceeds NQC |  | 5-Low | Software | New | 2016-10-13 | [5 empty] | 2016 |  |  | FALSE
43827 | CIRA | RSI-1A - CIRA - UAT - Outage exemption request functionality is missing the 5 business day validation rule which is available in RAAM |  | 3-High | Requirement Gap | Closed | 2016-10-13 | 2018-01-05 | 2018-03-05 |  | RSI-2017 |  | 2016 |  |  | 508 | [6 empty] | Y
43827 | CIRA | RSI-1A - UAT - Outage exemption request functionality is missing the 5 business day validation rule which is available in RAAM |  | 3-High | Software | Closed | 2016-10-13 | 2018-01-05 | 2018-03-05 |  | RSI-2017 |  | 2016 | 1 | 2018 | 508 | [6 empty] | Y
43889 | CIRA | (STAGE)->Substituation SEARCH button taking longer to display data |  | 4-Medium | Software | Closed | 2016-10-18 | 2018-03-05 | 2018-03-05 |  | RSI-2017 |  | 2016 |  |  | 503 | [6 empty] | Y
43904 | CIRA | CIRA-RSI-1A - The 'capacity Designation' field on the 'Other' tab in RA plan template is inconsistent with the error message |  | 5-Low | Data | Closed | 2016-10-19 | 2018-03-05 | NA |  |  |  | 2016 |  |  | 502 | [6 empty] | Y
43912 | CIRA | CIRA-RSI-1A- Real time substitution for Flex RA |  | 4-Medium | Requirement Gap | New | 2016-10-19 | [5 empty] | 2016 |  |  | FALSE
43955 | CIRA | (CIDI 00186092) Spelling error when downloading Obligation Report from the UI | 186092 | 5-Low | Functionality | Closed | 2016-10-20 | 2016-12-07 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 54 | [5 empty] | Y
43972 | OASIS | RA and Minimum Load data report - There was a fix that was deployed on 3/31/17 did not seem to have solved the issue reported in the CIDI. | 185424 | 3-High |  | Open | 2016-10-24 |  |  | 2017-08-31 |  |  | 2016 |  |  | FALSE
43994 | CIRA | CIRA - Replacement not allowed in system due to incorrectly calculated RA and validation of RA+Replacement <= PMAX/NQC fails |  | 4-Medium | Software | Closed | 2016-10-25 | 2018-03-05 | NA |  |  |  | 2016 |  |  | 496 | [6 empty] | Y
44035 | CIRA | Unable to approve future effective NQC for 1 resource in prod |  | 4-Medium | Functionality | Closed | 2016-10-27 | 2016-12-07 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 47 | [5 empty] | Y
44064 | CIRA | requesting CPM Mw on CPM Email | 186412 | 6-Enhancement | Design | Closed | 2016-10-27 | 2017-06-19 |  |  |  |  | 2016 | 6 | 2017 | 239 | [6 empty] | Y
44070 | CIRA | CIRA- user unable to substitute resource on the last day of November |  | 4-Medium | Software | New | 2016-10-31 | [5 empty] | 2016 |  |  | FALSE
44087 | CIRA | remove ReceiveResourceAdequacyCapacityData_MFv1_INT_AP from AI/ESB |  | 4-Medium | Install/Config | Closed | 2016-11-01 | 2016-11-09 | 2016-11-07 |  |  |  | 2016 | 11 | 2016 | 6 |  | Y
44097 | CIRA | RSI\CPM:App_cira_bid_read_ext role is unable to access Data Maintenance Search screen |  | 3-High | Software | Closed | 2016-11-01 | 2016-11-10 |  |  |  |  | 2016 | 11 | 2016 | 13 |  |  | Y
44102 | CIRA | CIRA - no data found error in annual transmission planning report |  | 3-High | Requirement Gap | Closed | 2016-11-01 | 2016-11-02 |  |  |  |  | 2016 | 11 | 2016 | 5 | Y
44133 | CIRA | CIDI 00186484- 'No LSE found for supplier x for resource y' error | 186484 | 4-Medium | Functionality | Closed | 2016-11-01 | 2016-11-17 | 2016-11-17 |  |  |  | 2016 | 11 | 2016 | 16 |  |  | Y
44136 | CIRA | change the scheduled time for 'SG_BroadcastResourceAdequacyCapacityData_CIRAv1' payload |  | 3-High | Install/Config | Closed | 2016-11-02 | 2016-11-02 | 2016-11-04 |  |  |  | 2016 | 11 | 2016 | 2 | Y
44211 | CIRA | Missing service for receciveRTMResourceAdequacyCapacityData to Settlements |  | 3-High | Install/Config | Closed | 2016-11-07 | 2016-11-07 | 2016-11-08 |  |  |  | 2016 | 11 | 2016 | 1 | Y
44212 | CIRA | CIRA: Flex Cap Requirement Yearly plan upload is failing. |  | 4-Medium | Software | Closed | 2016-11-03 | 2016-12-09 |  |  |  |  | 2016 | 12 | 2016 | 40 |  |  |  |  | Y
44214 | CIRA | CIRA - Annual CPUC Sub Poena Report not working |  | 4-Medium | Software | Closed | 2016-11-07 | 2016-12-09 |  |  |  |  | 2016 | 12 | 2016 | 36 |  |  |  |  | Y
44215 | CIRA | Annual CV calculations are incorrect |  | 3-High | Functionality | Closed | 2016-11-07 | 2016-11-17 | 2016-11-17 |  |  |  | 2016 | 11 | 2016 | 10 |  | Y
44216 | CIRA | Missing plans functionality not working for annual |  | 4-Medium | Functionality | Closed | 2016-11-07 | 2016-12-07 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 36 |  |  |  |  | Y
44231 | CIRA | CIDI 00186633 - Bilateral trade screen should allow SC ID same size as exists in MF | 186633 | 6-Enhancement | Functionality | Closed | 2016-11-07 | 2016-11-10 | 2016-11-11 |  |  |  | 2016 | 11 | 2016 | 4 | Y
44233 | CIRA | CIRA - Data Fixes for Bilateral trade due to date and SC ID length issues |  | 4-Medium | Data | Closed | 2016-11-07 | 2016-11-21 |  |  |  |  | 2016 | 11 | 2016 | 18 |  |  | Y
44257 | CIRA | ISO offers not created when SC did not bid for intra-monthly |  | 3-High | Functionality | Closed | 2016-11-08 | 2016-11-11 | 2016-11-11 |  |  |  | 2016 | 11 | 2016 | 3 | Y
44259 | CIRA | ISO user unable to approve saved NQC record for SC's with future effective date |  | 3-High | Functionality | Closed | 2016-11-08 | 2016-11-21 | 2016-11-17 |  |  |  | 2016 | 11 | 2016 | 9 |  | Y
44261 | CIRA | CIDI 00186601 - TG not allowed to submit CSP offer for Flex even when EFC/NQC exists for that month | 186601 | 6-Enhancement | Functionality | Closed | 2016-11-08 | 2016-12-07 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 35 |  |  |  |  | Y
44269 | CIRA | CIRA - Enhance CIRA to handle processing a larger volume of EDs |  | 3-High | Design | Postponed | 2016-11-08 | [5 empty] | 2016 |  |  | FALSE
44281 | CIRA | Ignore EDs with same start and end times i.e. cancelled EDs |  | 3-High | Functionality | Closed | 2016-11-08 | 2016-11-11 | 2016-11-11 |  |  |  | 2016 | 11 | 2016 | 3 | Y
44320 | CIRA | CIRA - Intra-monthly CSP offers not getting adjusted due to ED or Substitution |  | 3-High | Software | Closed | 2016-11-09 | 2016-12-15 |  |  |  |  | 2016 | 12 | 2016 | 40 |  |  |  |  | Y
44325 | CIRA | CSP offer not created for a res that has multiple records in MF for the same Resource- SC association |  | 3-High | Functionality | Closed | 2016-11-14 | 2016-12-02 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 18 |  |  | Y
44326 | CIRA | Resource area mapping is not updating when you upload and approve the NQC |  | 4-Medium | Functionality | Closed | 2016-11-14 | 2017-04-04 | 2017-04-10 |  |  |  | 2016 | 4 | 2017 | 147 | [6 empty] | Y
44346 | CIRA | MED integration issue - resources where RA = PMax need to be sent in the payload |  | 6-Enhancement | Functionality | Closed | 2016-11-14 | 2016-11-17 | 2016-11-17 |  |  |  | 2016 | 11 | 2016 | 3 | Y
44379 | CIRA | CIDI 00186979 Import allocation issue | 186979 | 3-High | Functionality | Closed | 2016-11-15 | 2016-12-01 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 17 |  |  | Y
44391 | CIRA | CIRA APP is producing errors in server log, the bigger log is causing diskspace issue in Production |  | 2-Very High | Functionality | Closed | 2016-11-17 | 2016-11-29 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 15 |  |  | Y
44414 | CIRA | Discrepancies on CIRA data sent to Settlements, regarding a resource in the payload if it does not qualify for a RAAIM exemption | 186775 | 3-High | Software | Closed | 2016-11-22 | 2016-12-02 |  |  |  |  | 2016 | 12 | 2016 | 14 |  |  | Y
44432 | CIRA | CIDI 186988: SC gets an error while trying to approve SRs | 186988 | 3-High | Functionality | Closed | 2016-11-23 | 2016-11-29 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 9 |  | Y
44462 | CIRA | CPM designation UI not displaying resources with multiple SC association |  | 3-High | Functionality | Closed | 2016-11-29 | 2016-12-02 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 3 | Y
44482 | CIRA | B2B webservices descoped from RSI 1B and CPGs |  | 6-Enhancement | Software | Postponed | 2016-11-29 | [5 empty] | 2016 |  |  | FALSE
44488 | CIRA | Date on RAAIM Pre-calc run details screen different from Excel download |  | 3-High | Functionality | Closed | 2016-11-30 | 2016-12-01 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 2 | Y
44497 | CIRA | app_cira_availcalc_int role user is unabe to access RAAIM Calculation functionality in CIRA application. |  | 3-High | Functionality | Closed | 2016-11-30 | 2016-12-01 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 2 | Y
44511 | CIRA | 2017 NQC resource validation using tech factor for 2016 | 187300 | 3-High |  | Closed | 2016-12-01 | 2016-12-02 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 1 | Y
44522 | CIRA | CIDI 00187331 - Obligation report missing data by Peak | 187331 | 3-High | Functionality | Closed | 2016-12-01 | 2016-12-01 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 1 | Y
44546 | CIRA | RAAM - SCP reruns in RAAM don't show as a recent run in the view |  | 4-Medium | Data | Closed | 2016-12-02 | 2016-12-02 |  |  |  |  | 2016 | 12 | 2016 | 4 | Y
44548 | CIRA | CIDI 00186598 - MOO flag needs to be derived at the time of payload broadcast | 186598 | 3-High | Functionality | Closed | 2016-12-02 | 2016-12-09 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 11 |  |  | Y
44553 | CIRA | multiple CPM designation emails generated for the same resource |  | 5-Low | Functionality | Closed | 2016-12-02 | 2016-12-12 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 11 |  |  | Y
44634 | CIRA | System does not allow user to upload plans for Import resources that are associated with a future dated BG | 187429 | 3-High | Software | Closed | 2016-12-08 | 2016-12-09 |  |  |  |  | 2016 | 12 | 2016 | 5 | Y
44635 | CIRA | CIDI-00187435: SCs are not able to access Approve/Reject OM Replacments screen | 187435 | 3-High | Functionality | Closed | 2016-12-08 | 2016-12-12 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 5 | Y
44641 | CIRA | ED CPM enhancement |  | 3-High | Functionality | Closed | 2016-12-09 | 2016-12-13 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 4 | Y
44675 | CIRA | CIRA - Calculate CPM at the end of the parent ED interval |  | 6-Enhancement | Requirement Gap | Closed | 2016-12-13 | 2017-02-03 |  |  |  |  | 2016 | 2 | 2017 | 56 | [5 empty] | Y
44681 | CIRA | Search for all resources on compatible resources view screen times out |  | 4-Medium | Functionality | Closed | 2016-12-13 | 2016-12-14 | 2016-12-20 |  |  |  | 2016 | 12 | 2016 | 7 |  | Y
44690 | CIRA | CIDI-00187618: CIRA doesn't bump up the RA capacity by 0.01 when RA=Pmin for SIBR | 187618 | 3-High | Functionality | Closed | 2016-12-13 | 2016-12-14 | 2016-12-14 |  |  |  | 2016 | 12 | 2016 | 1 | Y
44793 | CIRA | include null RMRFLAG records for CPM calculations |  | 3-High |  | Closed | 2016-12-20 | 2016-12-23 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 21 |  |  |  | Y
44810 | CIRA | annual optimization is failing |  | 3-High | Functionality | Closed | 2016-12-21 | 2016-12-23 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 20 |  |  | Y
44833 | CIRA | rules for updates to the CPM designation screen |  | 3-High | Functionality | Closed | 2016-12-22 | 2017-01-05 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 19 |  |  | Y
44835 | CIRA | defining allowable period for declining CPM |  | 3-High | Functionality | Closed | 2016-12-22 | 2017-01-04 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 19 |  |  | Y
44850 | CIRA | Request to provide Export Functionality in Review Substituions Screen | 187965 | 6-Enhancement | Enhancement | New | 2016-12-27 | [5 empty] | 2016 |  |  | FALSE
44869 | CIRA | CIRA - SC transfer details under Admin menu is non functional |  | 4-Medium | Software | Closed | 2016-12-28 | 2017-06-30 |  |  |  |  | 2016 | 6 | 2017 | 188 | [6 empty] | Y
44895 | CIRA | CIRA - SC transfer should have only 1 set of records for a unique effective date range |  | 4-Medium | Software | New | 2016-12-29 | [5 empty] | 2016 |  |  | FALSE
44911 | CIRA | CPM should be designated for only CISO resources with an active SC association |  | 3-High | Functionality | Closed | 2016-12-30 | 2017-01-11 | 2017-01-13 |  |  |  | 2016 | 1 | 2017 | 14 |  |  | Y
44913 | CIRA | CIDI 00187978 - RAAIM Pre-calc is not handling DST time | 187978 | 3-High | Functionality | Closed | 2016-12-30 | 2017-01-12 | 2017-01-13 |  |  | DST-Spring | 2016 | 1 | 2017 | 14 |  |  | Y
44914 | CIRA | CIDI 00188019 - RA report not taking into account multiple replacement records | 188019 | 3-High | Functionality | Closed | 2016-12-30 | 2017-01-05 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 11 |  |  | Y
44924 | CIRA | RTM RA payload to Settlements failed due to a resource end dating |  | 3-High | Functionality | Closed | 2017-01-03 | 2017-01-03 | 2017-01-03 |  |  |  | 2017 | 1 | 2017 | 0 | Y
44934 | CIRA | CIRA - not handling multiple records for penalty price and softoffer cap for the same year |  | 3-High | Data | Closed | 2017-01-04 | 2017-01-06 |  |  |  |  | 2017 | 1 | 2017 | 6 |  | Y
44935 | CIRA | CIRA - Per Updates on One CPM Records system trigger the CPMDesignation and RA Payload for all CPM Resources. |  | 4-Medium | Software | Closed | 2017-01-04 | 2017-02-03 |  |  |  |  | 2017 | 2 | 2017 | 34 |  |  |  |  | Y
44956 | CIRA | Modify CPM email verbiage |  | 6-Enhancement | Functionality | Closed | 2017-01-05 | 2017-01-12 | 2017-01-13 |  |  |  | 2017 | 1 | 2017 | 8 |  | Y
45036 | CIRA | CPM emails are triggered for more resources than the one submitted |  | 3-High | Functionality | Closed | 2017-01-12 | 2017-01-27 | 2017-02-01 |  |  |  | 2017 | 2 | 2017 | 20 |  |  | Y
45167 | CIRA | For FLEX RA category 3 resources RA not calculated correctly for days bordering weekends and holidays |  | 3-High |  | Closed | 2017-01-24 | 2017-01-27 | 2017-02-01 |  |  |  | 2017 | 2 | 2017 | 8 |  | Y
45241 | CIRA | RAAM -NOW conversion issue for SLIC data | ID22406 | 4-Medium | Software | New | 2017-01-26 | [5 empty] | 2017 |  |  | FALSE
45269 | CIRA | CIDI 188202 - availability calculation is incorrect for TG in RAAM | 188202 | 3-High | Functionality | Closed | 2017-01-27 | 2017-02-07 | 2017-02-13 |  |  |  | 2017 | 2 | 2017 | 17 |  |  | Y
45279 | CIRA | CIRA - CPM change email is not being triggered for all elements of the CPM record |  | 4-Medium | Software | Closed | 2017-01-27 | 2017-02-03 |  |  |  |  | 2017 | 2 | 2017 | 11 |  |  | Y
45287 | CIRA | Error in logs due to length of CSP_OFFER_SEGMENT.COMMENTS |  | 3-High |  | Closed | 2017-01-30 | 2017-01-31 | 2017-02-08 |  |  |  | 2017 | 2 | 2017 | 9 |  | Y
45333 | CIRA | Issue with reading the MOO flag from MF due to date/time offset |  | 3-High | Functionality | Closed | 2017-01-31 | 2017-02-08 | 2017-02-13 |  |  |  | 2017 | 2 | 2017 | 13 |  |  | Y
45399 | CIRA | Peak & TAC reports are displaying an incorrect 'Specified Replacement Increase' value on outage dates | 188973 | 3-High |  | Closed | 2017-02-03 | 2017-02-07 | 2017-02-13 |  |  |  | 2017 | 2 | 2017 | 10 |  | Y
45614 | CIRA | CIRA - Not displaying 'in service' resources on the outage exemption screen for retro-active exemptions |  | 4-Medium | Software | New | 2017-02-15 | [5 empty] | 2017 |  |  | FALSE
45695 | CIRA | CIRA - Rebroadcast RA for a specified resource for specified period |  | 4-Medium | Requirement Gap | New | 2017-02-21 | [5 empty] | 2017 |  |  | FALSE
45699 | CIRA | CIRA - Replacement MW higher than provided as S replacements in RA plan- occurred due to multiple resources with different RA plans used the same contract ID. Handled via training & CPG not code fix |  | 3-High | Functionality | Closed | 2017-02-21 | 2017-03-03 |  |  |  |  | 2017 | 2 | 2017 | 14 |  |  | Y
45799 | CIRA | CIRA - Review Substitution screen displays the Sub request ID instead of the Sub ID |  | 3-High | Requirement Gap | Closed | 2017-02-28 | 2017-02-28 |  |  |  |  | 2017 | 2 | 2017 | 4 | Y
45805 | CIRA | CIRA - Intra-monthly final offer automated run does not create an extension when there is no CSP offer from the SC. (manual work-around exists) |  | 4-Medium | Functionality | Open | 2017-02-28 |  |  | 2018-06-01 |  |  | 2017 |  |  | FALSE
46026 | CIRA | ReceiveResourceAdequacyCapacityData_SIBRv1_AP failure due to missing HE19 data |  | 3-High | Software | Closed | 2017-03-10 | 2018-03-08 | 2018-03-09 |  |  |  | 2017 | 3 | 2018 | 364 | [6 empty] | Y
46026 | CIRA | ReceiveResourceAdequacyCapacityData_SIBRv1_AP failure due to missing HE19 data |  | 4-Medium | Software | Closed | 2017-03-10 | 2018-03-08 | 2018-03-09 |  |  | DST-Spring | 2017 |  |  | 364 | [6 empty] | Y
46070 | CIRA | RAAIM calculation failure due to DST Short day |  | 3-High | Software | Closed | 2017-03-13 | 2018-03-09 | 2018-03-09 |  |  | DST-Spring | 2017 | 3 | 2018 | 361 | [6 empty] | Y
46070 | CIRA | RAAIM calculation failure due to DST Short day Data fix will be applied first; code fix will follow later |  | 4-Medium | Functionality | Closed | 2017-03-13 | 2018-03-09 | 2018-03-09 |  |  | DST-Spring | 2017 | 3 | 2018 | 361 | [6 empty] | Y
46143 | CIRA | CIRA - CIDI 00189853, 00189824 - RAAIM inconsistent with CAISO Tariff for Flex LF-MSS resources |  | 3-High | Functionality | Closed | 2017-03-17 | 2017-04-04 | 2017-04-10 |  |  |  | 2017 | 4 | 2017 | 24 |  |  |  | Y
46152 | CIRA | CIRA INT - rename RTM resource adequacy capacity payload as part of ESB replacement |  | 3-High | Install/Config | Closed | 2017-03-19 | 2017-03-20 | 2017-03-27 |  |  |  | 2017 | 3 | 2017 | 8 |  | Y
46736 | CIRA | CIRA must filter out revised set of ED instructions not eligible for CPM designations. |  | 3-High | Functionality | Closed | 2017-04-20 | 2017-04-27 | 2017-04-28 |  |  |  | 2017 | 4 | 2017 | 8 |  | Y
46776 | CIRA | Replacement requirement MW should not exceed RA plan MW | 191111, 191117, 191126, 191140, 191149, 191154, 191155, 191156, 191157 | 3-High | Functionality | Closed | 2017-04-24 | 2017-04-27 | 2017-04-28 |  |  |  | 2017 | 4 | 2017 | 4 | Y
46932 | CIRA | CIRA - Outages from OMS not being picked up by CIRA for a few days in April |  | 3-High | Monitoring | Closed | 2017-05-08 | 2017-06-21 |  |  |  |  | 2017 | 6 | 2017 | 48 | [5 empty] | Y
46934 | CIRA | RA tracker reflects cancelled Flex substitution incorrectly & substitution is not released | 00191513, 00191525 | 4-Medium | Software | Closed | 2017-05-08 | 2017-07-19 | 2017-07-24 |  |  |  | 2017 | 7 | 2017 | 77 | [6 empty] | Y
46945 | CIRA | CPM Enhancement to compute the Daily Max RA MW as max of both Gen & Flex |  | 3-High | Functionality | Closed | 2017-05-09 | 2017-06-01 | 2017-06-06 |  |  |  | 2017 | 6 | 2017 | 28 |  |  |  | Y
47041 | CIRA | CIRA:RA Report Monthly download for ALL resources is throwing error. |  | 3-High | Software | Closed | 2017-05-17 | 2017-05-25 |  |  |  |  | 2017 | 5 | 2017 | 12 |  |  | Y
47056 | CIRA | CIRA - additional reason codes to read to determine CPM eligibility |  | 3-High | Enhancement | Closed | 2017-05-18 | 2017-11-08 | 2017-11-13 | 2017-07-31 |  |  | 2017 | 11 | 2017 | 179 | [6 empty] | Y
47151 | CIRA | Sub_request_id on CIRA UI but Substitution_ID sent to OMS |  | 4-Medium | Software | Closed | 2017-05-28 | 2017-03-05 | 2017-03-05 |  |  |  | 2017 |  |  | -84 | Y
47248 | CIRA | Add 'pre-approved' to T45 approved & pending OIA run and OM Replacements logic | 192247 | 4-Medium | Functionality | Closed | 2017-06-06 | 2017-06-14 | 2017-06-19 |  |  |  | 2017 | 6 | 2017 | 13 |  |  | Y
47249 | CIRA | OM Replacements screen doesn't display 2nd page after a sort |  | 4-Medium | Functionality | Closed | 2017-06-06 | 2017-06-14 | 2017-06-19 |  |  |  | 2017 | 6 | 2017 | 13 |  |  | Y
47254 | CIRA | CIRA - remove the app_cira_om role |  | 6-Enhancement | Enhancement | Closed | 2017-06-06 | 2017-11-21 |  |  |  |  | 2017 | 11 | 2017 | 168 | [6 empty] | Y
47615 | CIRA | Replacement for Outage Details | 192247 | 3-High | Software | Closed | 2017-06-07 | 2017-06-08 |  |  |  |  | 2017 | 6 | 2017 | 5 | Y
47798 | CIRA | CIRA - Display label for environment the user is logged into |  | 4-Medium | Enhancement | Closed | 2017-06-21 | 2017-11-08 | 2017-11-13 |  |  |  | 2017 |  |  | 145 | [6 empty] | Y
47806 | CIRA | CIRA - TAC filter on Obligation report not working |  | 4-Medium | Software | Closed | 2017-06-21 | 2017-12-12 | 2018-03-05 |  | RSI-2017 |  | 2017 |  |  | 257 | [6 empty] | Y
47812 | CIRA | OM RA report data changes post the trade date |  | 3-High | Functionality | Closed | 2017-06-21 | 2017-06-30 | 2017-06-30 |  |  |  | 2017 | 6 | 2017 | 9 |  | Y
47870 | CIRA | ResourceAdequacyCapacity payload failures | 192418 | 3-High | Integration | Closed | 2017-06-24 | 2017-06-27 | 2017-06-27 |  |  |  | 2017 | 6 | 2017 | 3 | Y
47966 | CIRA | CIRA - CPM Enhancement to handle PMIN |  | 3-High | Enhancement | Closed | 2017-06-27 | 2017-11-08 | 2017-11-13 | 2017-07-31 |  |  | 2017 | 11 | 2017 | 139 | [6 empty] | Y
48047 | CIRA | SCE1 is getting an unknown error when they try to update August CSP Offers | 192592 | 3-High | Software | Closed | 2017-06-29 | 2017-06-30 |  |  |  |  | 2017 | 6 | 2017 | 5 | Y
48122 | RAAM | SCP Avail Data for resource for TDs in Septmeber2016 missing from the MF materialized view | 188697 | 3-High | Data | Closed | 2017-07-03 | 2017-07-13 |  |  |  |  | 2017 | 7 | 2017 | 14 |  |  | Y
48362 | CIRA | CIRA - OM Data report should disregard RA if deficiency config is set to N for obligation |  | 3-High | Requirement Gap | Closed | 2017-07-12 | 2017-07-20 |  |  |  |  | 2017 | 7 | 2017 | 12 |  |  | Y
48441 | CIRA | CIRA - NQC was uploaded with value as 0 |  | 4-Medium | Software | New | 2017-07-13 | [5 empty] | 2017 |  |  | FALSE
48679 | CIRA | Reduction in LSEs obligation did not reflect in the adjusted_obligation table | 193144 | 4-Medium | Software | New | 2017-07-21 | [5 empty] | 2017 |  |  | FALSE
48679 | CIRA | CIRA- CIDI 00193144 - Reduction in LSEs obligation did not reflect in the adjusted_obligation table |  | 4-Medium | Software | Open | 2017-07-21 | [5 empty] | 2017 |  |  | FALSE
49477 | CIRA | Nature of Work Rules need to be alighed with Reliability Requirement BPM | 193390 | 2-Very High | Requirement Gap | Closed | 2017-08-16 | 2017-08-25 |  |  |  |  | 2017 | 8 | 2017 | 13 |  |  | Y
49588 | CIRA | CIRA - release substitution did not reset Flex RA upon cancellation |  | 3-High | Software | Closed | 2017-08-21 | 2017-12-12 | 2018-03-05 |  | RSI-2017 |  | 2017 | 12 | 2017 | 196 | [6 empty] | Y
49589 | CIRA | CIRA - CIDI 00193890- October 2017 obligation for PGE TAC is different across the Obligation report and the CV | 193890 | 3-High | Software | Closed | 2017-08-21 | 2017-08-23 |  |  |  |  | 2017 | 8 | 2017 | 6 |  | Y
49868 | CIRA | Warning/Error/Confirmation messages does not refresh automatically when user navigate to new page |  | 4-Medium | Software | New | 2017-08-28 | [5 empty] | 2017 |  |  | FALSE
50484 | CIRA | RAAIM Precalc for Short-Term Use Limit Reached Nature of Work |  | 6-Enhancement |  | Closed | 2017-09-19 | 2018-03-26 | 2018-03-28 |  |  |  | 2017 |  |  | 190 | [6 empty] | Y
51246 | CIRA | Searching for Flex Resources is displaying all ITIE resources in the Forced Substitution screen |  | 6-Enhancement |  | Evaluated | 2017-10-12 | [5 empty] | 2017 |  |  | FALSE
51362 | CIRA | Import Allocations screen not allowing IA for 2018 | 195150 | 4-Medium | Software | Open | 2017-10-18 | [5 empty] | 2017 |  |  | FALSE
51373 | CIRA | During Flex CV run, LSE's Flex RA MW is not capped with Supplier's Flex RAMW. |  | 4-Medium | Software | Open | 2017-10-18 | [5 empty] | 2017 |  |  | FALSE
51694 | CIRA | Eligible Non-RA Capacity' is higher than the 'Availability MW' of external resource (TG) |  | 4-Medium | Software | Open | 2017-10-31 | [5 empty] | 2017 |  |  | FALSE
51778 | CIRA | ITC record added to Import Alloc screen does not show up for SC in the drop down - MWs do not show up for the LSE under view net allocation | 195863 | 6-Enhancement |  | Closed | 2017-11-03 | 2017-11-06 | 2017-11-06 |  |  |  | 2017 | 11 | 2017 | 3 | Y
51820 | CIRA | CIRA- Unable to upload annual obligation for 2018 from UI due to data volume |  | 4-Medium | Software | Open | 2017-11-06 | [5 empty] | 2017 |  |  | FALSE
51837 | CIRA | CIRA - Annual Obligation for LSE TPES does not match the output from CV |  | 3-High | Software | Closed | 2017-11-06 | 2017-11-07 | 2017-11-08 |  |  |  | 2017 | 11 | 2017 | 2 | Y
51904 | CIRA | CIRA handling of OMS ACL related outages |  | 3-High | Requirement Gap | Closed | 2017-11-08 | 2017-12-22 | 2018-01-08 |  |  |  | 2017 | 12 | 2017 | 61 | [6 empty] | Y
51915 | CIRA | Date filter for end date does not work as expected on import allocation screen |  | 5-Low | Software | New | 2017-11-09 | [5 empty] | 2017 |  |  | FALSE
51950 | CIRA | RA Report download needs label updates 'Flex MW' as 'Flex Supply MW' |  | 6-Enhancement |  | Closed | 2017-11-09 | 2018-03-27 | 2018-03-28 |  |  |  | 2017 | 3 | 2018 | 139 | [6 empty] | Y
52202 | CIRA | Monthly RA plan is allowing an end date = EOY in the Flex RA Capacity tab | 198570 | 4-Medium | Software | Open | 2017-11-20 | [5 empty] | 2017 |  |  | FALSE
52251 | CIRA | CIRA -CIDI 00198582 - OM Replacement UI is not showing outage records with status = IN_SERVICE |  | 3-High | Software | Closed | 2017-11-22 | 2017-11-23 | 2017-12-07 |  |  |  | 2017 | 11 | 2017 | 15 |  |  | Y
52336 | CIRA | SC transfer report date filters not working as expected |  | 4-Medium | Software | Open | 2017-11-28 | [5 empty] | 2017 |  |  | FALSE
52517 | CIRA | CIRA- CPM designation UI did not reflect the designated record because of multiple area records for the resource in the DB (past and present) |  | 3-High | Software | Closed | 2017-12-05 | 2017-12-15 | 2018-01-08 |  |  |  | 2017 | 12 | 2017 | 34 |  |  |  |  | Y
52572 | CIRA | EIM Enhancements - New NOW to be configured |  | 6-Enhancement |  | Closed | 2017-12-07 | 2017-12-22 | 2018-01-08 |  |  |  | 2017 | 12 | 2017 | 32 |  |  |  |  | Y
52693 | CIRA | CIRA- PMin should not be reduced from CPM MW for a non RA resource |  | 3-High | Requirement Gap | Closed | 2017-12-12 | 2017-12-22 | 2018-01-08 |  |  |  | 2017 | 12 | 2017 | 27 |  |  |  | Y
52763 | CIRA | CIRA - System does not trigger the broadcast when Annual CPMs are designated |  | 3-High | Software | Closed | 2017-12-13 | 2017-12-14 | 2017-12-18 |  |  |  | 2017 | 12 | 2017 | 5 | Y
52770 | CIRA | Adjust CPM job does not adjust CPMs these are outside of the month boundary |  | 4-Medium | Software | New | 2017-12-13 | [5 empty] | 2017 |  |  | FALSE
53214 | CIRA | Add TAC and local area to the Operational RA report output from OIA |  | 6-Enhancement |  | Closed | 2018-01-02 | 2018-03-22 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 85 | [6 empty] | Y
53279 | CIRA | Tracking substitution for outages with pro-rated POSO |  | 6-Enhancement |  | Closed | 2018-01-04 | 2018-03-26 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 83 | [6 empty] | Y
53675 | CIRA | Request to go back to the main RAAIM Pre-Calc screen from the Results screen | 201029 | 6-Enhancement |  | Open | 2018-01-18 | [5 empty] | 2018 |  |  | FALSE
53708 | CIRA | CPM should not be designated for TG & ITIE resources (until long term changes) |  | 6-Enhancement |  | Open | 2018-01-19 | [5 empty] | 2018 |  |  | FALSE
53847 | CIRA | Check to confirm user action prior to cancelling substitutions | 201256 | 6-Enhancement |  | Open | 2018-01-25 | [5 empty] | 2018 |  |  | FALSE
53859 | CIRA | Short' classification incorrect in some cases where RA exceeds obligation | 201261 | 3-High | Software | Closed | 2018-01-25 | 2018-02-02 | 2018-02-02 |  |  |  | 2018 | 2 | 2018 | 8 |  | Y
53906 | CIRA | The Outage Resource SCID and Potential Substitute Resource SCID columns have # character across some Outage Resources. |  | 4-Medium | Software | Open | 2018-01-29 | [5 empty] | 2018 |  |  | FALSE
53917 | CIRA | Search Outages grid in the Outage Exemptions screen does NOT have a progress indicator |  | 4-Medium | Software | Open | 2018-01-29 | [5 empty] | 2018 |  |  | FALSE
54040 | CIRA | Clean-up of plan validation status upon plan upload |  | 6-Enhancement |  | Open | 2018-02-02 | [5 empty] | 2018 |  |  | FALSE
54503 | CIRA | UNIT_TESTING NOW should be RAAIM Exempt (SDS#201611 and IMS#199963) | 201611 | 3-High | Requirement Gap | Closed | 2018-02-19 | 2018-03-06 | 2018-03-06 |  |  |  | 2018 | 3 | 2018 | 15 |  |  | Y
54512 | CIRA | Remove the 'substitution required' flag from the Create Forced Substitution UI |  | 6-Enhancement |  | Closed | 2018-02-20 | 2018-03-27 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 36 |  |  |  |  | Y
54786 | CIRA | RSI-2017 - Change message color to blue on Create Forced Sub UI | 202224 | 5-Low | Requirement Gap | Closed | 2018-03-01 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 7 |  | Y
54908 | CIRA | RA Operator role: Loss of mouse roll-over function for Menu Items |  | 3-High | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54909 | CIRA | Legacy data in RA Report |  | 3-High | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54910 | CIRA | Loss of type-ahead search capability on the RA Report |  | 3-High | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54914 | CIRA | Default view results to 500 on RA report |  | 4-Medium | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54915 | CIRA | Hide the top menu 'RA Validation' for the operator role |  | 4-Medium | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
55076 | CIRA | RAAIM Pre-calc missing an hour and duplicating the subsequent hour for Spring DST |  | 3-High | Software | Open | 2018-03-13 | 2018-03-19 | 2018-03-28 |  |  | DST-Spring | 2018 | 3 | 2018 | FALSE
55138 | CIRA | New OIA job should use the RSI-2017 date |  | 3-High | Software | Closed | 2018-03-15 | 2018-03-20 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 13 |  |  | Y
55360 | CIRA | RAAIM re-calc to send 0 MW in case of no exemption |  | 6-Enhancement |  | Closed | 2018-03-23 | 2018-03-26 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 5 | Y
55375 | CIRA | Forced substitution release not working as expected | 202861 | 3-High |  | Under test | 2018-03-26 | 2018-04-10 |  | 2018-04-30 |  |  | 2018 | 4 | 2018 | FALSE
55425 | CIRA | unable to approve replacements in production |  | 3-High | Software | Closed | 2018-03-28 | 2018-03-28 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 0 | Y
55510 | CIRA | OIA for RSI-2017 period throwing an error |  | 3-High | Software | Closed | 2018-04-04 | 2018-04-04 | 2018-04-04 |  |  |  | 2018 | 4 | 2018 | 0 | Y
55529 | CIRA | OIA fails for outage volume greater than 1000 |  | 3-High | Requirement Gap | Closed | 2018-04-05 | 2018-04-18 |  |  |  |  | 2018 | 4 | 2018 | 13 |  |  | Y
55560 | CIRA | Inflated exemption MW from RAAIM Pre-calc in case of 2 back-to-back exempt outages |  | 4-Medium | Requirement Gap | New | 2018-04-05 | [5 empty] | 2018 | 1 | 1900 | FALSE
55571 | CIRA | Choosing a SC which doesnt have any plans for a Month/Year is not giving an error message. |  | 4-Medium | Software | Closed | 2018-04-06 | 2018-04-09 |  |  |  |  | 2018 | 4 | 2018 | 3 | Y
55580 | CIRA | OIA performance for RSI-2017 code in production is slow |  | 3-High | Software | Closed | 2018-04-06 | 2018-04-18 |  |  |  |  | 2018 | 4 | 2018 | 12 |  |  | Y
55598 | CIRA | Forced Sub - RA Report not displaying correct FLEX RA for 3/10/2018 |  | 3-High | Data | Closed | 2018-04-09 | 2018-04-10 |  |  |  |  | 2018 | 4 | 2018 | 1 | Y
55754 | CIRA | Is_USE_LIMIT_curt flag is incorrect for USE_LIMIT_REACHED NOW | 194437 | 3-High | Config / Install | Closed | 2018-04-16 | 2018-04-17 | 2018-04-17 |  |  |  | 2018 | 4 | 2018 | 1 | Y
55772 | CIRA | ADD button for Deficiency Calc Config does not work |  | 4-Medium | Software | Closed | 2018-04-17 | 2018-04-17 |  |  |  |  | 2018 | 4 | 2018 | 0 | Y
55846 | CIRA | Download RA & Supply Plans unable to handle production volume of files |  | 4-Medium | Software | Closed | 2018-04-20 | 2018-05-22 |  |  |  |  | 2018 | 5 | 2018 | 32 |  |  |  |  | Y
55847 | CIRA | outage on S replacement resource not showing on the replacmeent required UI |  | 3-High | Software | Closed | 2018-04-20 | 2018-04-20 |  |  |  |  | 2018 | 4 | 2018 | 0 | Y
55873 | CIRA | End dating LSE ID causes the ID to drop off the drop-down list causing the plan file to no longer be visible from the UI | 202945 | 4-Medium | Software | New | 2018-04-23 | [5 empty] | 2018 | 1 | 1900 | FALSE
56161 | CIRA | POSO stack should not change due to forced outages |  | 3-High | Requirement Gap | Closed | 2018-05-04 | 2018-05-14 |  |  |  |  | 2018 | 5 | 2018 | 10 |  | Y
56323 | CIRA | Publish bilateral trades from CIRA to OASIS |  | 6-Enhancement |  | New | 2018-05-14 | [5 empty] | 2018 | 1 | 1900 | FALSE
56324 | CIRA | Add LRA ID to Flex Obligation Report |  | 6-Enhancement |  | New | 2018-05-14 | [5 empty] | 2018 | 1 | 1900 | FALSE
56326 | CIRA | OIA issue when outage point ends middle of the hour |  | 4-Medium | Requirement Gap | New | 2018-05-14 | [5 empty] | 2018 | 1 | 1900 | FALSE
56365 | CIRA | audit trail for admin parameters needed |  | 6-Enhancement | Requirement Gap | New | 2018-05-16 | [5 empty] | 2018 | 1 | 1900 | FALSE
56369 | CIRA | system does not allow plan submission on the cut-off date |  | 3-High | Requirement Gap | Closed | 2018-05-16 | 2018-06-19 | 2018-07-02 |  |  |  | 2018 | 6 | 2018 | 47 | [5 empty] | Y
56403 | CIRA | SC requesting API to retrieve OIA and POSO details |  | 6-Enhancement |  | New | 2018-05-17 | [5 empty] | 2018 | 1 | 1900 | FALSE
56481 | CIRA | Maintain latest templates in admin template list |  | 6-Enhancement | Documentation | New | 2018-05-21 | [5 empty] | 2018 | 1 | 1900 | FALSE
56767 | CIRA | pagination broken in create forced substitution screen |  | 3-High | Software | Closed | 2018-06-01 | 2018-06-05 |  |  |  |  | 2018 | 6 | 2018 | 4 | Y
56825 | CIRA | Bulk NQC upload did not occur in production due to performance issues |  | 4-Medium | Software | Closed | 2018-06-06 | 2018-08-21 |  |  |  |  | 2018 | 8 | 2018 | 76 | [6 empty] | Y
56890 | CIRA | Common confirmation message for plan and NQC upload needs to be broken up |  | 4-Medium | Design | Closed | 2018-06-11 | 2018-06-18 | 2018-07-02 |  |  |  | 2018 | 6 | 2018 | 21 |  |  |  | Y
56892 | CIRA | Hourly RT RAAIM pre-calc job is not processing exempt MW for planned outages correctly |  | 3-High | Software | Closed | 2018-06-11 | 2018-06-28 | 2018-07-02 |  |  |  | 2018 | 6 | 2018 | 21 |  |  |  | Y
56933 | CIRA | Ability to download substitutions from the Planned & Forced Substitution review screens |  | 6-Enhancement | Enhancement | New | 2018-06-12 | [5 empty] | 2018 | 1 | 1900 | FALSE
57070 | CIRA | Bulk download fails when there are multiple files with the same name in the zip file. |  | 4-Medium | Requirement Gap | Closed | 2018-06-19 | 2018-08-21 |  |  |  |  | 2018 | 8 | 2018 | 63 | [6 empty] | Y
57208 | CIRA | Flex exempt showing on non Flex hours when outage ends in between the hour |  | 4-Medium | Design | Closed | 2018-06-26 | 2018-06-26 |  |  |  |  | 2018 | 6 | 2018 | 0 | Y
57224 | CIRA | RAAIM Pre-calc to send 0 MW as positive confirmation when the outage is not exempt |  | 6-Enhancement | Enhancement | New | 2018-06-27 | [5 empty] | 2018 | 1 | 1900 | FALSE
57230 | CIRA | OIA Operation RA report results not viewed by internal user |  | 3-High | Design | Closed | 2018-06-27 | 2018-07-02 | 2018-07-03 |  |  |  | 2018 | 7 | 2018 | 6 |  | Y
57273 | CIRA | Resource-SC association not working as expected in CIRA |  | 6-Enhancement | Incident | Closed | 2018-06-28 | 2018-06-28 | 2018-06-28 |  |  |  | 2018 | 6 | 2018 | 0 | Y
57363 | CIRA | DAM payload not broadcasted for 7/1/18 |  | 3-High | Software | Closed | 2018-07-02 | 2018-07-05 | 2018-07-03 |  |  |  | 2018 | 7 | 2018 | 3 | Y
57391 | CIRA | manual recreation of DA RAAIM payload for 7/1 and 7/2 trade dates |  | 3-High | Software | Closed | 2018-07-03 | 2018-07-04 |  |  |  |  | 2018 | 7 | 2018 | 1 | Y
57397 | CIRA | Ability to re-publish day ahead for RAAIM Pre-calc |  | 6-Enhancement | Enhancement | Closed | 2018-07-03 | 2018-12-03 | 2018-12-26 |  |  |  | 2018 | 12 | 2018 | 176 | [6 empty] | Y
57416 | CIRA | Review production monitors for payloads broadcasted from CIRA |  | 4-Medium | Monitoring | New | 2018-07-05 | [5 empty] | 2018 | 1 | 1900 | FALSE
57596 | CIRA | RAAIM_PRECALC_CONFIG to be effective dated and have audit trail |  | 4-Medium | Enhancement | Closed | 2018-07-16 | 2018-12-03 | 2018-12-26 |  |  |  | 2018 | 12 | 2018 | 163 | [6 empty] | Y
57672 | CIRA | NQC bulk upload error handling for rejected files |  | 6-Enhancement | Enhancement | New | 2018-07-19 | [5 empty] | 2018 | 1 | 1900 | FALSE
57743 | CIRA | Ability to identify RA values at the time of DA closure |  | 6-Enhancement | Enhancement | Closed | 2018-07-24 | 2018-10-05 |  |  |  |  | 2018 | 10 | 2018 | 73 | [6 empty] | Y
57884 | CIRA | RAAIM pre-calc volume handling issue |  | 4-Medium | Enhancement | New | 2018-08-01 | [5 empty] | 2018 | 1 | 1900 | FALSE
58286 | CIRA | CPM designation screen not allowing the TAC area to be changed by the user |  | 3-High | Software | Closed | 2018-08-21 | 2018-08-28 | 2018-08-29 |  |  |  | 2018 | 8 | 2018 | 8 |  | Y
58287 | CIRA | OIA for planned & forced not reflecting Operational RA correctly |  | 3-High | Software | Closed | 2018-08-21 | 2018-08-28 | 2018-08-29 |  |  |  | 2018 | 8 | 2018 | 8 |  | Y
58340 | CIRA | DB is not processing OMS outages because of market organization ID length violation |  | 2-Very High | Requirement Gap | Closed | 2018-08-22 | 2018-08-22 | 2018-08-23 |  |  |  | 2018 | 8 | 2018 | 1 | Y
58350 | CIRA | NQC upload does not read the deliverability status correctly from the uploaded file |  | 4-Medium | Software | Closed | 2018-08-23 | 2018-08-28 | 2018-08-29 |  |  |  | 2018 | 8 | 2018 | 6 |  | Y
58480 | CIRA | error handling when CPM designation comments exceed 255 characters |  | 5-Low | Software | New | 2018-08-29 | [5 empty] | 2018 | 1 | 1900 | FALSE
58516 | CIRA | track outage IDs considered for RAAIM pre-calc run in the DB and allow the user to download this from the UI |  | 6-Enhancement | Enhancement | Closed | 2018-08-30 | 2018-12-19 | 2018-12-26 |  |  |  | 2018 | 12 | 2018 | 118 | [6 empty] | Y
58517 | CIRA | OMS: RA robustness |  | 6-Enhancement | Enhancement | New | 2018-08-30 | [5 empty] | 2018 | 1 | 1900 | FALSE
58586 | CIRA | Download files (Supply and RA) error out when there are multiple files with same name |  | 4-Medium | Software | New | 2018-09-04 | [5 empty] | 2018 | 1 | 1900 | FALSE
58594 | CIRA | handle resource termination as a warning rather than error for RAAIM pre-calc runs |  | 6-Enhancement | Enhancement | New | 2018-09-04 | [5 empty] | 2018 | 1 | 1900 | FALSE
58687 | CIRA | Ability to break-up RA into segments based on differing MOO flag when LF MSS sells capacity externally and also uses RA to self serve |  | 3-High | Enhancement | Closed | 2018-09-10 | 2018-09-20 |  |  |  |  | 2018 | 9 | 2018 | 10 |  | Y
58809 | CIRA | the application allowed NQC of 0 MW to be saved and |  | 4-Medium | Software | New | 2018-09-17 | [5 empty] | 2018 | 1 | 1900 | FALSE
58962 | CIRA | Missing curtailment MW - data clean-up and RAAIM pre-calc DA & RT re-run |  | 3-High | Data | Closed | 2018-09-25 | 2018-12-27 |  |  |  |  | 2018 | 12 | 2018 | 93 | [6 empty] | Y
59083 | CIRA | DB Script to create partitions |  | 4-Medium | Config / Install | Closed | 2018-10-01 | 2018-10-01 |  |  |  |  | 2018 | 10 | 2018 | 0 | Y
59114 | CIRA | Update CPM Designations End-Date |  | 4-Medium | Data | Closed | 2018-10-02 | 2018-10-02 |  |  |  |  | 2018 | 10 | 2018 | 0 | Y
59167 | CIRA | Handle error with OIA runs |  | 4-Medium | Software | New | 2018-10-04 | [5 empty] | 2018 | 1 | 1900 | FALSE
59179 | CIRA | Gen Obligation rpt - LSE sort not working for external users |  | 4-Medium | Software | New | 2018-10-05 | [5 empty] | 2018 | 1 | 1900 | FALSE
59194 | CIRA | Enhance POSO assignment UI to add outage start and end dates |  | 6-Enhancement | Enhancement | New | 2018-10-05 | [5 empty] | 2018 | 1 | 1900 | FALSE
59217 | CIRA | SC unable to perform future bilateral trades |  | 6-Enhancement | Enhancement | New | 2018-10-08 | [5 empty] | 2018 | 1 | 1900 | FALSE
59330 | CIRA | NQC approve_reject screen allows more records to be downloaded than a particular request ID provided by the user |  | 4-Medium | Software | New | 2018-10-11 | [5 empty] | 2018 | 1 | 1900 | FALSE
59377 | CIRA | CIRA Jobs stuck in InProgress |  | 4-Medium | Software | New | 2018-09-23 | [5 empty] | 2018 | 1 | 1900 | FALSE
59480 | CIRA | CPM designation for ITIEs needs to consider RA for the designation period not the trade month |  | 6-Enhancement |  | New | 2018-10-23 | [5 empty] | 2018 | 1 | 1900 | FALSE
59484 | CIRA | Dec Gen obligation report incorrect for many CPUC LSEs wherein the adj_DR does not reflect the 15% PRM |  | 4-Medium | Data | Closed | 2018-10-23 | 2018-10-24 |  |  |  |  | 2018 | 10 | 2018 | 1 | Y
59525 | CIRA | Upload NQC comments |  | 6-Enhancement | Data | Closed | 2018-10-25 | 2018-10-25 |  |  |  |  | 2018 | 10 | 2018 | 0 | Y
59575 | CIRA | DAM did not pick 2 outages that were not transmitted in time for the run to the system | 208166 | 3-High | Data | Closed | 2018-10-26 | 2018-11-12 | 2018-11-12 |  |  |  | 2018 | 11 | 2018 | 17 |  |  | Y
59943 | CIRA | Late calculation for the initial version of the plan submission is incorrect due to DST (extra hour) |  | 3-High | Software | Closed | 2018-11-15 | 2019-01-11 | 2019-01-23 |  |  |  | 2018 | 1 | 2019 | 69 | [6 empty] | Y
59955 | CIRA | LRA notification for short obligation should be based on LSEs only |  | 4-Medium | Software | Closed | 2018-11-15 | 2019-02-14 | 2019-01-23 |  |  |  | 2018 | 2 | 2019 | 91 | [6 empty] | Y
59991 | CIRA | RT and DA RAAIM pre-calc automated broadcasts failed since 11/14/19 |  | 3-High | Software | Closed | 2018-11-19 | 2018-11-20 |  |  |  |  | 2018 | 11 | 2018 | 1 | Y
60100 | CIRA | CIRA – Error handling capability during data upload for PEAK Demand Obligation and LCR by TAC Obligation. |  | 4-Medium | Software | New | 2018-11-29 | [5 empty] | 2018 | 1 | 1900 | FALSE
60168 | CIRA | Increase the length of LSE_SCID on table RR_IMPORT_ALLOC |  | 6-Enhancement | Enhancement | Closed | 2018-12-04 | 2018-12-05 | 2018-12-07 |  |  |  | 2018 | 12 | 2018 | 3 | Y
60433 | CIRA | Undo PMax/ PMin adjustments that was performed for a CPM resource, when the CPM is declined |  | 6-Enhancement | Requirement Gap | New | 2018-12-20 | [5 empty] | 2018 | 1 | 1900 | FALSE
60469 | CIRA | label incorrect on Late plans UI under Supply Plan download menu |  | 4-Medium | Software | Closed | 2018-12-26 | 2019-01-11 | 2019-01-23 |  |  |  | 2018 | 1 | 2019 | 28 |  |  |  | Y
60485 | CIRA | RAAIM pre-calc did not calculate exempt MW correctly for pre-RSI period |  | 3-High | Config / Install | Closed | 2018-12-27 | 2018-12-27 | 2018-12-27 |  |  |  | 2018 | 12 | 2018 | 0 | Y
60524 | CIRA | Handle OIA error when there is no data to return to the SC user (supplier roles) | 209378 | 4-Medium | Software | New | 2018-12-28 | [5 empty] | 2018 | 1 | 1900 | FALSE
60537 | CIRA | Error handling for telephone number on the Substitution screen |  | 4-Medium | Software | New | 2018-12-31 | [5 empty] | 2018 | 1 | 1900 | FALSE
60539 | CIRA | change in Flex RA Supply MW and category not reflected in RA tracker after Flex CV run |  | 3-High | Software | Closed | 2018-12-31 | 2019-01-11 | 2019-01-23 |  |  |  | 2018 | 1 | 2019 | 23 |  |  |  | Y
61114 | CIRA | LSE column heading incorrect on the LRA-LSE mapping UI |  | 6-Enhancement | Enhancement | New | 2019-01-29 | [5 empty] | 2019 | 1 | 1900 | FALSE
61116 | CIRA | Flex analysis shows 0 gap as 'short' incorrectly | 210059 | 4-Medium | Software | New | 2019-01-29 | [5 empty] | 2019 | 1 | 1900 | FALSE
61745 | CIRA | Configuration for LRA Notification job not completely set up |  | 4-Medium | Config / Install | New | 2019-02-26 | [5 empty] | 2019 | 1 | 1900 | FALSE
61832 | CIRA | Cannot view validation results |  | 3-High | Incident | Monitor | 2019-02-28 | [5 empty] | 2019 | 1 | 1900 | FALSE
61834 | CIRA | CIRA RA Validation Screen Error |  | 3-High | Software | Duplicate | 2019-02-28 | [5 empty] | 2019 | 1 | 1900 | FALSE
61911 | CIRA | User access denied error when SC ID is not picked in View Import allocation |  | 5-Low | Software | New | 2019-03-04 | [5 empty] | 2019 | 1 | 1900 | FALSE
44841, 51837 | CIRA | CIDI 00187927, CIRA's 2017 Annual CV LSE Obligation Details mismatch with Obligations rpt | 187927 | 4-Medium | Functionality | Closed | 2016-12-23 | 2017-11-20 | 2017-11-08 | 2017-10-01 |  |  | 2016 | 11 | 2017 | 332 | [6 empty] | Y