## PGaE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Jul 2022 TDF | Expected In-Service Oct 2022 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013 | Q1-2021 | Q1-2021 | In-Service | N/A | Q4-2018 | (blank)
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | Q3-2021 | Q3-2021 | In-Service | N/A | Q3-2021 | (blank)
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 |  | Q2-2022 | Q2-2022 | In-Service | N/A | Q3-2021 | (blank)
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023 | Q3-2022 | Q3-2022 | In-Service | N/A | Q3-2021 | (blank)
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015 | Q4-2022 | Q4-2022 | In-Flight | PTC: A.17-12-010 | Q3-2022 | (blank)
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021 | Q1-2023 | Q4-2022 | In-Flight | NOC: AL 5390-E | Q1-2022 | Q4 Notes: Reconductoring from Oro loma to Defrancesco Tap is complete. Remaining scope Expected complete Q4-2022
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019 | Q4-2022 | Q4-2022 | In-Flight | PTC: A.17-12-010 | Q3-2022 | (blank)
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015 | Q2-2023 | Q2-2023 | In-Flight | NOC: AL 5872E | Q2-2021 | (blank)
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E | 2018-2019 | 2023 | Q1-2023 | Q2-2023 | In-Flight | N/A | Q2-2022 | Q4 Notes: Construction Sequencing; Fault duty comes into target level after all reactors are replaced
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 |  | Q3-2023 | Q4-2023 | In-Flight | N/A | Q4-2021 | Q4 Notes: Material delays by vendor pushed FISD to Nov 2023.
Tesla 230 kV Bus Series Reactor project | PG&E | 2018-2019 | 2023 | Q3-2023 | Q4-2023 | In-Flight | N/A | Q2-2022 | Q4 Notes: Construction Sequencing
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA_230KV BUS REACTORS C – D | PG&E | 2018-2019 | 2023 | Q3-2023 | Q4-2023 | In-Flight | N/A | Q2-2023 | Q4 Notes: Construction Sequencing; Fault duty comes into target level after all reactors are replaced
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018 | Q4-2022 | Q4-2023 | In Flight | N/A | Q2-2020 | Q4 Notes: Work reprioritization.
Giffen Line Reconductoring Project | PG&E | 2018-2019 |  | Q1-2023 | Q1-2024 | In-Flight | NOC: AL 6600-E | Q4-2023 | Q4 Notes: Work reprioritization.
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013 | Q1-2024 | Q1-2024 | In-Flight | TBD | Q1-2024 | (blank)
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025 | Q2-2024 | Q2-2024 | In-Flight | N/A | Q1-2023 | Q4 Notes: Sensitive to supply chain risks and 3rd Party CEQA dependencies
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | Q3-2024 | Q2-2024 | In-Flight | TBD | Q4-2022 | Q4 Notes: The August 2024 date was a scheduling tool error and has been corrected to bring date back to Spring 2024.
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017 | Q2-2024 | Q2-2024 | In-Flight | NOC: AL 6047-E | Q2-2022 | Q4 Notes: BW Line: Q2-2023; BC Line: Q2-2024
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019 | Q4-2024 | Q4-2024 | Initiating | TBD | Q1-2024 | Q4 Notes: Project has not been initiated yet
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023 | Q4-2024 | Q4-2024 | Initiating | TBD | Q4-2023 | (blank)
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014 | Q4-2024 | Q4-2024 | In-Flight | N/A | Q3-2019 | (blank)
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016 | Q3-2024 | Q4-2024 | In-Flight | N/A | Q1-2024 | Q4 Notes: Work reprioritization.
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025 | Q3-2025 | Q1-2025 | In-Flight | TBD | Q4-2023 | Q4 Notes: Schedule Improvement. Further refinement to scope & schedule subject to change through the design process.
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011 | Q1-2025 | Q1-2025 | In-Flight | N/A | Q2-2024 | (blank)
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025 | Q2-2025 | Q2-2025 | Initiating | TBD | Q4-2024 | (blank)
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019 | Q1-2025 | Q2-2025 | In-Flight | N/A | Q4-2024 | Q4 Notes: Construction Sequencing starting with 115kV side followed by 230kV side.
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013 | Q2-2025 | Q2-2025 | In-Flight | N/A | Q2-2021 | (blank)
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009 | Q2-2024 | Q2-2025 | In-Flight | N/A | Q3-2022 | Q4 Notes: Work reprioritization.
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016 | Q2-2024 | Q3-2025 | In-Flight | N/A | Q2-2018 | Q4 Notes: Work reprioritization.
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014 | Q3-2025 | Q3-2025 | In-Flight | PTC: A.18-06-004 | Q2-2024 | Q4 Notes: Work reprioritization.
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024 | Q4-2025 | Q4-2025 | Initiating | TBD | Q4-2024 | (blank)
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019 | Q4-2025 | Q4-2025 | Initiating | TBD | Q4-2025 | Q4 Notes: Project has not been initiated yet
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023 | Q4-2025 | Q4-2025 | Initiating | TBD | Q4-2024 | (blank)
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021 | Q2-2024 | Q4-2025 | In-Flight | CPCN: A.17-12-021 | Q1-2024 | Q4 Notes: Work reprioritization.
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023 | Q3-2025 | Q4-2025 | In-Flight | TBD | Q3-2025 | Q4 Notes: PEA/permit to purchase the land is in progress (project cannot proceed without purchasing the land); PTC permit will take up to 2 years
Reedley 70 kV Reinforcement (Renamed to Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017 | Q4-2025 | Q4-2025 | In Flight | N/A | Q1-2024 | (blank)
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019 | Q4-2025 | Q4-2025 | In Flight | N/A | Q1-2025 | (blank)
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022 | Q4-2024 | Q1-2026 | In-Flight | N/A | Q4-2025 | Q4 Notes: Work reprioritization
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026 | Q2-2026 | Q2-2026 | Initiating | TBD | Q1-2025 | Q4 Notes: Project has not been initiated yet
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028 | Q2-2026 | Q2-2026 | Initiating | TBD | Q2-2025 | (blank)
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022 | Q2-2026 | Q2-2026 | Initiating | TBD | Q4-2025 | (blank)
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027 | Q2-2026 | Q2-2026 | Initiating | TBD | Q2-2025 | (blank)
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021 | Q2-2026 | Q2-2026 | In-Flight | NOC: AL 5200-E | Q1-2025 | (blank)
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019 | Q2-2026 | Q2-2026 | In Flight | NOC: AL 5026-E | Q4-2018 | Q4 Notes: The Midway-Kern #2 230kV depends on the Midway Section D Bus Upgrade project to provide a new open terminal position for the new 230kV line.
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | Q2-2026 | Q3-2026 | In-Flight | TBD | Q3-2026 | Q4 Notes: Awaiting PM Assignment
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026 | Q4-2026 | Q4-2026 | Initiating | TBD | Q2-2026 | Q4 Notes: Project has not been initiated yet
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022 | Q4-2026 | Q4-2026 | Initiating | TBD | Q4-2024 | Q4 Notes: Project has not been initiated yet
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026 | Q4-2026 | Q4-2026 | Initiating | TBD | Q2-2025 | Q4 Notes: Project has not been initiated yet
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024 | Q4-2026 | Q4-2026 | Initiating | TBD | Q4-2025 | (blank)
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024 | Q4-2026 | Q4-2026 | Initiating | TBD | Q4-2025 | Q4 Notes: Project has not been initiated yet
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020 | Q4-2026 | Q4-2026 | Initiating | N/A | Q1-2023 | (blank)
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021 | Q4-2026 | Q4-2026 | In-Flight | NOC - TBD on Filing Date | Q3-2025 | (blank)
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024 | Q2-2026 | Q4-2026 | In-Flight | TBD | Q3-2026 | Q4 Notes: Awaiting PM Assignment
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | Q4-2026 | Q4-2026 | In Flight | NOC - May 2024 | Q1-2026 | (blank)
Estrella Substation Project | PG&E | 2013-2014 | 2019 | Q3-2026 | Q1-2027 | In-Flight | PTC: A.17-01-023 | Q4-2023 | Q4 Notes: Permitting delays and unknown project scope until after PTC issuance is driving the project’s in-service delays.
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027 | Q2-2027 | Q2-2027 | Initiating | TBD | Q4-2025 | (blank)
South of San Mateo Capacity Increase | PG&E | 2007 | 2009 | Q2-2027 | Q2-2027 | Initiating | TBD | Q1-2026 | Q4 Notes: Project has not been initiated yet
South of Mesa Upgrade | PG&E | 2018-2019 | 2023 | Q2-2026 | Q2-2027 | In Flight | NOC - Feb 2024 | Q4-2025 | Q4 Notes: Work reprioritization.
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016 | Q3-2027 | Q3-2027 | In Flight | NOC - TBD on Filing Date | Q1-2025 | (blank)
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | (blank)
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | Q4 Notes: Project has not been initiated yet
Maple Creek Reactive Support | PG&E | 2009 | 2011 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | Q4 Notes: Project has not been initiated yet
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008 | Q4-2027 | Q4-2027 | Initiating | N/A | Q4-2026 | (blank)
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027 | Q4-2027 | Q4-2027 | Initiating | N/A | Q4-2025 | Q4 Notes: Project has not been initiated yet
Mosher Transmission Project | PG&E | 2013-2014 | 2017 | Q4-2027 | Q4-2027 | In Flight | NOC - April 2026 | Q1-2027 | (blank)
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022 | Q1-2028 | Q1-2028 | In-Flight | N/A | Q2-2026 | (blank)
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | Q3-2027 | Q1-2028 | In Flight | N/A | Q2-2025 | Q4 Notes: Work reprioritization.
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022 | Q2-2028 | Q2-2028 | Initiating | TBD | Q1-2025 | (blank)
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022 | Q2-2028 | Q2-2028 | In-Flight | TBD | Q1-2027 | (blank)
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018 | Q2-2028 | Q3-2028 | In Flight | NOC - April 2026 | Q3-2026 | (blank)
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q4 Notes: Project has not been initiated yet
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023 | Q4-2027 | Q4-2028 | Initiating | TBD | Q4-2026 | Q4 Notes: Work reprioritization.
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q4 Notes: Project has not been initiated yet
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q4 Notes: Project has not been initiated yet
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q2-2026 | Q4 Notes: Project has not been initiated yet
New Manning 500 kV substation | PG&E | 2021-2022 | 2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q1-2027 | Q4 Notes: Project has not been initiated yet
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q4 Notes: Project has not been initiated yet
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q4 Notes: Project has not been initiated yet
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028 | Q4-2028 | Q4-2028 | Initiating | TBD | Q1-2026 | Q4 Notes: Project has not been initiated yet
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017 | Q1-2029 | Q1-2029 | In-Flight | CPCN Expected Q4 2022 | Q4-2026 | Q4 Notes: CEQA process presently under way
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022 | Q2-2029 | Q2-2029 | In Flight | TBD | Q3-2027 | (blank)
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028 | Q4-2029 | Q4-2029 | Initiating | TBD | Q4-2028 | Q4 Notes: Project has not been initiated yet
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015 | Q4-2030 | Q1-2030 | Initiating | TBD | Q1-2028 | Q4 Notes: Schedule Improvement. Further refinement to scope & schedule subject to change through the design process.
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021 | Q3-2026 | Q2-2030 | In-Flight | NOC - TBD on Filing Date | Q1-2026 | Q4 Notes: Work reprioritization.
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020 | Q2-2029 | Q2-2029 | On-Hold (CAISO) | CPCN - TBD on Filing Date | Q3-2025 | Q4 Notes: Work reprioritization.
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019 | Q4-2029 | Q4-2029 | On-Hold (CAISO) | CPCN - TBD on Filing Date | Q1-2024 | (blank)
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023 |  |  | On-Hold (CAISO) | TBD |  | (blank)

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date July 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Laguna Bell Corridor Upgrade | SCE | 2015 | 2020-12-31 | N/A | N/A | In-Service | N/A | N/A | Currently in-service; completed as a portion of Mesa 500 kV Substation Loop-In
Moorpark-Pardee No. 4 230 kV Circuit | SCE | 2018 | 2020-12-31 | N/A | N/A | In-Service | N/A | N/A | In-service January 2022
Mesa 500 kV Substation Loop-In | SCE | 2014 | 2020-12-01 | 2022-05-22 | 2022-05-22 | In-Service | N/A | N/A | In-service May 2022
Lugo-Mohave series capacitor upgrade | SCE | 2013 | 2016 | 2023-06-01 | 2023-12-31 | Construction | 2018-05-01 | 2020-12-01 | Most of the project expected in-service by June 2023 with full compensation by December 2023
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2013 | 2016 | 2023-06-01 | 2023-12-31 | Construction | 2018-05-01 | 2020-12-01 | Most of the project expected in-service by June 2023 with full compensation by December 2023
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2025-12-31 | Design | Exempt | 2024-10-01
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2017 | 2018-12-31 | 2025-01-25 | 2025-01-31 | Construction | Exempt | Construction started | Joint SCE/LADWP project. SCE completed raising its towers and LADWP's are in progress. Substation upgrades (breakers and terminal equipment) require synchronizing outages with LADWP.
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | 2027-04-01 | 2027-04-30 | Permitting | 2009-09-01 | Pending | Alberhill dates contingent on licensing
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2027-07-01 | 2027-07-31 | Design | 2015-04-01 | 2023-05-01
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2020 | 2023-06-01 | 2024-06-01 | 2025-06-30 | Design | Exempt | 2022-10-22 | Joint SCE/LADWP project. ISD for SCE’s portion of the project remains June 2024 (as reported in July 2022 TDF). Expected ISD of June 2025 includes LADWP's portion of the project.
Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 2025-12-01 | 2025-12-31 | Construction | N/A | Construction started | The in-service dates range from September 2022 to December 2025
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | 2023-12-01 | 2023-12-31 | Design | Pending | 2023-12-31
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 | 2025-12-01 | 2025-12-31 | Planning | N/A | Pending
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | Pending | 2025-06-30 | Design | N/A | Pending
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | Pending | Pending | Initiation | N/A | Pending

## SDGaE
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service July 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-10-22 | 2021-11-01 | Close-out | Exempt | 2021-05-17
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-05-15 | 2022-05-15 | Construction | Exempt | 2022-02-04
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2022-12-27 | 2022-10-20 | Construction | 2017-06-28 | 2021-01-19
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-12-27 | 2022-11-18 | Construction | 2017-11-15 | 2022-01-03
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-12-13 | 2022-12-02 | Construction | 2016-08-17 | 2020-06-10
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2023-10-24 | 2023-10-24 | Construction | Exempt | 2021-07-26
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2024-05-28 | 2024-05-28 | Construction | 2012-05-18 | 2018-06-29
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2024-12-23 | 2024-10-21 | Design | 2023-08-22 | 2024-08-19
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 2022-06-01 | 2022-08-24 | 2024-10-21 | Planning | TBD | TBD
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 1905-07-08 | 2025-10-24 | 2025-08-28 | Design | 2016-04-25 | 2024-08-09
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2026-05-13 | 2026-04-16 | Design | 2023-09-01 | 2024-03-01
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2026-11-25 | 2027-03-12 | Design | Exempt | 2025-03-20
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-20 | 2027-10-14 | Design | 2026-07-24 | 2027-04-12
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 2022-06-01 | 2024-08-15 | 2029-06-04 | Planning | TBD | 2024-07-19

## VEA_GLW
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date July 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 2021 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service | In service | N/A | 2021
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2022-12-20 | 2022-12-20 | In Flight | N/A | Sept-21
GLW/VEA area upgrades | VEA/GLW | 2021-2022 | TBD |  |  | Permitting, engineering and design | N/A | TBD

## DCRT
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date July 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | Inflight | Approved

## LSPower
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date July 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01 | In-Flight
Round Mountain 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-12-01 | 2024-12-01 | In-Flight

## CitizensEnergy
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date July 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | In-Flight