## Roadmap
Theme | Category | Topic | Sub Topics | Target Release Date | B2B API Impact | Comments
Additional functionality | Usability | Populate queue number to be automatically on submission of a request | The queue number is for new NQC request from RIMS
Additional functionality | API | API to upload RA/Supply Plans | API Functionality supporting plan submittal, LSE/Supplier communication and daily RA commitments |  | Y - priority 3 | Descoped from RSI-1B
Additional functionality | API | API to submit CSP Offers |  |  | Y - priority 2 | Descoped from RSI-1B
Additional functionality | Reporting | Post bilateral trades and NQC report on OASIS |  | RSI 1B
Additional functionality | Automation of workflow | Acquired contracts |  | RSI 1B
Additional functionality | API | API to submit submit/retreive substitutions |  |  | Y - priority 1 | Descoped from RSI-1B
Additional functionality | Reporting | Public posting of CSP Offers |  | RSI 1B |  | Will be posted to OASIS
Additional functionality | Reporting | Ability to download/export non-RA capacity data |  | RSI 1B
Additional functionality | Notification | Notification to SC of any Outage replacement approval request |  | RSI 1B |  | POSO implementation
Additional functionality | Usability | Pre-population of compliance month on filters | Ability to not have to select the compliance month for every filter (validation, TAC obligation, Peak obligation, outage replacement, outage impact)
Additional functionality | Business process | More frequent processing of EFC requests |  | RSI 2
Additional functionality | API | API Functionality for Replacements |  |  | Y - will likely not be needed with replacements being phased out with RSI - 1B | Descoped from RSI-1B. However, given the importance to MPs, this is under assessment if it can be delivered earlier.
Additional functionality | Error handling | Error messages during uploads | Detailed error/warning codes on RA/Supply Plan uploads (resource not in matching plan is not sufficient to coordinate) |  |  | Need information from stakeholder
Additional functionality | Business process | Coordination of supply plans | Improved ability to coordinate supply plans with counterparties and better facilitate sales and re-sales |  |  | Need information from stakeholder
Performance | Business process | Frequent runs of validation | More timely validation runs. SCs do not have to wait until next day or late afternoon to see immediate results. Stakeholder requested every 30 mins if there are changes to Plans. | RSI 1B |  | ISO will schedule two additonal runs. One at noon and one at 3 PM.
Additional functionality | Policy | Ability to nominate and receive Import Allocations Steps 8-11
Additional functionality | Policy | Adopt the CPUC MCC buckets construct fully. | This will allow firm imports to count across the entire month instead of only on peak days.
Additional functionality | Notification | Requesting CPM Mw on CPM Email |  | RSI-1B |  | CIDI 00186412
Additional functionality | Export/ Import, New columns | Export substitutions, import/export CSP offers, new columns in review substitution screen | a. Request to provide Export Functionality in Review Substituions Screen. b. Import/export buttons in CSP offer screen. c. Import/export buttons in Review Substitution screen. d. Add two additional columns in Review Substitution screen with Gen & Flex substitution MW amount to be import/export easily & effectively. |  |  | CIDI-00187965; ALM 44850
Additional functionality | Usability | Supply and RA plans | System must have the ability for ISO users to download multiple RA/Supply Plans (excel files) across SCs for a given trade year and trade month. Note: ISO users must be able to select multiple RA/Supply Plans and then download them all at once. It will not be acceptable to download each RA/Supply Plan individually. |  |  | Impacts ISO efficiency
Additional functionality | Unification | Resource to area mapping | controlling the entry points to where updates to this information can be made in CIRA. |  |  | Impacts ISO's controls and error handling.
Additional functionality | Business process | CPM | CIDI-00181232: ability to cancel an ED once it has been declined We can put a warning "This action will result in supplemental revenue for the next 30 days. Do you wish to continue?“ CIDI-00181230: After search, the monthly/intra-monthly/annually and start and end dates should be available so that users shouldn't have to reload the screen to re-query the results. CIDI-00181223: CPM Type should be more descriptive |  |  | ALM 43448 postponed
Additional functionality | Business process | CSP offers | CIDI-00181431 -Allow users to load offers from Monthly and copy into Intra-monthly offers. |  |  | ALM 41007 postponed
Additional functionality | Business process | CSP offers | Make the CSP Offers window variable size. The search for available resources window is able to be variable size but the CSP offers window is not. It would be easier if the window can be made longer to let users see the entire list of offers. |  |  | ALM 41008 postponed
Additional functionality | Business process | Substitution | Not able to create RT Subs from Next Day onward |  |  | ALM 40824 postponed
Additional functionality? | Reporting | RA data, Outage data, Replacement data, Substitution data | CIDI 00185139 - Request for addition of operational RA data to the MPPF meetings, specifically: 1. Total RA Local/System/Flex requirements for the past, current and next month 2. Total RA Local/System/Flex resources provided to ISO daily 3. Total Planned Outage MWs that impacted the RA available MWs by day 4. Total Forced Outage MWs that impacted teh RA available MWs by day 5. Total MWs of replacement capacity provided for planned outages by day 6. Total MWs of substitute capacity provided for forced outages by day |  |  | SDG's request is with the Data Release Committee for consideration.
Additional functionality | API | API to retrieve POSO assignments |  |  | Y - priority 1
Additional functionality | API | API to retrieve RA Data | to include all data elements on the RA tracker in the MOO flag payload |  | Y - priority 4
Additional functionality | API | API to retrieve NQC data |  |  | Y - priority 4
Additional functionality | API | API to retrieve RAAIM pre-calculation run details |  |  | Y - priority 4

## Severity123
Issue # | System | Short Description | CIDI | Severity | Status | Deployment date | ETA | Deployment Month | Deployment Year
42018 | CIRA | RA Plan versioning is incorrect which impacts the validation run. |  | 3-High | Closed | 2016-08-25 |  | 8 | 2016
41877 | CIRA | CIRA Application was down and up frequently in Production |  | 3-High | Closed | 2016-08-25 |  | 8 | 2016
41754 | RAAM | Dispute #181646 SCP calculation run is not picking up Substitute resource in some cases |  | 3-High | Closed | 2016-08-25 |  | 8 | 2016
41557 | CIRA | Market participants are unable to submit replacements in CIRA |  | 3-High | Closed | 2016-08-25 |  | 8 | 2016
42138 | CIRA | RSI-Phase 1A: MKT SIM Jul16 Obligation Rpts Peak Demand Showing Not Reflecting Subset of Days Resource |  | 2-Very High | Closed | 2016-09-21 |  | 9 | 2016
42180 | CIRA | Export screen data from NQC results not matching the filter results on the screen |  | 3-High | Closed | 2016-09-21 |  | 9 | 2016
40569 | CIRA | RSI-Phase 1A: MKT SIM CIDI (00180481) CIRA calculates the NQC values for PV resources using SOLAR Tech Factor instead of PV Tech Factor | 180481 | 3-High | Closed | 2016-09-21 |  | 9 | 2016
40560 | CIRA | RSI-Phase-1A: MKT_SIM (00177093) The ResourceID column does not sort on CSP offer screen |  | 3-High | Closed | 2016-09-21 |  | 9 | 2016
38633 | CIRA | RSI-Phase 1A: MKT SIM CIDI 177117: Make the SC Email 2 editable for participants : On the CSP offers screen | 177117 | 3-High | Closed | 2016-09-21 |  | 9 | 2016
33967 | CIRA | RCINT-WebOMS - Modify- When transmission Outage status is modified from OUT to IN SERVICE EDITABLE ,the outage status is not updated on PeakRC |  | 3-High | Closed | 2016-09-21 |  | 9 | 2016
43565 | CIRA | CIRA Int - WebOMS recently switched to V2 version of the service |  | 2-Very High | Closed | 2016-09-29 |  | 9 | 2016
43555 | CIRA | Settlements not receiving Exempt_quantity from SCP Availability Calculations |  | 3-High | Closed | 2016-09-30 |  | 9 | 2016
43610 | CIRA | CV errors our Supply/RA resources with incorrect Import allocation check |  | 3-High | Closed | 2016-10-05 |  | 10 | 2016
43602 | CIRA | RSI1A - Adjust timing for day ahead RAAIM calculation (CIDI 00185167) | 185167 | 3-High | Closed | 2016-10-05 |  | 10 | 2016
44136 | CIRA | change the scheduled time for 'SG_BroadcastResourceAdequacyCapacityData_CIRAv1' payload |  | 3-High | Closed | 2016-11-04 |  | 11 | 2016
44087 | CIRA | remove ReceiveResourceAdequacyCapacityData_MFv1_INT_AP from AI/ESB |  | 4-Medium | Closed | 2016-11-07 |  | 11 | 2016
44211 | CIRA | Missing service for receciveRTMResourceAdequacyCapacityData to Settlements |  | 3-High | Closed | 2016-11-08 |  | 11 | 2016
44281 | CIRA | Ignore EDs with same start and end times i.e. cancelled EDs |  | 3-High | Closed | 2016-11-11 |  | 11 | 2016
44257 | CIRA | ISO offers not created when SC did not bid for intra-monthly |  | 3-High | Closed | 2016-11-11 |  | 11 | 2016
44231 | CIRA | CIDI 00186633 - Bilateral trade screen should allow SC ID same size as exists in MF | 186633 | 6-Enhancement | Closed | 2016-11-11 |  | 11 | 2016
44259 | CIRA | ISO user unable to approve saved NQC record for SC's with future effective date |  | 3-High | Closed | 2016-11-17 |  | 11 | 2016
44215 | CIRA | Annual CV calculations are incorrect |  | 3-High | Closed | 2016-11-17 |  | 11 | 2016
44133 | CIRA | CIDI 00186484- 'No LSE found for supplier x for resource y' error | 186484 | 4-Medium | Closed | 2016-11-17 |  | 11 | 2016
44346 | CIRA | MED integration issue - resources where RA = PMax need to be sent in the payload |  | 6-Enhancement | Closed | 2016-11-17 |  | 11 | 2016
44391 | CIRA | CIRA APP is producing errors in server log, the bigger log is causing diskspace issue in Production |  | 2-Very High | Closed | 2016-12-02 |  | 12 | 2016
44303 | CIRA | app_cira_bid_write_ext user is able to access\view Approve-Reject OM Replacements screen |  | 2-Very High | Closed | 2016-12-02 |  | 12 | 2016
44522 | CIRA | CIDI 00187331 - Obligation report missing data by Peak | 187331 | 3-High | Closed | 2016-12-02 |  | 12 | 2016
44511 | CIRA | CIDI 00187300 - 2017 NQC resource validation using tech factor for 2016 | 187300 | 3-High | Closed | 2016-12-02 |  | 12 | 2016
44497 | CIRA | app_cira_availcalc_int role user is unabe to access RAAIM Calculation functionality in CIRA application. |  | 3-High | Closed | 2016-12-02 |  | 12 | 2016
44488 | CIRA | Date on RAAIM Pre-calc run details screen different from Excel download |  | 3-High | Closed | 2016-12-02 |  | 12 | 2016
44462 | CIRA | CPM designation UI not displaying resources with multiple SC association |  | 3-High | Closed | 2016-12-02 |  | 12 | 2016
44432 | CIRA | CIDI 186988: SC gets an error while trying to approve SRs | 186988 | 3-High | Closed | 2016-12-02 |  | 12 | 2016
44379 | CIRA | CIDI 00186979 Import allocation issue | 186979 | 3-High | Closed | 2016-12-02 |  | 12 | 2016
44325 | CIRA | CSP offer not created for a res that has multiple records in MF for the same Resource- SC association |  | 3-High | Closed | 2016-12-02 |  | 12 | 2016
44635 | CIRA | CIDI-00187435: SCs are not able to access Approve/Reject OM Replacments screen | 187435 | 3-High | Closed | 2016-12-13 |  | 12 | 2016
44548 | CIRA | CIDI 00186598 - MOO flag needs to be derived at the time of payload broadcast | 186598 | 3-High | Closed | 2016-12-13 |  | 12 | 2016
44216 | CIRA | Missing plans functionality not working for annual |  | 4-Medium | Closed | 2016-12-13 |  | 12 | 2016
44035 | CIRA | Unable to approve future effective NQC for 1 resource in prod |  | 4-Medium | Closed | 2016-12-13 |  | 12 | 2016
44553 | CIRA | multiple CPM designation emails generated for the same resource |  | 5-Low | Closed | 2016-12-13 |  | 12 | 2016
43955 | CIRA | (CIDI 00186092) Spelling error when downloading Obligation Report from the UI | 186092 | 5-Low | Closed | 2016-12-13 |  | 12 | 2016
44641 | CIRA | ED CPM enhancement |  | 6-Enhancement | Closed | 2016-12-13 |  | 12 | 2016
44261 | CIRA | CIDI 00186601 - TG not allowed to submit CSP offer for Flex even when EFC/NQC exists for that month | 186601 | 6-Enhancement | Closed | 2016-12-13 |  | 12 | 2016
44690 | CIRA | CIDI-00187618: CIRA doesn't bump up the RA capacity by 0.01 when RA=Pmin for SIBR | 187618 | 3-High | Closed | 2016-12-14 |  | 12 | 2016
44681 | CIRA | Search for all resources on compatible resources view screen times out |  | 4-Medium | Closed | 2016-12-20 |  | 12 | 2016
44924 | CIRA | RTM RA payload to Settlements failed due to a resource end dating |  | 3-High | Closed | 2017-01-03 |  | 1 | 2017
| CIRA | Get map_stage in sync with prod code and then turn off the test CPM email notifications |  | 4-Medium | Closed | 2017-01-03 |  | 1 | 2017
| CIRA | open for provisioning CIRA read only role and CIRA external offer read only role |  | 4-Medium | Closed | 2017-01-05 |  | 1 | 2017
44914 | CIRA | CIDI 00188019 - RA report not taking into account multiple replacement records | 188019 | 3-High | Closed | 2017-01-10 |  | 1 | 2017
44810 | CIRA | annual optimization is failing |  | 3-High | Closed | 2017-01-10 |  | 1 | 2017
44793 | CIRA | include null RMRFLAG records for CPM calculations |  | 3-High | Closed | 2017-01-10 |  | 1 | 2017
43563 | CIRA | RSI-1A: Search not working as expected on CPM Designation screen (CIDI 00184091) | 184091 | 4-Medium | Closed | 2017-01-10 |  | 1 | 2017
39654 | CIRA | RSI_Phase1a_Search Substitution Requests_Substitutions are showing up when there is no substitution in compliance month |  | 4-Medium | Closed | 2017-01-10 |  | 1 | 2017
44835 | CIRA | defining allowable period for declining CPM |  | 6-Enhancement | Closed | 2017-01-10 |  | 1 | 2017
44833 | CIRA | rules for updates to the CPM designation screen |  | 6-Enhancement | Closed | 2017-01-10 |  | 1 | 2017
44913 | CIRA | CIDI 00187978 - RAAIM Pre-calc is not handling DST time | 187978 | 3-High | Closed | 2017-01-13 |  | 1 | 2017
44911 | CIRA | CPM should be designated for only CISO resources with an active SC association |  | 3-High | Closed | 2017-01-13 |  | 1 | 2017
44956 | CIRA | Modify CPM email verbiage |  | 4-Medium | Closed | 2017-01-13 |  | 1 | 2017
45167 | CIRA | For FLEX RA category 3 resources RA not calculated correctly for days bordering weekends and holidays |  | 3-High | Closed | 2017-02-01 |  | 2 | 2017
45036 | CIRA | CPM emails are triggered for more resources than the one submitted |  | 3-High | Closed | 2017-02-01 |  | 2 | 2017
45287 | CIRA | Error in logs due to length of CSP_OFFER_SEGMENT.COMMENTS |  | 3-High | Closed | 2017-02-08 |  | 2 | 2017
45399 | CIRA | CIDI 00188973 - Peak & TAC reports are displaying an incorrect 'Specified Replacement Increase' value on outage dates | 188973 | 3-High | Closed | 2017-02-13 |  | 2 | 2017
45333 | CIRA | Issue with reading the MOO flag from MF due to date/time offset |  | 3-High | Closed | 2017-02-13 |  | 2 | 2017
45269 | CIRA | CIDI 188202 - availability calculation is incorrect for TG in RAAM | 188202 | 3-High | Closed | 2017-02-13 |  | 2 | 2017
45699 | CIRA | CIRA - Replacement MW higher than provided as S replacements in RA plan- occurred due to multiple resources with different RA plans used the same contract ID. Handled via training & CPG not code fix |  | 3-High | Closed | NA |  | 2 | 2017
46152 | CIRA | CIRA INT - rename RTM resource adequacy capacity payload as part of ESB replacement |  | 3-High | Open |  | 2017-03-20 | 3 | 2017
46143 | CIRA | CIRA - CIDI 00189853, 00189824 - RAAIM inconsistent with CAISO Tariff for Flex LF-MSS resources |  | 3-High | Open |  | 2017-04-10 | 4 | 2017
46070 | CIRA | RAAIM calculation failure due to DST Short day Data fix will be applied first; code fix will follow later |  | 3-High | Open |  | 2017-04-10 | 4 | 2017
46026 | CIRA | ReceiveResourceAdequacyCapacityData_SIBRv1_AP failure due to missing HE19 data - (impact to spring forward date/time) Data fix applied; code fix will follow later |  | 3-High | Open |  | 2017-04-10 | 4 | 2017
43972 | OASIS | RA and Minimum Load data | 185424 | 3-High | Open |  | 2017-03-31 | 3 | 2017
45805 | CIRA | CIRA - Intra-monthly final offer automated run does not create an extension when there is no CSP offer from the SC (manual work-around exists) |  | 4-Medium | Open |  | 2017-04-10 | 4 | 2017
44841 | CIRA | CIDI 00187927, CIRA's 2017 Annual CV LSE Obligation Details mismatch with Obligations rpt | 187927 | 4-Medium | Open |  | 2017-04-10 | 4 | 2017
44326 | CIRA | Resource area mapping is not updating when you upload and approve the NQC |  | 4-Medium | Open |  | 2017-04-10 | 4 | 2017

## Statistics
Issue Counts by Status
Issue Status | Count
Closed | 64
Open | 8
Grand Total | 72
Issues resolved by deployment year and month
Count of Issues | Deployment Month & Year
| 2016 |  |  |  |  | 2016 Total | 2017 |  |  |  | 2017 Total | Grand Total
Severity | 8 | 9 | 10 | 11 | 12 |  | 1 | 2 | 3 | 4
2-Very High |  | 2 |  |  | 2 | 4 | [5 empty] | 4
Closed |  | 2 |  |  | 2 | 4 | [5 empty] | 4
3-High | 4 | 6 | 2 | 6 | 11 | 29 | 6 | 7 | 2 | 3 | 18 | 47
Closed | 4 | 6 | 2 | 6 | 11 | 29 | 6 | 7 |  |  | 13 | 42
Open | [8 empty] | 2 | 3 | 5 | 5
4-Medium |  |  |  | 2 | 3 | 5 | 5 |  |  | 3 | 8 | 13
Closed |  |  |  | 2 | 3 | 5 | 5 |  |  |  | 5 | 10
Open | [9 empty] | 3 | 3 | 3
5-Low |  |  |  |  | 2 | 2 | [5 empty] | 2
Closed |  |  |  |  | 2 | 2 | [5 empty] | 2
6-Enhancement |  |  |  | 2 | 2 | 4 | 2 |  |  |  | 2 | 6
Closed |  |  |  | 2 | 2 | 4 | 2 |  |  |  | 2 | 6
Grand Total | 4 | 8 | 2 | 10 | 20 | 44 | 13 | 7 | 2 | 6 | 28 | 72