## Roadmap Summary
Status | Open
Count of Topic | Column Labels
Initiative | API | Automation of workflow | Business process | Export/ Import, New columns | Policy | Reporting | Unification | Usability | Grand Total
TBD | 7 | 1 | 6 | 1 | 2 |  | 1 | 3 | 21
Future |  |  | 6 | 1 | 2 |  |  | 3 | 12
Ops Enhancements | 7 | 1 |  |  |  |  | 1 |  | 9
Fall 2018 |  | 2 | 1 | [5 empty] | 3
Ops Enhancements |  | 2 | 1 | [5 empty] | 3
Summer 2018 |  | 1 | 1 |  |  | 1 |  |  | 3
Ops Enhancements |  | 1 | 1 |  |  | 1 |  |  | 3
Grand Total | 7 | 4 | 8 | 1 | 2 | 1 | 1 | 3 | 27

## Roadmap
Theme | Category | Topic | Sub Topics | Status | Target Initiative | Target Period | B2B API Impact | Comments
Additional functionality | Business process | Substitution | Not able to create RT Subs from Next Day onward | Completed | RSI 1B | 2018-04-01 |  | ALM 40824 postponed
Additional functionality | Error handling | Error messages during uploads | Detailed error/warning codes on RA/Supply Plan uploads (resource not in matching plan is not sufficient to coordinate) | Completed | RSI 1B | 2018-04-01 |  | Need information from stakeholder
Additional functionality | Notification | Notification to SC of any Outage replacement approval request |  | Completed | RSI 1B | 2018-04-01 |  | POSO implementation
Additional functionality | Reporting | Public posting of CSP Offers |  | Completed | RSI 1B | 2018-04-01 |  | Will be posted to OASIS
Additional functionality | Reporting | Ability to download/export non-RA capacity data |  | Completed | RSI 1B | 2018-04-01
Performance | Business process | Frequent runs of validation | More timely validation runs. SCs do not have to wait until next day or late afternoon to see immediate results. Stakeholder requested every 30 mins if there are changes to Plans. | Completed | RSI 1B | 2018-04-01 |  | ISO will schedule two additonal runs. One at noon and one at 3 PM.
Additional functionality | Business process | More frequent processing of EFC requests |  | Open | Future | TBD
Additional functionality | Business process | Coordination of supply plans | Improved ability to coordinate supply plans with counterparties and better facilitate sales and re-sales | Open | Future | TBD |  | Need information from stakeholder
Additional functionality | Business process | CPM | CIDI-00181232: ability to cancel an ED once it has been declined We can put a warning "This action will result in supplemental revenue for the next 30 days. Do you wish to continue?“ CIDI-00181230: After search, the monthly/intra-monthly/annually and start and end dates should be available so that users shouldn't have to reload the screen to re-query the results. CIDI-00181223: CPM Type should be more descriptive | Open | Future | TBD |  | ALM 43448 postponed
Additional functionality | Business process | CSP offers | CIDI-00181431 -Allow users to load offers from Monthly and copy into Intra-monthly offers. | Open | Future | TBD |  | ALM 41007 postponed
Additional functionality | Business process | CSP offers | Make the CSP Offers window variable size. The search for available resources window is able to be variable size but the CSP offers window is not. It would be easier if the window can be made longer to let users see the entire list of offers. | Open | Future | TBD |  | ALM 41008 postponed
Additional functionality | API | API Functionality for Replacements |  | No longer needed |  |  | Y - will likely not be needed with replacements being phased out with RSI - 1B | Descoped from RSI-1B. However, given the importance to MPs, this is under assessment if it can be delivered earlier.
Additional functionality | Business process | Substitution | Single substitution screen for POSO and forced substitution. | Open | Future | TBD |  | No eta but cannot accommodate for RSI 2017 timelines.
Additional functionality | Export/ Import, New columns | Export substitutions, import/export CSP offers, new columns in review substitution screen | a. Request to provide Export Functionality in Review Substituions Screen. b. Import/export buttons in CSP offer screen. c. Import/export buttons in Review Substitution screen. d. Add two additional columns in Review Substitution screen with Gen & Flex substitution MW amount to be import/export easily & effectively. | Open | Future | TBD |  | CIDI-00187965; ALM 44850
Additional functionality | Policy | Ability to nominate and receive Import Allocations Steps 8-11 |  | Open | Future | TBD
Additional functionality | Policy | Adopt the CPUC MCC buckets construct fully. | This will allow firm imports to count across the entire month instead of only on peak days. | Open | Future | TBD
Additional functionality | Usability | Populate queue number to be automatically on submission of a request | The queue number is for new NQC request from RIMS | Open | Future | TBD
Additional functionality | Notification | Requesting CPM Mw on CPM Email |  | Closed |  |  |  | CIDI 00186412; NA - Info sec did not approve sending MW and price in an email, so request is being closed.
Additional functionality | Usability | Pre-population of compliance month on filters | Ability to not have to select the compliance month for every filter (validation, TAC obligation, Peak obligation, outage replacement, outage impact) | Open | Future | TBD
Additional functionality | Usability | Supply and RA plans | System must have the ability for ISO users to download multiple RA/Supply Plans (excel files) across SCs for a given trade year and trade month. Note: ISO users must be able to select multiple RA/Supply Plans and then download them all at once. It will not be acceptable to download each RA/Supply Plan individually. | Open | Future | TBD |  | Impacts ISO efficiency
Additional functionality | API | API to upload RA/Supply Plans | API Functionality supporting plan submittal, LSE/Supplier communication and daily RA commitments | Open | Ops Enhancements | TBD | Y - priority 3 | Descoped from RSI-1B
Additional functionality | API | API to submit CSP Offers |  | Open | Ops Enhancements | TBD | Y - priority 2 | Descoped from RSI-1B
Additional functionality | API | API to submit submit/retreive substitutions | Either an API solution or a bulk upload solution is being requested. | Open | Ops Enhancements | TBD | Y - priority 1 | Per CIDI:00190716 SC is requesting a bulk upload option to submit Planned Outage substitutions. For SC's that manage larger number of resources, a bulk upload option would assist in fufilling POS obligations.
Additional functionality | API | API to retrieve POSO assignments |  | Open | Ops Enhancements | TBD | Y - priority 1
Additional functionality | API | API to retrieve RA Data | to include all data elements on the RA tracker in the MOO flag payload | Open | Ops Enhancements | TBD | Y - priority 4
Additional functionality | Reporting | RA data, Outage data, Replacement data, Substitution data | CIDI 00185139 - Request for addition of operational RA data to the MPPF meetings, specifically: 1. Total RA Local/System/Flex requirements for the past, current and next month 2. Total RA Local/System/Flex resources provided to ISO daily 3. Total Planned Outage MWs that impacted the RA available MWs by day 4. Total Forced Outage MWs that impacted teh RA available MWs by day 5. Total MWs of replacement capacity provided for planned outages by day 6. Total MWs of substitute capacity provided for forced outages by day | Closed |  |  |  | SDG's request is with the Data Release Committee for consideration. Gautham to provide an update on May 17th, 2017 7/20 Gautham: Data was released for 2016, so this can be closed.
Additional functionality | API | API to retrieve NQC data |  | Open | Ops Enhancements | TBD | Y - priority 4
Additional functionality | API | API to retrieve RAAIM pre-calculation run details |  | Open | Ops Enhancements | TBD | Y - priority 4
Additional functionality | Automation of workflow | Acquired contracts |  | Open | Ops Enhancements | Fall 2018
Additional functionality | Automation of workflow | LRA role build-out & configuration |  | Open | Ops Enhancements | Summer 2018
Additional functionality | Automation of workflow | CPM Cost Allocation |  | Open | Ops Enhancements | Fall 2018
Additional functionality | Automation of workflow | Import Allocation Enhancements |  | Open | Ops Enhancements | TBD
Additional functionality | Business process | Credits application | Order of application of credits | Open | Ops Enhancements | Fall 2018
Additional functionality | Business process | LSE ID sourcing from MF | Unification of LSE IDs and process improvement | Open | Ops Enhancements | Summer 2018
Additional functionality | Reporting | NQC Enhancements | Comments from SC, bulk upload by ISO, posting of NQC to OASIS | Open | Ops Enhancements | Summer 2018
Additional functionality | Unification | Resource to area mapping | Controlling the entry points to where updates to this information can be made in CIRA. | Open | Ops Enhancements | TBD |  | Impacts ISO's controls and error handling.

## Summary Defect Backlog
Open versus Closed Defect Counts
Issue Counts by Status
Count of Issue # | Issue Status
Issue Status / Detected Year | Closed | Open | Evaluated | New | Postponed | Grand Total
2018 | 15 | 7 |  |  |  | 22
2017 | 52 | 8 | 1 | 8 |  | 69
2016 | 105 | 1 |  | 8 | 18 | 132
Grand Total | 172 | 16 | 1 | 16 | 18 | 223
Root Cause | (All)
Status | Closed
Issues resolved by deployment year and month
Count of Issues | Deployment Month & Year
Severity | 2-Very High | 3-High | 4-Medium | 5-Low | 6-Enhancement | Grand Total
2016 | 5 | 57 | 14 | 3 | 3 | 82
2017 | 1 | 40 | 12 |  | 6 | 59
2018 |  | 11 | 3 | 1 | 5 | 20
Grand Total | 6 | 108 | 29 | 4 | 14 | 161
For closures, # reported via CIDI
Status | Closed
Root Cause | (All)
Severity | # of s/w fixes | # reported through CIDI
2016
2-Very High | 5 | 2
3-High | 57 | 19
4-Medium | 14 | 2
5-Low | 3 | 1
6-Enhancement | 3 | 2
2017
2-Very High | 1 | 1
3-High | 40 | 10
4-Medium | 12 | 4
6-Enhancement | 6 | 2
2018
3-High | 11 | 2
4-Medium | 3
5-Low | 1 | 1
6-Enhancement | 5
Grand Total | 161 | 46
Status | Closed
Severity | (Multiple Items)
Root Cause | (Multiple Items)
Deployed with a Project? | (All)
Seasonal? | (All)
Deployment / Closure Year | Deployment/ Closure Month | Average of Turnaround days | Count of Issue #
2016 | 1 | 8 | 2
| 2 | 6.5 | 2
| 4 | 51.5 | 2
| 5 | 13.625 | 8
| 6 | 21.3333 | 3
| 7 | 26.6 | 5
| 8 | 30 | 7
| 9 | 31.5 | 4
| 10 | 5.3333 | 3
| 11 | 5.8571 | 7
| 12 | 9.25 | 16
2016 Total |  | 16.5932 | 59
2017 | 1 | 13.7778 | 9
| 2 | 13 | 7
| 3 | 8 | 1
| 4 | 12 | 3
| 5 | 12 | 1
| 6 | 16.3333 | 6
| 7 | 14 | 1
| 8 | 6 | 1
| 11 | 8.5 | 2
| 12 | 78.3333 | 3
2017 Total |  | 18.8529 | 34
2018 | 1 | 508 | 1
| 2 | 8 | 1
| 3 | 184.5 | 4
| 4 | 0 | 1
2018 Total |  | 179.1429 | 7
Grand Total |  | 28.74 | 100

## Defect Backlog
Issue # | System | Short Description | CIDI | Severity | Root Cause | Status | Detected on Date | Closing Date | Deployment date | ETA | Deployed with a Project? | Seasonal? | Detected Year | Deployment/ Closure Month | Deployment / Closure Year | Turnaround days | Turnaround <=5 days | Turnaround 6-10 days | Turnaround 11-20 days | Turnaround 21-30 days | Turnaround 31-45 days | Turnaround 46-60 days | Turnaround >60 days
42018 | CIRA | RA Plan versioning is incorrect which impacts the validation run. |  | 3-High | Functionality | Closed | 2016-07-25 | 2016-09-12 | 2016-08-25 |  |  |  | 2016 | 8 | 2016 | 31 |  |  |  |  | Y
41877 | CIRA | CIRA Application was down and up frequently in Production |  | 3-High |  | Closed | 2016-07-19 | 2016-08-12 | 2016-08-25 |  |  |  | 2016 | 8 | 2016 | 37 |  |  |  |  | Y
41754 | RAAM | Dispute #181646 SCP calculation run is not picking up Substitute resource in some cases |  | 3-High | Functionality | Closed | 2016-07-13 | 2016-07-15 | 2016-08-25 |  |  |  | 2016 | 8 | 2016 | 43 |  |  |  |  | Y
41557 | CIRA | Market participants are unable to submit replacements in CIRA |  | 3-High | Performance | Closed | 2016-06-29 | 2016-08-09 | 2016-08-25 |  |  |  | 2016 | 8 | 2016 | 57 | [5 empty] | Y
42138 | CIRA | RSI-Phase 1A: MKT SIM Jul16 Obligation Rpts Peak Demand Showing Not Reflecting Subset of Days Resource |  | 2-Very High | Functionality | Closed | 2016-07-26 | 2016-09-15 | 2016-09-21 |  |  |  | 2016 | 9 | 2016 | 57 | [5 empty] | Y
42180 | CIRA | Export screen data from NQC results not matching the filter results on the screen |  | 3-High | Functionality | Closed | 2016-07-27 | 2016-08-09 | 2016-09-21 |  |  |  | 2016 | 9 | 2016 | 56 | [5 empty] | Y
43555 | CIRA | Settlements not receiving Exempt_quantity from SCP Availability Calculations |  | 3-High | Functionality | Closed | 2016-09-26 | 2016-09-29 | 2016-09-30 |  |  |  | 2016 | 9 | 2016 | 4 | Y
43610 | CIRA | CV errors our Supply/RA resources with incorrect Import allocation check |  | 3-High |  | Closed | 2016-09-29 | 2016-10-04 | 2016-10-05 |  |  |  | 2016 | 10 | 2016 | 6 |  | Y
44136 | CIRA | change the scheduled time for 'SG_BroadcastResourceAdequacyCapacityData_CIRAv1' payload |  | 3-High | Install/Config | Closed | 2016-11-02 | 2016-11-02 | 2016-11-04 |  |  |  | 2016 | 11 | 2016 | 2 | Y
44087 | CIRA | remove ReceiveResourceAdequacyCapacityData_MFv1_INT_AP from AI/ESB |  | 4-Medium | Install/Config | Closed | 2016-11-01 | 2016-11-09 | 2016-11-07 |  |  |  | 2016 | 11 | 2016 | 6 |  | Y
44211 | CIRA | Missing service for receciveRTMResourceAdequacyCapacityData to Settlements |  | 3-High | Install/Config | Closed | 2016-11-07 | 2016-11-07 | 2016-11-08 |  |  |  | 2016 | 11 | 2016 | 1 | Y
44281 | CIRA | Ignore EDs with same start and end times i.e. cancelled EDs |  | 3-High | Functionality | Closed | 2016-11-08 | 2016-11-11 | 2016-11-11 |  |  |  | 2016 | 11 | 2016 | 3 | Y
44257 | CIRA | ISO offers not created when SC did not bid for intra-monthly |  | 3-High | Functionality | Closed | 2016-11-08 | 2016-11-11 | 2016-11-11 |  |  |  | 2016 | 11 | 2016 | 3 | Y
44231 | CIRA | CIDI 00186633 - Bilateral trade screen should allow SC ID same size as exists in MF | 186633 | 6-Enhancement | Functionality | Closed | 2016-11-07 | 2016-11-10 | 2016-11-11 |  |  |  | 2016 | 11 | 2016 | 4 | Y
44259 | CIRA | ISO user unable to approve saved NQC record for SC's with future effective date |  | 3-High | Functionality | Closed | 2016-11-08 | 2016-11-21 | 2016-11-17 |  |  |  | 2016 | 11 | 2016 | 9 |  | Y
44215 | CIRA | Annual CV calculations are incorrect |  | 3-High | Functionality | Closed | 2016-11-07 | 2016-11-17 | 2016-11-17 |  |  |  | 2016 | 11 | 2016 | 10 |  | Y
44133 | CIRA | CIDI 00186484- 'No LSE found for supplier x for resource y' error | 186484 | 4-Medium | Functionality | Closed | 2016-11-01 | 2016-11-17 | 2016-11-17 |  |  |  | 2016 | 11 | 2016 | 16 |  |  | Y
44346 | CIRA | MED integration issue - resources where RA = PMax need to be sent in the payload |  | 6-Enhancement | Functionality | Closed | 2016-11-14 | 2016-11-17 | 2016-11-17 |  |  |  | 2016 | 11 | 2016 | 3 | Y
44391 | CIRA | CIRA APP is producing errors in server log, the bigger log is causing diskspace issue in Production |  | 2-Very High | Functionality | Closed | 2016-11-17 | 2016-11-29 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 15 |  |  | Y
44522 | CIRA | CIDI 00187331 - Obligation report missing data by Peak | 187331 | 3-High | Functionality | Closed | 2016-12-01 | 2016-12-01 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 1 | Y
44511 | CIRA | 2017 NQC resource validation using tech factor for 2016 | 187300 | 3-High |  | Closed | 2016-12-01 | 2016-12-02 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 1 | Y
44497 | CIRA | app_cira_availcalc_int role user is unabe to access RAAIM Calculation functionality in CIRA application. |  | 3-High | Functionality | Closed | 2016-11-30 | 2016-12-01 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 2 | Y
44488 | CIRA | Date on RAAIM Pre-calc run details screen different from Excel download |  | 3-High | Functionality | Closed | 2016-11-30 | 2016-12-01 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 2 | Y
44462 | CIRA | CPM designation UI not displaying resources with multiple SC association |  | 3-High | Functionality | Closed | 2016-11-29 | 2016-12-02 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 3 | Y
44432 | CIRA | CIDI 186988: SC gets an error while trying to approve SRs | 186988 | 3-High | Functionality | Closed | 2016-11-23 | 2016-11-29 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 9 |  | Y
44379 | CIRA | CIDI 00186979 Import allocation issue | 186979 | 3-High | Functionality | Closed | 2016-11-15 | 2016-12-01 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 17 |  |  | Y
44325 | CIRA | CSP offer not created for a res that has multiple records in MF for the same Resource- SC association |  | 3-High | Functionality | Closed | 2016-11-14 | 2016-12-02 | 2016-12-02 |  |  |  | 2016 | 12 | 2016 | 18 |  |  | Y
44641 | CIRA | ED CPM enhancement |  | 3-High | Functionality | Closed | 2016-12-09 | 2016-12-13 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 4 | Y
44635 | CIRA | CIDI-00187435: SCs are not able to access Approve/Reject OM Replacments screen | 187435 | 3-High | Functionality | Closed | 2016-12-08 | 2016-12-12 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 5 | Y
44548 | CIRA | CIDI 00186598 - MOO flag needs to be derived at the time of payload broadcast | 186598 | 3-High | Functionality | Closed | 2016-12-02 | 2016-12-09 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 11 |  |  | Y
44216 | CIRA | Missing plans functionality not working for annual |  | 4-Medium | Functionality | Closed | 2016-11-07 | 2016-12-07 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 36 |  |  |  |  | Y
44035 | CIRA | Unable to approve future effective NQC for 1 resource in prod |  | 4-Medium | Functionality | Closed | 2016-10-27 | 2016-12-07 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 47 | [5 empty] | Y
44553 | CIRA | multiple CPM designation emails generated for the same resource |  | 5-Low | Functionality | Closed | 2016-12-02 | 2016-12-12 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 11 |  |  | Y
43955 | CIRA | (CIDI 00186092) Spelling error when downloading Obligation Report from the UI | 186092 | 5-Low | Functionality | Closed | 2016-10-20 | 2016-12-07 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 54 | [5 empty] | Y
44261 | CIRA | CIDI 00186601 - TG not allowed to submit CSP offer for Flex even when EFC/NQC exists for that month | 186601 | 6-Enhancement | Functionality | Closed | 2016-11-08 | 2016-12-07 | 2016-12-13 |  |  |  | 2016 | 12 | 2016 | 35 |  |  |  |  | Y
44690 | CIRA | CIDI-00187618: CIRA doesn't bump up the RA capacity by 0.01 when RA=Pmin for SIBR | 187618 | 3-High | Functionality | Closed | 2016-12-13 | 2016-12-14 | 2016-12-14 |  |  |  | 2016 | 12 | 2016 | 1 | Y
44681 | CIRA | Search for all resources on compatible resources view screen times out |  | 4-Medium | Functionality | Closed | 2016-12-13 | 2016-12-14 | 2016-12-20 |  |  |  | 2016 | 12 | 2016 | 7 |  | Y
44924 | CIRA | RTM RA payload to Settlements failed due to a resource end dating |  | 3-High | Functionality | Closed | 2017-01-03 | 2017-01-03 | 2017-01-03 |  |  |  | 2017 | 1 | 2017 | 0 | Y
44914 | CIRA | CIDI 00188019 - RA report not taking into account multiple replacement records | 188019 | 3-High | Functionality | Closed | 2016-12-30 | 2017-01-05 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 11 |  |  | Y
44835 | CIRA | defining allowable period for declining CPM |  | 3-High | Functionality | Closed | 2016-12-22 | 2017-01-04 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 19 |  |  | Y
44833 | CIRA | rules for updates to the CPM designation screen |  | 3-High | Functionality | Closed | 2016-12-22 | 2017-01-05 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 19 |  |  | Y
44810 | CIRA | annual optimization is failing |  | 3-High | Functionality | Closed | 2016-12-21 | 2016-12-23 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 20 |  |  | Y
44793 | CIRA | include null RMRFLAG records for CPM calculations |  | 3-High |  | Closed | 2016-12-20 | 2016-12-23 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 21 |  |  |  | Y
43563 | CIRA | RSI-1A: Search not working as expected on CPM Designation screen (CIDI 00184091) | 184091 | 4-Medium | Functionality | Closed | 2016-09-27 | 2016-12-27 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 105 | [6 empty] | Y
39654 | CIRA | RSI_Phase1a_Search Substitution Requests_Substitutions are showing up when there is no substitution in compliance month |  | 4-Medium | Functionality | Closed | 2016-01-29 | 2016-12-22 | 2017-01-10 |  |  |  | 2016 | 1 | 2017 | 347 | [6 empty] | Y
44913 | CIRA | CIDI 00187978 - RAAIM Pre-calc is not handling DST time | 187978 | 3-High | Functionality | Closed | 2016-12-30 | 2017-01-12 | 2017-01-13 |  |  | DST-Spring | 2016 | 1 | 2017 | 14 |  |  | Y
44911 | CIRA | CPM should be designated for only CISO resources with an active SC association |  | 3-High | Functionality | Closed | 2016-12-30 | 2017-01-11 | 2017-01-13 |  |  |  | 2016 | 1 | 2017 | 14 |  |  | Y
44956 | CIRA | Modify CPM email verbiage |  | 6-Enhancement | Functionality | Closed | 2017-01-05 | 2017-01-12 | 2017-01-13 |  |  |  | 2017 | 1 | 2017 | 8 |  | Y
45167 | CIRA | For FLEX RA category 3 resources RA not calculated correctly for days bordering weekends and holidays |  | 3-High |  | Closed | 2017-01-24 | 2017-01-27 | 2017-02-01 |  |  |  | 2017 | 2 | 2017 | 8 |  | Y
45036 | CIRA | CPM emails are triggered for more resources than the one submitted |  | 3-High | Functionality | Closed | 2017-01-12 | 2017-01-27 | 2017-02-01 |  |  |  | 2017 | 2 | 2017 | 20 |  |  | Y
45287 | CIRA | Error in logs due to length of CSP_OFFER_SEGMENT.COMMENTS |  | 3-High |  | Closed | 2017-01-30 | 2017-01-31 | 2017-02-08 |  |  |  | 2017 | 2 | 2017 | 9 |  | Y
45399 | CIRA | Peak & TAC reports are displaying an incorrect 'Specified Replacement Increase' value on outage dates | 188973 | 3-High |  | Closed | 2017-02-03 | 2017-02-07 | 2017-02-13 |  |  |  | 2017 | 2 | 2017 | 10 |  | Y
45333 | CIRA | Issue with reading the MOO flag from MF due to date/time offset |  | 3-High | Functionality | Closed | 2017-01-31 | 2017-02-08 | 2017-02-13 |  |  |  | 2017 | 2 | 2017 | 13 |  |  | Y
45269 | CIRA | CIDI 188202 - availability calculation is incorrect for TG in RAAM | 188202 | 3-High | Functionality | Closed | 2017-01-27 | 2017-02-07 | 2017-02-13 |  |  |  | 2017 | 2 | 2017 | 17 |  |  | Y
46070 | CIRA | RAAIM calculation failure due to DST Short day Data fix will be applied first; code fix will follow later |  | 4-Medium | Functionality | Closed | 2017-03-13 | 2018-03-09 | 2018-03-09 |  |  | DST-Spring | 2017 | 3 | 2018 | 361 | [6 empty] | Y
46152 | CIRA | CIRA INT - rename RTM resource adequacy capacity payload as part of ESB replacement |  | 3-High | Install/Config | Closed | 2017-03-19 | 2017-03-20 | 2017-03-27 |  |  |  | 2017 | 3 | 2017 | 8 |  | Y
46143 | CIRA | CIRA - CIDI 00189853, 00189824 - RAAIM inconsistent with CAISO Tariff for Flex LF-MSS resources |  | 3-High | Functionality | Closed | 2017-03-17 | 2017-04-04 | 2017-04-10 |  |  |  | 2017 | 4 | 2017 | 24 |  |  |  | Y
44326 | CIRA | Resource area mapping is not updating when you upload and approve the NQC |  | 4-Medium | Functionality | Closed | 2016-11-14 | 2017-04-04 | 2017-04-10 |  |  |  | 2016 | 4 | 2017 | 147 | [6 empty] | Y
46776 | CIRA | Replacement requirement MW should not exceed RA plan MW | 191111, 191117, 191126, 191140, 191149, 191154, 191155, 191156, 191157 | 3-High | Functionality | Closed | 2017-04-24 | 2017-04-27 | 2017-04-28 |  |  |  | 2017 | 4 | 2017 | 4 | Y
46736 | CIRA | CIRA must filter out revised set of ED instructions not eligible for CPM designations. |  | 3-High | Functionality | Closed | 2017-04-20 | 2017-04-27 | 2017-04-28 |  |  |  | 2017 | 4 | 2017 | 8 |  | Y
46945 | CIRA | CPM Enhancement to compute the Daily Max RA MW as max of both Gen & Flex |  | 3-High | Functionality | Closed | 2017-05-09 | 2017-06-01 | 2017-06-06 |  |  |  | 2017 | 6 | 2017 | 28 |  |  |  | Y
47249 | CIRA | OM Replacements screen doesn't display 2nd page after a sort |  | 4-Medium | Functionality | Closed | 2017-06-06 | 2017-06-14 | 2017-06-19 |  |  |  | 2017 | 6 | 2017 | 13 |  |  | Y
47248 | CIRA | Add 'pre-approved' to T45 approved & pending OIA run and OM Replacements logic | 192247 | 4-Medium | Functionality | Closed | 2017-06-06 | 2017-06-14 | 2017-06-19 |  |  |  | 2017 | 6 | 2017 | 13 |  |  | Y
47870 | CIRA | ResourceAdequacyCapacity payload failures | 192418 | 3-High | Integration | Closed | 2017-06-24 | 2017-06-27 | 2017-06-27 |  |  |  | 2017 | 6 | 2017 | 3 | Y
47812 | CIRA | OM RA report data changes post the trade date |  | 3-High | Functionality | Closed | 2017-06-21 | 2017-06-30 | 2017-06-30 |  |  |  | 2017 | 6 | 2017 | 9 |  | Y
45699 | CIRA | CIRA - Replacement MW higher than provided as S replacements in RA plan- occurred due to multiple resources with different RA plans used the same contract ID. Handled via training & CPG not code fix |  | 3-High | Functionality | Closed | 2017-02-21 | 2017-03-03 |  |  |  |  | 2017 | 2 | 2017 | 14 |  |  | Y
42858 | CIRA | CIRA: Updating RA data in RR_RA table for SMUD Supporting Resources |  | 2-Very High | Data | Closed | 2016-08-19 | 2016-08-24 |  |  |  |  | 2016 | 8 | 2016 | 9 |  | Y
41486 | RAAM | RAAM not allowing users to submit Subs | 182460, 182420, 182456 | 2-Very High | Software | Closed | 2016-06-23 | 2016-07-07 |  |  |  |  | 2016 | 7 | 2016 | 18 |  |  | Y
40856 | RAAM | Error when trying to load valid MW for Substitutions | 181256 | 2-Very High | Software | Closed | 2016-04-29 | 2016-05-13 |  |  |  |  | 2016 | 5 | 2016 | 18 |  |  | Y
48362 | CIRA | CIRA - OM Data report should disregard RA if deficiency config is set to N for obligation |  | 3-High | Requirement Gap | Closed | 2017-07-12 | 2017-07-20 |  |  |  |  | 2017 | 7 | 2017 | 12 |  |  | Y
48122 | RAAM | SCP Avail Data for resource for TDs in Septmeber2016 missing from the MF materialized view | 188697 | 3-High | Data | Closed | 2017-07-03 | 2017-07-13 |  |  |  |  | 2017 | 7 | 2017 | 14 |  |  | Y
48047 | CIRA | SCE1 is getting an unknown error when they try to update August CSP Offers | 192592 | 3-High | Software | Closed | 2017-06-29 | 2017-06-30 |  |  |  |  | 2017 | 6 | 2017 | 5 | Y
47966 | CIRA | CIRA - CPM Enhancement to handle PMIN |  | 3-High | Enhancement | Closed | 2017-06-27 | 2017-11-08 | 2017-11-13 | 2017-07-31 |  |  | 2017 | 11 | 2017 | 139 | [6 empty] | Y
47615 | CIRA | Replacement for Outage Details | 192247 | 3-High | Software | Closed | 2017-06-07 | 2017-06-08 |  |  |  |  | 2017 | 6 | 2017 | 5 | Y
47056 | CIRA | CIRA - additional reason codes to read to determine CPM eligibility |  | 3-High | Enhancement | Closed | 2017-05-18 | 2017-11-08 | 2017-11-13 | 2017-07-31 |  |  | 2017 | 11 | 2017 | 179 | [6 empty] | Y
47041 | CIRA | CIRA:RA Report Monthly download for ALL resources is throwing error. |  | 3-High | Software | Closed | 2017-05-17 | 2017-05-25 |  |  |  |  | 2017 | 5 | 2017 | 12 |  |  | Y
46934 | CIRA | RA tracker reflects cancelled Flex substitution incorrectly & substitution is not released | 00191513, 00191525 | 4-Medium | Software | Closed | 2017-05-08 | 2017-07-19 | 2017-07-24 |  |  |  | 2017 | 7 | 2017 | 77 | [6 empty] | Y
46932 | CIRA | CIRA - Outages from OMS not being picked up by CIRA for a few days in April |  | 3-High | Monitoring | Closed | 2017-05-08 | 2017-06-21 |  |  |  |  | 2017 | 6 | 2017 | 48 | [5 empty] | Y
45799 | CIRA | CIRA - Review Substitution screen displays the Sub request ID instead of the Sub ID |  | 3-High | Requirement Gap | Closed | 2017-02-28 | 2017-02-28 |  |  |  |  | 2017 | 2 | 2017 | 4 | Y
44934 | CIRA | CIRA - not handling multiple records for penalty price and softoffer cap for the same year |  | 3-High | Data | Closed | 2017-01-04 | 2017-01-06 |  |  |  |  | 2017 | 1 | 2017 | 6 |  | Y
44634 | CIRA | System does not allow user to upload plans for Import resources that are associated with a future dated BG | 187429 | 3-High | Software | Closed | 2016-12-08 | 2016-12-09 |  |  |  |  | 2016 | 12 | 2016 | 5 | Y
44414 | CIRA | Discrepancies on CIRA data sent to Settlements, regarding a resource in the payload if it does not qualify for a RAAIM exemption | 186775 | 3-High | Software | Closed | 2016-11-22 | 2016-12-02 |  |  |  |  | 2016 | 12 | 2016 | 14 |  |  | Y
44320 | CIRA | CIRA - Intra-monthly CSP offers not getting adjusted due to ED or Substitution |  | 3-High | Software | Closed | 2016-11-09 | 2016-12-15 |  |  |  |  | 2016 | 12 | 2016 | 40 |  |  |  |  | Y
44269 | CIRA | CIRA - Enhance CIRA to handle processing a larger volume of EDs |  | 3-High | Design | Postponed | 2016-11-08 | [5 empty] | 2016 |  |  | FALSE
44102 | CIRA | CIRA - no data found error in annual transmission planning report |  | 3-High | Requirement Gap | Closed | 2016-11-01 | 2016-11-02 |  |  |  |  | 2016 | 11 | 2016 | 5 | Y
44097 | CIRA | RSI\CPM:App_cira_bid_read_ext role is unable to access Data Maintenance Search screen |  | 3-High | Software | Closed | 2016-11-01 | 2016-11-10 |  |  |  |  | 2016 | 11 | 2016 | 13 |  |  | Y
43972 | OASIS | RA and Minimum Load data report - There was a fix that was deployed on 3/31/17 did not seem to have solved the issue reported in the CIDI. | 185424 | 3-High |  | Open | 2016-10-24 |  |  | 2017-08-31 |  |  | 2016 |  |  | FALSE
43912 | CIRA | CIRA-RSI-1A- Real time substitution for Flex RA |  | 4-Medium | Requirement Gap | New | 2016-10-19 | [5 empty] | 2016 |  |  | FALSE
43827 | CIRA | RSI-1A - CIRA - UAT - Outage exemption request functionality is missing the 5 business day validation rule which is available in RAAM |  | 3-High | Requirement Gap | Closed | 2016-10-13 | 2018-01-05 | 2018-03-05 |  | RSI-2017 |  | 2016 |  |  | 508 | [6 empty] | Y
43773 | CIRA | ResourceAdequacyCapacity payload has a 7 hour offset | 185410 | 3-High | Software | Closed | 2016-10-10 | 2016-10-11 |  |  |  |  | 2016 | 10 | 2016 | 5 | Y
43675 | CIRA | CIRA - Resource Adequacy Showing line is incorrectly being calculated |  | 3-High | Data | Closed | 2016-10-03 | 2016-10-04 |  |  |  |  | 2016 | 10 | 2016 | 5 | Y
43444 | CIRA | CIRA PROD: Record count is increased when user sorts by a resource on OM Replacements screen. |  | 3-High | Software | Closed | 2016-09-16 | 2016-09-21 |  |  |  |  | 2016 | 9 | 2016 | 9 |  | Y
42655 | CIRA | CIRA - RAAM tool hanging when new SCP calculation was run |  | 3-High | Software | Closed | 2016-08-11 | 2016-08-11 |  |  |  |  | 2016 | 8 | 2016 | 4 | Y
41698 | RAAM | RAAM not showing the updated NQC values that are approved in CIRA | 182626 | 3-High | Software | Closed | 2016-07-07 | 2016-07-11 |  |  |  |  | 2016 | 7 | 2016 | 8 |  | Y
41697 | CIRA | update the correct mw volumes for NOB_BG Import for the September showing | 182745 | 3-High | Data | Closed | 2016-07-07 | 2016-08-01 |  |  |  |  | 2016 | 8 | 2016 | 29 |  |  |  | Y
41694 | CIRA | CIRA - some resources not in 'Saved NQC request' Excel export |  | 3-High | Software | Closed | 2016-07-07 | 2016-07-20 |  |  |  |  | 2016 | 7 | 2016 | 17 |  |  | Y
41339 | CIRA | CIRA - TAC Results are showing incorrect data |  | 3-High | Software | Closed | 2016-06-09 | 2016-07-07 |  |  |  |  | 2016 | 7 | 2016 | 32 |  |  |  |  | Y
41333 | RAAM | Resource ID Drop-Down list does not populate the resources for newly created SCs. | 181822 | 3-High | Software | Closed | 2016-06-09 | 2016-06-10 |  |  |  |  | 2016 | 6 | 2016 | 5 | Y
41229 | CIRA | Prod Issue: bulk update all records in the SCP_GF_RES table to include the timestamp 23:59:59 for EFF_END_DTS |  | 3-High | Software | Closed | 2016-06-02 | 2016-06-07 |  |  |  |  | 2016 | 6 | 2016 | 9 |  | Y
41102 | CIRA | Error in the NQC Submission - CIRA shows the resource is not valid | 181717 | 3-High | Software | Closed | 2016-05-20 | 2016-05-25 |  |  |  |  | 2016 | 5 | 2016 | 9 |  | Y
41082 | CIRA | CIRA: Annual Obligation report shows incorrect data |  | 3-High | Software | Closed | 2016-05-18 | 2016-07-11 |  |  |  |  | 2016 | 7 | 2016 | 58 | [5 empty] | Y
41075 | CIRA | CIRA - Monthly Obligation report and Peak Results report are incorrect |  | 3-High | Software | Closed | 2016-05-18 | 2016-05-24 |  |  |  |  | 2016 | 5 | 2016 | 10 |  | Y
40999 | CIRA | CIRA needs to round down fractional MW values on Interties to the integer level | 179200 | 3-High | Requirement Gap | Closed | 2016-05-11 | 2016-05-18 |  |  |  |  | 2016 | 5 | 2016 | 11 |  |  | Y
40998 | CIRA | Need data fix for July Supply plan as the system is enforcing the SCID Import allocation check incorrectly | 181472 | 3-High | Software | Closed | 2016-05-11 | 2016-05-11 |  |  |  |  | 2016 | 5 | 2016 | 4 | Y
40995 | CIRA | CIRA: MF to CIRA refresh failure due to LSE SCIDs length more than defined constraint |  | 3-High | Software | Closed | 2016-05-11 | 2016-05-17 |  |  |  |  | 2016 | 5 | 2016 | 10 |  | Y
40994 | CIRA | Outage Availability Report - Unavailable | 177387 | 3-High | Software | Closed | 2016-05-03 | 2016-05-19 |  |  |  |  | 2016 | 5 | 2016 | 20 |  |  | Y
40854 | CIRA | RAAM Prod error - Availability calculation fails when there are multiple substitutions in a request and calculation invoked specific to the substituted resources. |  | 3-High | Software | Closed | 2016-04-29 | 2016-05-17 |  |  |  |  | 2016 | 5 | 2016 | 22 |  |  |  | Y
40851 | CIRA | Peak results screen error in Prod | 181047 | 3-High | Software | Closed | 2016-04-29 | 2016-05-11 |  |  |  |  | 2016 | 5 | 2016 | 16 |  |  | Y
40788 | CIRA | TAC Results Report errors out in Prod | 181052 | 3-High | Software | Closed | 2016-04-25 | 2016-06-10 |  |  |  |  | 2016 | 6 | 2016 | 50 | [5 empty] | Y
40213 | CIRA | CIRA-RSI-Phase 1A: Not Published RAAIM Pre-Calcs are visible to External SCs (No data disclosure) |  | 4-Medium | Software | Closed | 2016-03-04 | 2017-07-05 |  |  |  |  | 2016 | 7 | 2017 | 492 | [6 empty] | Y
40203 | CIRA | CIRA_RSI Phase 1A Menu bar is incorrectly rendered on user access exception |  | 3-High | Software | Closed | 2016-03-04 | 2016-04-20 |  |  |  |  | 2016 | 4 | 2016 | 51 | [5 empty] | Y
40183 | CIRA | CIRA-RSI-Phase 1A: Unauthorized user is able view & Download Outage Impact Report for both outage view T45 and OTD |  | 3-High | Software | Closed | 2016-03-03 | 2016-04-20 |  |  |  |  | 2016 | 4 | 2016 | 52 | [5 empty] | Y
40045 | CIRA | SCP Availability Calc Publish is erroring out for Trade Date 02-22-2016 |  | 3-High | Software | Closed | 2016-02-23 | 2016-02-25 |  |  |  |  | 2016 | 2 | 2016 | 6 |  | Y
40014 | CIRA | RAAM: Missing SCP_AVAIL payload for TD 2/21/16 |  | 3-High | Software | Closed | 2016-02-22 | 2016-02-25 |  |  |  |  | 2016 | 2 | 2016 | 7 |  | Y
39918 | CIRA | CIRA Should round down the RA numbers to the lower integers for down-stream systems if the original RA capacity is a fractional number |  | 3-High | Enhancement | Closed | 2016-02-16 | 2016-04-04 |  |  |  |  | 2016 | 4 | 2016 | 52 | [5 empty] | Y
39258 | CIRA | SC Transfer Job does not transfer the Flex RA to the New Supplier when resource ownership is changed |  | 3-High | Software | Closed | 2016-01-06 | 2016-01-10 |  |  |  |  | 2016 | 1 | 2016 | 8 |  | Y
39242 | CIRA | SC Transfer Job not transferring all resources to the new SC |  | 3-High | Software | Closed | 2016-01-06 | 2016-01-10 |  |  |  |  | 2016 | 1 | 2016 | 8 |  | Y
48679 | CIRA | Reduction in LSEs obligation did not reflect in the adjusted_obligation table | 193144 | 4-Medium | Software | New | 2017-07-21 | [5 empty] | 2017 |  |  | FALSE
48441 | CIRA | CIRA - NQC was uploaded with value as 0 |  | 4-Medium | Software | New | 2017-07-13 | [5 empty] | 2017 |  |  | FALSE
47806 | CIRA | CIRA - TAC filter on Obligation report not working |  | 4-Medium | Software | Closed | 2017-06-21 | 2017-12-12 | 2018-03-05 |  | RSI-2017 |  | 2017 |  |  | 257 | [6 empty] | Y
47798 | CIRA | CIRA - Display label for environment the user is logged into |  | 4-Medium | Enhancement | Closed | 2017-06-21 | 2017-11-08 | 2017-11-13 |  |  |  | 2017 |  |  | 145 | [6 empty] | Y
47151 | CIRA | Sub_request_id on CIRA UI but Substitution_ID sent to OMS |  | 4-Medium | Software | Closed | 2017-05-28 | 2017-03-05 | 2017-03-05 |  |  |  | 2017 |  |  | -84 | Y
45805 | CIRA | CIRA - Intra-monthly final offer automated run does not create an extension when there is no CSP offer from the SC. (manual work-around exists) |  | 4-Medium | Functionality | Open | 2017-02-28 |  |  | 2018-06-01 |  |  | 2017 |  |  | FALSE
45695 | CIRA | CIRA - Rebroadcast RA for a specified resource for specified period |  | 4-Medium | Requirement Gap | New | 2017-02-21 | [5 empty] | 2017 |  |  | FALSE
45614 | CIRA | CIRA - Not displaying 'in service' resources on the outage exemption screen for retro-active exemptions |  | 4-Medium | Software | New | 2017-02-15 | [5 empty] | 2017 |  |  | FALSE
45279 | CIRA | CIRA - CPM change email is not being triggered for all elements of the CPM record |  | 4-Medium | Software | Closed | 2017-01-27 | 2017-02-03 |  |  |  |  | 2017 | 2 | 2017 | 11 |  |  | Y
45241 | CIRA | RAAM -NOW conversion issue for SLIC data | ID22406 | 4-Medium | Software | New | 2017-01-26 | [5 empty] | 2017 |  |  | FALSE
44935 | CIRA | CIRA - Per Updates on One CPM Records system trigger the CPMDesignation and RA Payload for all CPM Resources. |  | 4-Medium | Software | Closed | 2017-01-04 | 2017-02-03 |  |  |  |  | 2017 | 2 | 2017 | 34 |  |  |  |  | Y
44895 | CIRA | CIRA - SC transfer should have only 1 set of records for a unique effective date range |  | 4-Medium | Software | New | 2016-12-29 | [5 empty] | 2016 |  |  | FALSE
44869 | CIRA | CIRA - SC transfer details under Admin menu is non functional |  | 4-Medium | Software | Closed | 2016-12-28 | 2017-06-30 |  |  |  |  | 2016 | 6 | 2017 | 188 | [6 empty] | Y
44841, 51837 | CIRA | CIDI 00187927, CIRA's 2017 Annual CV LSE Obligation Details mismatch with Obligations rpt | 187927 | 4-Medium | Functionality | Closed | 2016-12-23 | 2017-11-20 | 2017-11-08 | 2017-10-01 |  |  | 2016 | 11 | 2017 | 332 | [6 empty] | Y
44546 | CIRA | RAAM - SCP reruns in RAAM don't show as a recent run in the view |  | 4-Medium | Data | Closed | 2016-12-02 | 2016-12-02 |  |  |  |  | 2016 | 12 | 2016 | 4 | Y
44233 | CIRA | CIRA - Data Fixes for Bilateral trade due to date and SC ID length issues |  | 4-Medium | Data | Closed | 2016-11-07 | 2016-11-21 |  |  |  |  | 2016 | 11 | 2016 | 18 |  |  | Y
44214 | CIRA | CIRA - Annual CPUC Sub Poena Report not working |  | 4-Medium | Software | Closed | 2016-11-07 | 2016-12-09 |  |  |  |  | 2016 | 12 | 2016 | 36 |  |  |  |  | Y
44212 | CIRA | CIRA: Flex Cap Requirement Yearly plan upload is failing. |  | 4-Medium | Software | Closed | 2016-11-03 | 2016-12-09 |  |  |  |  | 2016 | 12 | 2016 | 40 |  |  |  |  | Y
44070 | CIRA | CIRA- user unable to substitute resource on the last day of November |  | 4-Medium | Software | New | 2016-10-31 | [5 empty] | 2016 |  |  | FALSE
43994 | CIRA | CIRA - Replacement not allowed in system due to incorrectly calculated RA and validation of RA+Replacement <= PMAX/NQC fails |  | 4-Medium | Software | Closed | 2016-10-25 | 2018-03-05 | NA |  |  |  | 2016 |  |  | 496 | [6 empty] | Y
43889 | CIRA | (STAGE)->Substituation SEARCH button taking longer to display data |  | 4-Medium | Software | Closed | 2016-10-18 | 2018-03-05 | 2018-03-05 |  | RSI-2017 |  | 2016 |  |  | 503 | [6 empty] | Y
43788 | CIRA | Import Allocation Bilateral Trade not taking into account the start and end dates on the screen | 185544 | 4-Medium | Software | Closed | 2016-10-10 | 2016-11-10 |  |  |  |  | 2016 | 11 | 2016 | 35 |  |  |  |  | Y
43685 | CIRA | CIRA-RSI-1A - Annual CPM miscellaneous issues |  | 4-Medium | Software | New | 2016-10-03 | [5 empty] | 2016 |  |  | FALSE
43491 | CIRA | CIRA-RSI-Phase 1A: New SC and/or ISO user is not able to submit the bid on behalf of new SC when resource ownership changes mid of the month. |  | 4-Medium | Software | Postponed | 2016-09-22 | [5 empty] | 2016 |  |  | FALSE
42910 | CIRA | CIRA: HTTP Status 404 error is displayed when user tries the URL manipulation when expected text is User Access Denied. |  | 4-Medium | Software | Closed | 2016-08-22 | 2016-08-29 |  |  |  |  | 2016 | 8 | 2016 | 11 |  |  | Y
42807 | CIRA | CIRA is keeping the comments from Old CV instead of updating per new CV |  | 4-Medium | Software | Closed | 2016-08-18 | 2016-08-18 |  |  |  |  | 2016 | 8 | 2016 | 4 | Y
41141 | CIRA | CIRA-Yearly CV shows no records |  | 4-Medium | Software | Closed | 2016-05-24 | 2016-06-14 |  |  |  |  | 2016 | 6 | 2016 | 25 |  |  |  | Y
41140 | CIRA | CIRA-Total RA calculation during RA Plan reupload is incorrect |  | 4-Medium | Software | Closed | 2016-05-24 | 2016-06-16 |  |  |  |  | 2016 | 6 | 2016 | 27 |  |  |  | Y
41091 | CIRA | CIRA: Outage Availability report performance does not meet specified requirements |  | 4-Medium | Requirement Gap | Closed | 2016-05-19 | 2018-03-05 |  |  |  |  | 2016 |  |  | 655 | [6 empty] | Y
41073 | CIRA | CIRA TAC Results report performance does not meet specified requirements |  | 4-Medium | Documentation | Postponed | 2016-05-18 | 2016-05-26 |  |  |  |  | 2016 |  |  | FALSE
40270 | CIRA | CIRA-RSI-Phase 1A; Performance Requirement Details Missing from SRS |  | 4-Medium | Software | Closed | 2016-03-10 | 2017-07-20 |  |  |  |  | 2016 | 7 | 2017 | 501 | [6 empty] | Y
43904 | CIRA | CIRA-RSI-1A - The 'capacity Designation' field on the 'Other' tab in RA plan template is inconsistent with the error message |  | 5-Low | Data | Closed | 2016-10-19 | 2018-03-05 | NA |  |  |  | 2016 |  |  | 502 | [6 empty] | Y
43824 | CIRA | RSI-1A - CIRA - UAT - Two substitution requests submitted 2 seconds apart on the same unit because of which RA exceeds NQC |  | 5-Low | Software | New | 2016-10-13 | [5 empty] | 2016 |  |  | FALSE
43467 | CIRA | CIRA- OM Replacements screen shows additional pages after sort is applied on resource ID column |  | 5-Low | Software | Closed | 2016-09-21 | 2016-12-06 |  |  |  |  | 2016 | 12 | 2016 | 80 | [6 empty] | Y
39974 | CIRA | CIRA_RSI Phase 1A_BSC ids are populating in SC in Substitute Resource Selection section. |  | 5-Low | Software | New | 2016-02-18 | [5 empty] | 2016 |  |  | FALSE
47254 | CIRA | CIRA - remove the app_cira_om role |  | 6-Enhancement | Enhancement | Closed | 2017-06-06 | 2017-11-21 |  |  |  |  | 2017 | 11 | 2017 | 168 | [6 empty] | Y
46026 | CIRA | ReceiveResourceAdequacyCapacityData_SIBRv1_AP failure due to missing HE19 data |  | 4-Medium | Software | Closed | 2017-03-10 | 2018-03-08 | 2018-03-09 |  |  | DST-Spring | 2017 |  |  | 364 | [6 empty] | Y
44850 | CIRA | Request to provide Export Functionality in Review Substituions Screen | 187965 | 6-Enhancement | Enhancement | New | 2016-12-27 | [5 empty] | 2016 |  |  | FALSE
44675 | CIRA | CIRA - Calculate CPM at the end of the parent ED interval |  | 6-Enhancement | Requirement Gap | Closed | 2016-12-13 | 2017-02-03 |  |  |  |  | 2016 | 2 | 2017 | 56 | [5 empty] | Y
44482 | CIRA | B2B webservices descoped from RSI 1B and CPGs |  | 6-Enhancement | Software | Postponed | 2016-11-29 | [5 empty] | 2016 |  |  | FALSE
44064 | CIRA | requesting CPM Mw on CPM Email | 186412 | 6-Enhancement | Design | Closed | 2016-10-27 | 2017-06-19 |  |  |  |  | 2016 | 6 | 2017 | 239 | [6 empty] | Y
43448 | CIRA | RSI-1A - CIRA screen enhancements from CIDI for CPM Designation UI | 00181230, 00181232, 00181223 | 6-Enhancement | Enhancement | Postponed | 2016-09-21 | [5 empty] | 2016 |  |  | FALSE
43201 | CIRA | SDGE requests the addition of CPM Capacity MWs for Generic/Flexible capacity on the API and RA Tracker | 184495 | 6-Enhancement | Enhancement | Postponed | 2016-09-06 | [5 empty] | 2016 |  |  | FALSE
42899 | CIRA | CIRA- RT Substitution for Flex RA |  | 6-Enhancement | Requirement Gap | Postponed | 2016-08-23 | [5 empty] | 2016 |  |  | FALSE
42735 | CIRA | CIRA- Review and make consistent jobs accross environments based on dependencies and business requirements |  | 6-Enhancement | Config / Install | New | 2016-08-15 | [5 empty] | 2016 |  |  | FALSE
41008 | CIRA | CIRA-RSI-Phase 1A: MKT SIM -CSP Offer Screen - Enhancement | 181434 | 6-Enhancement | Enhancement | Postponed | 2016-05-11 | [5 empty] | 2016 |  |  | FALSE
41007 | CIRA | CIRA-RSI-Phase 1A: MKT SIM -Load CSP Offers Enhancement | 181431 | 6-Enhancement | Enhancement | Postponed | 2016-05-11 | [5 empty] | 2016 |  |  | FALSE
40848 | CIRA | CIRA-RSI-Phase 1A: Show warning if resources are missing in resubmital plan were involved in any Substitution, Replacements and CPMs |  | 6-Enhancement | Enhancement | Postponed | 2016-04-28 | [5 empty] | 2016 |  |  | FALSE
40824 | CIRA | CIRA-RSI-Phase 1A: MKT SIM- Not able to create RT Subs from Next Day onward |  | 6-Enhancement | Enhancement | Postponed | 2016-04-27 | [5 empty] | 2016 |  |  | FALSE
40805 | CIRA | CIRA-RSI-Phase 1A: MKT SIM -CPM CSP Email Notification | 180944 | 6-Enhancement | Enhancement | Postponed | 2016-04-26 | [5 empty] | 2016 |  |  | FALSE
40798 | CIRA | CIRS-RSI-Phase 1A: CIRA should not show ISO price for CPM to MPs in Data Maintenance Search screen as well as it should not send to settlement/MQS |  | 6-Enhancement | Enhancement | Postponed | 2016-04-26 | [5 empty] | 2016 |  |  | FALSE
40575 | CIRA | CIRA_RSI_Phase 1A: Flexible RA does not reflect all the hours it has been committed |  | 6-Enhancement | Requirement Gap | Postponed | 2016-04-07 | [5 empty] | 2016 |  |  | FALSE
40414 | CIRA | CIRA Enhancement CIDI 00180350: CIRA Notifications should show the environment name |  | 6-Enhancement | Enhancement | Postponed | 2016-03-23 | [5 empty] | 2016 |  |  | FALSE
40313 | CIRA | CIRA-RSI-Phase 1A: Timestamp of SC Request Date does not update properly for Proxy details on OM Screen |  | 6-Enhancement | Software | Closed | 2016-03-14 | 2018-03-05 | NA |  |  |  | 2016 |  |  | #VALUE!
40207 | CIRA | Enhancements to CSP offer submission | 179737 | 6-Enhancement | Enhancement | Postponed | 2016-03-04 | [5 empty] | 2016 |  |  | FALSE
39962 | CIRA | CIRA: Cleaning unnecessary information from CIRA_MSTR. CIRA_DB_PROCESS_LOG table |  | 6-Enhancement | Enhancement | Postponed | 2016-02-18 | [5 empty] | 2016 |  |  | FALSE
39287 | CIRA | CIRA RSI_Phase 1A: As an ISO user Unable to reject approved NQC records |  | 6-Enhancement | Requirement Gap | Postponed | 2016-01-09 | [5 empty] | 2016 |  |  | FALSE
49477 | CIRA | Nature of Work Rules need to be alighed with Reliability Requirement BPM | 193390 | 2-Very High | Requirement Gap | Closed | 2017-08-16 | 2017-08-25 |  |  |  |  | 2017 | 8 | 2017 | 13 |  |  | Y
49589 | CIRA | CIRA - CIDI 00193890- October 2017 obligation for PGE TAC is different across the Obligation report and the CV | 193890 | 3-High | Software | Closed | 2017-08-21 | 2017-08-23 |  |  |  |  | 2017 | 8 | 2017 | 6 |  | Y
49588 | CIRA | CIRA - release substitution did not reset Flex RA upon cancellation |  | 3-High | Software | Closed | 2017-08-21 | 2017-12-12 | 2018-03-05 |  | RSI-2017 |  | 2017 | 12 | 2017 | 196 | [6 empty] | Y
48679 | CIRA | CIRA- CIDI 00193144 - Reduction in LSEs obligation did not reflect in the adjusted_obligation table |  | 4-Medium | Software | Open | 2017-07-21 | [5 empty] | 2017 |  |  | FALSE
52763 | CIRA | CIRA - System does not trigger the broadcast when Annual CPMs are designated |  | 3-High | Software | Closed | 2017-12-13 | 2017-12-14 | 2017-12-18 |  |  |  | 2017 | 12 | 2017 | 5 | Y
52693 | CIRA | CIRA- PMin should not be reduced from CPM MW for a non RA resource |  | 3-High | Requirement Gap | Closed | 2017-12-12 | 2017-12-22 | 2018-01-08 |  |  |  | 2017 | 12 | 2017 | 27 |  |  |  | Y
52517 | CIRA | CIRA- CPM designation UI did not reflect the designated record because of multiple area records for the resource in the DB (past and present) |  | 3-High | Software | Closed | 2017-12-05 | 2017-12-15 | 2018-01-08 |  |  |  | 2017 | 12 | 2017 | 34 |  |  |  |  | Y
52251 | CIRA | CIRA -CIDI 00198582 - OM Replacement UI is not showing outage records with status = IN_SERVICE |  | 3-High | Software | Closed | 2017-11-22 | 2017-11-23 | 2017-12-07 |  |  |  | 2017 | 11 | 2017 | 15 |  |  | Y
51904 | CIRA | CIRA handling of OMS ACL related outages |  | 3-High | Requirement Gap | Closed | 2017-11-08 | 2017-12-22 | 2018-01-08 |  |  |  | 2017 | 12 | 2017 | 61 | [6 empty] | Y
51837 | CIRA | CIRA - Annual Obligation for LSE TPES does not match the output from CV |  | 3-High | Software | Closed | 2017-11-06 | 2017-11-07 | 2017-11-08 |  |  |  | 2017 | 11 | 2017 | 2 | Y
51820 | CIRA | CIRA- Unable to upload annual obligation for 2018 from UI due to data volume |  | 4-Medium | Software | Open | 2017-11-06 | [5 empty] | 2017 |  |  | FALSE
51694 | CIRA | Eligible Non-RA Capacity' is higher than the 'Availability MW' of external resource (TG) |  | 4-Medium | Software | Open | 2017-10-31 | [5 empty] | 2017 |  |  | FALSE
52336 | CIRA | SC transfer report date filters not working as expected |  | 4-Medium | Software | Open | 2017-11-28 | [5 empty] | 2017 |  |  | FALSE
52202 | CIRA | Monthly RA plan is allowing an end date = EOY in the Flex RA Capacity tab | 198570 | 4-Medium | Software | Open | 2017-11-20 | [5 empty] | 2017 |  |  | FALSE
51373 | CIRA | During Flex CV run, LSE's Flex RA MW is not capped with Supplier's Flex RAMW. |  | 4-Medium | Software | Open | 2017-10-18 | [5 empty] | 2017 |  |  | FALSE
51362 | CIRA | Import Allocations screen not allowing IA for 2018 | 195150 | 4-Medium | Software | Open | 2017-10-18 | [5 empty] | 2017 |  |  | FALSE
51915 | CIRA | Date filter for end date does not work as expected on import allocation screen |  | 5-Low | Software | New | 2017-11-09 | [5 empty] | 2017 |  |  | FALSE
51778 | CIRA | ITC record added to Import Alloc screen does not show up for SC in the drop down - MWs do not show up for the LSE under view net allocation | 195863 | 6-Enhancement |  | Closed | 2017-11-03 | 2017-11-06 | 2017-11-06 |  |  |  | 2017 | 11 | 2017 | 3 | Y
51246 | CIRA | Searching for Flex Resources is displaying all ITIE resources in the Forced Substitution screen |  | 6-Enhancement |  | Evaluated | 2017-10-12 | [5 empty] | 2017 |  |  | FALSE
50484 | CIRA | RAAIM Precalc for Short-Term Use Limit Reached Nature of Work |  | 6-Enhancement |  | Closed | 2017-09-19 | 2018-03-26 | 2018-03-28 |  |  |  | 2017 |  |  | 190 | [6 empty] | Y
52770 | CIRA | Adjust CPM job does not adjust CPMs these are outside of the month boundary |  | 4-Medium | Software | New | 2017-12-13 | [5 empty] | 2017 |  |  | FALSE
49868 | CIRA | Warning/Error/Confirmation messages does not refresh automatically when user navigate to new page |  | 4-Medium | Software | New | 2017-08-28 | [5 empty] | 2017 |  |  | FALSE
52572 | CIRA | EIM Enhancements - New NOW to be configured |  | 6-Enhancement |  | Closed | 2017-12-07 | 2017-12-22 | 2018-01-08 |  |  |  | 2017 | 12 | 2017 | 32 |  |  |  |  | Y
53859 | CIRA | Short' classification incorrect in some cases where RA exceeds obligation | 201261 | 3-High | Software | Closed | 2018-01-25 | 2018-02-02 | 2018-02-02 |  |  |  | 2018 | 2 | 2018 | 8 |  | Y
43827 | CIRA | RSI-1A - UAT - Outage exemption request functionality is missing the 5 business day validation rule which is available in RAAM |  | 3-High | Software | Closed | 2016-10-13 | 2018-01-05 | 2018-03-05 |  | RSI-2017 |  | 2016 | 1 | 2018 | 508 | [6 empty] | Y
54909 | CIRA | Legacy data in RA Report |  | 3-High | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54910 | CIRA | Loss of type-ahead search capability on the RA Report |  | 3-High | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54908 | CIRA | RA Operator role: Loss of mouse roll-over function for Menu Items |  | 3-High | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54914 | CIRA | Default view results to 500 on RA report |  | 4-Medium | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54915 | CIRA | Hide the top menu 'RA Validation' for the operator role |  | 4-Medium | Requirement Gap | Closed | 2018-03-06 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 2 | Y
54786 | CIRA | RSI-2017 - Change message color to blue on Create Forced Sub UI | 202224 | 5-Low | Requirement Gap | Closed | 2018-03-01 | 2018-03-07 | 2018-03-08 |  |  |  | 2018 | 3 | 2018 | 7 |  | Y
46026 | CIRA | ReceiveResourceAdequacyCapacityData_SIBRv1_AP failure due to missing HE19 data |  | 3-High | Software | Closed | 2017-03-10 | 2018-03-08 | 2018-03-09 |  |  |  | 2017 | 3 | 2018 | 364 | [6 empty] | Y
46070 | CIRA | RAAIM calculation failure due to DST Short day |  | 3-High | Software | Closed | 2017-03-13 | 2018-03-09 | 2018-03-09 |  |  | DST-Spring | 2017 | 3 | 2018 | 361 | [6 empty] | Y
54503 | CIRA | UNIT_TESTING NOW should be RAAIM Exempt (SDS#201611 and IMS#199963) | 201611 | 3-High | Requirement Gap | Closed | 2018-02-19 | 2018-03-06 | 2018-03-06 |  |  |  | 2018 | 3 | 2018 | 15 |  |  | Y
55138 | CIRA | New OIA job should use the RSI-2017 date |  | 3-High | Software | Closed | 2018-03-15 | 2018-03-20 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 13 |  |  | Y
55076 | CIRA | RAAIM Pre-calc missing an hour and duplicating the subsequent hour for Spring DST |  | 3-High | Software | Open | 2018-03-13 | 2018-03-19 | 2018-03-28 |  |  | DST-Spring | 2018 | 3 | 2018 | FALSE
53917 | CIRA | Search Outages grid in the Outage Exemptions screen does NOT have a progress indicator |  | 4-Medium | Software | Open | 2018-01-29 | [5 empty] | 2018 |  |  | FALSE
53906 | CIRA | The Outage Resource SCID and Potential Substitute Resource SCID columns have # character across some Outage Resources. |  | 4-Medium | Software | Open | 2018-01-29 | [5 empty] | 2018 |  |  | FALSE
53847 | CIRA | Check to confirm user action prior to cancelling substitutions | 201256 | 6-Enhancement |  | Open | 2018-01-25 | [5 empty] | 2018 |  |  | FALSE
53675 | CIRA | Request to go back to the main RAAIM Pre-Calc screen from the Results screen | 201029 | 6-Enhancement |  | Open | 2018-01-18 | [5 empty] | 2018 |  |  | FALSE
54512 | CIRA | Remove the 'substitution required' flag from the Create Forced Substitution UI |  | 6-Enhancement |  | Closed | 2018-02-20 | 2018-03-27 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 36 |  |  |  |  | Y
53708 | CIRA | CPM should not be designated for TG & ITIE resources (until long term changes) |  | 6-Enhancement |  | Open | 2018-01-19 | [5 empty] | 2018 |  |  | FALSE
54040 | CIRA | Clean-up of plan validation status upon plan upload |  | 6-Enhancement |  | Open | 2018-02-02 | [5 empty] | 2018 |  |  | FALSE
53214 | CIRA | Add TAC and local area to the Operational RA report output from OIA |  | 6-Enhancement |  | Closed | 2018-01-02 | 2018-03-22 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 85 | [6 empty] | Y
51950 | CIRA | RA Report download needs label updates 'Flex MW' as 'Flex Supply MW' |  | 6-Enhancement |  | Closed | 2017-11-09 | 2018-03-27 | 2018-03-28 |  |  |  | 2017 | 3 | 2018 | 139 | [6 empty] | Y
55360 | CIRA | RAAIM re-calc to send 0 MW in case of no exemption |  | 6-Enhancement |  | Closed | 2018-03-23 | 2018-03-26 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 5 | Y
53279 | CIRA | Tracking substitution for outages with pro-rated POSO |  | 6-Enhancement |  | Closed | 2018-01-04 | 2018-03-26 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 83 | [6 empty] | Y
55425 | CIRA | unable to approve replacements in production |  | 3-High | Software | Closed | 2018-03-28 | 2018-03-28 | 2018-03-28 |  |  |  | 2018 | 3 | 2018 | 0 | Y
55510 | CIRA | OIA for RSI-2017 period throwing an error |  | 3-High | Software | Closed | 2018-04-04 | 2018-04-04 | 2018-04-04 |  |  |  | 2018 | 4 | 2018 | 0 | Y
55375 | CIRA | Forced substitution release not working as expected | 202861 | 3-High |  | Under test | 2018-03-26 | 2018-04-10 |  | 2018-04-30 |  |  | 2018 | 4 | 2018 | FALSE