## Policy Development Milestones
s | [9 empty] | November 2019 (Unless formally noticed, dates are tentative and are subject to change) |  |  |  |  | December 2019 (Unless formally noticed, dates are tentative and are subject to change) |  |  |  |  | January 2020 (Unless formally noticed, dates are tentative and are subject to change)
Calendar | Initiatives (Updated Weekly) | Initiative / Process Lead | Start | Discuss at MSC | EIM Category (E1-E4) | Proposed EIM Governing Body Meeting | Proposed Board Meeting | Notes | Proposed Tariff Filing Date | Publish Paper | Meeting/ Call | Comments Due | Training or Working Group | ISO Posts Draft Tariff Language | Publish Paper | Meeting/ Call | Comments Due | Training or Working Group | ISO Posts Draft Tariff Language | Publish Paper | Meeting/ Call | Comments Due | Training or Working Group | ISO Posts Draft Tariff Language
Recurring Meetings | ISO Board of Governors | N/A | Recurring | [7 empty] | 13, 14 |  |  |  |  | 18, 19
| EIM Governing Body | N/A | Recurring | [12 empty] | 4
| Market Performance and Planning Forum | J. Morris | Recurring | [12 empty] | 11
Policy Development | Capacity Procurement Mechanism Soft-Offer Cap | G. Murtaugh | Q3 2019 |  |  |  | Q1 2020 | Assessing next steps based on RA direction
| Day-Ahead Market Enhancements | M. Poage | Q1 2019 | 2019-08-19 | E2 | 2021 | 2021 | Next step: Publish straw proposal in Jan 2020 | [11 empty] | 27
| Energy Storage and Distributed Energy Resource Phase 4 | E. Kim | Q1 2019 | 2019-08-19 | E2 | Q3 2020 | Q3 2020 |  |  |  |  | 11 |  |  |  | 3 |  |  |  |  | 27
| Extend Day-Ahead Market Enhancements to EIM Entities | D. Tretheway | Q1 2020 |  | E1 | 2021 | 2021 |  |  |  |  | 22 | 29 |  |  |  |  | 12
| Generation Deliverability Assessment | R. Sparks | Q2 2019 |  |  |  | 2019-11-01 |  |  |  | 4, 25 | 21 |  | 7
| Hybrid Resources | C. Devon | Q3 2019 | 2019-08-19 | E2 |  | Q2 2020 | Targeting full implmentation by Fall 2021 | [6 empty] | 10 | 17 | [5 empty] | 14
| FERC Order 831 - Import Bidding and Market Parameters | P. Servedio | Q2 2019 |  | E2 | Spring 2020 | Spring 2020 |  |  | 21 | [5 empty] | 3 | 17 |  |  | 21 | 29 | 12
| Local Capacity Technical Study Criteria Update | C Micsa | Q2 2019 |  |  |  | 2019-11-01 |  |  |  | 12 | 26 |  | 5
| Market Settlement Timeline | P. Servedio | Q2 2019 |  | E2 | 2019-10-01 | 2019-11-01
| Price Performance Analysis | G. Bautista | Q2 2019 | 2019-10-11 |  |  | TBD
| Resource Adequacy Enhancements | C. Devon | Q4 2018 |  |  |  | May/June 2020 | [7 empty] | 17 | [5 empty] | 7, 8 | 22
| Transmission Access Charge Structure Enhancements | C. Devon | Q3 2017 |  |  | Q4 2020 | 2020-02-01 | On hold to ensure coordination and alignment with EDAM
| System Market Power Mitigation | P. Servedio | Q1 2019 | 2019-10-11 | E2 | Dec 2019 (Briefing) | Nov 2019 (briefing) |  |  |  |  | 4 |  |  | 9 | 16 |  |  |  | 8 | 15 | 6, 29
Recurring Processes / Initiatives | Customer Partnership Group series | N/A | Recurring |  |  |  | N/A
| Variable Operations and Maintenance Cost Definitions | G. Bautista | Q4 2019 |  | E2 | TBD | TBD |  | TBD
| Flexible Capacity Needs Technical Study Process | C. Loutan | Recurring |  |  |  | N/A
| Budget and Grid Management Charge Process | A. Gordon | Recurring |  |  |  | 2018-12-01 | 2019 process completed, 2020 process in progress |  | 1 | 20 | 27
| Local Capacity Requirements | C.Micsa | Recurring |  |  |  | N/A | 2020 process completed, 2021 process in progress |  |  |  | 14
| Participating Transmission Owner Per-Unit Cost | R. Emmert/ M.Wu | Recurring |  |  |  | N/A
| Annual Policy Initiatives Roadmap | B.Dean | Q3 2016 |  |  | Dec 2019 (Briefing) | Dec 2019 (Briefing) |  | N/A | 25 | [5 empty] | 2 | 9
| 2018-2019 Transmission Planning Process | R. Sparks | Recurring |  |  |  | 2019-03-01 |  | N/A
| 2019-2020 Transmission Planning Process | R. Sparks | Recurring |  |  |  | Q2 2020 |  | N/A |  | 18 | [5 empty] | 2
| 2017 Tariff Clarifications Filing Process | K. Meeusen | Recurring |  |  |  | N/A
| Western Regions Planning Coordination | G. DeShazo | Recurring |  |  |  | N/A | hosted in Jan 2019
|  | Legal Lead | Start
Tariff Development | Amendment to ISO Section 20 | J. Spomer | May 2019 |  |  |  | 2019-11-01 |  | TBD
| Aliso Canyon Gas-Electric Coordination Phase 5 | B. Dean | Q3 2019 |  | E2 |  | TBD |  | Q3 2019
| Commitment Costs and Default Energy Bid Enhancements | B. Dean | Q4 2016 |  | E2 |  | 2018-03-01 |  | 2019-08-30
| Contingency Modeling Enhancements | P. Servedio | Mar 2013 |  |  |  | 2017-12-01 | Tariff development timeline currently TBD | TBD
| Excess Behind the Meter Production | G. Murtaugh | Q2 2018 |  |  |  | 2019-05-01 |  | Q1 2020 | 4 |  | 18 |  |  |  | 2
| Effective Flexible Capacity Ratings Process Clarification | A. Motley | May 2019 |  |  |  | N/A |  | Q4 2019
| Energy Storage and Aggregated Distributed Energy Resource Phase 3 | E. Kim | Q3 2017 |  | E2 | 2018-08-01 | 2018-09-01 |  | 2019-09-03
| Local Market Power Mitigation Enhancements | B. Dean | Q3 2018 |  | E1, E2 * | 2019-03-01 | 2019-03-01 | Pending FERC ruling | 2019-07-02
| Real-Time Market Neutrality Settlement | D. Tretheway | Q2 2019 |  | E1 | 2019-06-01 | 2019-07-01 | pending FERC ruling | 2019-07-30
| Reliability Must-Run and Capacity Procurement Mechanism Enhancements | G. Murtaugh | Q1 2018 |  |  |  | 2019-03-01 | RMR filed | ?
| Intertie Deviation Settlement | M. Poage | Q2 2018 |  | E2 | 2019-01-01 | 2019-02-01 |  | TBD
* For E1 - E4 category designations, * denotes category applies only to certain proposal elements

## Inactive Initiatives
* For EIM E1 - E4 category designations, * denotes category applies only to certain proposal elements
Calendar | Initiatives | Initiative Lead | Start | Discuss at MSC | EIM Category (E1-E4) | Proposed EIM Governing Body Meeting | Proposed Board Meeting | Notes | Proposed Tariff Filing Date
Policy Development | Bid Cost Recovery Enhancements (Formerly Two-Tier Allocation) | P. Servedio | Q4 2015 |  | E2 |  | TBD | Subsequent activities on this initiative have not been planned or scheduled. | TBD
| Flexible Resource Adequacy Criteria and Must-Run Obligation Phase 2 | K. Meeusen | Jun 2015 |  |  |  | 2018-11-01
| Frequency Response Phase 2 | C.Colbert | Dec 2016 |  |  |  | TBD | Subsequent activities on this initiative have not been planned or scheduled. | TBD
| Storage as a Transmission Asset | K. Meeusen | Q2 2018 |  |  |  | Q3 2019 | Deferred to 2020 for storage dispatch policy resoution in ESDER 4 | TBD
| Self-Schedules Bid Cost Recovery Allocation and Bid Floor |  | Aug 2016 |  |  |  | TBD | Subsequent activities on this initiative have not been planned or scheduled. | TBD
Regional Integration | Regional Resource Adequacy | C. Devon | Nov 2015 |  |  |  | TBD | Subsequent activities on this initiative have not been planned or scheduled. | TBD
| Transmission Access Charge Options | L. Kristov | Oct 2015 |  |  |  | TBD | Subsequent activities on this initiative have not been planned or scheduled. | TBD
Recurring Initiatives | N/A
|  | Legal Lead | Start |  |  |  | Filing Date
Tariff Development | N/A
* For E1 - E4 category designations, * denotes category applies only to certain proposal elements

## Implementation Milestones
Calendar | Release / Implementation (Updated Monthly) | Deployment | Market Simulation Start - End |  | Activation | Project Manager
Fall 2019 | Commitment Costs and Default Energy Bid Enhancements Phase 1 | 2019-11-13 | 2019-09-03 | 2019-10-11 | 2019-11-01 | Ray Riley
| Energy Storage and Aggregated Distributed Energy Resource, Phase 3A | 2019-11-13 | 2019-09-03 | 2019-10-11 | 2019-11-01 | Mohan Koya
| Reliability Must Run and Capacity Procurement Mechanism Enhancements | 2019-11-13 | 2019-09-03 | 2019-10-11 | 2020-01-01 | LeAnn McLaughlin
| Local Market Power Mitigation Enhancements | 2019-11-13 | 2019-09-03 | 2019-10-11 | 2019-11-01 | Ray Riley
| EIM Enhancements 2019 | 2019-11-13 | 2019-09-03 | 2019-10-11 | 2019-11-01 | Ayman Fattah
| FERC Order 841 – Energy Storage Resources | 2019-11-13 | 2019-09-03 | 2019-10-11 | 2019-11-01 | David Luk
| Real-Time Market Neutrality Settlement | 2019-11-13 | 2019-09-03 | 2019-10-11 | 2019-08-01 | LeAnn McLaughlin
Independent 2020 | ADS Replacement | TBD | TBD | TBD | TBD | John Williams
Spring 2020 | EIM - Salt River Project | 2020-04-01 | 2019-12-01 | 2020-01-31 | 2020-04-01 | Joanne Alai
| EIM - Seattle City Light | 2020-04-01 | 2019-12-01 | 2020-01-31 | 2020-04-01 | Ayman Fattah
Fall 2020 | Commitment Costs and Default Energy Bid Enhancements Phase 2 | 2020-10-01 | TBD | TBD | 2020-10-01 | Ray Riley
| Import Bid Cost Verification | 2020-10-01 | TBD | TBD | 2020-10-01 | Ray Riley
| Contingency Modeling Enhancements - Transmission | 2020-10-01 | TBD | TBD | 2020-10-01 | Mohan Koya
| Energy Storage and Aggregated Distributed Energy Resource, Phase 3B | 2020-10-01 | TBD | TBD | 2020-10-01 | Mohan Koya
| Dispatch Operating Target Tariff Clarifications | 2020-10-01 | TBD | TBD | 2020-10-01 | John Williams
| Intertie Deviation Settlement | 2020-10-01 | TBD | TBD | 2020-10-01 | LeAnn McLaughlin
| Capacity Procurement Mechanism Soft Offer Cap | 2020-10-02 | TBD | TBD | 2020-10-02 | Adrian Chiosea
| Excess Behind the Meter Production | 2020-10-01 | TBD | TBD | 2020-10-01 | Adrian Chiosea
Spring 2021 | EIM - Public Service Company of New Mexico | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | Ayman Fattah
| EIM - Northwestern Energy | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | Ayman Fattah
| EIM - LADWP | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | Joanne Alai
| EIM - Turlock Irrigation District | 2021-04-01 | 2020-12-01 | 2021-01-31 | 2021-04-01 | Joanne Alai
Fall 2021 | DAME - Flexible Ramping Product | TBD | TBD | TBD | TBD | Adrian Chiosea
| RA Enhancements | TBD | TBD | TBD | TBD | Adrian Chiosea
| Energy Storage and Aggregated Distributed Energy Resource Phase 4 | TBD | TBD | TBD | TBD | Adrian Chiosea
| Market Settlement Timeline Transformation | TBD | TBD | TBD | TBD | Adrian Chiosea
| Transmission Access Charge Structure Enhancements | TBD | TBD | TBD | TBD | Adrian Chiosea
Spring 2022 | EIM - Avista | 2022-04-01 | 2021-12-01 | 2022-01-31 | 2022-04-01 | Adrian Chiosea
| EIM - Tucson Electric Power | 2022-04-01 | 2021-12-01 | 2022-01-31 | 2022-04-01 | Adrian Chiosea
TBD | Extend Day-Ahead Market Enhancements to EIM Entities | TBD | TBD | TBD | TBD | Adrian Chiosea