DRAFT- 2022-2023 Transmission Planning Process Phase 3 Sequence Schedule

|  |  |  |  |
| --- | --- | --- | --- |
| Sequence | 1st Sequence | 2nd Sequence |  3rd Sequence |
| Projects |  |  |  |
|  | Bid Window Open | June 26, 2023 | June 26, 2023 | June 26, 2023 |
|  | Voluntary notification to ISO of interest in collaboration | July 11, 2023 |  July 11, 2023 | July 11, 2023 |
| Application Sufficient and Valid | Bid Window Close  | Sept 29th, 2023 | October 13, 2023 | October 27, 2023 |
| Validation | October 20, 2023 | November 3, 2023 | November 20, 2023 |
| Cure  | November 3, 2023 | November 20, 2023 | December 5, 2023 |
| Final Validation | November 20, 2023 | December 5, 2023 | December 19, 2023 |
| Post List of Valid and Sufficient Project Sponsor Applications | November 20 , 2023 | December 5, 2023 | December 19, 2023 |
| Proposal and Project Sponsor Qualification | Qualification | December 12, 2023 | December 27, 2023 | January 11, 2024 |
| Cure  | December 27, 2023 | January 11, 2024 | January 26, 2024 |
| Final Qualification | January 11, 2024 | January 26, 2024 | February 9, 2024 |
| Post List of Qualified Project Sponsors and Proposals | January 11, 2024 | January 26, 2024 | February 9, 2024 |
|  | Comparative Analysis | April 8, 2024 | April 22, 2024 | May 6, 2024 |
| Post Approved Project Sponsor | April 8, 2024 | April 22, 2024 | May 6, 2024 |
| Post Selection Report | April 22, 2024 | May 6, 2024 | May 20, 2024 |