## IOU MRTU Criteria
MRTU |  | MRTU
IOU Criteria To Be Met By December 1, 2008 for Feb 1, 2009 Go-Live
As Of 10/17/2008
| Criteria # | Criteria Description | CAISO * | IOU
Priority 1 IMS Update 2 Exit Criteria | U2.02 | CAISO will allow all SCs to participate. | C | C
| U2.04 | Publish daily settlement statements and supporting documentation by TD+5BD. | C | S
| U2.05 | Publish two monthly settlement statements and supporting documentation by TD+25BD. | C | N
| U2.06 | Publish CRR Auction settlement statements and supporting documentation. | C | N
| U2.07 | Publish two accurate monthly invoices. | S | N
| U2.08 | DAM successfully solves and publishes by 1300 for 7 consecutive days. | S | S
| U2.09 | No more than 5 consecutive 5 minute RT cases fail for 7 consecutive trading days. | C | S
| U2.10 | 97.5% availability of external facing applications and interfaces. | C | S
| U2.13 | 90% AC solution over the last 4 weeks. | C | C
| U2.14 | Every charge code exercised and valid. | S | S
| U2.15 | Scenarios successfully completed. | S | S
| U2.17 | CAISO systems patches will be fully tested, installed, and validated. | S | S
| U2.18 | HASP successfully solves and publishes ontime 95% of the time for 7 consecutive days. | S | N
| U2.19 | RTM successfully solves and publishes ontime 95% of the time for 7 consecutive days. | S | N
|  | Number of Priority 1 Exit Criteria Met | 7 | 2
Priority 2 Exit Criteria | U2.01 | No open Critical and Very High variances. Mitigate or repair High variances. | S | S
| U2.03 | CAISO to publish a daily participation list. | C | C
| U2.11 | CAISO backup and restore plans executed. | S | S
| U2.12 | CAISO archiving and data retention plans performed. | S | S
| U2.16 | Market results based on inputs and consistent across external applications. | C | N
|  | Number of Priority 2 Exit Criteria Met | 2 | 1
Additional Criteria | CR.01 | CAISO systems performance and stability are proven reasonable | C | S
| CR.02 | Market Prices are Reasonable | C | N
| CR.03 | Resource ID issue is resolved and tested | S | S
| CR.04 | CAISO achieves satisfactory progress towards providing a high level of confidence in the CAISO's market gaming prevention processes and protocols and market monitoring tools** | S | S
| CR.05 | Number of charge codes passing Bid to Bill Shadow Validation at acceptable Level (C is above 60, S is between 30 and 59, N is less than 30) | Not Applicable | N
| CR.06 | System changes controlled by production quality change management process | C | S
| CR.07 | MRTU Tariff and Policy issues are finalized | C | N
[C] Completed
[S] Started, not completed
[N] Not Started, or not tracking to complete by December 1, 2008
Priority 1 Exit Criteria was to be met prior to 90-day market participation testing phase.
Priority 2 Exit Criteria can be met after 12/1/2008.
Additional Criteria must be met by 60-day FERC readiness filing.
* The CAISO assesment of Exit Criteria is interpreted based on published exit criteria statistics and daily conference calls.
** CAISO needs to complete Readiness Criteria ORG - 3.3: "A Market simulation tool (the MRTU Sandbox/DMM Tool) that is based on the actual CAISO market software will be developed and tested by the CAISO MRTU Team and made available to the DMM three months prior to Go Live." For February 1 go-live, this is November 1.

## 1, 17
CAISO Exit Criteria Tracking - U2.01, U2.17
Number | Criteria |  |  |  | Comments
U2.01 | Simulation concludes without any open Critical and Very High variances. At least one meeting will be scheduled with Market Participants as a collaborative effort to review all variances prior to exiting IMS U2. High variances will be repaired and tested when possible while remaining High variances will be mitigated. |  |  |  | There are still Very High issues open. Many open High issues still remain to be repaired or mitigated.
U2.17 | Patches in CAISO systems to address Critical ,Very High, or High variances that require market participant software changes will be fully tested, installed by CAISO and validated by participants prior to exiting IMS U2. |  |  |  | - Still have remaining Very High, and High issues that may require market participant software changes. Some patched issues have been reopened.
Qualifying Period |  | N/A |  |  |  | Reviewer |  | Mahesh Koduri
Summary of Open Issues
Date | Week | Critical | Very High | High | Medium | Low | TOTAL | TOTAL >= High
2008-06-06 | 13 | 0 | 11 | 279 | 36 | 2 | 328 | 290
2008-06-13 | 14 | 0 | 9 | 270 | 36 | 4 | 319 | 279
2008-06-20 | 15 | 0 | 8 | 296 | 50 | 4 | 358 | 304
2008-06-27 | 16 | 0 | 10 | 316 | 55 | 4 | 385 | 326
2008-07-03 | 17 | 1 | 10 | 341 | 53 | 4 | 409 | 352
2008-07-11 | 18 | 1 | 21 | 325 | 56 | 4 | 407 | 347
2008-07-18 | 19 | 1 | 17 | 355 | 51 | 5 | 429 | 373
2008-07-25 | 20 | 1 | 27 | 373 | 47 | 4 | 452 | 401
2008-08-01 | 21 | 1 | 33 | 376 | 51 | 4 | 465 | 410
2008-08-08 | 22 | 1 | 36 | 357 | 47 | 4 | 445 | 394
2008-08-22 | 23 | 1 | 24 | 264 | 40 | 4 | 333 | 289
2008-08-29 | 24 | 0 | 25 | 259 | 40 | 4 | 328 | 284
2008-09-05 | 25 | 0 | 27 | 255 | 44 | 3 | 329 | 282
2008-09-12 | 26 | 0 | 20 | 233 | 40 | 4 | 297 | 253
2008-09-19 | 27 | 0 | 21 | 230 | 37 | 5 | 293 | 251
2008-09-26 | 28 | 0 | 20 | 224 | 43 | 5 | 292 | 244
2008-10-03 | 29 | 0 | 17 | 193 | 42 | 2 | 254 | 210
2008-10-10 | 30 | 0 | 17 | 196 | 41 | 3 | 257 | 213
2008-10-17 | 31 | 0 | 19 | 204 | 36 | 2 | 261 | 223

## 2, 3,11, 12
CAISO Exit Criteria Tracking - U2.02, U2.03
Number | Criteria |  | Comments
U2.02 | CASIO will make all externally facing MRTU applications available for 100% of SCs to participate. |  | Completed.
U2.03 | CASIO will publish the daily list of SCs participating in IMS U2 for SIBR, BAPI, and CMRI for Market Participants to evaluate what SCs that have an obligation to bid resources but are not participating. |  | Completed.
Qualifying Period |  | Criterion applies for a two-week period prior to the end of IMS U2. |  | Reviewer | Jack Peterson
CAISO Exit Criteria Tracking - U2.11, U2.12
Number | Criteria |  | Comments
U2.11 | Backup and restore plans executed for 100% of the Market Simulation impacted servers deemed operational critical during normal operating hours. |  | To be tested later.
U2.12 | Archiving and data retention plans for all Market Simulation systems performed for each day of phase. |  | To be tested later.
Qualifying Period |  | N/A |  | Reviewer | Jack Peterson

## 4, 5, 6, 7, 14
CAISO Exit Criteria Tracking - U2.04-U2.07
Number | Criteria |  | Comments
U2.04 | CAISO publishes Settlement Statements and all supporting Settlements documentation including Configuration Guides and Bill Determinants for each Trade Date within TD+5 BD each initial settlement statement for each SC that participated in IMS U2 consistent with the respective SC's participation. |  | Statements have not been accurate or complete (missing attributes result in incorrect results being produced)
U2.05 | CAISO publishes Settlement Statements and all supporting Settlements documentation for Month End within TD + 25 BD for each SC that participated in IMS U2 consistent with the respective SC's participation. |  | CAISO has not published monthly statements with any consistency. Daily statement amounts do not add up to the monthly statement totals. CAISO monthly statements have not contained complete and accurate data due to changes made during the course of the month.
U2.06 | CAISO publishes Settlement Statements and all supporting Settlements documentation for CRR Auction for each SC that participated in IMS U2 consistent with the respective SC's participation. |  | There are still consistent payload issues that are preventing participants from fully validating the charge codes associated with CRRs.
U2.07 | CAISO publishes accurate Invoices and supporting Settlements documentation for a Trade Month based on respective monthly Settlement Statements for each SC that participated in IMS U2. |  | CAISO has not published monthly invoices with any consistency. Invoice amounts have not contained complete and accurate data.
U2.14 | Every Charge Type must be exercised and valid in accordance with the BPM for Settlements & Billing and CAISO Tariff during IMS Update 1 or 2 between the 4/7/2008 and TD -5 BD Trade Dates. Not every SC will necessarily be assessed the Charge Type |  | Not all charge code types have been exercised due to lack of data. A number of charge codes that have been exercised have failed to produce correct results.
Qualifying Period |  | Criterion applies for last two months. |  | Reviewer | Dave Bartholomew
Further details provided in other reports/presentations.

## 8
CAISO Exit Criteria Tracking - U2.08
Number | Criteria |  |  | Comments
U2.08 | Day Ahead market successfully solves and results are published by 1:00 PM for 7 consecutive trading days during IMS U2 Semi-structured testing |  |  | CAISO has not successfully published 7 weekdays before 1300. The closest over the last two months are two 5-day periods where results were published before 1320.
Qualifying Period |  | Criterion applies for the month prior to the end of IMS U2 (i.e. 7 days must occur within final month before exit). |  |  | Reviewer | Sean Yovan
Date | On Time (Yes/No) | Actual time published if No | Reason for Delays
2008-09-01 | N/A
2008-09-02 | NO | 1:04pm | N/A
2008-09-03 | YES
2008-09-04 | YES
2008-09-05 | NO | 1:04pm | N/A
2008-09-06 | N/A
2008-09-07 | N/A
2008-09-08 | YES
2008-09-09 | NO | 2:20PM | RUN DA SCENARIO 29
2008-09-10 | YES
2008-09-11 | NO | 1:26PM | RAN DA SCENARIO 25D
2008-09-12 | NO | 2:33PM | RAN DA SCENARIO 25D
2008-09-13 | N/A
2008-09-14 | N/A
2008-09-15 | YES
2008-09-16 | YES
2008-09-17 | YES
2008-09-18 | NO | 1:19PM | RAN DA SCENARIO 25J
2008-09-19 | YES
2008-09-20 | N/A
2008-09-21 | N/A
2008-09-22 | NO | OASIS YES, CMRI NO | CAISO DATABASE ISSUE
2008-09-23 | YES |  | (IST publication at 1:08pm)
2008-09-24 | YES
2008-09-25 | NO | Time of Publication Unavailable | NO EXPLANATION - RAN SCENARIO 24A
2008-09-26 | NO | 1:25PM | RAN DA SCENARIO 11
2008-09-27 | N/A
2008-09-28 | N/A
2008-09-29 | YES
2008-09-30 | NO | 1:34PM | NO DA SCENARIO
2008-10-01 | NO | 1:10PM | NO DA SCENARIO
2008-10-02 | YES
2008-10-03 | NO | 1:31PM | NO DA SCENARIO
2008-10-04 | N/A
2008-10-05 | N/A
2008-10-06 | YES
2008-10-07 | NO | Time of Publication Unavailable | DA SCENARIO 40
2008-10-08 | NO | No Publication | PORTAL DOWN
2008-10-09 | NO | 2:02PM | DA SCENARIO 7
2008-10-10 | YES |  | DA SCENARIO 29B
2008-10-11 | N/A
2008-10-12 | N/A
2008-10-13 | NO | 1:30PM | DA SCENARIO 24A & 45
2008-10-14 | YES
2008-10-15 | YES
2008-10-16 | NO | 1:33PM | DA SCENARIO 7
2008-10-17 | NO | Time of Publication Unavailable
2008-10-18 | N/A
2008-10-19 | N/A
2008-10-20 | N/A
2008-10-21 | N/A
2008-10-22 | N/A
2008-10-23 | N/A
2008-10-24 | N/A
2008-10-25 | N/A
2008-10-26 | N/A
2008-10-27 | N/A
2008-10-28 | N/A
2008-10-29 | N/A
2008-10-30 | N/A
2008-10-31 | N/A
Formulas:
Number = [Number, row above]+1
CAISO PLANNED DOWNTIME

## 9
CAISO Exit Criteria Tracking - U2.09
Number | Criteria |  |  | Comments
U2.09 | No more than 5 consecutive 5 minute RT cases fail for 7 consecutive trading days during IMS U2 Semi-Structured testing (except in scenarios specifically testing RT failure and contingency plans or during planned outages for patch deployment). RT case failure means no dispatchable solution was reached; does not include DC solutions or solutions achieved through constraint relaxation. |  |  | This criteria has not been met, the best performance so far has been 6 consecutive days where two of the days had 5 failures each.
Qualifying Period |  | Criterion applies for the month prior to the end of IMS U2 (i.e. 7 days must occur within final month before exit). |  |  | Reviewer | Josh Wood
Date | No more than 5 consecutive 5 min RT intervals failure (Yes/No) | If No, # of consecutive failure intervals | Hours failed
2008-09-01
2008-09-02 | Yes
2008-09-03 | No | 72 | 6 through 11
2008-09-04 | Yes
2008-09-05 | No | 46 | 19 through 22, 24
2008-09-06
2008-09-07
2008-09-08 | Yes
2008-09-09 | Yes
2008-09-10 | No | 24 | 2, 5, 6
2008-09-11 | Yes
2008-09-12 | No | 6 | 10
2008-09-13
2008-09-14
2008-09-15 | Yes
2008-09-16 | No | 10 | 6, 7
2008-09-17 | Yes
2008-09-18 | Yes
2008-09-19 | Yes
2008-09-20
2008-09-21
2008-09-22 | Yes
2008-09-23 | Yes | 5 | 13
2008-09-24 | Yes | 5 | 15
2008-09-25 | No | 6 | 15
2008-09-26 | No | 36 | 20 through 22
2008-09-27
2008-09-28
2008-09-29 | Yes
2008-09-30 | Yes
2008-10-01 | Yes
2008-10-02 | Yes
2008-10-03 | No | 21 | 10, 21, 22, 24
2008-10-04
2008-10-05
2008-10-06 | Yes
2008-10-07 | No | 12 | 9
2008-10-08 | Yes
2008-10-09 | No | 35 | 1 through 4
2008-10-10 | No | 16 | 23, 24
2008-10-11
2008-10-12
2008-10-13 | Yes
2008-10-14 | Yes
2008-10-15 | Yes
2008-10-16 | No | 9 | 4, 5
2008-10-17 | Yes
2008-10-18
2008-10-19
2008-10-20
2008-10-21
2008-10-22
2008-10-23
2008-10-24
2008-10-25
2008-10-26
2008-10-27
2008-10-28
2008-10-29
2008-10-30
2008-10-31
Formulas:
Number = [Number, row above]+1

## 10
CAISO Exit Criteria Tracking - U2.10
Number | Criteria |  |  |  | Comments
U2.10 | Market Portal, SIBR, CMRI, OASIS, SLIC, ADS, BAPI, OMAR, and Programmatic Interfaces are available 97.5% of the time during the last 4 weeks of IMS U2 (other than periods of disaster recovery testing and backup and restore testing). |  |  |  | This past week has shown degradation across most external facing systems.
Qualifying Period |  | N/A |  |  |  | Reviewer |  | TJ Ferreira
Date | PORTAL | SIBR | CMRI | OASIS | OASIS Prices | SLIC | BAPI | OMAR | API Market Results | API Clean Bid Set | API Current Bid Set
2008-09-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-02 | 100% | 100% | 100% | 100% | 96.53% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-03 | 100% | 100% | 100% | 100% | 96.53% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-04 | 100% | 100% | 100% | 100% | 99.31% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-05 | 100% | 100% | 100% | 97.6% | 98.08% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-08 | 100% | 100% | 100% | 100% | 91.91% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-09 | 100% | 100% | 98.61% | 100% | 94.1% | 100% | 98.26% | 100% | 100% | N/A | N/A
2008-09-10 | 100% | 97.92% | 97.57% | 95.83% | 83.68% | 100% | 98.26% | 100% | 100% | N/A | N/A
2008-09-11 | 100% | 100% | 97.92% | 92.36% | 64.93% | 100% | 98.61% | 100% | 100% | N/A | N/A
2008-09-12 | 100% | 100% | 96.53% | 96.53% | 77.43% | 100% | 94.44% | 100% | 100% | N/A | N/A
2008-09-13 | 100% | 100% | 100% | 98.26% | 100% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-14 | 100% | 100% | 100% | 100% | 97.57% | 100% | 99.65% | 100% | 100% | N/A | N/A
2008-09-15 | 100% | 100% | 100% | 100% | 96.85% | 100% | 99.3% | 100% | 100% | N/A | N/A
2008-09-16 | 100% | 99.29% | 100% | 100% | 98.23% | 100% | 95.41% | 100% | 100% | N/A | N/A
2008-09-17 | 99.65% | 99.31% | 99.65% | 99.31% | 97.22% | 99.31% | 99.65% | 99.31% | 100% | N/A | N/A
2008-09-18 | 100% | 100% | 100% | 100% | 96.27% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-19 | 100% | 100% | 100% | 97.92% | 95.49% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-20 | 100% | 100% | 100% | 100% | 96.88% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-21 | 98.61% | 100% | 100% | 100% | 99.31% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-22 | 100% | 100% | 100% | 100% | 96.88% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-23 | 100% | 100% | 97.92% | 99.65% | 97.57% | 100% | 99.31% | 100% | 100% | N/A | N/A
2008-09-24 | 100% | 100% | 97.55% | 96.85% | 91.26% | 100% | 97.9% | 100% | 100% | N/A | N/A
2008-09-25 | 100% | 100% | 100% | 100% | 99.31% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-26 | 100% | 92.33% | 100% | 99.3% | 97.91% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-27 | 100% | 100% | 100% | 100% | 99.31% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-28 | 100% | 100% | 100% | 100% | 99.31% | 100% | 100% | 100% | 100% | N/A | N/A
2008-09-29 | 100% | 100% | 100% | 100% | 97.36% | 100% | 100% | 100% | 100% | 100% | 100%
2008-09-30 | 100% | 100% | 100% | 96.89% | 93.43% | 100% | 100% | 100% | 99.65% | 99.65% | 100%
2008-10-01 | 100% | 100% | 100% | 96.18% | 93.75% | 100% | 100% | 100% | 99.31% | 98.96% | 99.65%
2008-10-02 | 100% | 100% | 100% | 100% | 99.65% | 100% | 100% | 100% | 99.65% | 98.61% | 98.96%
2008-10-03 | 99.65% | 100% | 100% | 100% | 98.95% | 100% | 100% | 100% | 98.61% | 98.61% | 98.61%
2008-10-04 | 100% | 99.31% | 100% | 100% | 98.96% | 100% | 100% | 100% | 97.92% | 98.26% | 97.92%
2008-10-05 | 100% | 100% | 100% | 100% | 99.65% | 100% | 100% | 100% | 98.61% | 98.96% | 99.31%
2008-10-06 | 100% | 100% | 100% | 100% | 98.94% | 100% | 100% | 100% | 88.38% | 97.89% | 100%
2008-10-07 | 100% | 100% | 100% | 100% | 98.21% | 100% | 100% | 100% | 37.94% | 57.09% | 100%
2008-10-08 | 95.49% | 95.49% | 95.83% | 100% | 97.92% | 100% | 95.49% | 90.97% | 100% | 98.61% | 99.31%
2008-10-09 | 100% | 99.31% | 100% | 100% | 96.53% | 100% | 100% | 100% | 89.27% | 88.89% | 85.07%
2008-10-10 | 100% | 100% | 100% | 100% | 98.26% | 100% | 98.26% | 100% | 89.9% | 89.58% | 85.07%
2008-10-11 | 100% | 100% | 99.65% | 100% | 96.88% | 100% | 100% | 100% | 88.54% | 99.65% | 99.31%
2008-10-12 | 99.65% | 100% | 100% | 100% | 97.57% | 100% | 100% | 100% | 47.57% | 96.88% | 97.22%
2008-10-13 | 99.65% | 100% | 100% | 96.88% | 88.19% | 100% | 100% | 100% | 44.44% | 99.65% | 98.96%
2008-10-14 | 100% | 100% | 100% | 100% | 97.2% | 100% | 100% | 100% | 46.15% | 98.95% | 99.65%
2008-10-15 | 100% | 99.65% | 100% | 100% | 96.86% | 100% | 100% | 100% | 49.48% | 99.65% | 99.3%
2008-10-16 | 99.23% | 100% | 100% | 100% | 95.75% | 100% | 100% | 100% | 37.84% | 93.46% | 94.62%
2008-10-17 | 100% | 99.62% | 100% | 100% | 89.73% | 70.23% | 100% | 100% | 49.43% | 66.03% | 67.18%

## 13, 16
CAISO Exit Criteria Tracking - U2.13
Number | Criteria |  | Comments
U2.13 | Quality of solution to be 90% AC solution over the last 4 weeks of IMS U2. |  | Passed
Qualifying Period |  | N/A |  | Reviewer | Willy Wang
CAISO Exit Criteria Tracking - U2.16
Number | Criteria |  | Comments
U2.16 | Market results are based on market inputs and consistent across external markets application |  | There are many large issues remaining to be resolved before this criteria can be completed.
Qualifying Period |  | Criterion applies for the month prior to the end of IMS U2. |  | Reviewer | Willy Wang
Further details provided in other reports/presentations.

## 15
CAISO Exit Criteria Tracking - U2.15
Number | Criteria |  |  | Comments
U2.15 | All scenarios agreed to by Market Participants and CAISO will be successfully completed and MPs affirm completion in accordance with Scenario Dashboard. |  |  | Two final reports published. Many unanswered questions for market participants. Scope changes after some scenarios were already completed which necessitates rerun.
Qualifying Period |  | N/A |  |  | Reviewer |  | Sean Yovan
Execution Date | Scenario # | Scenario Description | Scenario Category | CAISO | SCE | SCE Comments on Scenrarios and analysis
2008-09-08 | 34A | PROCURE EXCESS RUC | DAM | PASS | PASS | No issues noted.
2008-09-08 | 29 | HIGH IMPACT LINE OUTAGE | DAM | RERUN | RERUN | Modeling errors needs to be corrected.
2008-09-09 | 34B | PROCURE EXCESS RUC | RTM | PASS | RERUN | Manual decommitment not honored in RTD. Why large negative prices at interties? What was cause of STUC failures on this day?
2008-09-11 | 25E | DERATE: MEAD, ELDORADO | DAM | PASS | RERUN | Price reached almost -550$/MWh but SS was not curtailed. All versions of 25 should be rerun once the pro-rata method is corrected to include all schedules.
2008-09-11 | 8 | HASP EXPORT SCHED PRIORITY | RTM | PASS | Reviewing | Possible to submit a bid to achieve an export priority (PT) which is higher than what is deserved (LPT) (Issue 15812)
2008-09-12 | 25D | VERIFY LMPs ON OVERSCHEDULED LINE | DAM | PASS | RERUN | Rerun all versions of 25.
2008-09-15 | 25A | DERATE PACI, TESLA, TRACY | DAM | PASS | RERUN | Rerun all versions of 25.
2008-09-15 | 28A | INSUFFICIENT BIDS TO CLEAR CONG | DAM | PASS | PASS | Met expectations
2008-09-16 | 39 | SCIT | DAM | PASS | PASS | Met expectations
2008-09-16 | 28B | INSUFFICIENT BIDS TO CLEAR CONG | RTM | PASS | Reviewing | Bay Area only - No SCE participation.
2008-09-17 | 35 | UNDERPROCUREMENT OF RUC | RTM | PASS | Reviewing | Underprocurement simulated by raising RT load forecast for HASP; however, RT actual load remained low for RTD. Saw expensive RTPD commitment (as expected given high RT load forecast) but did not see inexpensive RTD (since actual load < forecast load)
2008-09-17 | 15 | EXCEPTIONAL DISPATCH | RTM | PASS | Reviewing | SCE did not receive any Exceptional Dispatches
2008-09-18 | 25J | DERATE NOB, SMUD, SYLMAR | DAM | PASS | RERUN | Rerun all versions of 25.
2008-09-19 | 10 | INSUFFICIENT SUPPLY IN IFM | DAM | PASS | PASS | Met expectations
2008-09-20 | 4 | DAILY ENERGY LIMITS | DAM | PASS | Reviewing | No SCE involvment
2008-09-20 | 5 | DAILY ENERGY LIMITS | RTM | PASS | Reviewing | ISO tested with just one unit (BALCHS_7_UNIT 1) - no SCE units were involved; however, Daily Energy limits are repeatedly violated in RTM (Issues 13698, 13796)
2008-09-22 | 2A & 2B | COND. QUALIFIED SELF PROVIDED A/S | DAM | PASS | Reviewing | Bay Area only - No SCE participation.
2008-09-23 | 25C | DERATE: PALOVERDE | DAM | Reviewing | RERUN | Rerun all versions of 25.
2008-09-24 | 29 | HIGH IMPACT LINE OUTAGE | DAM | PASS | Reviewing
2008-09-24 | 13 | CONTINGENCY DISPATCH | RTM | RERUN | RERUN | SCE did not receive any Contingency Dispatches - CAISO has released a patch that will impact this scenario and needs to test.
2008-09-24 | 14 | MANUAL DISPATCH | RTM | Reviewing | Reviewing | SCE did not receive any Manual Dispatches
2008-09-25 | 24A | INSUFFICIENT A/S PROCUREMENT IN DA IFM MARKET | DAM | Reviewing | Reviewing | No issues noted.
2008-09-25 | 45 | INTERACTION OF A/S ZONE CONSTRAINTS | DAM | Reviewing | Reviewing
2008-09-26 | 11 | INSUFFICIENT DEMAND IN IFM | DAM | Reviewing | Reviewing
2008-09-26 | 24B | CASCADING A/S PROCUREMENT | RTM | Reviewing | Reviewing | No issues noted.
2008-10-07 | 40 | SCIT TCOR | DAM | PASS | Reviewing
2008-10-29 | 29b | HIGH IMPACT LINE OUTAGE | RTM | Reviewing | Reviewing
2008-10-13 | 24a | INSUFFICIENT A/S PROCUREMENT IN DA IFM MARKET | DAM | Reviewing | Reviewing
2008-10-13 | 45 | INTERACTION OF A/S ZONE CONSTRAINTS | DAM | Reviewing | Reviewing
2008-10-16 | 7 | PSEUDO TIES | DAM | Reviewing | Reviewing | WAPA

## 18, 19
CAISO Exit Criteria Tracking - U2.18, U2.19
Number | Criteria | [8 empty] | Comments
U2.18 | HASP Market successfully solves and publishes within timing guidelines 95% of the time for 7 consecutive trading days during Update 2 Semi-Structured testing | [8 empty] | Even using the CAISO numbers this criteria has not been met. The primary difference between CAISO and SCE metrics is the measurement point: the CAISO does not monitor the publication of data to the external systems and SCE has nothing to look at but the external systems. This implies that there are persistent flaws in the publishing process.
U2.19 | Real-Time Market successfully solves and publishes within timing guidelines 95% of the time for 7 consecutive trading days during Update 2 Semi-Structured testing | [8 empty] | Barely accomplished using CAISO data (failed day before and day after 7 day period). When using SCE data this does not pass. The same comment above regarding publication applies here.
Qualifying Period |  |  | Criterion applies for the month prior to the end of IMS U2 (i.e. 7 days must occur within final month before exit). | [6 empty] | Reviewer |  |  |  | Josh Wood
|  | 24 |  | 96 |  | 288 |  |  | 408
Legend |  | Count | [7 empty] | Percentage
ISO < 95% |  | HASP |  | RTPD |  | RTD |  | TOTAL |  | HASP |  | RTPD |  | RTD |  | TOTAL
SCE < 95% |  | ISO | SCE | ISO | SCE | ISO | SCE | ISO | SCE | ISO | SCE | ISO | SCE | ISO | SCE | ISO | SCE
Mon | 2008-09-01
Tue | 2008-09-02 | 24 | 24 | 95 | 95 | 288 | 288 | 407 | 407 | 100% | 100% | 98.96% | 98.96% | 100% | 100% | 99.75% | 99.75%
Wed | 2008-09-03 | 23 | 23 | 95 | 95 | 216 | 214 | 334 | 332 | 95.83% | 95.83% | 98.96% | 98.96% | 75% | 74.31% | 81.86% | 81.37%
Thur | 2008-09-04 | 22 | 20 | 95 | 91 | 286 | 286 | 403 | 397 | 91.67% | 83.33% | 98.96% | 94.79% | 99.31% | 99.31% | 98.77% | 97.3%
Fri | 2008-09-05 | 22 | 19 | 85 | 81 | 233 | 232 | 340 | 332 | 91.67% | 79.17% | 88.54% | 84.38% | 80.9% | 80.56% | 83.33% | 81.37%
Sat | 2008-09-06
Sun | 2008-09-07
Mon | 2008-09-08 | 24 | 24 | 95 | 95 | 282 | 272 | 401 | 391 | 100% | 100% | 98.96% | 98.96% | 97.92% | 94.44% | 98.28% | 95.83%
Tue | 2008-09-09 | 23 | 23 | 84 | 84 | 274 | 245 | 381 | 352 | 95.83% | 95.83% | 87.5% | 87.5% | 95.14% | 85.07% | 93.38% | 86.27%
Wed | 2008-09-10 | 17 | 16 | 76 | 67 | 248 | 229 | 341 | 312 | 70.83% | 66.67% | 79.17% | 69.79% | 86.11% | 79.51% | 83.58% | 76.47%
Thur | 2008-09-11 | 23 | 23 | 94 | 94 | 287 | 262 | 404 | 379 | 95.83% | 95.83% | 97.92% | 97.92% | 99.65% | 90.97% | 99.02% | 92.89%
Fri | 2008-09-12 | 20 | 20 | 89 | 89 | 269 | 240 | 378 | 349 | 83.33% | 83.33% | 92.71% | 92.71% | 93.4% | 83.33% | 92.65% | 85.54%
Sat | 2008-09-13
Sun | 2008-09-14
Mon | 2008-09-15 | 24 | 15 | 96 | 96 | 288 | 269 | 408 | 380 | 100% | 62.5% | 100% | 100% | 100% | 93.4% | 100% | 93.14%
Tue | 2008-09-16 | 19 | 18 | 83 | 75 | 269 | 246 | 371 | 339 | 79.17% | 75% | 86.46% | 78.12% | 93.4% | 85.42% | 90.93% | 83.09%
Wed | 2008-09-17 | 23 | 23 | 90 | 87 | 287 | 262 | 400 | 372 | 95.83% | 95.83% | 93.75% | 90.62% | 99.65% | 90.97% | 98.04% | 91.18%
Thur | 2008-09-18 | 24 | 24 | 93 | 93 | 288 | 262 | 405 | 379 | 100% | 100% | 96.88% | 96.88% | 100% | 90.97% | 99.26% | 92.89%
Fri | 2008-09-19 | 23 | 23 | 87 | 84 | 288 | 275 | 398 | 382 | 95.83% | 95.83% | 90.62% | 87.5% | 100% | 95.49% | 97.55% | 93.63%
Sat | 2008-09-20
Sun | 2008-09-21
Mon | 2008-09-22 | 23 | 23 | 94 | 90 | 284 | 266 | 401 | 379 | 95.83% | 95.83% | 97.92% | 93.75% | 98.61% | 92.36% | 98.28% | 92.89%
Tue | 2008-09-23 | 21 | 21 | 91 | 90 | 283 | 221 | 395 | 332 | 87.5% | 87.5% | 94.79% | 93.75% | 98.26% | 76.74% | 96.81% | 81.37%
Wed | 2008-09-24 | 22 | 22 | 91 | 91 | 278 | 261 | 391 | 374 | 91.67% | 91.67% | 94.79% | 94.79% | 96.53% | 90.62% | 95.83% | 91.67%
Thur | 2008-09-25 | 23 | 20 | 92 | 92 | 276 | 276 | 391 | 388 | 95.83% | 83.33% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.1%
Fri | 2008-09-26 | 21 | 19 | 91 | 91 | 251 | 251 | 363 | 361 | 87.5% | 79.17% | 94.79% | 94.79% | 87.15% | 87.15% | 88.97% | 88.48%
Sat | 2008-09-27
Sun | 2008-09-28
Mon | 2008-09-29 | 24 | 24 | 96 | 96 | 287 | 285 | 407 | 405 | 100% | 100% | 100% | 100% | 99.65% | 98.96% | 99.75% | 99.26%
Tue | 2008-09-30 | 24 | 24 | 93 | 93 | 287 | 287 | 404 | 404 | 100% | 100% | 96.88% | 96.88% | 99.65% | 99.65% | 99.02% | 99.02%
Wed | 2008-10-01 | 24 | 24 | 89 | 89 | 287 | 286 | 400 | 399 | 100% | 100% | 92.71% | 92.71% | 99.65% | 99.31% | 98.04% | 97.79%
Thur | 2008-10-02 | 23 | 23 | 92 | 92 | 288 | 288 | 403 | 403 | 95.83% | 95.83% | 95.83% | 95.83% | 100% | 100% | 98.77% | 98.77%
Fri | 2008-10-03 | 22 | 22 | 90 | 82 | 260 | 252 | 372 | 356 | 91.67% | 91.67% | 93.75% | 85.42% | 90.28% | 87.5% | 91.18% | 87.25%
Sat | 2008-10-04
Sun | 2008-10-05
Mon | 2008-10-06 | 24 | 24 | 96 | 96 | 286 | 286 | 406 | 406 | 100% | 100% | 100% | 100% | 99.31% | 99.31% | 99.51% | 99.51%
Tue | 2008-10-07 | 24 | 23 | 93 | 92 | 283 | 274 | 400 | 389 | 100% | 95.83% | 96.88% | 95.83% | 98.26% | 95.14% | 98.04% | 95.34%
Wed | 2008-10-08 | 23 | 22 | 93 | 82 | 288 | 288 | 404 | 392 | 95.83% | 91.67% | 96.88% | 85.42% | 100% | 100% | 99.02% | 96.08%
Thur | 2008-10-09 | 21 | 21 | 86 | 67 | 282 | 252 | 389 | 340 | 87.5% | 87.5% | 89.58% | 69.79% | 97.92% | 87.5% | 95.34% | 83.33%
Fri | 2008-10-10 | 22 | 22 | 86 | 67 | 271 | 269 | 379 | 358 | 91.67% | 91.67% | 89.58% | 69.79% | 94.1% | 93.4% | 92.89% | 87.75%
Sat | 2008-10-11
Sun | 2008-10-12
Mon | 2008-10-13 | 22 | 22 | 91 | 91 | 280 | 280 | 393 | 393 | 91.67% | 91.67% | 94.79% | 94.79% | 97.22% | 97.22% | 96.32% | 96.32%
Tue | 2008-10-14 | 24 | 24 | 96 | 95 | 284 | 281 | 404 | 400 | 100% | 100% | 100% | 98.96% | 98.61% | 97.57% | 99.02% | 98.04%
Wed | 2008-10-15 | 23 | 22 | 95 | 91 | 277 | 276 | 395 | 389 | 95.83% | 91.67% | 98.96% | 94.79% | 96.18% | 95.83% | 96.81% | 95.34%
Thur | 2008-10-16 | 21 | 21 | 85 | 74 | 272 | 271 | 378 | 366 | 87.5% | 87.5% | 88.54% | 77.08% | 94.44% | 94.1% | 92.65% | 89.71%
Fri | 2008-10-17 | 23 | 22 | 94 | 90 | 283 | 280 | 400 | 392 | 95.83% | 91.67% | 97.92% | 93.75% | 98.26% | 97.22% | 98.04% | 96.08%
Formulas:
Criteria = [Criteria, row above]+1

## C1 (Stability)
PG&E metric to determine if CAISO systems performance and stability are proven reasonable
Week Begin | Overall System Instability | PG&E Submitted Issues (High, Very High, and Critical Priority) |  |  | CAISO DA Market Results Published by 1PM | CAISO Published Real Time Execution | Open PG&E High and above issues score | Open PG&E High and above issues | % Variance from Prior Week (Total Open Issues) | Open CAISO High and above issues score | Total Open High and Above Issues | % Variance from Prior Week (Total Open Issues) | Completeness of Functionality
|  | SIBR | OASIS/SLIC/ADS | CMRI/IFM
2008-08-18 | 2.0367 | 0 | 0 | 2 | 75% | 94% | 0.5 | 104 | 8.33% | 0 | 289 | -26.9% | 0.5
2008-08-25 | 1.8061 | 1 | 0 | 0 | 60% | 83.86% | 0 | 77 | -25.96% | 0.25 | 284 | -1.73% | 0.5
2008-09-01 | 2.0325 | 1 | 0 | 0 | 50% | 90.04% | 0.25 | 70 | -9.091% | 0.25 | 282 | -0.7042% | 0.5
2008-09-08 | 3.7153 | 4 | 1 | 2 | 50% | 93.4% | 0 | 46 | -34.29% | 0.25 | 253 | -10.28% | 0.5
2008-09-15 | 2.9113 | 2 | 0 | 2 | 75% | 96.1% | 0.5 | 55 | 19.57% | 0.25 | 251 | -0.7905% | 0.5
2008-09-22 | 1.8093 | 1 | 0 | 0 | 40% | 93.7% | 0 | 39 | -29.09% | 0.25 | 244 | -2.789% | 0.5
2008-09-29 | 2.4542 | 2 | 0 | 1 | 60% | 97.29% | 0.25 | 37 | -5.128% | 0.25 | 210 | -13.93% | 0.5
2008-10-06 | 4.8645 | 2 | 1 | 5 | 40% | 95.11% | 0.5 | 41 | 10.81% | 0.5 | 213 | 1.429% | 0.5
2008-10-13 | 2.928 | 2 | 0 | 1 | 40% | 96.1% | 0.25 | 37 | -9.756% | 0.5 | 223 | 4.695% | 0.5
Target | 0 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0% | 0 | 0 | 0% | 0
| Key | Measure of Overall Instability is Sum of:
| 0-2 | Average of number of SIBR, OASIS/ADS/SLIC, and CMRI/IFM issues found by PG&E
| 2-5 | Percentage of DAM results not published on time
| >5 | Percentage of RTM results not published succesfully (multiplied by 2 - heavier weight is given to CAISO metrics)
Score measuring resolution progressof open high and above market-wide issues
Score measuring resolution progress of open high and above PG&E issues
Score measuring completeness of functionality
Contributing Factors | [8 empty] | Incomplete Functionality
SIBR | Submitting bids and schedules into market (green 0, amber 1-5, red > 5) | [7 empty] | SIBR - ETC/TOR contract level validation information reports not available
CMRI / IFM | IFM and RTM results (green 0, amber 1-5, red > 5) | [7 empty] | Extra Long Start process needs to be validated
OASIS, SLIC, ADS | Public market results, outage scheduling, generator dispatches (green 0, amber 1-5, red > 5) | [7 empty] | SIBR - Rule additions / changes needed, e.g. SIBR rule allowing intertie self schedule to satisfy RA obligation
DAM Published by 1PM | % days published on time out of 5 business days (green 100%, amber 75-100%, red <75%) | [7 empty] | CMRI - Reports noted as "Semi-Operational" on page 58 of the Market Simulation Funcationality List Version 2.2 (last updated 9/23/2008)
Real Time Execution | Average of MPM/HASP, RTPD, RTD % pass rates | [7 empty] | OASIS - Reports noted as "Semi-Operational" on page 62 of the Market Simulation Funcationality List Version 2.2
Open PG&E High and above issues | Red: if issue count increased from prior week, amber is decrease between 0 and 25%, green if decrease is more than 25% (reasoning is that at a rate of 25% decrease most issues should be resolved by end of October) If the Issue count = 0 then score = 0. | [7 empty] | Resource ID issue - proposed solution implemented in Market Simulation
Complete functionality | Red - No (score=.5) Green - Yes (score=0). Factor will be set to Green when we are confident that all functionality is enabled and working. | [7 empty] | CAS - currently can see tags in market results for DA only.
Note on F6: On 8/25, market closed on time but critical reports were not available.