## PGaE
Project | PTO | Transmission Plan Approved | In-service Year at Approval in Transmission Plan | Expected In-Service Year (2020-2021 Transmission Plan) | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service Jul 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Filing | Expected Const start | Notes
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015-12-01 | 2022-11-01 | 2022-11-01 | 2023-03-15 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 Approved | 2022-09-22 | In-Service
Dinuba Energy Storage (Rescoped from Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017-05-01 | 2025-12-01 | 2025-12-25 | 2025-08-14 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2026-09-29 | 2026-09-29 | N/A | N/A | Cancelled | N/A | N/A | Cancelled per CAISO 2023-24 Transmission Plan.
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015-03-01 | 2022-12-01 | 2022-12-23 | 2023-03-10 | 2023-05-31 | 2023-05-31 | 2023-12-29 | 2023-12-29 | 2023-12-29 | 2023-12-29 | 2024-03-18 | 2023-10-31 | 2023-10-31 | In-Service | NOC: AL 5872-E/AL 6709-E Approved | 2021-06-01 | In-Service
Equipment Upgrade at CCSF Owned Warnerville 230 kV Substation | PG&E | 2022-2023 | 2024-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-04-28 | In-Service | N/A | 2023-02-16 | In-Service
Giffen Line Reconductoring Project | PG&E | 2018-2019 | TBD | 2023-01-19 | 2023-01-13 | 2023-01-19 | 2023-01-11 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2023-12-29 | 2023-12-29 | 2023-12-21 | 2023-12-21 | 2023-12-21 | In-Service | NOC: AL 6600-E Approved | 2023-11-01 | In-Service
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018-03-01 | 2022-12-01 | 2022-12-21 | 2022-12-12 | 2022-10-19 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-16 | 2024-05-30 | 2024-05-30 | 2024-03-28 | 2024-03-28 | In-Service | N/A | 2020-04-30 | In-Service
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023-12-31 | 2027-06-01 | 2027-06-28 | 2025-11-12 | 2026-04-09 | 2026-08-07 | 2026-10-02 | 2023-11-22 | 2023-12-19 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | In-Service | N/A | 2023-09-21 | In-Service
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024-12-31 | 2027-06-01 | 2027-06-28 | 2026-01-14 | 2026-06-19 | 2026-10-19 | 2025-01-15 | 2025-01-31 | 2025-02-20 | 2025-01-06 | 2025-06-20 | 2025-06-20 | 2024-12-23 | In-Service | NOC: AL 7359-E Approved | 2024-12-09 | Q1-2025: In-Service. Project ISD improved due to schedule/construction adjustments and available funding to proceed in 2024 Q4.
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013-05-01 | 2025-05-01 | N/A | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | In-Service | N/A | 2018-10-16 | In-Service
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019-12-01 | On Hold | N/A | 2029-12-04 | 2029-12-04 | 2029-12-04 | 2029-08-28 | 2032-10-21 | 2032-10-21 | 2029-12-04 | N/A | N/A | N/A | Cancelled | N/A | N/A | Cancelled per CAISO 2022-23 Transmission Plan.
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 | TBD | 2023-03-01 | N/A | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | In-Service | N/A | 2021-08-03 | In-Service
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023-12-31 | 2022-07-01 | 2022-07-06 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | In-Service | N/A | 2021-07-01 | In-Service
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021-05-01 | 2023-03-01 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2022-12-30 | 2024-05-31 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-04-19 | 2024-04-09 | 2024-04-09 | In-Service | NOC: AL 5390-E Approved | 2022-01-17 | In-Service
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019-02-01 | 2023-01-01 | 2023-01-13 | 2023-01-16 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 Approved | 2022-09-22 | In-Service
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-12-01 | 2027-12-01 | TBD | N/A | Cancelled | N/A | N/A | Rescoped in 2023-24 CAISO Transmission Plan to Salinas Area Reinforcement
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS C - D | PG&E | 2018-2019 | 2023-12-31 | 2023-08-01 | 2023-10-31 | 2023-10-27 | 2023-09-28 | 2023-11-29 | 2023-12-19 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-04-18 | 2024-03-25 | 2024-03-25 | In-Service | N/A | 2023-06-15 | In-Service
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E | 2018-2019 | 2023-12-31 | 2023-08-01 | 2023-10-31 | 2023-04-05 | 2023-03-28 | 2023-05-01 | 2023-06-13 | 2023-07-27 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | In-Service | N/A | 2022-04-19 | In-Service
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | N/A | N/A | N/A | N/A | In-Service | N/A | N/A | Q1-2025: Tulucay-Napa #2 60 kV Line Capacity Increase project approved in 2020: this project would upgrade line terminals in Tulucay and Basalt subs. PG&E discovered that with records update, it was found the substation equipment already met ampacity requirement. So this project is no longer needed.
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023-12-01 | 2026-07-01 | 2022-08-31 | 2022-07-29 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | In-Service | N/A | 2021-07-26 | In-Service
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017-12-31 | 2024-12-01 | 2024-12-27 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-05-31 | 2024-04-30 | 2024-03-31 | 2024-03-31 | In-Service | NOC: AL 6047-E Approved | 2022-06-01 | In-Service
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020-12-31 | 2022-03-01 | 2022-03-01 | 2022-12-14 | 2022-12-14 | 2024-02-23 | 2023-12-19 | 2023-11-27 | 2023-11-28 | 2023-12-22 | 2023-12-18 | 2023-12-18 | 2023-12-18 | In-Service | NOC: AL 5293-E Approved | 2021-01-05 | In-Service
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026-01-01 | 2026-12-31 | N/A | 2026-01-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-12-01 | 2027-12-01 | 2029-11-15 | 2027-04-23 | In-Flight | TBD | 2026-11-20 | Q1-2025: Project ISD improved due to schedule/construction sequencing date adjustments.
Atlantic High Voltage Mitigation | PG&E | 2023-2024 | 2029-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-04-23 | In-Flight | TBD | 2026-11-20 | Q1-2025: New addition
Banta 60 kV Bus Voltage Conversion | PG&E | 2022-2023 | 2024-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2028-03-30 | 2027-12-10 | In-Flight | TBD | 2024-10-28 | Q1-2025: Project ISD improved due to schedule/construction sequencing date adjustments.
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025-07-17 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2026-04-01 | 2026-04-01 | 2028-04-13 | 2028-05-30 | In-Flight | TBD | 2026-11-20 | Q1-2025: Schedule/construction sequencing date adjustments.
Borden-Storey 230 kV 1 and 2 Line Reconductoring | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2029-05-01 | 2029-05-01 | 2030-05-01 | 2030-04-12 | Initiating | TBD | 2028-11-06 | Q1-2025: Schedule/construction sequencing date adjustments.
Camden 70 kV Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014-03-01 | 2023-12-01 | 2023-12-29 | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2025-07-11 | 2025-07-11 | 2025-06-13 | 2025-12-15 | In-Flight | N/A | 2019-07-09 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-02-01 | 2028-02-01 | 2028-02-01 | Initiating | NOC - TBD on Filing Date | 2027-01-01 | Q1-2025: No date changes at this time
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012-03-01 | 2027-02-01 | 2027-02-01 | 2027-02-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-07-01 | 2029-07-01 | 2029-07-01 | 2030-10-07 | Initiating | PTC - TBD on Filing Date | 2030-09-10 | Q1-2025: Project ISD delayed due to adjusting project schedule as a result of project kickoff & PM assignment.
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022-05-01 | 2029-06-01 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2030-09-06 | In Flight | TBD | 2028-09-28 | Q1-2025: Project ISD delayed due to delay in initiating the project and project development
Collinsville 230 kV Reactor | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-05-01 | Initiating | TBD | 2033-05-01 | Q1-2025: New addition
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025-05-01 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-27 | 2025-09-15 | In-Flight | N/A | 2024-12-06 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026-01-01 | 2026-12-31 | N/A | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-18 | 2025-04-22 | In-Flight | TBD | 2025-03-24 | Q1-2025: Project ISD improved due to improved material availability and scope reduction (not needed)
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-13 | Initiating | TBD | 2027-05-04 | Q1-2025: Project ISD delayed due to adjusting project schedule as a result of project kickoff & PM assignment.
Cortina #1 60 kV Line Reconductoring | PG&E | 2023-2024 | 2028-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | In-Flight | TBD | 2026-08-27 | Q1-2025: New addition
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-01 | 2028-06-01 | 2027-09-21 | In-Flight | TBD | 2027-04-01 | Q1-2025: Project ISD improved due to schedule/construction sequencing date adjustments
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022-12-31 | 2025-10-01 | 2025-10-02 | 2025-03-31 | 2024-12-24 | 2026-02-26 | 2026-02-26 | 2026-03-25 | 2025-11-12 | 2026-10-05 | 2026-06-19 | 2027-01-25 | 2028-02-24 | In-Flight | N/A | 2026-12-30 | Q1-2025: Project ISD delayed due to long lead materials and schedule/construction sequencing date adjustments
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019-11-01 | 2024-10-01 | 2024-10-02 | 2025-03-31 | 2025-02-14 | 2025-05-15 | 2025-08-11 | 2025-07-18 | 2025-11-19 | 2026-10-20 | 2026-10-20 | 2027-12-31 | 2028-10-20 | In-Flight | N/A | 2027-01-04 | Q1-2025: Bank 1 replaced under separate emergency replacement project on 8/2/24. Bank 4 still to be replaced on this project. Project ISD delayed due to long lead materials and schedule/construction sequencing date adjustments
Covelo 60 kV Voltage Support | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Crazy Horse Canyon - Salinas - Soledad #1 and #2 115 kV Line Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Diablo Canyon Area 230 kV High Voltage Mitigation | PG&E | 2023-2024 | 2027-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-07-25 | In-Flight | TBD | 2028-04-11 | Q1-2025: New addition
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022-12-31 | 2027-10-01 | 2027-11-10 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2033-02-02 | Initiating | TBD | 2027-06-17 | Q1-2025: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024-12-31 | 2026-12-01 | 2026-12-31 | 2026-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2027-06-30 | 2027-05-06 | In-Flight | TBD | 2027-01-08 | Q1-2025: Schedule/construction sequencing date adjustments.
Estrella Substation Project | PG&E | 2013-2014 | 2019-05-01 | 2026-05-01 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | 2029-07-16 | 2029-11-01 | 2029-07-05 | 2029-07-03 | 2029-03-30 | In flight | PTC: A.17-01-023 Approved | 2025-03-03 | Q1-2025: Project ISD improved due to schedule/construction sequencing date adjustments
French Camp Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Garberville Area Reinforcement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2030-12-31 | 2030-12-31 | 2029-11-21 | 2027-12-28 | In-Flight | NOC - Expected 2025 Q2 | 2027-04-02 | Q1-2025: Project ISD improved due to project development. By moving through the design ahead of schedule, PG&E has determined the project will require NOC. Removing the PTC from the schedule saved significant time.
Gates 230/70 kV Transformer Addition | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025-07-16 | 2025-03-01 | 2025-03-28 | 2024-06-03 | 2024-04-30 | 2024-04-30 | 2024-07-12 | 2024-08-30 | 2024-12-04 | 2024-09-30 | 2025-01-01 | 2025-01-25 | 2025-03-25 | In-Flight | N/A | 2023-04-03 | Q1-2025: Schedule/construction sequencing date adjustments.
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022-12-31 | 2028-06-01 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2030-04-12 | 2029-06-22 | In-Flight | TBD | 2027-08-16 | Q1-2025: Project ISD improved due to improved material delivery date
Henrietta 230/115 kV Bank 3 Replacement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2027-06-01 | 2027-06-01 | 2028-07-21 | 2028-07-12 | In-Flight | TBD | 2026-07-08 | Q1-2025: Schedule/construction sequencing date adjustments.
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021-01-01 | 2026-12-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-12-31 | In-Flight | NOC - TBD on Filing Date | 2026-07-01 | Q1-2025: Project ISD delayed due to adjusting project schedule as a result of project coming out of deferral & PM assignment.
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-06-26 | 2028-02-10 | In-Flight | NOC - TBD on Filing Date | 2027-07-20 | Q1-2025: Project ISD improved due to prior PM scheduling incorrectly in P6. The in-service date was pushed out passed the Required In-Service Date in the AA at project kick-off. When new PM took the project over, the ISD was brought in to meet the requirements of the AA. Due to the project being roughly a year behind schedule, there may be a request to push back out pending engineering timelines.
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022-12-31 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-10-12 | 2026-11-06 | In-Flight | N/A | 2026-05-06 | Q1-2025: Schedule/construction sequencing date adjustments.
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016-03-01 | 2027-08-01 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2029-08-10 | 2029-08-10 | 2030-12-31 | 2029-08-10 | In flight | NOC - TBD on Filing Date | 2027-01-08 | Q1-2025: Project ISD improved due to ISD recalibration in PG&E's work portfolio.
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-10-01 | Q1-2025: No date changes at this time
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017-03-01 | 2027-06-01 | 2027-06-21 | 2028-12-29 | 2029-01-01 | 2029-01-01 | 2029-01-01 | 2029-01-11 | 2029-01-11 | 2029-06-08 | 2029-12-25 | 2029-12-10 | 2029-12-10 | In-Flight | CPCN: A.23-09-001 Filed & Under Review | 2028-06-28 | Q1-2025: No date changes at this time
Lone Tree–Cayetano–Newark Corridor Series Compensation | PG&E | 2022-2023 | 2027-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-02 | Initiating | TBD | 2027-07-19 | Q1-2025: No date changes at this time
Los Banos 230 kV Circuit Breakers Replacement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Initiating | TBD | 2026-07-01 | Q1-2025: No date changes at this time
Los Banos 70 kV Area Reinforcement | PG&E | 2022-2023 | 2029-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2030-09-12 | Initiating | TBD | 2027-07-08 | Q1-2025: Project ISD delayed due to dependency with Dos Amigos Pumping Plant - Panoche 230 kV New Switching Station (NU). This project has no procured land or ordered 230 kV breakers yet.
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028-05-01 | 2028-12-31 | N/A | 2028-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-05-31 | 2029-02-02 | 2029-10-09 | 2029-10-09 | In-Flight | TBD | 2028-04-21 | Q1-2025: No date changes at this time
Maple Creek Reactive Support | PG&E | 2009 | 2011-03-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-10-01 | 2027-10-01 | 2027-10-01 | Initiating | TBD | 2026-01-01 | Q1-2025: No date changes at this time
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021-12-01 | 2024-05-01 | 2024-05-24 | 2024-05-10 | 2024-05-24 | 2025-11-14 | 2025-11-13 | 2025-11-13 | 2026-04-23 | 2027-02-12 | 2028-10-13 | 2029-12-18 | 2029-10-17 | In-Flight | CPCN: A.17-12-021 Approved | 2027-05-14 | Q1-2025: Schedule/construction sequencing date adjustments.
Martin-Millbrae 60 kV Area Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Mesa 230/115kV Spare Transformer | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-05-01 | 2028-04-01 | 2028-04-01 | 2029-04-01 | 2029-03-14 | In-Flight | TBD | 2027-06-18 | Q1-2025: Schedule/construction sequencing date adjustments.
Metcalf 230 / 115 kV Transformers Circuit Breaker Addition | PG&E | 2022-2023 | 2026-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2027-06-01 | 2027-06-01 | 2026-09-01 | 2027-06-23 | In-Flight | TBD | 2026-12-16 | Q1-2025: Project ISD delayed due to long-lead materials delay
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008-12-31 | 2029-04-01 | 2029-04-01 | 2029-04-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-03-01 | 2027-03-01 | 2028-05-12 | Initiating | NOC - TBD on Filing Date | 2027-10-12 | Q1-2025: Project ISD delayed due to changes in project scope, awaiting Transmission System planning and CAISO approval on updated scope.
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019-05-01 | 2024-06-01 | 2024-06-06 | 2025-07-03 | 2026-06-23 | 2026-06-23 | 2027-04-07 | 2027-04-07 | 2027-04-07 | 2027-04-29 | 2027-04-29 | 2028-12-31 | 2028-06-14 | In flight | NOC: AL 5026-E Approved | 2018-11-01 | Q1-2025: Project ISD improved due to ISD recalibration in PG&E's work portfolio.
Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019-05-01 | 2024-06-01 | 2024-06-06 | 2027-06-03 | 2027-09-01 | 2027-11-30 | 2028-02-25 | 2028-05-23 | 2028-08-21 | 2027-10-28 | 2028-01-24 | 2030-05-28 | 2030-05-28 | In flight | NOC: AL 5924-E Approved | 2026-04-27 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-08-29 | 2025-08-29 | 2027-10-08 | 2030-08-22 | 2030-08-22 | In-Flight | N/A | 2021-04-07 | Q1-2025: No date changes at this time
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018-05-01 | 2027-10-01 | 2027-10-20 | 2028-02-16 | 2028-05-16 | 2028-08-14 | 2028-11-09 | 2029-02-05 | 2029-04-06 | 2029-08-01 | 2029-10-26 | 2030-07-16 | 2029-02-15 | In flight | NOC - TBD on Filing Date | 2027-12-07 | Q1-2025: Project ISD improved due to ISD recalibration in PG&E's work portfolio.
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016-05-01 | 2024-08-01 | 2024-08-06 | 2024-07-17 | 2024-05-08 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-01 | 2025-08-07 | 2025-08-07 | 2025-09-23 | 2026-03-06 | In-Flight | N/A | 2021-08-17 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-01-01 | Q1-2025: No date changes at this time
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013-05-01 | 2025-12-01 | 2023-09-22 | 2023-11-06 | 2024-03-07 | 2024-03-20 | 2024-06-20 | 2024-10-25 | 2024-10-16 | 2026-03-25 | 2026-03-25 | 2024-11-24 | 2025-05-05 | In-Flight | N/A | 2024-08-21 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023-12-31 | On Hold | N/A | N/A | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | On-Hold (CAISO) | TBD | TBD | Q1-2025: Project on CAISO Hold.
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021-12-01 | 2026-04-01 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2027-09-29 | 2027-09-29 | 2027-09-29 | 2029-01-30 | 2029-02-27 | 2028-12-28 | 2029-01-22 | In-Flight | NOC: AL 5200-E Approved | 2027-03-31 | Q1-2025: Schedule/construction sequencing date adjustments.
Mosher Transmission Project | PG&E | 2013-2014 | 2017-12-01 | 2027-12-01 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2028-02-17 | In Flight | NOC - TBD on Filing Date | 2027-03-11 | Q1-2025: Schedule/construction sequencing date adjustments.
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026-01-01 | 2026-12-31 | N/A | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2028-04-01 | 2028-04-01 | 2028-09-01 | 2028-09-01 | Initiating | TBD | 2026-10-01 | Q1-2025: No date changes at this time
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2028-05-01 | In-Flight | TBD | 2027-06-09 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments.
New Humboldt 115/115 kV Phase Shifter with 115 kV line to Humboldt 115kV Substation | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2025: New addition
New Humboldt 500 kV Substation with 500 kV line to Collinsville [HVDC operated as AC] | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2025: New addition
New Humboldt to Fern Road 500 kV Line | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2025: New addition
New Manning 500 kV substation | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-01 | 2028-04-01 | In-Flight | TBD | 2026-04-29 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments.
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2029-02-20 | Initiating | TBD | 2028-07-28 | Q1-2025: Project ISD delayed due to long lead material delivery and delay in initiating project
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019-06-01 | 2022-11-01 | 2022-11-01 | 2023-04-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-06-01 | 2025-06-01 | 2025-07-01 | 2027-05-06 | In-Flight | TBD | 2026-09-16 | Q1-2025: Project ISD delayed due to scope addition at Milpitas sub
North Dublin -Vineyard 230 kV Reconductoring | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2025: New addition
North East Kern 115 kV Line Reconductoring | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2033-12-31 | 2033-12-31 | 2032-12-31 | 2029-08-20 | Initiating | TBD | 2029-05-24 | Q1-2025: Project ISD improved due to ISD recalibration in PG&E's work portfolio. Project has not kicked off yet.
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015-05-01 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2028-02-01 | 2028-02-01 | 2029-02-01 | 2029-02-01 | Initiating | TBD | 2028-01-01 | Q1-2025: No date changes at this time
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 | TBD | 2023-03-01 | 2023-03-04 | 2023-05-19 | 2023-07-18 | 2023-11-21 | 2023-10-30 | 2025-04-01 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-07-29 | 2025-06-24 | In-Flight | N/A | 2021-11-16 | Q1-2025: Schedule/construction sequencing date adjustments.
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2026-12-01 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2028-08-28 | In-Flight | NOC - TBD on Filing Date | 2027-09-15 | Q1-2025: Project ISD delayed due to adjusting project schedule as a result of project being re-kicked off
Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-28 | 2028-06-01 | 2028-04-28 | 2028-03-31 | In-Flight | TBD | 2026-04-20 | Q1-2025: Schedule/construction sequencing date adjustments.
Pittsburg 115 kV Bus Reactor project | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2028-05-12 | 2028-05-12 | 2028-05-12 | 2028-05-30 | In-Flight | TBD | 2027-10-07 | Q1-2025: Schedule/construction sequencing date adjustments.
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011-05-01 | 2025-01-01 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2026-06-17 | 2026-06-17 | 2026-09-04 | 2026-06-15 | 2028-05-09 | 2028-09-27 | In-Flight | N/A | 2028-03-24 | Q1-2025: Project ISD delayed due to long lead materials and schedule/construction sequencing date adjustments
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019-12-31 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-06-01 | 2025-06-01 | 2026-12-22 | 2028-06-13 | Initiating | TBD | 2027-12-08 | Q1-2025: Project is no longer needed and will be canceled.
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-02-02 | 2028-08-16 | 2028-02-01 | In-Flight | TBD | 2027-08-13 | Q1-2025: Project ISD improved due to matching available clearances. This line generally is limited to wintertime clearances due to summer loading. Therefore, line construction start will be winter 2027 and hopefully wrapped up Q1 2028. If we do not meet these dates, then we will most likely have to delay construction start to Q3/Q4 2028 which will require an in-service date extension.
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2030-04-11 | Q1-2025: No date changes at this time
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2025-11-01 | 2025-11-19 | 2026-08-18 | 2026-08-18 | 2030-05-23 | 2031-11-19 | 2029-03-30 | 2028-11-07 | 2028-05-23 | 2029-03-06 | 2029-08-27 | 2029-03-28 | In-Flight | NOC - TBD on Filing Date | 2026-07-22 | Q1-2025: Project ISD improved due to Schedule/construction sequencing date adjustments.
Redwood City 115kV System Reinforcement | PG&E | 2022-2023 | 2030-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-12-01 | 2029-12-01 | 2029-12-01 | 2028-07-05 | 2030-03-14 | Initiating | TBD | 2027-03-10 | Q1-2025: Project ISD delayed due to RFP process & creation and execution of engineering contract, internal land delays to obtain L3 LiDAR data required for all three circuits.
Reedley 70 kV Capacity Increase | PG&E | 2023-2024 | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Rio Oso - W. Sacramento Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009-05-01 | 2024-04-01 | 2024-04-30 | 2024-06-30 | 2024-04-30 | 2025-04-17 | 2025-12-31 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2026-04-06 | 2025-05-21 | 2025-05-21 | In-Flight | N/A | 2022-07-05 | Q1-2025: No date changes at this time. Bank 1 replaced under separate emergency replacement project on 12/4/24. Bank 3 still to be replaced on this project.
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016-05-01 | 2024-10-01 | 2024-10-11 | 2024-10-31 | 2024-08-26 | 2024-12-09 | 2025-05-30 | 2025-06-04 | 2025-06-04 | 2025-06-19 | 2025-09-01 | 2026-05-14 | 2026-05-14 | In-Flight | N/A | 2025-09-18 | Q1-2025: No date changes at this time
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024-12-31 | 2024-05-01 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | 2024-11-21 | 2024-12-31 | 2024-12-31 | TBD | TBD | In-Flight | N/A | 2023-02-15 | Q1-2025: Schedule/construction sequencing date adjustments.
Salinas Area Reinforcement | PG&E | 2023-2024 | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | Initiating | TBD | 2029-12-01 | Q1-2025: New addition
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-11-30 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | In-Flight | 851 - TBD on Filing Date | 2025-10-17 | Q1-2025: No date changes at this time
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-04-30 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | In-Flight | NOC: AL 7391-E Filed & Under Review | 2025-05-05 | Q1-2025: No date changes at this time
Santa Rosa 115 kV lines Reconductoring project | PG&E | 2022-2023 | 2028-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-10-31 | 2029-10-31 | Initiating | TBD | 2031-09-23 | Q1-2025: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023-06-01 | 2023-12-31 | N/A | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-12-23 | 2025-12-23 | 2026-03-03 | 2025-12-30 | In-Flight | TBD | 2025-06-13 | Q1-2025: Schedule/construction sequencing date adjustments.
Sobrante 230/115 kV Transformer Bank Addition | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2025: New addition
South Bay Area Limiting Element Upgrade | PG&E | 2022-2023 | 2027-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2026-03-01 | 2026-03-01 | 2025-05-01 | 2026-04-10 | In-Flight | TBD | 2024-06-01 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments.
South of Mesa Upgrade | PG&E | 2018-2019 | 2023-12-31 | 2026-09-01 | 2026-09-03 | 2026-05-26 | 2026-05-26 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-15 | 2027-04-15 | 2031-03-10 | 2029-06-06 | In flight | NOC - TBD on Filing Date | 2027-11-15 | Q1-2025: Project ISD improved due to ISD recalibration in PG&E's work portfolio.
South of San Mateo Capacity Increase | PG&E | 2007 | 2009-05-01 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2028-12-01 | 2028-12-01 | 2027-10-29 | 2028-06-22 | In-Flight | NOC - TBD on Filing Date | 2027-09-03 | Q1-2025: Project ISD delayed due to RFP process & creation and execution of engineering contract, internal land delays to obtain L3 LiDAR data required for all three circuits
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027-01-01 | 2027-12-31 | N/A | 2027-01-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-06-01 | 2028-06-01 | 2026-09-28 | 2027-10-13 | In-Flight | TBD | 2026-05-19 | Q1-2025: Project ISD delayed due to long-lead materials delay
Tejon Area Reinforcement | PG&E | 2023-2024 | 2027-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-08-01 | Initiating | TBD | 2026-08-01 | Q1-2025: New addition
Tesla - Newark 230 kV Line No. 2 Reconductoring | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2025: New addition
Tesla 115 kV Bus Reconfiguration | PG&E | 2022-2023 | 2030-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-12-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | Initiating | TBD | 2026-07-01 | Q1-2025: No date changes at this time
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-16 | 2027-08-16 | 2028-02-09 | 2028-02-09 | 2028-12-28 | 2026-07-08 | In-Flight | N/A | 2024-05-13 | Q1-2025: Project ISD improved due to scope reduction (site cancellations)
Tulucay-Napa #2 60 kV line Reconductoring project | PG&E | 2022-2023 | 2028-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-12-01 | 2026-12-31 | 2026-12-31 | 2026-12-01 | 2027-07-23 | In-Flight | TBD | 2027-06-15 | Q1-2025: Project ISD delayed due to input error by PM. The schedule and ISD will be revised as soon as the Transmission Planning have made a definitive decision on Re-rate vs. Reconductor. Once that decision is made, there is a possibility there will be no “delay” to the ISD at all.
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-03-01 | 2027-03-01 | 2027-09-20 | 2027-09-30 | In-Flight | TBD | 2027-04-06 | Q1-2025: No date changes at this time
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023-12-01 | 2026-07-01 | 2026-07-10 | 2026-08-21 | 2025-08-18 | 2025-12-25 | 2025-12-30 | 2026-02-06 | 2026-02-06 | 2026-04-29 | 2027-04-12 | 2027-04-30 | 2027-04-30 | In-Flight | PTC: A.24-06-008 Filed & Under Review (Plainfield) NOC - Expected 2025 Q1 (Woodland-Davis) | 2025-10-02 | Q1-2025: No date changes at this time
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019-10-01 | 2027-04-01 | 2027-04-01 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-05-08 | 2025-10-20 | 2025-10-20 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-11-18 | In Flight | N/A | 2026-04-22 | Q1-2025: Project ISD delayed due to scope development
Vaca-Plainfield 60 kV Line Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2025: New addition
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025-05-01 | 2025-12-31 | N/A | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2026-08-31 | 2026-07-27 | In flight | TBD | 2026-04-27 | Q1-2025: Schedule/construction sequencing date adjustments.
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014-05-01 | 2025-06-01 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | 2026-05-29 | 2026-07-31 | 2027-05-06 | 2027-04-23 | 2027-05-10 | In-Flight | PTC: A.18-06-004 Approved | 2024-05-21 | Q1-2025: Triggered by Generation Agreements. Schedule/construction sequencing date adjustments.
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-05-31 | 2029-02-02 | 2027-12-06 | 2027-04-12 | In-Flight | NOC - Expected 2025 Q1 | 2026-12-03 | Q1-2025: Project ISD improved due to schedule/construction sequencing date adjustments
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020-05-01 | On Hold | N/A | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | 2034-03-28 | 2029-05-04 | 2033-12-31 | 2032-12-01 | 2033-07-11 | In-Flight | PTC - Expected 2025 Q3 | 2027-12-31 | Q1-2025: Project ISD delayed due to schedule/construction sequencing date adjustments. In addition, working with key stakeholders in project scope confirmation.
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2026-09-01 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2029-08-16 | In Flight | N/A | 2026-10-12 | Q1-2025: Project ISD delayed due to adjusting project schedule as a result of project being re-kicked off
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026-12-31 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | Initiating | NOC - TBD on Filing Date | 2026-10-01 | Q1-2025: No date changes at this time

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-10-01 | 2029-12-01 | Licensing | 2009-09-01 | 2026-06-01 | Alberhill dates contingent on licensing
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 | N/A | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | Construction | Exempt | 2024-10-01 | Material delay caused shift in construction start
Antelope-Whirlwind Line Upgrade | SCE | 2022-2023 | 2025 | N/A | New | New | New | New | New | New | Pending | Pending | 2025-12-31 | 2025-12-01 | 2025-12-01 | Preliminary Engineering | Pending | 2025-10-01 | Project approved by CAISO in May 2023
Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | Pending | 2026-06-01 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-06-01 | 2026-06-01 | Final Design | Exempt | 2025-01-01 | No change in the expected ISD between October 2023 TDF and January 2024 TDF
Colorado River-Red Bluff 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-02-01 | 2027-12-01 | Initiation | Pending | 2025-10-01 | Resource availability and outage sequencing.
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2027-06-01 | 2027-06-01 | Final Engineering | Exempt | 2024-06-01 | Project sequencing and increase in scope has pushed the initial ISD out two years to 2027.
Devers-Red Bluff 500 kV 1 and 2 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 1930-03-01 | 1930-01-01 | Initiation | Pending | 2027-10-01 | Resource availability, outage sequencing and material availability.
Devers-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-04-01 | 2027-12-01 | Initiation | Pending | 2026-10-01 | Resource availability, outage sequencing and material availability.
Inyo 230 kV Shunt Reactor | SCE | 2023-2024 | 2027 | N/A | New | New | New | New | New | New | Pending | N/A | N/A | 2027-12-31 | 2026-12-01 | Engineering Design | Pending | 2026-06-01 | Project is expected to be completed in December 2026 because the estimated delivery date of the circuit breaker is mid-2026
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | N/A | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | 2024-05-31 | 2024-05-01 | 2024-06-01 | 2024-06-01 | 2025-06-01 | 2025-05-15 | Construction | Exempt | Construction started | Project is on track and expected to finish on time
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2012-2013 | 2016 | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2024-12-01 | 2025-05-01 | Construction | 2018-05-01 | 2020-12-01 | Unable to achieve the required capacitor balancing during testing and commissioning, which requires five additional months to complete the work.
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2016-2017 | 2018-12-31 | 2023-06-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2026-01-01 | 2027-01-31 | 2027-01-01 | 2025-05-01 | Construction | Exempt | Construction started | SCE portion on track to finish in May 2025. LADWP portion exepected to be finished Jan 2027.
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-30 | 2025-12-01 | 2026-12-30 | 2029-12-01 | 2029-12-01 | Design | Exempt | 2028-10-01 | Project sequencing and outage constraints has slipped the construction start to 2028.
Lugo-Mohave series capacitor upgrade | SCE | 2013-2014 | 2016 | 2022-06-01 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2025-04-01 | 2025-05-01 | Construction | 2018-05-01 | 2020-12-01 | Unable to achieve the required capacitor balancing during testing and commissioning, which requires five additional months to complete the work.
Lugo-Victor-Kramer Upgrade (1/3) Add 3rd Lugo 500/230 kV Transformer | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | 2028-12-01 | Preliminary Engineering | Pending | 2027-01-01 | Project approved by CAISO in May 2023 (Lugo–Victor–Kramer 230 kV Upgrade project)
Lugo-Victor-Kramer Upgrade (2/3) Reconductor Lugo–Victor 230 kV No. 1, 2, 3 & 4 lines using HTLS | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | 2028-05-01 | Preliminary Engineering | Pending | 2025-10-01 | Resource availability, outage sequencing and material availability.
Lugo-Victor-Kramer Upgrade (3/3) Rebuild/build Kramer–Victor 115 kV lines to 230 kV and Loop the old segment of Kramer–Victor 115 kV into Roadway | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | Pending | 2033-06-30 | 1933-06-01 | 1933-06-01 | Preliminary Design | Pending | 1931-01-01 | Project approved by CAISO in May 2023 (Lugo–Victor–Kramer 230 kV Upgrade project)
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | TBD | 2029-10-01 | 2029-10-01 | Initiation | 2015-04-01 | 2025-06-01 | Project released from hold and SCE working on construction start in June 2025.
Mira Loma 500 kV CB Upgrade Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2028-12-01 | 2028-08-14 | 2028-12-01 | 2028-12-01 | Design | Exempt | 2028-05-01 | Material Lead times have increased to 5 years pushing project completion to 2028.
Mira Loma-Mesa Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | 2026-12-01 | Preliminary Engineering | Pending | 2026-03-01 | While the "Expected In-Service Date" has not changed, the "Expected Construction Start Date" should be March 2026.
New CoolwaterA 115/230 kV Bank | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2027-12-10 | 2027-12-10 | 2027-12-01 | 2027-04-01 | Preliminary Engineering | Exempt | TBD | Pending GO131D review; potential scope decrease; engineering evaluating
New Serrano 4AA Bank & 230kV GIS Rebuild | SCE | 2022-2023 | 2027 | N/A | New | New | New | New | New | New | Pending | Pending | 2027-12-30 | 2027-12-01 | 2027-12-01 | Final Design | Exempt | 2027-03-01 | Project approved by CAISO in May 2023
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2019-2020 | 2023-06-01 | 2023-05-01 | 2023-06-23 | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-25 | 2027-10-31 | 2027-10-31 | 2027-10-01 | 2029-06-01 | Construction | Exempt | 2027-01-01 | Joint SCE/LADWP project. ISD for SCE’s portion of the project is complete. ISD for LADWP portion of the project at Sylmar Substation is June 2029.
San Bernardino-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 1931-04-01 | 2029-03-01 | Initiation | Pending | 2026-10-01 | Resource availability, outage sequencing and material availability.
San Bernardino-Vista 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2029-12-01 | 2029-03-01 | Initiation | Pending | 2026-10-01 | Resource availability, outage sequencing and material availability.
Serrano-Alberhill-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-12-01 | 2027-12-01 | Engineering | Pending | 2027-03-01 | Project approved by CAISO in May 2023
Serrano–Del Amo–Mesa 500 kV Transmission Reinforcement | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | 2033-12-31 | 2033-12-31 | 1933-12-01 | 2033-12-01 | Licensing | 2027-02-01 | 2031-01-01 | Project approved by CAISO in May 2023
Sylmar Transformer Replacement | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | 2026-12-01 | Engineering | Pending | No Construction. Procurement only. | Project approved by CAISO in May 2023. Joint SCE/LADWP project.
Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 44531 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2024-02-28 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-09-01 | Pending | Construction | N/A | Construction started | Installation of 1 PMU is pending.
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | Pending | 2025-04-01 | 2025-04-01 | 2025-04-30 | 2025-04-30 | 2025-04-30 | Pending | Pending | Preliminary Engineering | N/A | Pending | Dates modified due to material lead time. Materials like CB has the most long lead time and is Critical for Construction.
Vista-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 2031-12-01 | 2029-03-01 | Initiation | Pending | 2026-10-01 | Resource availability, outage sequencing and material availability.
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Adrian Franco, can you confirm dates and status for this project?

## SDGaE
Project | PTO | Transmission Plan Approved | In-Service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2023-05-01 |  | 2023-12-01 | 2024-05-28 | 2024-05-28 | 2024-11-05 | 2024-11-05 | 2025-08-07 | 2024-02-01 | 2023-12-23 | 2023-12-07 |  |  | Close-out | 2012-05-18 | 2018-06-29
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-04-01 | 2022-05-01 | 2022-05-02 | 2022-05-31 | 2022-05-15 | 2022-05-15 | 2022-05-15 | In-Service | In-Service |  |  |  |  | Close-out | Exempt | 2022-02-04
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2021-10-01 | 2022-11-01 | 2022-12-01 | 2022-12-09 | 2022-12-27 | 2022-11-18 | 2022-11-18 | In-Service | In-Service |  |  |  |  | Close-out | 2017-06-28 | 2021-01-19
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-05-01 | 2023-02-01 | 2022-09-01 | 2022-12-14 | 2022-12-27 | 2023-02-08 | 2023-02-08 | In-Service | In-Service |  |  |  |  | Close-out | 2017-11-15 | 2022-01-03
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-06-01 |  | 2022-06-01 | 2022-12-14 | 2022-12-13 | Completed | Completed | In-Service | In-Service |  |  |  |  | Close-out | 2016-08-17 | 2020-06-10
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-12-01 |  | 2023-05-01 | 2021-11-01 | 2021-10-22 | Completed | Completed | In-Service | In-Service |  |  |  |  | Close-out | Exempt | 2021-05-17
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2022-11-01 |  | 2023-06-27 | 2023-08-25 | 2023-10-24 | Completed | Completed | In-Service | In-Service |  |  |  |  | Close-out | Exempt | 2021-07-26
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2027-06-01 | 2024-06-01 | 2024-05-02 | 2024-12-23 | 2024-12-23 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-26 | 2024-07-01 | 2024-08-23 | 2024-10-30 | 2024-11-20 | Close-out | Exempt | 2024-01-15
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2024-12-01 |  |  | 2022-08-24 | 2024-12-17 | 2024-12-17 | 2024-10-18 | 2024-08-07 | 2024-08-07 | 2024-08-20 | 2024-10-30 | 2024-11-27 | Close-out | Exempt | 2024-06-24
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 2016 | 2023-04-01 | 2023-02-01 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2023-02-13 | 2023-02-13 | 2026-02-24 | 2026-08-05 | 2026-08-01 | 2026-12-16 | 2027-05-12 | 2028-01-27 | Design | 2016-04-25 | 2026-04-22
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-11-01 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-11-14 | 2027-11-14 | 2027-11-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2026-07-16 | Design | TBD | 2025-11-05
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2026-06-01 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-06-08 | 2026-06-08 | 2026-07-29 | 2026-08-10 | 2026-10-12 | 2026-12-21 | 2027-05-11 | 2027-03-31 | Design | 2025-05-23 | 2025-10-03
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-11-01 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2026-11-10 | 2026-11-10 | 2026-12-09 | 2028-03-23 | 2028-03-16 | 2028-07-01 | 2028-05-03 | 2028-12-20 | Design | Exempt | 2028-01-03
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2029-02-01 |  |  | 2024-08-15 | 2029-02-27 | 2029-02-27 | 2029-04-30 | 2029-09-28 | 2029-12-04 | 1930-02-26 | 2029-07-27 | 2026-11-24 | Planning | TBD | 2026-09-09
3 Ohm Series Reactor on Sycamore-Penasquitos 230 kV line | SDG&E | 2022-2023 | 2032 |  | 1905-07-24 | [6 empty] | TBD | 1905-07-24 | 1905-07-24 | 1905-07-24 | 2026-10-01 | Planning | TBD | 2025-04-01 | Approved in 2022-2023 TPP
Miguel-Sycamore Canyon (TL23021) 230 kV line Loop-in to Suncrest | SDG&E | 2022-2023 | 2032 |  | 1905-07-24 | [6 empty] | TBD | 1905-07-24 | 1905-07-24 | 1905-07-24 | 1905-07-24 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 1905-07-24 | [6 empty] | TBD | 1905-07-24 | 1905-07-24 | 1905-07-24 | 1905-07-24 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Reconductor TL680C San Marcos -Melrose Tap | SDG&E | 2022-2023 | 2032 |  | 1905-07-24 | [6 empty] | TBD | 1905-07-24 | 1905-07-24 | 1905-07-24 | 1905-07-24 | Planning | TBD | TBD | Approved in 2022-2023 TPP
SG and OT Redundant Bus Differential Relay | SDG&E | 2022-2023 | 2024 |  | 1905-07-16 | [6 empty] | TBD | 1905-07-16 | 1905-07-16 | 1905-07-24 | 1905-07-24 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Upgrade TL13820 Sycamore-Chicarita 138 kV | SDG&E | 2022-2023 | 2032 |  | 1905-07-24 | [6 empty] | TBD | 1905-07-24 | 1905-07-24 | 1905-07-24 | 1905-07-24 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Valley Center System Improvement | SDG&E | 2023-2024 | 2028 | [11 empty] | 1905-07-20 | 1905-07-20 | Planning | TBD | TBD | Newly approved in 2023-2024 TPP
Short Circuit Mitigation for Imperial Valley 230 kV Circuit Breakers Project | SDG&E | 2023-2024 | 2035 | [11 empty] | 1905-07-27 | 1905-07-27 | Planning | TBD | TBD | Newly approved in 2023-2024 TPP
Short Circuit Mitigation for Miguel 230 kV Circuit Breakers Project | SDG&E | 2023-2024 | 2035 | [11 empty] | 1905-07-27 | 1905-07-27 | Planning | TBD | TBD | Newly approved in 2023-2024 TPP
Upgrade TL13820 Sycamore-Chicarita 138 kV | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 |  | Planning | TBD | TBD | Approved in 2022-2023 TPP

## VEA_GLW
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Current In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 1905-07-13 | 2021-09-01 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service | In service | In service | [5 empty] | N/A | 2021 | In Service
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 |  | 2023-06-23 | 2023-09-23 | 2023-12-23 | 2023-12-23 | Q1/Q2-2024 | Q4/2024 | Q2/2025 | In Flight | N/A | Sept-21 | Waiting on AT&T WISP network construction.
GLW/VEA area upgrades - revised scope | VEA/GLW | 2021-2022 (revised scope 2022-2023) | TBD |  | N/A | TBD | TBD | TBD | TBD | TBD | 2027-12-31 | 2027-12-31 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | Permitting, engineering and design | N/A | 2026-01-01 | Project's targeted In-Service date is Dec-27. Trout Canyon-Sloan Canyon 500kV is being prioritized. In addition, the ISD for the overall project is planned to be expedited by 6 months. However, the expidited date is subject to change based on the federal permitting process with BLM.
Beatty 230 kV Project | VEA/GLW | 2022-2023 | 2027-12-31 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | Permitting, engineering and design | N/A | 2026-01-01 | Project's targeted In-Service date is Dec-27; project is on schedule.

## DCRT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-24 | 2024-04-01 | 2024-04-24 | 2024-04-24 | 2024-05-24 | 2024-06-07 |  | In-Service | Approved | 2022-10-22 | Energized 6/7/2024

## LSPower
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service April 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support (Orchard Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | Construction | 2021-02-19 | 2023-04-01 | Construction in progress
Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TBD | TBD | TBD | Construction | 2022-04-06 | 2024-03-25 | Construction in progress
Collinsville 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Permitting | Q3 2024 | 2026 | CPCN filed
Manning 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Permitting | 2024-06-28 | 2026 | CPCN filed
Metcalf - San José B HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-04-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | Permitting | 2024-04-29 | 2026 | CPCN filed
Newark - NRS HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-05-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Permitting | 2024-05-17 | 2026 | CPCN filed
Collinsville 230kV Reactor Project | LS Power | 2023-2024 | 2028 | [10 empty] | 2028-06-01 | 2028-06-01 | Permitting | Q4 2024 | TBD
SWIP-North 500kV Transmission Project | GBT | 2022-2023 | 2027 | [11 empty] | 2028-05-01 | Permitting | N/A | 2026
* LSPGC is LS Power Grid California, LLC, an LS Power affiliate, an Approved Project Sponsor that will become a PTO upon energization of the Orchard Substation.
GBT is Great Basin Transmission, LLC, an LS Power affiliate that is the selected Project Sponsor for SWIP-North and is approved to become a PTO at energization.

## CitizensEnergy
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | Completed |  | 2023-07-21

## Lotus Partners
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
North of Songs-Sorreno 500 kV Line

## HWT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
North-Gila 500 kV line | HWT | 2022-2023 | 2032-06-01 | 2032-06-01 | N/A | 2031-12-31 | Permitting, Engineering and Design | 2025-09-02 | 2030-07-15
IV-North of Songs 500 kV line and North of Songs Substation | HWT | 2022-2023 | 2034-06-01 | 2034-06-01 | N/A | 2032-10-19 | Permitting, engineering and design | 2026-10-02 | 2030-12-23