## PGaE
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Year at Approval in Transmission Plan | Expected In-Service Year (2020-2021 Transmission Plan) | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Current In-Service Jan 2026 TDF | Project Status | Expected CPUC Filing | Expected Construction Start | Notes
2425-R-02 | Ames Distribution – Palo Alto 115 kV transmission line | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2026: No date changes at this time.
2324-R-01 | Atlantic High Voltage Mitigation | PG&E | 2023-2024 | 2029-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-04-23 | 2028-04-05 | 2028-12-21 | In-Flight | TBD | 2028-06-07 | Q1-2026: Delay due to LLM Delay With 200MVA Bank
2223-R-02 | Banta 60 kV Bus Voltage Conversion | PG&E | 2022-2023 | 2024-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2028-03-30 | 2027-12-10 | 2027-12-10 | 2028-01-20 | In-Flight | N/A | 2024-10-28 | Q1-2026: Schedule/construction sequencing date adjustments.
1920-R-01 | Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025-07-17 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2026-04-01 | 2026-04-01 | 2028-04-13 | 2028-05-30 | 2028-05-30 | 2029-03-30 | In-Flight | TBD | 2025-12-01 | Q1-2026: Delay due to clearance constraints. Project is being implemented in multiple clearances
2223-P-03 | Borden-Storey 230 kV 1 and 2 Line Reconductoring | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2029-05-01 | 2029-05-01 | 2030-05-01 | 2030-04-12 | 2029-05-08 | 2030-01-14 | In-Flight | TBD | 2029-07-16 | Q1-2026: Delay due to challenges executing a contract due to federal special provisions. ISD still within required ISD of CAISO Transmission Plan.
2324-R-02 | Camden 70 kV Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-03-19 | In-Flight | TBD | 2028-10-18 | Q1-2026: Schedule/construction sequencing date adjustments.
1011-R-01 | Cascade 115/60 kV No.2 Transformer Project and Cascade - Benton 60 kV Line Project | PG&E | 2010-2011 | 2014-03-01 | 2023-12-01 | 2023-12-29 | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2025-07-11 | 2025-07-11 | 2025-06-13 | 2025-12-15 | 2025-12-15 | 2026-04-15 | In-Flight | N/A | 2019-07-09 | Q1-2026: Delay due to LLM (60 kV CB did not arrive until Nov 2025) & resource constraints (additional support has been provided to complete by April 2026)
1819-R-01 | Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-02-01 | 2028-02-01 | 2028-02-01 | 2028-02-01 | 2029-12-31 | Initiating | NOC - TBD on Filing Date | 2031-05-09 | Q1-2026: Delay due to schedule being re-baselined after project initiation with kick off scheduled for February 2026
09-R-01 | Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012-03-01 | 2027-02-01 | 2027-02-01 | 2027-02-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-07-01 | 2029-07-01 | 2029-07-01 | 2030-10-07 | 2030-10-07 | 2030-10-07 | In-Flight | PTC - TBD on Filing Date | 2027-12-22 | Q1-2026: No date changes at this time.
1718-R-01 | Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022-05-01 | 2029-06-01 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2030-09-06 | 2031-09-05 | 2031-09-05 | In flight | TBD | 2029-09-27 | Q1-2026: No date changes at this time.
2122-P-03 | Collinsville 500/230 kV Substation Project | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-30 | In-Flight | TBD | 2027-05-28 | Q1-2026: Schedule/construction sequencing date adjustments.
2122-R-03 | Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025-05-01 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-27 | 2025-09-15 | 2026-01-21 | 2026-02-27 | In-Flight | NOC - TBD on Filing Date | 2024-12-06 | Q1-2026: Schedule/construction sequencing date adjustments.
2122-R-05 | Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-13 | 2030-04-05 | 2030-04-05 | In-Flight | N/A | 2027-01-04 | Q1-2026: No date changes at this time.
2324-R-03 | Cortina #1 60 kV Line Reconductoring | PG&E | 2023-2024 | 2028-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2028-02-28 | 2028-05-01 | In-Flight | TBD | 2026-10-06 | Q1-2026: Schedule/construction sequencing date adjustments
2425-R-05 | Cortina #3 60 kV Reconductoring | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-05-01 | 2031-12-31 | In-Flight | NOC - Expected 2026 Q1 | 2028-06-22 | Q1-2026: Delay due to schedule being re-baselined after project initiation with kick off scheduled for March 2026
2122-R-06 | Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-01 | 2028-06-01 | 2027-09-21 | 2027-10-13 | 2028-12-29 | Initiating | TBD | 2026-09-10 | Q1-2026: Delay due to LLM
1819-R-02 | Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022-12-31 | 2025-10-01 | 2025-10-02 | 2025-03-31 | 2024-12-24 | 2026-02-26 | 2026-02-26 | 2026-03-25 | 2025-11-12 | 2026-10-05 | 2026-06-19 | 2027-01-25 | 2028-02-24 | 2028-03-29 | 2028-08-25 | In-Flight | TBD | 2027-11-18 | Q1-2026: Delay due to Schedule/construction sequencing date adjustments. The project expected delivery is still within the baselined and approved CRODT date of 8/2028. The OPDAT has moved based upon project evolution and detail development as this is part of a larger substation upgrade project including breaker replacements and MPAC & relay installation.
1718-R-16 | Cottonwood 230/115 kV Transformers 1 and 4 Replacement | PG&E | 2017-2018 | 2019-11-01 | 2024-10-01 | 2024-10-02 | 2025-03-31 | 2025-02-14 | 2025-05-15 | 2025-08-11 | 2025-07-18 | 2025-11-19 | 2026-10-20 | 2026-10-20 | 2027-12-31 | 2028-10-20 | 2028-05-09 | 2028-10-06 | In-Flight | N/A | 2026-09-01 | Q1-2026: Delay due to Schedule/construction sequencing date adjustments. The project expected delivery is still within the baselined and approved CRODT date of 10/2028. The OPDAT has moved based upon project evolution and detail development as this is part of a larger substation upgrade project including breaker replacements and MPAC & relay installation.
2324-R-04 | Covelo 60 kV Voltage Support | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | In-Flight | N/A | 2029-05-01 | Q1-2026: No date changes at this time.
2324-R-05 | Crazy Horse Canyon - Salinas - Soledad #1 and #2 115 kV Line Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-04-23 | Initiating | TBD | 2030-09-05 | Q1-2026: Schedule/construction sequencing date adjustments.
2324-R-06 | Diablo Canyon Area 230 kV High Voltage Mitigation | PG&E | 2023-2024 | 2027-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-07-25 | 2028-10-10 | 2030-04-30 | In-Flight | TBD | 2027-04-14 | Q1-2026: Delay due to LLM durations.
2425-P-01 | Eagle Rock- Fulton- Silverado 115 kV Line Reconductor | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2029-08-09 | In-Flight | TBD | 2028-08-04 | Q1-2026: Improved due to initial scope significantly reduced. Project expected to finish well ahead of the requested in-service date.
1819-E-01 | East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022-12-31 | 2027-10-01 | 2027-11-10 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2033-02-02 | 2029-07-17 | 2030-01-29 | Initiating | TBD | 2028-02-09 | Q1-2026: Delay due to scope changes/challenges. Scope will be eliminating capacitor bank at Pease. PG&E will need concurrence from CAISO.
1920-R-02 | East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024-12-31 | 2026-12-01 | 2026-12-31 | 2026-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2027-06-30 | 2027-05-06 | 2027-07-07 | N/A | In-Flight | TBD | N/A | Q1-2026: This project may no longer be needed. Under review by the CAISO.
2223-R-06 | Equipment Upgrade at CCSF Owned Warnerville 230 kV Substation | PG&E | 2022-2023 | 2024-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2027-01-01 | 2027-01-01 | Cancelled | TBD | 2026-08-01 | Q1-2026: Project to be implemented by CCSF. No date changes at this time.
1314-R-06 | Estrella Substation Project | PG&E | 2013-2014 | 2019-05-01 | 2026-05-01 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | 2029-07-16 | 2029-11-01 | 2029-07-05 | 2029-07-03 | 2029-03-30 | 2029-03-30 | 2029-03-30 | In-Flight | N/A | 2025-11-13 | Q1-2026: No date changes at this time.
2324-R-09 | French Camp Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | In-Flight | PTC: A.17-01-023 Approved | 2032-10-29 | Q1-2026: Project has risk that PG&E is currently evaluating. No date changes at this time.
2223-R-07 | Garberville Area Reinforcement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2030-12-31 | 2030-12-31 | 2029-11-21 | 2027-12-28 | 2028-08-28 | 2028-12-07 | In-Flight | TBD | 2027-06-08 | Q1-2026: Delay due to advanced conductor study, and how to install fiber for protection need. The issue is now resolved. The project is moving forward with design. ISD still within required ISD of CAISO Transmission Plan.
2324-R-10 | Gates 230/70 kV Transformer Addition | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | In-Flight | NOC - Expected 2026 Q3 | 2029-05-01 | Q1-2026: No date changes at this time.
1819-R-04 | Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022-12-31 | 2028-06-01 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2030-04-12 | 2029-06-22 | 2030-01-07 | 2030-01-07 | Initiating | TBD | 2028-07-17 | Q1-2026: No date changes at this time.
2425-R-07 | Gold Hill-El Dorado Reinforcement | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | In-Flight | TBD | 2031-05-02 | Q1-2026: No date changes at this time.
2425-R-08 | Greater Bay Area 500 kV Transmission Reinforcement | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2026: No date changes at this time.
2223-P-07 | Henrietta 230/115 kV Bank 3 Replacement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2027-06-01 | 2027-06-01 | 2028-07-21 | 2028-07-12 | 2028-10-02 | 2029-06-29 | Initiating | TBD | 2027-05-25 | Q1-2026: Delay due to schedule/construction sequencing date adjustments
1718-R-03 | Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021-01-01 | 2026-12-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-12-31 | 2028-02-22 | 2028-02-22 | In-Flight | TBD | 2027-04-19 | Q1-2026: No date changes at this time.
1718-R-15 | Ignacio Area Reinforcement | PG&E | 2017-2018 | 2023-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-06-26 | 2028-02-10 | 2029-01-03 | 2030-12-31 | In-Flight | NOC - TBD on Filing Date | 2027-12-01 | Q1-2026: Department of Energy grant uncertainty led to delays in engineering contract acquisition and scope uncertainty.
1819-R-05 | Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022-12-31 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-10-12 | 2026-11-06 | 2028-06-13 | 2028-06-26 | In-Flight | NOC - TBD on Filing Date | 2028-01-18 | Q1-2026: Schedule/construction sequencing date adjustments.
2425-R-09 | Jefferson-Stanford 60 kV Recabling | PG&E | 2024-2025 | 2029-05-01 | 2026-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-05-01 | 2029-05-01 | In-Flight | TBD | 2027-03-01 | Q1-2026: No date changes at this time.
1112-R-10 | Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016-03-01 | 2027-08-01 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2029-08-10 | 2029-08-10 | 2030-12-31 | 2029-08-10 | 2029-08-10 | 2029-08-23 | In-Flight | NOC - Expected 2026 Q3 | 2028-01-10 | Q1-2026: Schedule/construction sequencing date adjustments.
2425-R-11 | Konocti – Eagle Rock 60 kV Line Reconductoring | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-31 | In flight | NOC - TBD on Filing Date | 2030-04-22 | Q1-2026: Schedule/construction sequencing date adjustments.
1718-R-04 | Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | In-Flight | TBD | 2027-10-01 | Q1-2026: No date changes at this time.
1213-R-14 | Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017-03-01 | 2027-06-01 | 2027-06-21 | 2028-12-29 | 2029-01-01 | 2029-01-01 | 2029-01-01 | 2029-01-11 | 2029-01-11 | 2029-06-08 | 2029-12-25 | 2029-12-10 | 2029-12-10 | 2029-12-10 | 2031-06-30 | Initiating | NOC - TBD on Filing Date | 2029-06-13 | Q1-2026: Delay due to CPCN permitting. Prior ISD was placeholder pending approval of CPCN upon which scheduled would be re-baselined. The CPCN testimony will include the new OPDAT of Q2 2031.
2223-R-08 | Lone Tree – Cayetano – Newark Corridor Series Compensation | PG&E | 2022-2023 | 2027-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-02 | 2027-10-13 | 2028-08-30 | In-Flight | CPCN: A.23-09-001 Filed & Under Review | 2028-04-17 | Q1-2026: Delay due to scoping challenges. There was a mismatch on technical requirements required by CAISO (flexible impedance) vs PG&E system protection provided fixed reactance use only. The CAISO has concurred for the use of the device either at zero or full impedance injection under contingency conditions. Flexible impedance is not required.
2223-R-09 | Los Banos 230 kV Circuit Breaker Replacement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2029-12-04 | 2028-12-28 | In-Flight | TBD | 2027-09-30 | Q1-2026: Improved due to recalibration in PG&E's work portfolio.
2223-R-10 | Los Banos 70 kV Area Reinforcement Project | PG&E | 2022-2023 | 2029-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2030-09-12 | 2030-08-27 | 2031-01-29 | In-Flight | N/A | 2029-01-08 | Q1-2026: Delay to dependencies. Project depends on Dos Amigos Pumping Plant - Panoche 230 kV New Switching Station.
2122-P-04 | Manning 500/230 kV Substation Project | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | In-Flight | TBD | 2026-03-16 | Q1-2026: No date changes at this time.
2122-R-08 | Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028-05-01 | 2028-12-31 | N/A | 2028-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-05-31 | 2029-02-02 | 2029-10-09 | 2029-10-09 | 2029-07-13 | 2027-09-30 | Initiating | TBD | 2026-03-02 | Q1-2026: Improved due to recalibration in PG&E's work portfolio.
09-R-02 | Maple Creek Reactive Support | PG&E | 2009 | 2011-03-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-10-01 | 2027-10-01 | 2027-10-01 | 2029-11-28 | 2028-10-27 | In-Flight | NOC: AL 7706-E Approved | 2027-02-01 | Q1-2026: Improved due to recalibration in PG&E's work portfolio.
1415-R-03 | Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021-12-01 | 2024-05-01 | 2024-05-24 | 2024-05-10 | 2024-05-24 | 2025-11-14 | 2025-11-13 | 2025-11-13 | 2026-04-23 | 2027-02-12 | 2028-10-13 | 2029-12-18 | 2029-10-17 | 2030-02-07 | 2030-05-01 | In-Flight | TBD | 2028-02-25 | Q1-2026: Schedule/construction sequencing date adjustments.
2324-R-12 | Martin-Millbrae 60 kV Area Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2029-08-23 | 2029-12-28 | In-Flight | CPCN: A.17-12-021 Approved | 2028-04-06 | Q1-2026: Delay due to scope development. ISD still within required ISD of CAISO Transmission Plan.
2223-R-11 | Mesa Spare Transformer Installation | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-05-01 | 2028-04-01 | 2028-04-01 | 2029-04-01 | 2029-03-14 | 2027-07-27 | 2028-02-09 | In-Flight | TBD | 2027-10-13 | Q1-2026: Delay due to clearance restraints at Metcalf given concurrent work at Metcalf (HVDC & MPAC projects)
2223-R-12 | Metcalf 230/115 kV Transformers Circuit Breaker Addition | PG&E | 2022-2023 | 2026-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2027-06-01 | 2027-06-01 | 2026-09-01 | 2027-06-23 | 2034-05-01 | 2034-05-01 | In-Flight | TBD | 2033-05-01 | Q1-2026: No date changes at this time.
2425-R-13 | Metcalf Substation 500/230 kV Transformer Bank Addition | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-04-04 | 2030-12-26 | In-Flight | TBD | 2027-01-08 | Q1-2026: Delay due to schedule being re-baselined after project kicked off in December 2025
2425-R-14 | Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade Re-scope | PG&E | 2003 | 2008-12-31 | 2029-04-01 | 2029-04-01 | 2029-04-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-03-01 | 2027-03-01 | 2028-05-12 | 2028-06-14 | 2028-12-29 | Initiating | TBD | 2028-03-01 | Q1-2026: Delay due to schedule being re-baselined after project re-kicked off in January 2026
1314-R-13 | Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019-05-01 | 2024-06-01 | 2024-06-06 | 2025-07-03 | 2026-06-23 | 2026-06-23 | 2027-04-07 | 2027-04-07 | 2027-04-07 | 2027-04-29 | 2027-04-29 | 2028-12-31 | 2028-06-14 | 2032-01-07 | 2032-01-07 | In-Flight | NOC - TBD on Filing Date | 2026-04-27 | Q1-2026: No date changes at this time.
1314-R-13 | Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019-05-01 | 2024-06-01 | 2024-06-06 | 2027-06-03 | 2027-09-01 | 2027-11-30 | 2028-02-25 | 2028-05-23 | 2028-08-21 | 2027-10-28 | 2028-01-24 | 2030-05-28 | 2030-09-30 | 2030-02-01 | 2029-02-07 | In-flight | NOC: AL 5026-E Approved | 2021-04-07 | Q1-2026: Improved due to recalibration in PG&E's work portfolio.
1011-R-12 | Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-08-29 | 2025-08-29 | 2027-10-08 | 2030-08-22 | 2030-08-22 | 2028-12-26 | 2029-02-01 | In flight | NOC: AL 5924-E Approved | 2027-10-18 | Q1-2026: Schedule/construction sequencing date adjustments.
1213-R-19 | Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018-05-01 | 2027-10-01 | 2027-10-20 | 2028-02-16 | 2028-05-16 | 2028-08-14 | 2028-11-09 | 2029-02-05 | 2029-04-06 | 2029-08-01 | 2029-10-26 | 2030-07-16 | 2029-02-15 | 2026-03-04 | 2028-06-02 | In-Flight | N/A | 2021-08-17 | Q1-2026: Delay due to clearances. Project schedule did not reflect a complete clearance schedule. Project schedule now reflect full scope and associated clearances
1213-R-21 | Monte Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016-05-01 | 2024-08-01 | 2024-08-06 | 2024-07-17 | 2024-05-08 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-01 | 2025-08-07 | 2025-08-07 | 2025-09-23 | 2026-03-06 | 2029-05-01 | 2029-05-01 | In-Flight | NOC - Expected 2026 Q3 | 2028-05-01 | Q1-2026: No date changes at this time.
1920-R-04 | Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2031-05-01 | 2031-05-01 | In-Flight | N/A | 2027-11-09 | Q1-2026: No date changes at this time.
2425-R-15 | Moraga 230/115 kV Transformer Bank Addition | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Initiating | N/A | TBD | Q1-2026: Project on CAISO Hold.
1819-R-06 | Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023-12-31 | On Hold | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 2028-12-26 | 2028-12-29 | Initiating | TBD | 2026-05-14 | Q1-2026: Schedule/construction sequencing date adjustments.
1314-R-17 | Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021-12-01 | 2026-04-01 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2027-09-29 | 2027-09-29 | 2027-09-29 | 2029-01-30 | 2029-02-27 | 2028-12-28 | 2029-01-22 | 2028-11-17 | 2028-11-17 | On-Hold (CAISO) | TBD | 2027-10-01 | Q1-2026: No date changes at this time.
1314-R-18 | Mosher Transmission Project | PG&E | 2013-2014 | 2017-12-01 | 2027-12-01 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2028-02-17 | 2026-12-04 | 2027-08-25 | In-Flight | NOC - Expected 2026 Q1 | 2027-04-16 | Q1-2026: Delay due to a cluster 13 study that needs to be completed to determine capacity.
2122-E-01 | Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026-01-01 | 2026-12-31 | N/A | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2028-04-01 | 2028-04-01 | 2028-09-01 | 2028-09-01 | 2034-05-01 | 2034-05-01 | In-flight | NOC - TBD on Filing Date | 2033-05-01 | Q1-2026: No date changes at this time.
2425-P-02 | New Helm 230/70 kV Bank #2 | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2026: No date changes at this time.
2324-P-02 | New Humboldt 115/115 kV Phase Shifter with 115 kV line to Humboldt 115kV Substation | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2026: No date changes at this time.
2324-P-03 | New Humboldt 500 kV Substation with 500 kV line to Collinsville [HVDC operated as AC] | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2026: No date changes at this time.
2324-P-04 | New Humboldt to Fern Road 500 kV Line | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2027-07-13 | 2027-07-13 | Initiating | TBD | 2027-05-24 | Q1-2026: No date changes at this time.
1920-R-05 | Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2029-02-20 | 2027-07-08 | 2026-12-04 | In-Flight | TBD | 2026-08-11 | Q1-2026: Improved due to bundling efficiency with the Newark HVDC project, which will provide the MPAC this project will use
1718-R-07 | Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019-06-01 | 2022-11-01 | 2022-11-01 | 2023-04-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-06-01 | 2025-06-01 | 2025-07-01 | 2027-05-06 | 2028-04-01 | 2028-04-01 | Initiating | TBD | 2026-07-02 | Q1-2026: No date changes at this time.
2324-P-05 | North Dublin -Vineyard 230 kV Reconductoring | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | In-Flight | NOC - TBD on Filing Date | 2030-04-23 | Q1-2026: No date changes at this time.
2223-R-15 | North East Kern 115 kV Line Reconductoring | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2033-12-31 | 2033-12-31 | 2032-12-31 | 2029-08-20 | 2031-12-01 | 2032-03-16 | Initiating | TBD | 2028-01-28 | Q1-2026: Delay due to challenges executing a contract due to federal special provisions. ISD still within required ISD of CAISO Transmission Plan.
2425-R-16 | North Oakland Reinforcement Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q1-2026: No date changes at this time.
1112-R-15 | North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015-05-01 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2028-02-01 | 2028-02-01 | 2029-02-01 | 2029-02-01 | 2029-02-01 | 2029-11-19 | In-Flight | NOC - TBD on Filing Date | 2030-12-24 | Q1-2026: Delay due to schedule being re-baselined after project initiation with kick off scheduled for June 2026
1011-R-16 | Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2026-12-01 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2028-08-28 | 2028-05-16 | 2028-05-23 | In-Flight | TBD | 2027-10-12 | Q1-2026: Schedule/construction sequencing date adjustments.
2223-R-16 | Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-28 | 2028-06-01 | 2028-04-28 | 2028-03-31 | 2028-04-26 | 2028-04-28 | In-Flight | NOC - TBD on Filing Date | 2026-08-17 | Q1-2026: Schedule/construction sequencing date adjustments.
2223-R-17 | Pittsburg 115 kV Bus Reactor project | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2028-05-12 | 2028-05-12 | 2028-05-12 | 2028-05-30 | 2028-05-26 | 2028-05-26 | In-Flight | N/A | 2027-06-29 | Q1-2026: No date changes at this time.
07-R-02 | Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011-05-01 | 2025-01-01 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2026-06-17 | 2026-06-17 | 2026-09-04 | 2026-06-15 | 2028-05-09 | 2028-09-27 | 2029-01-31 | 2029-01-03 | Initiating | TBD | 2027-10-20 | Q1-2026: Schedule/construction sequencing date adjustments.
2425-R-17 | Pittsburg-Kirker 115 kV Line Section Limiting Elements Upgrade | PG&E | 2024-2025 | 2028-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-05-01 | 2028-05-01 | In-Flight | TBD | 2027-05-02 | Q1-2026: No date changes at this time.
2122-P-05 | Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-02-02 | 2028-08-16 | 2028-02-01 | 2028-02-29 | 2028-02-29 | Initiating | TBD | 2027-11-02 | Q1-2026: No date changes at this time.
2425-P-03 | Reconductor of GWF – Kingsburg 115 kV line | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | In-Flight | TBD | 2033-05-01 | Q1-2026: No date changes at this time.
2122-P-06 | Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-12-31 | 2030-02-01 | In-Flight | NOC: AL 7766-E Approved | 2029-10-04 | Q1-2026: Schedule/construction sequencing date adjustments.
1718-R-14 | Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2025-11-01 | 2025-11-19 | 2026-08-18 | 2026-08-18 | 2030-05-23 | 2031-11-19 | 2029-03-30 | 2028-11-07 | 2028-05-23 | 2029-03-06 | 2029-08-27 | 2029-03-28 | 2028-01-31 | 2028-03-20 | In-Flight | NOC - TBD on Filing Date | 2026-09-28 | Q1-2026: Schedule/construction sequencing date adjustments.
2223-R-18 | Redwood City Area 115 kV System Reinforcement | PG&E | 2022-2023 | 2030-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-12-01 | 2029-12-01 | 2029-12-01 | 2028-07-05 | 2030-03-14 | 2029-02-15 | 2030-02-13 | In-Flight | TBD | 2028-09-12 | Q1-2026: Delay due to environmental limitations. Strict environmental work windows in the wetlands only allow construction from September 1st to January 15th each year. Given these restrictions, we anticipate being able to replace only 20 structures per year under optimal conditions. Since a total of 80 structures need replacement on the Ravenswood-San Mateo 115 kV Line, it will take approximately four years to complete all replacements. Furthermore, the Ravenswood-San Mateo 115kV line will be converted to 230kV structures with a 3000A line rating.
2324-R-14 | Reedley 70 kV Capacity Increase | PG&E | 2023-2024 | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | In-Flight | TBD | 2028-08-24 | Q1-2026: No date changes at this time.
2324-R-15 | Rio Oso - W. Sacramento Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2029-09-04 | 2029-09-06 | In-Flight | N/A | 2028-11-21 | Q1-2026: Schedule/construction sequencing date adjustments.
1112-R-21 | Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016-05-01 | 2024-10-01 | 2024-10-11 | 2024-10-31 | 2024-08-26 | 2024-12-09 | 2025-05-30 | 2025-06-04 | 2025-06-04 | 2025-06-19 | 2025-09-01 | 2026-05-14 | 2026-05-14 | 2026-10-15 | 2026-10-30 | In-Flight | N/A | 2026-02-13 | Q1-2026: Schedule/construction sequencing date adjustments.
1819-R-08 | Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | PG&E | 2018-2019 | 2024-12-31 | 2024-05-01 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | 2024-11-21 | 2024-12-31 | 2024-12-31 | TBD | TBD | 2026-03-26 | 2026-05-26 | In-Flight | TBD | 2023-02-15 | Q1-2026: Schedule/construction sequencing date adjustments. Round Mountain & Table Mountain Series Capacitors to be operational in December 2026. This work can/will be completed post-energization of Fern Road.
2324-R-16 | Salinas Area Reinforcement | PG&E | 2023-2024 | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2032-12-31 | 2032-12-31 | In-Flight | N/A | 2027-05-21 | Q1-2026: No date changes at this time.
2122-R-11 | San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-11-30 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-05-01 | 2028-05-01 | In-Flight | NOC: AL 7391-E Approved | 2026-01-05 | Q1-2026: No date changes at this time.
2122-R-10 | San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-04-30 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2030-06-28 | 2030-06-28 | In-Flight | TBD | 2028-11-17 | Q1-2026: No date changes at this time.
2122-R-10 | San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2026: No date changes at this time.
2425-R-18 | San Jose B – NRS 230 kV line | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q1-2026: No date changes at this time.
2425-R-19 | San Mateo 230/115 kV Transformer Bank Addition Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q1-2026: No date changes at this time.
2425-R-20 | San Miguel New 70 kV Line | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-21 | 2032-05-21 | In flight | TBD | 2030-09-23 | Q1-2026: No date changes at this time.
2223-R-19 | Santa Rosa 115 kV lines Reconductoring project | PG&E | 2022-2023 | 2028-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-10-31 | 2032-05-21 | 2026-02-10 | 2026-04-23 | In-Flight | TBD | 2026-01-08 | Q1-2026: Schedule/construction sequencing date adjustments.
2122-R-12 | Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023-06-01 | 2023-12-31 | N/A | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-12-23 | 2025-12-23 | 2026-03-03 | 2025-12-30 | 2033-05-01 | 2033-05-01 | Initiating | TBD | 2032-05-01 | Q1-2026: No date changes at this time.
2425-R-24 | Sobrante 230 kV Bus Upgrade | PG&E | 2024-2025 | 2033-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q1-2026: No date changes at this time.
2324-P-06 | Sobrante 230/115 kV Transformer Bank Addition | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2026-06-10 | 2026-07-29 | In-Flight | N/A | 2026-07-07 | Q1-2026: Schedule/construction sequencing date adjustments.
2223-R-21 | South Bay Area Limiting Elements Upgrade | PG&E | 2022-2023 | 2027-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2026-03-01 | 2026-03-01 | 2025-05-01 | 2026-04-10 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2027-04-08 | Q1-2026: No date changes at this time.
2425-R-25 | South Bay Reinforcement Project | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q1-2026: No date changes at this time.
2425-R-26 | South Oakland Reinforcement Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-06-06 | 2029-06-06 | In-flight | NOC - TBD on Filing Date | 2027-07-09 | Q1-2026: No date changes at this time.
1819-R-09 | South of Mesa Upgrade | PG&E | 2018-2019 | 2023-12-31 | 2026-09-01 | 2026-09-03 | 2026-05-26 | 2026-05-26 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-15 | 2027-04-15 | 2031-03-10 | 2029-06-06 | 2029-02-21 | 2031-12-31 | In-Flight | NOC - TBD on Filing Date | 2027-12-01 | Q1-2026: Delay due to environmental limitations. Strict environmental work windows in the wetlands only allow construction from September 1st to January 15th each year. Given these restrictions, we anticipate being able to replace only 20 structures per year under optimal conditions. Since a total of 80 structures need replacement on the Ravenswood-San Mateo 115 kV Line, it will take approximately four years to complete all replacements. Furthermore, the Ravenswood-San Mateo 115kv line will be converted to 230kv structures with 3000A line rating.
07-R-01 | South of San Mateo Capacity Increase | PG&E | 2007 | 2009-05-01 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2028-12-01 | 2028-12-01 | 2027-10-29 | 2028-06-22 | 2029-05-09 | 2029-05-18 | In-Flight | TBD | 2027-07-06 | Q1-2026: Schedule/construction sequencing date adjustments.
2122-R-13 | Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027-01-01 | 2027-12-31 | N/A | 2027-01-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-06-01 | 2028-06-01 | 2026-09-28 | 2027-10-13 | 2028-08-30 | 2029-04-26 | In-Flight | TBD | 2027-02-08 | Q1-2026: Delay due to clearance constraints. Project sequencing requirements determined as the project progressed through the scoping phase. Operational clearance constraints limit us to only clear and construction one line at a time. There is a total of 3 lines to be reconductored. Best case and current schedule is for the first line to be completed by 4/2027, Second line by 4/2028 and third line by 4/2029. Dates subject to change based on engineering, operations, permitting and construction input
2324-R-17 | Tejon Area Reinforcement | PG&E | 2023-2024 | 2027-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-08-01 | 2034-12-29 | 2034-12-29 | In-Flight | TBD | 2027-12-22 | Q1-2026: No date changes at this time.
2324-P-07 | Tesla - Newark 230 kV Line No. 2 Reconductoring | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2028-06-30 | 2028-06-30 | In-Flight | TBD | 2027-11-23 | Q1-2026: No date changes at this time.
2223-R-23 | Tesla 115 kV Bus Reconfiguration Project | PG&E | 2022-2023 | 2030-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-12-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | 2027-12-31 | 2027-12-31 | In-Flight | N/A | 2024-05-13 | Q1-2026: No date changes at this time.
1718-R-11 | Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-16 | 2027-08-16 | 2028-02-09 | 2028-02-09 | 2028-12-28 | 2027-12-01 | 2026-12-17 | 2026-12-14 | In-Flight | NOC - Expected 2026 Q2 | 2026-11-03 | Q1-2026: Schedule/construction sequencing date adjustments.
2223-R-24 | Tulucay-Napa #2 60 kV line Reconductoring project | PG&E | 2022-2023 | 2028-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-12-01 | 2026-12-31 | 2026-12-31 | 2026-12-01 | 2027-07-23 | 2028-01-05 | 2028-03-31 | In-Flight | TBD | 2027-12-07 | Q1-2026: Schedule/construction sequencing date adjustments.
1819-R-11 | Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-03-01 | 2027-03-01 | 2027-09-20 | 2027-09-30 | 2027-04-30 | 2028-06-30 | In-Flight | PTC: A.24-06-008 Filed & Under Review/NOC: AL 7542-E Approved | 2025-09-26 | Q1-2026: Delay due to scope change. Flicker study resulted in changes to cap bank configuration and need to procure 4 additional breakers.
1718-R-17 | Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023-12-01 | 2026-07-01 | 2026-07-10 | 2026-08-21 | 2025-08-18 | 2025-12-25 | 2025-12-30 | 2026-02-06 | 2026-02-06 | 2026-04-29 | 2027-04-12 | 2027-04-30 | 2027-04-30 | 2027-11-17 | 2027-11-17 | In flight | N/A | 2027-04-20 | Q1-2026: No date changes at this time.
1718-R-13 | Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019-10-01 | 2027-04-01 | 2027-04-01 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-05-08 | 2025-10-20 | 2025-10-20 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-11-18 | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q1-2026: No date changes at this time.
2324-R-18 | Vaca-Plainfield 60 kV Line Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2026-06-02 | 2027-04-06 | In-Flight | TBD | 2026-07-31 | Q1-2026: Delay due to clearance restraints at Metcalf and delays in MPAC building delivery. This scope is a component of overall Metcalf 230kV & 115kV MPAC dependent on schedule of the overall project.
2122-R-14 | Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025-05-01 | 2025-12-31 | N/A | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2026-08-31 | 2026-07-27 | 2026-06-03 | 2026-06-24 | In-Flight | PTC: A.18-06-004 Approved | 2024-05-21 | Q1-2026: Schedule/construction sequencing date adjustments.
1011-R-30 | Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014-05-01 | 2025-06-01 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | 2026-05-29 | 2026-07-31 | 2027-05-06 | 2027-04-23 | 2027-05-10 | 2027-05-13 | 2027-07-26 | In-Flight | NOC - Expected 2026 Q1 | 2026-12-28 | Q1-2026: Schedule/construction sequencing date adjustments.
2122-R-16 | Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-05-31 | 2029-02-02 | 2027-12-06 | 2027-04-12 | 2031-05-01 | 2031-05-01 | Initiating | TBD | 2030-05-01 | Q1-2026: No date changes at this time.
2425-R-28 | West Fresno 115 kV Voltage Support | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-19 | In-Flight | PTC - Expected 2026 Q1 | 2028-09-18 | Q1-2026: Schedule/construction sequencing date adjustments.
1314-R-27 | Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020-05-01 | On Hold | N/A | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | 2034-03-28 | 2029-05-04 | 2033-12-31 | 2032-12-01 | 2033-07-11 | 2027-11-22 | 2028-03-06 | In-Flight | TBD | 2027-10-15 | Q1-2026: Delay due to Scope Addition (new bank is needed & existing service center will need to relocate) & LLM (Hitachi supplier of STATCOM/Transformer)
1011-R-32 | Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2026-09-01 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2029-08-16 | 2029-12-21 | 2030-05-02 | In-Flight | N/A | 2027-11-10 | Q1-2026: Delay due to schedule/construction sequencing date adjustments
1920-R-09 | Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026-12-31 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-02-12 | 2028-07-03 | In-Flight | NOC - TBD on Filing Date | 2027-08-11 | Q1-2026: Delay due to schedule being re-baselined after project kicked off in August 2025

## SCE
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Current In-Service Jan 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
2122-P-02 | Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | N/A | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | 2024-05-31 | 2024-05-01 | 2024-06-01 | 2024-06-01 | 2025-06-01 | Complete | 2025-04-02 | In Service | In Service | Exempt | 2024-05-02 | In-Service. Project will be removed in future TDF.
2223-P-10 | Mira Loma-Mesa Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2025-01-31 | In Service | Exempt | 2026-03-01 | CB replacement cancelled in lieu of addition of TRV capacitance to affected units, project complete.
2425-R-01 | Alamitos 230 kV SCD Upgrade | SCE | 2024-2025 | 2032 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | 1932-06-01 | New | Exempt | Pending | Project was approved in May 2025.
09-R-03 | Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-10-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | Engineering | 2009-09-01 | 2026-06-01 | Alberhill dates contingent on licensing. Initial site construction due to commence summer 2026.
2122-R-01 | Antelope 66 kV Short Circuit Duty Mitigation Project | SCE | 2021-2022 | 2026 | N/A | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2026-12-26 | 2026-12-26 | Construction | Exempt | 2024-10-01 | Material delay caused shift in construction start and outage coordination is extending project construction duration.
2223-R-01 | Antelope-Whirlwind 500 kV Line Upgrade | SCE | 2022-2023 | 2025 | N/A | New | New | New | New | New | New | Pending | Pending | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2026-01-26 | Construction | Exempt | 2025-12-04 | ISD delayed due to construction postponement caused by weather.
2223-R-03 | Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | Pending | 2026-06-01 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-06-01 | 2026-06-01 | 2027-12-31 | 2027-12-31 | Construction | Exempt | 2025-08-04 | Previous change in ISD (reported at July TDF) due to delays in engineering drawings and long lead materials.
2223-P-04 | Colorado River-Red Bluff 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-02-01 | 2027-12-01 | 2026-12-31 | 2027-04-01 | Preliminary Engineering | Pending | 2026-10-01 | Preliminary design estimated to be completed Q1 2026.
2122-R-07 | Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2027-06-01 | 2027-06-01 | 2027-04-13 | 2027-04-13 | Final Engineering | Exempt | 2024-06-01 | Construction partially complete.
2223-P-05 | Devers-Red Bluff 500 kV 1 and 2 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 1930-03-01 | 1930-01-01 | 2030-12-31 | 2030-12-31 | Preliminary Engineering | Pending | 2028-10-02 | Original ISD due to material lead time for substation equipment. Preliminary design estimated to be completed Q1 2026. Construction sequencing dependent upon outage constraints.
2223-P-06 | Devers-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-04-01 | 2027-12-01 | 2028-04-28 | 2028-12-01 | Preliminary Engineering | Pending | 2027-01-04 | Preliminary design estimated to be completed Q1 2026. Construction sequencing dependent upon outage constraints.
2324-R-07 | Eldorado 230 kV Short Circuit Duty Mitigation Project | SCE | 2023-2024 | 2029 | N/A | New | New | New | New | New | New | New | New | New | Pending | Pending | 2029-12-01 | 2029-12-01 | Engineering | Exempt | Q1-2028 | This project/work is located in Nevada.
2324-R-11 | Inyo 230 kV Shunt Reactor | SCE | 2023-2024 | 2027 | N/A | New | New | New | New | New | New | Pending | N/A | N/A | 2027-12-31 | 2026-12-01 | 2026-09-25 | 2026-12-02 | Engineering Design | Pending | 2026-03-02 | Minor schedule slip due to engineering delay.
2425-R-10 | Julian Hinds-Mirage 230 kV Advanced Reconductor | SCE | 2024-2025 | 2030 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | TBD | Initiation | Exempt | Pending | Project reassessment under consideration
2425-R-12 | Kramer-Coolwater 115 kV Line Looping into Tortilla 115 kV Substation | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | TBD | Initiation | Pending | Pending | Project reassessment under consideration
1213-P-02 | Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2012-2013 | 2016 | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2024-12-01 | 2025-05-01 | 2026-06-30 | 2026-06-30 | Construction | 2018-05-01 | 2020-12-01 | The operating date for the ELM Project is being pushed to June 2026 due to the delayed SoCal Gas pipeline mitigation construction.
1516-R-09 | Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2016-2017 | 2018-12-31 | 2023-06-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2026-01-01 | 2027-01-31 | 2027-01-01 | 2025-05-01 | 2025-12-30 | 2027-03-31 | Construction | Exempt | Construction started | The completion of LADWP portion of the work requires clearance modifications to resolve line infractions in addition to the replacement of CB's at Victorville Substation. The completion date for both SCE and LADWP work is expected to be by December 31st of 2027.
08-R-01 | Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-30 | 2025-12-01 | 2026-12-30 | 2029-12-01 | 2029-12-01 | 2031-06-30 | 2031-06-30 | Design | Exempt | 2030-01-01 | Project sequencing and outage constraints has slipped the construction start to 2030.
1314-P-01 | Lugo-Mohave series capacitor upgrade | SCE | 2013-2014 | 2016 | 2022-06-01 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2025-04-01 | 2025-05-01 | 2026-06-30 | 2026-06-30 | Construction | 2018-05-01 | 2020-12-01 | The operating date for the ELM Project is being pushed to June 2026 due to the delayed SoCal Gas pipeline mitigation construction.
2223-P-09 | Lugo-Victor-Kramer Upgrade (1/3) Add 3rd Lugo 500/230 kV Transformer | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | 2028-12-01 | 2029-06-30 | 2029-06-30 | Preliminary Engineering | Exempt | 2028-01-01 | Project sequencing and outage constraints has slipped the construction start to 2028 with a OD in June 2029.
2223-P-09 | Lugo-Victor-Kramer Upgrade (2/3) Reconductor Lugo–Victor 230 kV No. 1, 2, 3 & 4 lines using HTLS | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | 2028-05-01 | 2026-12-20 | 2028-12-20 | On Hold | Pending | 2025-10-01 | CAISO is reassessing in 2025-2026 TPP
2223-P-09 | Lugo-Victor-Kramer Upgrade (3/3) Rebuild/build Kramer–Victor 115 kV lines to 230 kV and Loop the old segment of Kramer–Victor 115 kV into Roadway | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | Pending | 2033-06-30 | 1933-06-01 | 1933-06-01 | 2032-12-01 | 2032-09-01 | On Hold | 2028-06-01 | 2030-07-01 | CAISO is reassessing in 2025-2026 TPP
07-R-03 | Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | TBD | 2029-10-01 | 2029-10-01 | 2029-10-01 | 2029-10-01 | Construction | 2028-06-01 | 2029-10-01 | Project released from hold and SCE construction in progress.
2223-R-14 | Mira Loma 500 kV Circuit Breaker Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2028-12-01 | 2028-08-14 | 2028-12-01 | 2028-12-01 | 2028-08-14 | 2028-08-14 | Design | Exempt | 2028-05-01 | Expected CB delivery is May 2028. Outage restrictions unkown, pushing completion to years end.
2223-R-05 | New Coolwater A 230/115 kV Bank | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2027-12-10 | 2027-12-10 | 2027-12-01 | 2027-04-01 | 2028-06-02 | TBD | On Hold | Exempt | 2026-08-03 | CAISO is reassessing in 2025-2026 TPP
1920-R-06 | Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2019-2020 | 2023-06-01 | 2023-05-01 | 2023-06-23 | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-25 | 2027-10-31 | 2027-10-31 | 2027-10-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | Construction | Exempt | 2024-10-31 | Joint SCE/LADWP project. ISD for SCE’s portion of the project is complete. ISD for LADWP portion of the project at Sylmar Substation is June 2029.
2223-P-15 | San Bernardino-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 1931-04-01 | 2029-03-01 | 2031-12-31 | 2031-12-01 | Design | Exempt | 2027-10-01 | ISD has been updated to reflect material lead time for major materials.
2223-P-16 | San Bernardino-Vista 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2029-12-01 | 2029-03-01 | 2029-12-31 | 2031-12-01 | Design | Exempt | 2027-06-01 | ISD has been updated to reflect material lead time for major materials.
2425-R-21 | Serrano 230 kV SCD GIS Bus Split | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | 2033-10-28 | Engineering | Exempt | Pending | 2022-2023 and 2024-2025 TPP projects at Serrano will be constructed as one integrated effort, ISD dependent on vendor lead times for major GIS materials.
2223-R-20 | Serrano 4AA 500/230 kV Transformer Bank Addition | SCE | 2022-2023 | 2027 | N/A | New | New | New | New | New | New | Pending | Pending | 2027-12-30 | 2027-12-01 | 2027-12-01 | 2033-05-24 | 2033-05-24 | Engineering | Exempt | 2027-05-29 | 2022-2023 and 2024-2025 TPP projects at Serrano will be constructed as one integrated effort, ISD dependent on vendor lead times for major GIS materials.
2425-R-22 | Serrano 500 kV SCD Mitigation | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | 2033-08-29 | Engineering | Exempt | Pending | 2022-2023 and 2024-2025 TPP projects at Serrano will be constructed as one integrated effort, ISD dependent on vendor lead times for major GIS materials.
2223-P-17 | Serrano-Alberhill-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-12-01 | 2027-12-01 | 2031-06-01 | 2031-08-29 | Engineering | Exempt | 2027-03-15 | 2022-2023 and 2024-2025 TPP projects at Serrano will be constructed as one integrated effort, ISD dependent on vendor lead times for major GIS materials.
2223-P-18 | Serrano–Del Amo–Mesa 500 kV Transmission Reinforcement | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | 2033-12-31 | 2033-12-31 | 1933-12-01 | 2033-12-01 | 2033-12-01 | 1935-01-01 | On Hold | 2027-02-01 | 2031-01-01 | CAISO is reassessing in 2025-2026 TPP
2223-R-22 | Sylmar Transformer Replacement | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | 2026-12-01 | 2028-01-07 | 2028-01-07 | Engineering | Exempt | No Construction. Procurement only | Transformer delivery date has been delayed.
1718-R-11 | Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 44531 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2024-02-28 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-09-01 | Pending | 2025-12-31 | 2025-12-31 | Construction | Exempt | In progress | Construction reopened due identfication of additional scope, network updates.
2425-R-27 | Tortilla 115 kV Capacitor Replacement | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | 2029-06-30 | Preliminary Engineering | Exempt | Pending | Project was approved in May 2025.
2122-R-15 | Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | Pending | 2025-04-01 | 2025-04-01 | 2025-04-30 | 2025-04-30 | 2025-04-30 | Pending | Pending | 2027-06-01 | 2027-06-09 | Preliminary Engineering | Exempt | 2026-10-01 | In service date of June 2027 pending confirmation on material lead time.
2223-P-21 | Vista-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 2031-12-01 | 2029-03-01 | 2027-01-29 | 2027-06-01 | Design | Exempt | 2026-10-01 | This project is being coordinated with other TPP work in the region.

## SDGaE
TP Project ID | Project | PTO | Transmission Plan Approved | In-Service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Current In-Service Jan 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
2223-P-01 | 3 Ohm Series Reactor on Sycamore-Penasquitos 230 kV line | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2026-10-01 | 2026-06-30 | 2027-07-16 | Construction | Exempt | 2025-12-15 | Below grade construction started on 12/15/2025.
2223-P-08 | IV-North of Songs 500 kV line | SDG&E | 2022-2023 | 2034-06-01 | [14 empty] | 2032-01-01 | Planning | 2026-11-26 | 2026-09-29
2223-R-13 | Miguel-Sycamore Canyon (TL23021) 230 kV line Loop-in to Suncrest | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2032-12-31 | Design | 2026-03-01 | 2027-10-01
2223-P-13 | Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2031-08-04 | Planning | TBD | 2030-12-30
2223-P-14 | Reconductor TL680C San Marcos-Melrose Tap | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2031-09-01 | Planning | TBD | 2026-10-01
1718-R-09 | San Ysidro 69 kV Reconductoring (TL623C) | SDG&E | 2017-2018 | 2022-06-01 |  | 2029-02-01 |  |  | 2024-08-15 | 2029-02-27 | 2029-02-27 | 2029-04-30 | 2029-09-28 | 2029-12-04 | 1930-02-26 | 2029-07-27 | 2026-11-24 | 2027-04-19 | 2027-03-02 | Design | Exempt | 2026-12-14
2324-R-22 | SG and OT Redundant Bus Differential Relay | SDG&E | 2022-2023 | 2024 |  | 2024 | [6 empty] | TBD | 2024 | 2024 | 2032 | 2032 | 2025-12-31 | 2026-06-30 | Design | Exempt | 2026-03-31
2324-R-20 | Short Circuit Mitigation for Imperial Valley 230 kV Circuit Breakers | SDG&E | 2023-2024 | 2035 | [11 empty] | 2035 | 2035 | 2035 | 2035-10-02 | Planning | 2028-10-17 | 2032-05-12
2324-R-21 | Short Circuit Mitigation for Miguel 230 kV Circuit Breakers | SDG&E | 2023-2024 | 2035 | [11 empty] | 2035 | 2035 | 2035 | 2028-02-21 | Design | Exempt | 2027-05-11
1213-R-32 | Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-11-01 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-11-14 | 2027-11-14 | 2027-11-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2026-07-16 | 2026-07-21 | 2027-03-15 | Design | TBD | 2025-10-15 | In construction
1415-R-07 | TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2026-06-01 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-06-08 | 2026-06-08 | 2026-07-29 | 2026-08-10 | 2026-10-12 | 2026-12-21 | 2027-05-11 | 2027-03-31 | 2027-02-25 | 2027-02-15 | Design | 2025-05-23 | 2025-09-02 | In construction and on schedule.
1314-R-24 | TL690E Stuart Tap-Las Pulgas 69 kV Sections Re-Conductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-11-01 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2026-11-10 | 2026-11-10 | 2026-12-09 | 2028-03-23 | 2028-03-16 | 2028-07-01 | 2028-05-03 | 2028-12-20 | 2029-06-08 | 2029-07-23 | Design | Exempt | 2028-07-18
1112-R-27 | TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 2016 | 2023-04-01 | 2023-02-01 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2023-02-13 | 2023-02-13 | 2026-02-24 | 2026-08-05 | 2026-08-01 | 2026-12-16 | 2027-05-12 | 2028-01-27 | 2028-01-26 | 2028-05-16 | Design | 2016-03-22 | 2026-08-12
2223-P-19 | Upgrade on Hoodoo Wash-North Gila and Hassayampa-North Gila Transmission Lines | SDG&E | 2022-2023 | 2032 |  | 2032 | [12 empty] | 2032-05-01 | Planning | N/A |  | Construction managed by APS
2223-P-20 | Upgrade TL13820 Sycamore-Chicarita 138 kV | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2031-09-01 | Planning | Exempt | 2028-02-01
2324-R-19 | Valley Center System Improvement | SDG&E | 2023-2024 | 2028 | [11 empty] | 2028 | 2028 | 2030 | 2031-01-22 | Planning | 2026-12-26 | 2030-01-22 | Initiated design - schedule dependent on long lead permitting requirements which are yet to be determined.

## VEA_GLW
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Current In-Service Jan 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
2223-P-02 | Beatty 230 kV Project | VEA/GLW | 2022-2023 | 2027-12-31 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2028-05-31 | 2028-05-31 | Permitting, engineering and design | N/A | 2026-06-01 | Project's targeted In-Service date is Dec-27; project is on schedule.
2122-P-01 | GLW/VEA Area Upgrades - revised scope | VEA/GLW | 2021-2022 (revised scope 2022-2023) | TBD |  | N/A | TBD | TBD | TBD | TBD | TBD | 2027-12-31 | 2027-12-31 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | 2028-06-28 | 2028-06-28 | Permitting, engineering and design | N/A | 2026-06-01 | BLM delays have pushed ISD into 2028. Trout Canyon-Sloan Canyon 500kV is still being prioritized. Project is in final stages of BLM permitting for both 500kV and 230kV options.
1718-R-11 | Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 |  | 2023-06-23 | 2023-09-23 | 2023-12-23 | 2023-12-23 | Q1/Q2-2024 | Q4/2024 | Q2/2025 | Q3/2025 | 2026-09-30 | In Flight | N/A | Sept-21 | Waiting on AT&T WISP network construction.

## LSPower
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Current In-Service Jan 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
1819-R-03 | Gates 500 kV Dynamic Voltage Support (Orchard Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-03-25 | In-Service | In-Service | 2021-02-19 | 2023-04-01 | In-Service
2324-P-01 | Collinsville 230kV Reactor Project | LS Power | 2023-2024 | 2028 | [10 empty] | 2028-06-01 | 2028-06-01 | 2028-05-01 | 2028-12-28 | Permitting | N/A | 2026
2122-P-03 | Collinsville 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-05-01 | 2028-12-28 | Permitting | Q3 2024 | 2026 | CPCN filed
2122-P-04 | Manning 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Permitting | 2024-06-28 | 2026 | CPCN Approved
1819-R-08 | Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TBD | TBD | TBD | 2026-03-26 | 2026-05-26 | Construction | 2022-04-06 | 2024-03-25 | Construction in progress
2122-R-11 | San Jose Area HVDC 230 kV Line (Newark - NRS) | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-05-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Permitting | 2024-05-17 | 2026 | CPCN filed
2122-R-10 | San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-04-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | Permitting | 2024-04-29 | 2026 | CPCN filed
2223-P-22 | SWIP-North 500kV Transmission Project | GBT | 2022-2023 | 2027 | [6 empty] | 2028-05-01: 2028-05-01; 2028-05-01: 2028-05-01; 2028-05-01: 2028-05-01 | Permitting | N/A | 2026
* LSPGC is LS Power Grid California, LLC, an LS Power affiliate that became a PTO on 3/12/25.
GBT is Great Basin Transmission, LLC, an LS Power affiliate that is the selected Project Sponsor for SWIP-North and is approved to become a PTO at energization.

## Lotus
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Current In-Service Jan 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
2223-P-12 | North of Songs-Sorreno 500 kV Line | Lotus Infrastructure Global Operations | 2024 | 2032-01-01 | 2034-07-01 | 2032-01-01 | 2032-01-01 | 2032-01-01 |  | In development | Q3-Q4 2025 | August 2028 Note 1 | The Project team has filed interconnection applications with the PTO's on both terminus' of the line. The team has prepared a draft SOW for the environmental permitting process and is reviewing the proposals from environmental consultants for routing of the line between North of SONGS and Serrano substations. Please note that a portion of the route differs from that proposed by the Lotus Partners team. The team is expected to have a pre-filing meeting with CPUC in Q2 2025. The in-service date for this line is dependent upon depend on certain external factors including the in-service date of HORIZON's proposed North of SONGS substation. The team will adjust the Project Schedule and the in-service date to align with HORIZON's schedule to ensure that the North of SONGS - Serrano line is completed in the most efficient and cost effective manner.
Note 1 - The August 2028 listed here is the expected date for start of pre-construction activities for the Project. This date will be adjusted to align the Project Schedule with the in-service date for the proposed North of SONGS substation.

## HWT
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Current In-Service Jan 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
2223-P-11 | North Gila–Imperial Valley 500 kV line | HWT | 2022-2023 | 2032-06-01 | 2032-06-01 | N/A | 2031-12-31 | 2031-12-31 | 2031-12-31 | Permitting, engineering and design | 2025-09-02 | 2030-07-15
2223-P-08 | IV-North of Songs 500 kV line and North of Songs Substation | HWT | 2022-2023 | 2034-06-01 | 2034-06-01 | N/A | 2032-10-19 | 2032-10-31 | 2032-10-31 | Permitting, engineering and design | 2026-10-02 | 2030-12-23

## CalGrid
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Current In-Service Jan 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
2324-P-03 | Humboldt 500 kV Substation with 500 kV line to Collinsville [HVDC operated as AC] | CalGrid | 2023-2024 | 2034-06-01 | N/A | N/A | N/A | N/A | 2034-06-01 | Initial Development Activities | Q3 2027 | 2031
2324-P-04 | Humboldt to Fern Road 500 kV Line | CalGrid | 2023-2024 | 2034-06-01 | N/A | N/A | N/A | N/A | 2034-06-01 | Initial Development Activities | Q3 2027 | 2031

## CitizensEnergy
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
1718-E-02 | IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | Completed |  | 2023-07-21

## DCRT
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Current In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
1314-E-01 | Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-24 | 2024-04-01 | 2024-04-24 | 2024-04-24 | 2024-05-24 | 2024-06-07 | 2024-06-07 | In-Service | Approved | 2022-10-22 | Energized 6/7/2024