## PGaE
Project | PTO | Transmission Plan Approved | In-service Year at Approval in Transmission Plan | Expected In-Service Year (2020-2021 Transmission Plan) | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service Jul 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Expected In-Service July 2025 TDF | Project Status | Expected CPUC Filing | Expected Const start | Notes
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026-01-01 | 2026-12-31 | N/A | 2026-01-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-12-01 | 2027-12-01 | 2029-11-15 | 2027-04-23 | N/A | Cancelled | N/A | N/A | Q3-2025: Rescoped in 2023-24 CAISO Transmission Plan to Atlantic High Voltage Mitigation
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026-01-01 | 2026-12-31 | N/A | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-18 | 2025-04-22 | 2025-04-07 | In-Service | N/A | 2025-04-02 | Q3-2025: In-service
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015-12-01 | 2022-11-01 | 2022-11-01 | 2023-03-15 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 Approved | 2022-09-22 | Q3-2025: In-service
Dinuba Energy Storage (Rescoped from Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017-05-01 | 2025-12-01 | 2025-12-25 | 2025-08-14 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2026-09-29 | 2026-09-29 | N/A | N/A | N/A | Cancelled | N/A | N/A | Q3-2025: Cancelled per CAISO 2023-24 Transmission Plan.
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015-03-01 | 2022-12-01 | 2022-12-23 | 2023-03-10 | 2023-05-31 | 2023-05-31 | 2023-12-29 | 2023-12-29 | 2023-12-29 | 2023-12-29 | 2024-03-18 | 2023-10-31 | 2023-10-31 | 2023-10-31 | In-Service | NOC: AL 5872-E/AL 6709-E Approved | 2021-06-01 | Q3-2025: In-service
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025-07-16 | 2025-03-01 | 2025-03-28 | 2024-06-03 | 2024-04-30 | 2024-04-30 | 2024-07-12 | 2024-08-30 | 2024-12-04 | 2024-09-30 | 2025-01-01 | 2025-01-25 | 2025-03-25 | 2025-03-25 | In-Service | N/A | 2023-04-03 | Q3-2025: In-service
Giffen Line Reconductoring Project | PG&E | 2018-2019 | TBD | 2023-01-19 | 2023-01-13 | 2023-01-19 | 2023-01-11 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2023-12-29 | 2023-12-29 | 2023-12-21 | 2023-12-21 | 2023-12-21 | 2023-12-21 | In-Service | NOC: AL 6600-E Approved | 2023-11-01 | Q3-2025: In-service
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018-03-01 | 2022-12-01 | 2022-12-21 | 2022-12-12 | 2022-10-19 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-16 | 2024-05-30 | 2024-05-30 | 2024-03-28 | 2024-03-28 | 2024-03-28 | In-Service | N/A | 2020-04-30 | Q3-2025: In-service
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023-12-31 | 2027-06-01 | 2027-06-28 | 2025-11-12 | 2026-04-09 | 2026-08-07 | 2026-10-02 | 2023-11-22 | 2023-12-19 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | In-Service | N/A | 2023-09-21 | Q3-2025: In-service
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024-12-31 | 2027-06-01 | 2027-06-28 | 2026-01-14 | 2026-06-19 | 2026-10-19 | 2025-01-15 | 2025-01-31 | 2025-02-20 | 2025-01-06 | 2025-06-20 | 2025-06-20 | 2024-12-23 | 2024-12-23 | In-Service | NOC: AL 7359-E Approved | 2024-12-09 | Q3-2025: In-service
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013-05-01 | 2025-05-01 | N/A | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | In-Service | N/A | 2018-10-16 | Q3-2025: In-service
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013-05-01 | 2025-12-01 | 2023-09-22 | 2023-11-06 | 2024-03-07 | 2024-03-20 | 2024-06-20 | 2024-10-25 | 2024-10-16 | 2026-03-25 | 2026-03-25 | 2024-11-24 | 2025-05-05 | 2025-04-07 | In-Service | N/A | 2024-08-22 | Q3-2025: In-service
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019-12-01 | On Hold | N/A | 2029-12-04 | 2029-12-04 | 2029-12-04 | 2029-08-28 | 2032-10-21 | 2032-10-21 | 2029-12-04 | N/A | N/A | N/A | N/A | Cancelled | N/A | N/A | Q3-2025: Cancelled per CAISO 2022-23 Transmission Plan.
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 | TBD | 2023-03-01 | 2023-03-04 | 2023-05-19 | 2023-07-18 | 2023-11-21 | 2023-10-30 | 2025-04-01 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-07-29 | 2025-06-24 | 2025-06-27 | In-Service | N/A | 2021-11-16 | Q3-2025: In-service
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 | TBD | 2023-03-01 | N/A | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | In-Service | N/A | 2021-08-03 | Q3-2025: In-service
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023-12-31 | 2022-07-01 | 2022-07-06 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | In-Service | N/A | 2021-07-01 | Q3-2025: In-service
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021-05-01 | 2023-03-01 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2022-12-30 | 2024-05-31 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-04-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 | In-Service | NOC: AL 5390-E Approved | 2022-01-17 | Q3-2025: In-service
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019-02-01 | 2023-01-01 | 2023-01-13 | 2023-01-16 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 Approved | 2022-09-22 | Q3-2025: In-service
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019-12-31 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-06-01 | 2025-06-01 | 2026-12-22 | 2028-06-13 | N/A | Cancelled | N/A | N/A | Q3-2025: Cancelled per CAISO 2024-25 Transmission Plan.
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009-05-01 | 2024-04-01 | 2024-04-30 | 2024-06-30 | 2024-04-30 | 2025-04-17 | 2025-12-31 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2026-04-06 | 2025-05-21 | 2025-05-21 | 2025-04-30 | In-Service | N/A | 2022-07-05 | Q3-2025: In-service
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-12-01 | 2027-12-01 | TBD | N/A | N/A | Cancelled | N/A | N/A | Q3-2025: Rescoped in 2023-24 CAISO Transmission Plan to Salinas Area Reinforcement
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS C - D | PG&E | 2018-2019 | 2023-12-31 | 2023-08-01 | 2023-10-31 | 2023-10-27 | 2023-09-28 | 2023-11-29 | 2023-12-19 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-04-18 | 2024-03-25 | 2024-03-25 | 2024-03-25 | In-Service | N/A | 2023-06-15 | Q3-2025: In-service
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E | 2018-2019 | 2023-12-31 | 2023-08-01 | 2023-10-31 | 2023-04-05 | 2023-03-28 | 2023-05-01 | 2023-06-13 | 2023-07-27 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | In-Service | N/A | 2022-04-19 | Q3-2025: In-service
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | N/A | N/A | N/A | N/A | N/A | Cancelled | N/A | N/A | Q3-2025: Project no longer needed. Tulucay-Napa #2 60 kV Line Capacity Increase project approved in 2020: this project would upgrade line terminals in Tulucay and Basalt subs. PG&E discovered that with records update, it was found the substation equipment already met ampacity requirement.
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023-12-01 | 2026-07-01 | 2022-08-31 | 2022-07-29 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | In-Service | N/A | 2021-07-26 | Q3-2025: In-service
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017-12-31 | 2024-12-01 | 2024-12-27 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-05-31 | 2024-04-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | In-Service | NOC: AL 6047-E Approved | 2022-06-01 | Q3-2025: In-service
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020-12-31 | 2022-03-01 | 2022-03-01 | 2022-12-14 | 2022-12-14 | 2024-02-23 | 2023-12-19 | 2023-11-27 | 2023-11-28 | 2023-12-22 | 2023-12-18 | 2023-12-18 | 2023-12-18 | 2023-12-18 | In-Service | NOC: AL 5293-E Approved | 2021-01-05 | Q3-2025: In-service
Ames Distribution – Palo Alto 115 kV transmission line | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: New Addition
Atlantic High Voltage Mitigation | PG&E | 2023-2024 | 2029-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-04-23 | 2028-04-05 | In-Flight | TBD | 2027-11-02 | Q3-2025: Project ISD delayed due to project being rescoped in 2023-24 CAISO Transmission Planning Process
Banta 60 kV Bus Voltage Conversion | PG&E | 2022-2023 | 2024-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2028-03-30 | 2027-12-10 | 2027-12-10 | In-Flight | N/A | 2024-10-28 | Q3-2025: No date changes at this time
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025-07-17 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2026-04-01 | 2026-04-01 | 2028-04-13 | 2028-05-30 | 2028-05-30 | In-Flight | TBD | 2026-11-20 | Q3-2025: No date changes at this time
Borden-Storey 230 kV 1 and 2 Line Reconductoring | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2029-05-01 | 2029-05-01 | 2030-05-01 | 2030-04-12 | 2029-05-08 | In-Flight | TBD | 2028-01-27 | Q3-2025: Project ISD improved due to Schedule/construction sequencing date adjustments
Camden 70 kV Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: No date changes at this time
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014-03-01 | 2023-12-01 | 2023-12-29 | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2025-07-11 | 2025-07-11 | 2025-06-13 | 2025-12-15 | 2025-12-15 | In-Flight | N/A | 2019-07-09 | Q3-2025: No date changes at this time
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-02-01 | 2028-02-01 | 2028-02-01 | 2028-02-01 | Initiating | NOC - TBD on Filing Date | 2027-01-01 | Q3-2025: No date changes at this time
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012-03-01 | 2027-02-01 | 2027-02-01 | 2027-02-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-07-01 | 2029-07-01 | 2029-07-01 | 2030-10-07 | 2030-10-07 | In-Flight | PTC - TBD on Filing Date | 2027-07-23 | Q3-2025: No date changes at this time
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022-05-01 | 2029-06-01 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2030-09-06 | 2031-09-05 | In flight | TBD | 2029-06-15 | Q3-2025: Project ISD delayed due to project development, resulting in a delay in initiation
Collinsville 230 kV Reactor | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-05-01 | N/A | N/A | N/A | N/A | Q3-2025: LS Power project
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025-05-01 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-27 | 2025-09-15 | 2026-01-21 | In-Flight | N/A | 2024-12-06 | Q3-2025: Project ISD delayed due to schedule/clearance date adjustments for Phase 2. Phase 1 completed 5/30/25: two relocated line terminations/CB410/CB520/CCVTs/Switches/Protection Upgrades/two control enclosures and associated equipment.
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-13 | 2030-04-05 | In-Flight | TBD | 2027-01-04 | Q3-2025: Project ISD delayed due to long lead time for substation equipment
Cortina #1 60 kV Line Reconductoring | PG&E | 2023-2024 | 2028-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2028-02-28 | In-Flight | NOC - Expected 2026 Q3 | 2026-06-30 | Q3-2025: Schedule/construction sequencing date adjustments.
Cortina #3 60 kV Reconductoring | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-05-01 | Initiating | TBD | 2030-05-01 | Q3-2025: New Addition
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-01 | 2028-06-01 | 2027-09-21 | 2027-10-13 | In-Flight | TBD | 2026-09-10 | Q3-2025: Schedule/construction sequencing date adjustments.
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022-12-31 | 2025-10-01 | 2025-10-02 | 2025-03-31 | 2024-12-24 | 2026-02-26 | 2026-02-26 | 2026-03-25 | 2025-11-12 | 2026-10-05 | 2026-06-19 | 2027-01-25 | 2028-02-24 | 2028-03-29 | In-Flight | N/A | 2027-06-22 | Q3-2025: Schedule/construction sequencing date adjustments.
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019-11-01 | 2024-10-01 | 2024-10-02 | 2025-03-31 | 2025-02-14 | 2025-05-15 | 2025-08-11 | 2025-07-18 | 2025-11-19 | 2026-10-20 | 2026-10-20 | 2027-12-31 | 2028-10-20 | 2028-05-09 | In-Flight | N/A | 2026-05-20 | Q3-2025: Project ISD improved due to Schedule/construction sequencing date adjustments.
Covelo 60 kV Voltage Support | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: No date changes at this time
Crazy Horse Canyon - Salinas - Soledad #1 and #2 115 kV Line Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: No date changes at this time
Diablo Canyon Area 230 kV High Voltage Mitigation | PG&E | 2023-2024 | 2027-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-07-25 | 2028-10-10 | In-Flight | TBD | 2026-10-19 | Q3-2025: Schedule/construction sequencing date adjustments.
Eagle Rock-Fulton-Silverado 115 kV Line Reconductor | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: New Addition
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022-12-31 | 2027-10-01 | 2027-11-10 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2033-02-02 | 2029-07-17 | Initiating | TBD | 2027-12-03 | Q3-2025: Project ISD improved due to recalibration in PG&E's work portfolio. Project has not kicked off yet.
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024-12-31 | 2026-12-01 | 2026-12-31 | 2026-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2027-06-30 | 2027-05-06 | 2027-07-07 | In-Flight | TBD | 2027-03-10 | Q3-2025: Schedule/construction sequencing date adjustments.
Equipment Upgrade at CCSF Owned Warnerville 230 kV Substation | PG&E | 2022-2023 | 2024-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2027-01-01 | Initiating | N/A | 2026-08-01 | Q3-2025: The Warnerville upgrade has not been completed yet. The 2023 in-service date reflects the work completed at Warnerville as part of T.0000043 Bellota-Warnerville 230kV Reinforcement. This scope, however, is not the same scope as Equipment Upgrade at CCSF Owned Warnerville 230 kV Substation. The breaker and bus are being upgraded by CCSF. These facilities cause the Bellota-Warnerville 230 kv to have a limited rating of 1200Amps.
Estrella Substation Project | PG&E | 2013-2014 | 2019-05-01 | 2026-05-01 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | 2029-07-16 | 2029-11-01 | 2029-07-05 | 2029-07-03 | 2029-03-30 | 2029-03-30 | In-Flight | PTC: A.17-01-023 Approved | 2025-11-03 | Q3-2025: No date changes at this time
French Camp Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: No date changes at this time
Garberville Area Reinforcement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2030-12-31 | 2030-12-31 | 2029-11-21 | 2027-12-28 | 2028-08-28 | In-Flight | NOC - TBD on Filing Date | 2027-03-31 | Q3-2025: Project ISD delayed due to advanced conductor study, and how to install fiber for protection need
Gates 230/70 kV Transformer Addition | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: No date changes at this time
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022-12-31 | 2028-06-01 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2030-04-12 | 2029-06-22 | 2030-01-07 | In-Flight | TBD | 2028-10-05 | Q3-2025: Project ISD delayed due to updated LLM delivery schedule
Gold Hill-El Dorado Reinforcement | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q3-2025: New Addition
Greater Bay Area 500 kV Transmission Reinforcement | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: New Addition
Henrietta 230/115 kV Bank 3 Replacement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2027-06-01 | 2027-06-01 | 2028-07-21 | 2028-07-12 | 2028-10-02 | In-Flight | TBD | 2026-09-28 | Q3-2025: Schedule/construction sequencing date adjustments.
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021-01-01 | 2026-12-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-12-31 | 2028-02-22 | In-Flight | NOC - TBD on Filing Date | 2027-05-20 | Q3-2025: Schedule/construction sequencing date adjustments.
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-06-26 | 2028-02-10 | 2029-01-03 | In-Flight | NOC - TBD on Filing Date | 2027-04-30 | Q3-2025: Project ISD delayed due to RFP process & creation and execution of engineering contract, Substation & Distribution related study
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022-12-31 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-10-12 | 2026-11-06 | 2028-06-13 | In-Flight | TBD | 2026-11-05 | Q3-2025: Project ISD delayed due to LLM will not be received until November 2027. This CB is being taken/swap from Los Banos project.
Jefferson-Stanford 60 kV Recabling | PG&E | 2024-2025 | 2029-05-01 | 2026-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-05-01 | Initiating | TBD | 2028-05-01 | Q3-2025: New Addition
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016-03-01 | 2027-08-01 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2029-08-10 | 2029-08-10 | 2030-12-31 | 2029-08-10 | 2029-08-10 | In flight | NOC - TBD on Filing Date | 2027-01-08 | Q3-2025: No date changes at this time
Konocti – Eagle Rock 60 kV Line Reconductoring | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: New Addition
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | NOC - TBD on Filing Date | 2027-10-01 | Q3-2025: No date changes at this time
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017-03-01 | 2027-06-01 | 2027-06-21 | 2028-12-29 | 2029-01-01 | 2029-01-01 | 2029-01-01 | 2029-01-11 | 2029-01-11 | 2029-06-08 | 2029-12-25 | 2029-12-10 | 2029-12-10 | 2029-12-10 | In-Flight | CPCN: A.23-09-001 Filed & Under Review | 2028-07-06 | Q3-2025: No date changes at this time
Lone Tree–Cayetano–Newark Corridor Series Compensation | PG&E | 2022-2023 | 2027-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-02 | 2027-10-13 | In-Flight | TBD | 2027-05-28 | Q3-2025: Schedule/construction sequencing date adjustments.
Los Banos 230 kV Circuit Breakers Replacement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2029-12-04 | In-Flight | N/A | 2027-06-03 | Q3-2025: Project ISD delayed due to dependency on WRO New SS for Los Banos-Panoche 230kV. This project plans to build a new switching station (which will turn into a substation later) and loop the sub into the existing Los Banos - Dos Amigos line. At Los Banos sub, the 230kV CBs will be relocated to the new BAAH bay, existing line protection is power line carrier which will be replaced with new line differential protection. PG&E cannot do any line relay upgrade without remote end being built. This project still needs to aquire land for the switching station.
Los Banos 70 kV Area Reinforcement | PG&E | 2022-2023 | 2029-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2030-09-12 | 2030-08-27 | Initiating | TBD | 2028-08-07 | Q3-2025: Schedule/construction sequencing date adjustments.
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028-05-01 | 2028-12-31 | N/A | 2028-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-05-31 | 2029-02-02 | 2029-10-09 | 2029-10-09 | 2029-07-13 | In-Flight | TBD | 2026-09-01 | Q3-2025: Schedule/construction sequencing date adjustments. Dates for this project will continue to improve as incremental scope is driving the expected in-service of the entire T.dot.
Maple Creek Reactive Support | PG&E | 2009 | 2011-03-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-10-01 | 2027-10-01 | 2027-10-01 | 2027-11-22 | In-Flight | TBD | 2027-07-09 | Q3-2025: Schedule/construction sequencing date adjustments.
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021-12-01 | 2024-05-01 | 2024-05-24 | 2024-05-10 | 2024-05-24 | 2025-11-14 | 2025-11-13 | 2025-11-13 | 2026-04-23 | 2027-02-12 | 2028-10-13 | 2029-12-18 | 2029-10-17 | 2029-11-28 | In-Flight | CPCN: A.17-12-021 Approved | 2027-05-14 | Q3-2025: Schedule/construction sequencing date adjustments.
Martin-Millbrae 60 kV Area Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-02-07 | Initiating | TBD | 2029-09-13 | Q3-2025: Schedule/construction sequencing date adjustments.
Mesa 230/115kV Spare Transformer | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-05-01 | 2028-04-01 | 2028-04-01 | 2029-04-01 | 2029-03-14 | 2029-08-23 | In-Flight | TBD | 2027-12-02 | Q3-2025: Project ISD delayed due to scope development study. Transmission Planning evaluated options to either proceed with a temporary transformer connection or invest in a more permanent solution involving a new 230kV breaker bay. Planning has opted to pursue the permanent solution. Final decisions are still being made, with next steps dependent on system requirements, cost, and constructability.
Metcalf 230 / 115 kV Transformers Circuit Breaker Addition | PG&E | 2022-2023 | 2026-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2027-06-01 | 2027-06-01 | 2026-09-01 | 2027-06-23 | 2027-07-27 | In-Flight | TBD | 2027-04-02 | Q3-2025: Schedule/construction sequencing date adjustments.
Metcalf Substation 500/230 kV Transformer Bank Addition | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: New Addition
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008-12-31 | 2029-04-01 | 2029-04-01 | 2029-04-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-03-01 | 2027-03-01 | 2028-05-12 | 2030-04-04 | In-Flight | NOC - TBD on Filing Date | 2027-12-16 | Q3-2025: Project ISD delayed due to changes in project scope in 2024-2025 CAISO Transmission Planning Process. Added reconductoring of McKee-Piercy 115kV line to scope. Project undergoing design changes, project charter, and Gate Review Board process due to scope change.
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019-05-01 | 2024-06-01 | 2024-06-06 | 2025-07-03 | 2026-06-23 | 2026-06-23 | 2027-04-07 | 2027-04-07 | 2027-04-07 | 2027-04-29 | 2027-04-29 | 2028-12-31 | 2028-06-14 | 2028-06-14 | In flight | NOC: AL 5026-E Approved | 2018-11-01 | Q3-2025: No date changes at this time
Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019-05-01 | 2024-06-01 | 2024-06-06 | 2027-06-03 | 2027-09-01 | 2027-11-30 | 2028-02-25 | 2028-05-23 | 2028-08-21 | 2027-10-28 | 2028-01-24 | 2030-05-28 | 2030-09-30 | 2032-01-07 | In flight | NOC: AL 5924-E Approved | 2026-04-27 | Q3-2025: Project ISD delayed due to PG&E assessing and confirming need for project
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-08-29 | 2025-08-29 | 2027-10-08 | 2030-08-22 | 2030-08-22 | 2030-02-01 | In-Flight | N/A | 2021-04-07 | Q3-2025: Project ISD improved due to recalibration in PG&E's work portfolio.
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018-05-01 | 2027-10-01 | 2027-10-20 | 2028-02-16 | 2028-05-16 | 2028-08-14 | 2028-11-09 | 2029-02-05 | 2029-04-06 | 2029-08-01 | 2029-10-26 | 2030-07-16 | 2029-02-15 | 2028-12-26 | In-Flight | NOC - TBD on Filing Date | 2027-09-27 | Q3-2025: Schedule/construction sequencing date adjustments.
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016-05-01 | 2024-08-01 | 2024-08-06 | 2024-07-17 | 2024-05-08 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-01 | 2025-08-07 | 2025-08-07 | 2025-09-23 | 2026-03-06 | 2026-03-04 | In-Flight | N/A | 2021-08-17 | Q3-2025: Schedule/construction sequencing date adjustments.
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-05-01 | Initiating | N/A | 2028-05-01 | Q3-2025: Project ISD delayed due to recalibration in PG&E's work portfolio. Project has not kicked off yet.
Moraga 230/115 kV Transformer Bank Addition | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-05-01 | Initiating | TBD | 2030-05-01 | Q3-2025: New Addition
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023-12-31 | On Hold | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | On-Hold (CAISO) | TBD | TBD | Q3-2025: Project on CAISO Hold.
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021-12-01 | 2026-04-01 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2027-09-29 | 2027-09-29 | 2027-09-29 | 2029-01-30 | 2029-02-27 | 2028-12-28 | 2029-01-22 | 2028-12-26 | In-Flight | TBD | 2027-04-27 | Q3-2025: Schedule/construction sequencing date adjustments.
Mosher Transmission Project | PG&E | 2013-2014 | 2017-12-01 | 2027-12-01 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2028-02-17 | 2028-11-17 | In flight | NOC - TBD on Filing Date | 2027-03-11 | Q3-2025: Project ISD delayed due to recalibration in PG&E's work portfolio. Project kicked off in July 2025
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026-01-01 | 2026-12-31 | N/A | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2028-04-01 | 2028-04-01 | 2028-09-01 | 2028-09-01 | 2026-12-04 | In-Flight | TBD | 2026-05-22 | Q3-2025: Project ISD improved due to the change in technology. Transmission planning changed their recommendation to use conventional air core reactor which is different from the original SmartValve technology
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2028-05-01 | 2028-05-01 | In-Flight | NOC - TBD on Filing Date | 2027-05-28 | Q3-2025: No date changes at this time
New Helm 230/70 kV Bank #2 | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: New Addition
New Humboldt 115/115 kV Phase Shifter with 115 kV line to Humboldt 115kV Substation | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: No date changes at this time
New Humboldt 500 kV Substation with 500 kV line to Collinsville [HVDC operated as AC] | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: No date changes at this time
New Humboldt to Fern Road 500 kV Line | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: No date changes at this time
New Manning 500 kV substation | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-01 | 2028-04-01 | 2028-04-01 | In-Flight | TBD | 2026-04-23 | Q3-2025: No date changes at this time
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2029-02-20 | 2027-07-13 | In-Flight | TBD | 2027-01-22 | Q3-2025: Project ISD improved due to bundling efficiency with the Newark HVDC project, which will provide the MPAC this project will use
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019-06-01 | 2022-11-01 | 2022-11-01 | 2023-04-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-06-01 | 2025-06-01 | 2025-07-01 | 2027-05-06 | 2027-07-08 | In-Flight | TBD | 2026-07-20 | Q3-2025: Schedule/construction sequencing date adjustments.
North Dublin -Vineyard 230 kV Reconductoring | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2032-05-01 | Q3-2025: No date changes at this time
North East Kern 115 kV Line Reconductoring | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2033-12-31 | 2033-12-31 | 2032-12-31 | 2029-08-20 | 2031-12-01 | In-Flight | TBD | 2027-12-23 | Q3-2025: Project ISD delayed due to recalibration in PG&E's work portfolio. Project kicked off in March 2025
North Oakland Reinforcement Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q3-2025: New Addition
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015-05-01 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2028-02-01 | 2028-02-01 | 2029-02-01 | 2029-02-01 | 2029-02-01 | Initiating | TBD | 2028-01-01 | Q3-2025: No date changes at this time
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2026-12-01 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2028-08-28 | 2028-05-16 | In-Flight | NOC - TBD on Filing Date | 2027-07-07 | Q3-2025: Project ISD improved due to Schedule/construction sequencing date adjustments
Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-28 | 2028-06-01 | 2028-04-28 | 2028-03-31 | 2028-04-26 | In-Flight | TBD | 2026-05-11 | Q3-2025: Schedule/construction sequencing date adjustments.
Pittsburg 115 kV Bus Reactor project | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2028-05-12 | 2028-05-12 | 2028-05-12 | 2028-05-30 | 2028-05-26 | In-Flight | NOC - TBD on Filing Date | 2027-06-29 | Q3-2025: Schedule/construction sequencing date adjustments.
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011-05-01 | 2025-01-01 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2026-06-17 | 2026-06-17 | 2026-09-04 | 2026-06-15 | 2028-05-09 | 2028-09-27 | 2029-01-31 | In-Flight | N/A | 2027-10-01 | Q3-2025: Project ISD delayed due to delay with long lead material delivery.
Pittsburg-Kirker 115 kV Line Section Limiting Elements Upgrade | PG&E | 2024-2025 | 2028-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-05-01 | Initiating | TBD | 2027-05-02 | Q3-2025: New Addition
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-02-02 | 2028-08-16 | 2028-02-01 | 2028-02-29 | In-Flight | TBD | 2026-08-26 | Q3-2025: Schedule/construction sequencing date adjustments.
Reconductor of GWF – Kingsburg 115 kV line | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: New Addition
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-12-31 | In-Flight | TBD | 2029-12-11 | Q3-2025: Project ISD delayed due to scope development study. PG&E evaluated if looping in the Rio Oso-Gold Hill 230kV line into Atlantic as an alternative to reconductoring the Rio Oso-Lincoln 115kV line. PG&E is continuing with original scope
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2025-11-01 | 2025-11-19 | 2026-08-18 | 2026-08-18 | 2030-05-23 | 2031-11-19 | 2029-03-30 | 2028-11-07 | 2028-05-23 | 2029-03-06 | 2029-08-27 | 2029-03-28 | 2028-01-31 | In-Flight | NOC - TBD on Filing Date | 2026-07-09 | Q3-2025: Project ISD improved due to Schedule/construction sequencing date adjustments
Redwood City 115kV System Reinforcement | PG&E | 2022-2023 | 2030-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-12-01 | 2029-12-01 | 2029-12-01 | 2028-07-05 | 2030-03-14 | 2029-02-15 | In-Flight | NOC - TBD on Filing Date | 2028-02-10 | Q3-2025: Project ISD improved due to planning and adjusting to do the Engineering and construction at the same time with South of San Mateo (T.0009639) at the same time
Reedley 70 kV Capacity Increase | PG&E | 2023-2024 | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: No date changes at this time
Rio Oso - W. Sacramento Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2029-09-04 | Initiating | TBD | 2029-01-18 | Q3-2025: Project ISD improved due to recalibration in PG&E's work portfolio. Project kicked off in Feb 2025
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016-05-01 | 2024-10-01 | 2024-10-11 | 2024-10-31 | 2024-08-26 | 2024-12-09 | 2025-05-30 | 2025-06-04 | 2025-06-04 | 2025-06-19 | 2025-09-01 | 2026-05-14 | 2026-05-14 | 2026-10-15 | In-Flight | N/A | 2025-10-01 | Q3-2025: Project ISD delayed due to scope change resulting in project being dependent on the overall Rio Oso Substation Rebuild Project.
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024-12-31 | 2024-05-01 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | 2024-11-21 | 2024-12-31 | 2024-12-31 | TBD | TBD | 2026-03-26 | In-Flight | N/A | 2023-02-15 | Q3-2025: Schedule/construction sequencing date adjustments. Round Mountain & Table Mountain Series Capacitors to be operational in October 2026. This work can/will be completed post-energization of Fern Road.
Salinas Area Reinforcement | PG&E | 2023-2024 | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2032-12-31 | In-Flight | TBD | 2027-06-09 | Q3-2025: Schedule/construction sequencing date adjustments.
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-11-30 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | In-Flight | 851 - TBD on Filing Date | 2026-03-25 | Q3-2025: No date changes at this time
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-04-30 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | In-Flight | NOC: AL 7391-E Filed & Under Review | 2026-09-28 | Q3-2025: No date changes at this time
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) - San Jose B Scope | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-06-28 | In-Flight | TBD | 2028-06-26 | Q3-2025: New Addition. CAISO added San Jose B 230 kV GIS BAAH scope in November 2024. This scope will not deter LS Power from interconnecting.
San Jose B – NRS 230 kV line | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: New Addition
San Mateo 230/115 kV Transformer Bank Addition Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q3-2025: New Addition
San Miguel New 70 kV Line | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q3-2025: New Addition
Santa Rosa 115 kV lines Reconductoring project | PG&E | 2022-2023 | 2028-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-10-31 | 2032-05-21 | 2032-05-21 | In flight | TBD | 2031-09-23 | Q3-2025: No date changes at this time
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023-06-01 | 2023-12-31 | N/A | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-12-23 | 2025-12-23 | 2026-03-03 | 2025-12-30 | 2026-02-10 | In-Flight | TBD | 2025-09-01 | Q3-2025: Schedule/construction sequencing date adjustments.
Sobrante 230 kV Bus Upgrade | PG&E | 2024-2025 | 2033-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2033-05-01 | Initiating | TBD | 2032-05-01 | Q3-2025: New Addition
Sobrante 230/115 kV Transformer Bank Addition | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: No date changes at this time
South Bay Area Limiting Element Upgrade | PG&E | 2022-2023 | 2027-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2026-03-01 | 2026-03-01 | 2025-05-01 | 2026-04-10 | 2026-06-10 | In-Flight | N/A | 2024-06-01 | Q3-2025: Schedule/construction sequencing date adjustments. Metcalf-El Patio #1 115 kV line limited elements upgraded June 2024
South Bay Reinforcement Project | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | Q3-2025: New Addition
South Oakland Reinforcement Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-02 | Q3-2025: New Addition
South of Mesa Upgrade | PG&E | 2018-2019 | 2023-12-31 | 2026-09-01 | 2026-09-03 | 2026-05-26 | 2026-05-26 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-15 | 2027-04-15 | 2031-03-10 | 2029-06-06 | 2029-06-06 | In flight | NOC - TBD on Filing Date | 2027-11-15 | Q3-2025: No date changes at this time
South of San Mateo Capacity Increase | PG&E | 2007 | 2009-05-01 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2028-12-01 | 2028-12-01 | 2027-10-29 | 2028-06-22 | 2029-02-21 | In-Flight | NOC - TBD on Filing Date | 2028-05-03 | Q3-2025: Project ISD delayed due to advanced conductor study and internal land delays to obtain L3 LiDAR data required for all three circuits
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027-01-01 | 2027-12-31 | N/A | 2027-01-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-06-01 | 2028-06-01 | 2026-09-28 | 2027-10-13 | 2029-05-09 | In-Flight | TBD | 2027-05-17 | Q3-2025: Project ISD delayed due to long lead time materials delay
Tejon Area Reinforcement | PG&E | 2023-2024 | 2027-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-08-01 | 2028-08-30 | Initiating | TBD | 2028-06-14 | Q3-2025: Project ISD delayed due to recalibration in PG&E's work portfolio. Project has not kicked off yet.
Tesla - Newark 230 kV Line No. 2 Reconductoring | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-12-29 | In-Flight | TBD | 2029-12-11 | Q3-2025: Project ISD delayed due to recalibration in PG&E's work portfolio. Project kicked off in Feb 2025
Tesla 115 kV Bus Reconfiguration | PG&E | 2022-2023 | 2030-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-12-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | 2028-06-30 | In-Flight | TBD | 2027-06-28 | Q3-2025: Schedule/construction sequencing date adjustments.
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-16 | 2027-08-16 | 2028-02-09 | 2028-02-09 | 2028-12-28 | 2027-12-01 | 2027-12-31 | In-Flight | N/A | 2024-05-13 | Q3-2025: Schedule/construction sequencing date adjustments.
Tulucay-Napa #2 60 kV line Reconductoring project | PG&E | 2022-2023 | 2028-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-12-01 | 2026-12-31 | 2026-12-31 | 2026-12-01 | 2027-07-23 | 2026-12-17 | In-Flight | NOC - Expected 2026 Q2 | 2026-11-06 | Q3-2025: Project ISD improved due to ISD correction back to original ISD reported in July 2024 TDF
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-03-01 | 2027-03-01 | 2027-09-20 | 2027-09-30 | 2028-01-05 | In-Flight | TBD | 2027-09-08 | Q3-2025: Project ISD delayed due to scope development study
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023-12-01 | 2026-07-01 | 2026-07-10 | 2026-08-21 | 2025-08-18 | 2025-12-25 | 2025-12-30 | 2026-02-06 | 2026-02-06 | 2026-04-29 | 2027-04-12 | 2027-04-30 | 2027-04-30 | 2027-04-30 | In-Flight | PTC: A.24-06-008 Filed & Under Review/NOC: AL 7542-E Approved | 2025-10-01 | Q3-2025: No date changes at this time
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019-10-01 | 2027-04-01 | 2027-04-01 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-05-08 | 2025-10-20 | 2025-10-20 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-11-18 | 2027-11-17 | In flight | N/A | 2027-04-20 | Q3-2025: Project ISD delayed due to scope development. The parcel will be at Vaca Dixon and Smart valve needs to be installed at the Parcel in conjunction of other associated equipment.
Vaca-Plainfield 60 kV Line Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | Q3-2025: No date changes at this time
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025-05-01 | 2025-12-31 | N/A | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2026-08-31 | 2026-07-27 | 2026-06-02 | In-Flight | TBD | 2026-03-04 | Q3-2025: Schedule/construction sequencing date adjustments.
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014-05-01 | 2025-06-01 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | 2026-05-29 | 2026-07-31 | 2027-05-06 | 2027-04-23 | 2027-05-10 | 2026-06-03 | In-Flight | PTC: A.18-06-004 Approved | 2024-05-21 | Q3-2025: Project ISD improved due to Schedule/construction sequencing date adjustments
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-05-31 | 2029-02-02 | 2027-12-06 | 2027-04-12 | 2027-05-13 | In-Flight | NOC - Expected 2025 Q3 | 2027-01-06 | Q3-2025: Schedule/construction sequencing date adjustments.
West Fresno 115 kV Voltage Support | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-05-01 | Initiating | TBD | 2030-05-01 | Q3-2025: New Addition
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020-05-01 | On Hold | N/A | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | 2034-03-28 | 2029-05-04 | 2033-12-31 | 2032-12-01 | 2033-07-11 | 2034-05-01 | In-Flight | PTC - Expected 2026 Q1 | 2028-03-01 | Q3-2025: Project ISD delayed due to project team working on the engineering and permitting process (PEA for PTC permit)
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2026-09-01 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2029-08-16 | 2029-12-21 | In-Flight | N/A | 2026-11-24 | Q3-2025: Project ISD delayed due to schedule/construction sequencing date adjustments
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026-12-31 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-02-12 | Initiating | NOC - TBD on Filing Date | 2026-08-20 | Q3-2025: Schedule/construction sequencing date adjustments.

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Expected In-Service July 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-10-01 | 2029-12-01 | 2029-12-01 | Engineering | 2009-09-01 | 2026-06-01 | Alberhill dates contingent on licensing.
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 | N/A | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2026-12-26 | Construction | Exempt | 2024-10-01 | Material delay caused shift in construction start and outage coordination is extending project construction duration.
Antelope-Whirlwind Line Upgrade | SCE | 2022-2023 | 2025 | N/A | New | New | New | New | New | New | Pending | Pending | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-31 | Design | N/A | 2025-12-04 | Project approved by CAISO in May 2023.
Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | Pending | 2026-06-01 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-06-01 | 2026-06-01 | 2027-12-31 | Engineering | Exempt | 2025-08-04 | Change in ISD due to delays in engineering drawings and long lead materials.
Colorado River-Red Bluff 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-02-01 | 2027-12-01 | 2026-12-31 | Preliminary Engineering | Pending | 2026-10-01 | This project has been accelerated to accommodate other TPP work in the region.
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2027-06-01 | 2027-06-01 | 2027-04-13 | Final Engineering | Exempt | 2024-06-01 | Project sequencing and increase in scope has pushed the initial ISD out two years to 2027.
Devers-Red Bluff 500 kV 1 and 2 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 1930-03-01 | 1930-01-01 | 2030-04-30 | Preliminary Engineering | Pending | 2028-10-02 | This project has been deferred to accommodate other TPP work in the region.
Devers-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-04-01 | 2027-12-01 | 2028-04-28 | Preliminary Engineering | Pending | 2027-01-04 | This project has been deferred to accommodate other TPP work in the region.
Inyo 230 kV Shunt Reactor | SCE | 2023-2024 | 2027 | N/A | New | New | New | New | New | New | Pending | N/A | N/A | 2027-12-31 | 2026-12-01 | 2026-09-25 | Engineering Design | Pending | 2026-03-02 | Project is expected to be completed in September 2026 because the estimated delivery date of the circuit breaker is mid-2026.
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | N/A | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | 2024-05-31 | 2024-05-01 | 2024-06-01 | 2024-06-01 | 2025-06-01 | Complete | 2025-04-02 | Construction | Pending | 2024-05-02 | In-Service. Project will be removed in future TDF.
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2012-2013 | 2016 | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2024-12-01 | 2025-05-01 | 2026-06-30 | Construction | 2018-05-01 | 2020-12-01 | The operating date for the ELM Project is being pushed to June 2026 due to the delayed SoCal Gas pipeline mitigation construction.
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2016-2017 | 2018-12-31 | 2023-06-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2026-01-01 | 2027-01-31 | 2027-01-01 | 2025-05-01 | 2025-12-30 | Construction | Exempt | Construction started | Segment 1 projected to be completed by end of July 2025. Segment 2 projected to be completed by end of October 2025.
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-30 | 2025-12-01 | 2026-12-30 | 2029-12-01 | 2029-12-01 | 2031-06-30 | Design | Exempt | 2030-01-01 | Project sequencing and outage constraints has slipped the construction start to 2030.
Lugo-Mohave series capacitor upgrade | SCE | 2013-2014 | 2016 | 2022-06-01 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2025-04-01 | 2025-05-01 | 2026-06-30 | Construction | 2018-05-01 | 2020-12-01 | The operating date for the ELM Project is being pushed to June 2026 due to the delayed SoCal Gas pipeline mitigation construction.
Lugo-Victor-Kramer Upgrade (1/3) Add 3rd Lugo 500/230 kV Transformer | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | 2028-12-01 | 2029-06-30 | Preliminary Engineering | Exempt | 2028-01-01 | Project sequencing and outage constraints has slipped the construction start to 2028 with a OD in June 2029.
Lugo-Victor-Kramer Upgrade (2/3) Reconductor Lugo–Victor 230 kV No. 1, 2, 3 & 4 lines using HTLS | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | 2028-05-01 | 2026-12-20 | Design | Pending | 2025-10-01 | This project has been accelerated to avoid outage conflicts with other work in the region.
Lugo-Victor-Kramer Upgrade (3/3) Rebuild/build Kramer–Victor 115 kV lines to 230 kV and Loop the old segment of Kramer–Victor 115 kV into Roadway | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | Pending | 2033-06-30 | 1933-06-01 | 1933-06-01 | 2032-12-01 | Initiation | 2028-06-01 | 2030-07-01 | The project is now projected to be in service 6 months earlier than originally identified in the CAISO Transmission Plan.
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | TBD | 2029-10-01 | 2029-10-01 | 2029-10-01 | Construction | 2028-06-01 | 2029-10-01 | Project released from hold and SCE working on construction start in June 2025.
Mira Loma 500 kV CB Upgrade Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2028-12-01 | 2028-08-14 | 2028-12-01 | 2028-12-01 | 2028-08-14 | Design | Exempt | 2028-05-01 | Expected CB delivery is May 2028. Outage restrictions unkown, pushing completion to years end.
Mira Loma-Mesa Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Engineering | Pending | 2026-03-01 | While the "Expected In-Service Date" has not changed, the "Expected Construction Start Date" should be March 2026.
New CoolwaterA 115/230 kV Bank | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2027-12-10 | 2027-12-10 | 2027-12-01 | 2027-04-01 | 2028-06-02 | Preliminary Engineering | Exempt | 2026-08-03 | Pending GO131D review; potential scope decrease; engineering evaluating.
New Serrano 4AA Bank & 230kV GIS Rebuild | SCE | 2022-2023 | 2027 | N/A | New | New | New | New | New | New | Pending | Pending | 2027-12-30 | 2027-12-01 | 2027-12-01 | 2033-05-24 | Engineering | Exempt | 2027-05-29 | Material lead times from the GIS switchgear vendor pushing out the projected ISD.
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2019-2020 | 2023-06-01 | 2023-05-01 | 2023-06-23 | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-25 | 2027-10-31 | 2027-10-31 | 2027-10-01 | 2029-06-01 | 2029-06-01 | Construction | Exempt | 2024-10-31 | Joint SCE/LADWP project. ISD for SCE’s portion of the project is complete. ISD for LADWP portion of the project at Sylmar Substation is June 2029.
San Bernardino-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 1931-04-01 | 2029-03-01 | 2028-04-28 | Preliminary Engineering | Pending | 2027-10-01 | This project has been accelerated to accommodate other TPP work in the region.
San Bernardino-Vista 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2029-12-01 | 2029-03-01 | 2027-04-30 | Preliminary Engineering | Pending | 2027-02-01 | This project has been accelerated to accommodate other TPP work in the region.
Serrano-Alberhill-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-12-01 | 2027-12-01 | 2031-06-01 | Engineering | Exempt | 2027-03-15 | Material lead time from EPC (Engineering, Procurement, and Construction) contractor is pushing out projected OD.
Serrano–Del Amo–Mesa 500 kV Transmission Reinforcement | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | 2033-12-31 | 2033-12-31 | 1933-12-01 | 2033-12-01 | 2033-12-01 | Licensing | 2027-02-01 | 2031-01-01 | No change ISD from January 2025 TDF.
Sylmar Transformer Replacement | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | 2026-12-01 | 2028-01-07 | Engineering | Exempt | No Construction. Procurement only | Transformer delivery date has been delayed.
Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 44531 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2024-02-28 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-09-01 | Pending | 2025-12-31 | Construction | N/A | In progress | Construction reopened due identfication of additional scope, network updates.
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | Pending | 2025-04-01 | 2025-04-01 | 2025-04-30 | 2025-04-30 | 2025-04-30 | Pending | Pending | 2027-06-01 | Preliminary Engineering | Exempt | 2026-10-01 | In service date of June 2027 pending confirmation on material lead time.
Vista-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 2031-12-01 | 2029-03-01 | 2027-01-29 | Preliminary Engineering | N/A | 2026-10-01 | This project has been accelerated to accommodate other TPP work in the region.
Alamitos 230 kV SCD Upgrade | SCE | 2024-2025 | 2032 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | New | N/A | Pending | Project was approved in May 2025.
Julian Hinds-Mirage 230 kV Advanced Reconductor | SCE | 2024-2025 | 2030 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | New | N/A | Pending | Project was approved in May 2025.
Kramer-Coolwater 115 kV Line Looping into Tortilla 115 kV Substation | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | New | N/A | Pending | Project was approved in May 2025.
Serrano 230 kV SCD GIS Bus Split | SCE | 2024-2025 | 2039 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | New | N/A | Pending | Project was approved in May 2025.
Serrano 500 kV SCD Mitigation | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | New | N/A | Pending | Project was approved in May 2025.
Tortilla 115 kV Capacitor Replacement | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | New | N/A | Pending | Project was approved in May 2025.
Eldorado 230 kV Short Circuit Duty Mitigation Project | SCE | 2023-2024 | 2029 | N/A | New | New | New | New | New | New | New | New | New | Pending | Pending | 2029-12-01 | Engineering | Exempt | Q1-2028 | This project/work is located in Nevada.

## SDGaE
Project | PTO | Transmission Plan Approved | In-Service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Expected In-Service July 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-05-01 | 2023-02-01 | 2022-09-01 | 2022-12-14 | 2022-12-27 | 2023-02-08 | 2023-02-08 | In-Service | In-Service | [5 empty] | Close-out | 2017-11-15 | 2022-01-03
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-06-01 |  | 2022-06-01 | 2022-12-14 | 2022-12-13 | Completed | Completed | In-Service | In-Service | [5 empty] | Close-out | 2016-08-17 | 2020-06-10
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2027-06-01 | 2024-06-01 | 2024-05-02 | 2024-12-23 | 2024-12-23 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-26 | 2024-07-01 | 2024-08-23 | 2024-10-30 | 2024-11-20 | 2024-11-20 | Close-out | Exempt | 2024-01-15
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-12-01 |  | 2023-05-01 | 2021-11-01 | 2021-10-22 | Completed | Completed | In-Service | In-Service | [5 empty] | Close-out | Exempt | 2021-05-17
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2022-11-01 |  | 2023-06-27 | 2023-08-25 | 2023-10-24 | Completed | Completed | In-Service | In-Service | [5 empty] | Close-out | Exempt | 2021-07-26
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2023-05-01 |  | 2023-12-01 | 2024-05-28 | 2024-05-28 | 2024-11-05 | 2024-11-05 | 2025-08-07 | 2024-02-01 | 2023-12-23 | 2023-12-07 |  |  |  | Close-out | 2012-05-18 | 2018-06-29
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-04-01 | 2022-05-01 | 2022-05-02 | 2022-05-31 | 2022-05-15 | 2022-05-15 | 2022-05-15 | In-Service | In-Service | [5 empty] | Close-out | Exempt | 2022-02-04
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2024-12-01 |  |  | 2022-08-24 | 2024-12-17 | 2024-12-17 | 2024-10-18 | 2024-08-07 | 2024-08-07 | 2024-08-20 | 2024-10-30 | 2024-11-27 | 2024-12-16 | Close-out | Exempt | 2024-06-24
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2021-10-01 | 2022-11-01 | 2022-12-01 | 2022-12-09 | 2022-12-27 | 2022-11-18 | 2022-11-18 | In-Service | In-Service | [5 empty] | Close-out | 2017-06-28 | 2021-01-19
3 Ohm Series Reactor on Sycamore-Penasquitos 230 kV line | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2026-10-01 | 2026-06-30 | Construction | Exempt | 2025-06-30
Miguel-Sycamore Canyon (TL23021) 230 kV line Loop-in to Suncrest | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | Planning | TBD | TBD
Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | Planning | TBD | TBD
Reconductor TL680C San Marcos -Melrose Tap | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | Planning | TBD | TBD
SG and OT Redundant Bus Differential Relay | SDG&E | 2022-2023 | 2024 |  | 2024 | [6 empty] | TBD | 2024 | 2024 | 2032 | 2032 | 2025-12-31 | Design | Exempt | TBD
Short Circuit Mitigation for Imperial Valley 230 kV Circuit Breakers Project | SDG&E | 2023-2024 | 2035 | [11 empty] | 2035 | 2035 | 2035 | Planning | TBD | TBD
Short Circuit Mitigation for Miguel 230 kV Circuit Breakers Project | SDG&E | 2023-2024 | 2035 | [11 empty] | 2035 | 2035 | 2035 | Planning | TBD | TBD
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-11-01 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-11-14 | 2027-11-14 | 2027-11-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2026-07-16 | 2026-07-21 | Design | TBD | 2022-11-29
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2029-02-01 |  |  | 2024-08-15 | 2029-02-27 | 2029-02-27 | 2029-04-30 | 2029-09-28 | 2029-12-04 | 1930-02-26 | 2029-07-27 | 2026-11-24 | 2027-04-19 | Design | Exempt | 2027-02-02
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2026-06-01 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-06-08 | 2026-06-08 | 2026-07-29 | 2026-08-10 | 2026-10-12 | 2026-12-21 | 2027-05-11 | 2027-03-31 | 2027-02-25 | Design | 2025-05-23 | 2025-08-29
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-11-01 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2026-11-10 | 2026-11-10 | 2026-12-09 | 2028-03-23 | 2028-03-16 | 2028-07-01 | 2028-05-03 | 2028-12-20 | 2029-06-08 | Design | Exempt | 2028-06-05
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 2016 | 2023-04-01 | 2023-02-01 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2023-02-13 | 2023-02-13 | 2026-02-24 | 2026-08-05 | 2026-08-01 | 2026-12-16 | 2027-05-12 | 2028-01-27 | 2028-01-26 | Design | 2016-04-25 | 2026-04-21
Upgrade TL13820 Sycamore-Chicarita 138 kV | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | Planning | TBD | TBD
Valley Center System Improvement | SDG&E | 2023-2024 | 2028 | [11 empty] | 2028 | 2028 | 2028 | Planning | TBD | TBD

## VEA_GLW
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Current In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Expected In-Service July 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 1905-07-13 | 2021-09-01 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service | In service | In service | [6 empty] | N/A | 2021 | In Service
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 |  | 2023-06-23 | 2023-09-23 | 2023-12-23 | 2023-12-23 | Q1/Q2-2024 | Q4/2024 | Q2/2025 | Q3/2025 | In Flight | N/A | Sept-21 | Waiting on AT&T WISP network construction.
GLW/VEA area upgrades - revised scope | VEA/GLW | 2021-2022 (revised scope 2022-2023) | TBD |  | N/A | TBD | TBD | TBD | TBD | TBD | 2027-12-31 | 2027-12-31 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | 2028-06-28 | Permitting, engineering and design | N/A | 2026-01-01 | BLM delays have pushed ISD into 2028. Trout Canyon-Sloan Canyon 500kV is still being prioritized. Project is in final stages of BLM permitting for both 500kV and 230kV options.
Beatty 230 kV Project | VEA/GLW | 2022-2023 | 2027-12-31 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2028-05-31 | Permitting, engineering and design | N/A | 2026-01-01 | Project's targeted In-Service date is Dec-27; project is on schedule.

## DCRT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-24 | 2024-04-01 | 2024-04-24 | 2024-04-24 | 2024-05-24 | 2024-06-07 | 2024-06-07 | In-Service | Approved | 2022-10-22 | Energized 6/7/2024

## LSPower
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service April 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Expected In-Service July 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support (Orchard Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-03-25 | In-service | 2021-02-19 | 2023-04-01 | In-service
Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TBD | TBD | TBD | 2026-03-26 | Construction | 2022-04-06 | 2024-03-25 | Construction in progress
Collinsville 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-05-01 | Permitting | Q3 2024 | 2026 | CPCN filed
Manning 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-04-01 | 2028-04-01 | Permitting | 2024-06-28 | 2026 | CPCN filed
Metcalf - San José B HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-04-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | Permitting | 2024-04-29 | 2026 | CPCN filed
Newark - NRS 230kV AC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-05-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Permitting | 2024-05-17 | 2026 | CPCN filed
Collinsville 230kV Reactor Project | LS Power | 2023-2024 | 2028 | [10 empty] | 2028-06-01 | 2028-06-01 | 2028-05-01 |  | N/A | 2026
SWIP-North 500kV Transmission Project | GBT | 2022-2023 | 2027 | [11 empty] | 2028-05-01 | 2028-05-01 | Permitting | N/A | 2026
* LSPGC is LS Power Grid California, LLC, an LS Power affiliate that became a PTO on 3/12/25.
GBT is Great Basin Transmission, LLC, an LS Power affiliate that is the selected Project Sponsor for SWIP-North and is approved to become a PTO at energization.

## CitizensEnergy
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | Completed |  | 2023-07-21

## Lotus
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Expected In-Service July 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
North of Songs-Sorreno 500 kV Line | Lotus Infrastructure Global Operations | 2024 | 2032-01-01 | 2034-07-01 | 2032-01-01 | 2032-01-01 | 2032-01-01 | In development | Q3-Q4 2025 | August 2028 Note 1 | The Project team has filed interconnection applications with the PTO's on both terminus' of the line. The team has prepared a draft SOW for the environmental permitting process and is reviewing the proposals from environmental consultants for routing of the line between North of SONGS and Serrano substations. Please note that a portion of the route differs from that proposed by the Lotus Partners team. The team is expected to have a pre-filing meeting with CPUC in Q2 2025. The in-service date for this line is dependent upon depend on certain external factors including the in-service date of HORIZON's proposed North of SONGS substation. The team will adjust the Project Schedule and the in-service date to align with HORIZON's schedule to ensure that the North of SONGS - Serrano line is completed in the most efficient and cost effective manner.
Note 1 - The August 2028 listed here is the expected date for start of pre-construction activities for the Project. This date will be adjusted to align the Project Schedule with the in-service date for the proposed North of SONGS substation.

## HWT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service July 2024 TDF | Expected In-Service Jan 2025 TDF | Expected In-Service July 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
North-Gila 500 kV line | HWT | 2022-2023 | 2032-06-01 | 2032-06-01 | N/A | 2031-12-31 | 2031-12-31 | Permitting, engineering and design | 2025-09-02 | 2030-07-15
IV-North of Songs 500 kV line and North of Songs Substation | HWT | 2022-2023 | 2034-06-01 | 2034-06-01 | N/A | 2032-10-19 | 2032-10-31 | Permitting, engineering and design | 2026-10-02 | 2030-12-23