## PGaE
Project | PTO | Transmission Plan Approved | In-service Year at Approval in Transmission Plan | Expected In-Service Year (2020-2021 Transmission Plan) | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service Jul 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Project Status | Expected CPUC Filing | Expected Const start | Notes
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015 | 2022 | 2022-11-01 | 2023-03-15 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 | 2022-09-22 | In-Service
Dinuba Energy Storage (Rescoped from Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017 | 2025 | 2025-12-25 | 2025-08-14 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | TBD | 2026-09-29 | N/A | Cancelled | N/A | N/A | Cancelled per CAISO 2023-24 Transmission Plan.
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015 | 2022 | 2022-12-23 | 2023-03-10 | 2023-05-31 | 2023-05-31 | 2023-12-29 | 2023-12-29 | 2023-12-29 | 2023-12-29 | 2024-03-18 | 2023-10-31 | In-Service | NOC: AL 5872-E/AL 6709-E | 2021-06-01 | Q3-2024: In-Service. Should have been reported in-service in Q1, future ISD was for EDES: 115KV RECONDUCT FIBER INTERCONNECT
Equipment Upgrade at CCSF Owned Warnerville 230 kV Substation | PG&E | 2022-2023 | 2024 | [6 empty] | N/A | 2024-12-31 | 2023-04-28 | 2023-04-28 | 2023-04-28 | In-Service | N/A | 2023-02-16 | Q3-2024: In-Service. Scope extensions to the previously approved project Bellota-Warrenville 230kV Reinforcement (T.0000043). Approved in 2022-2023 CAISO Transmission Plan.
Giffen Line Reconductoring Project | PG&E | 2018-2019 |  | 2023 | 2023-01-13 | 2023-01-19 | 2023-01-11 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2023-12-29 | 2023-12-29 | 2023-12-21 | 2023-12-21 | In-Service | NOC: AL 6600-E | 2023-11-01 | In-Service
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018 | 2022 | 2022-12-21 | 2022-12-12 | 2022-10-19 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-16 | 2024-05-30 | 2024-05-30 | 2024-03-28 | In-Service | N/A | 2020-04-30 | In-Service
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2027 | 2027-06-28 | 2025-11-12 | 2026-04-09 | 2026-08-07 | 2026-10-02 | 2023-11-22 | 2023-12-19 | 2023-09-25 | 2023-09-25 | 2023-09-25 | In-Service | N/A | 2023-09-21 | In-Service
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013 | 2025 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | In-Service | N/A | 2018-10-16 | In-Service
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019 |  |  | 2029-12-04 | 2029-12-04 | 2029-12-04 | 2029-08-28 | 2032-10-21 | 2032-10-21 | 2029-12-04 | N/A | N/A | Cancelled | N/A | N/A | Cancelled per CAISO 2022-23 Transmission Plan.
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 |  | 2023 |  | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | In-Service | N/A | 2021-08-03 | In-Service
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2022 | 2022-07-06 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | In-Service | N/A | 2021-07-01 | In-Service
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021 | 2023 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2022-12-30 | 2024-05-31 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-04-19 | 2024-04-09 | In-Service | NOC: AL 5390-E | 2022-01-17 | In-Service
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019 | 2023 | 2023-01-13 | 2023-01-16 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 | 2022-09-22 | In-Service
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS C - D | PG&E | 2018-2019 | 2023 | 2023 | 2023-10-31 | 2023-10-27 | 2023-09-28 | 2023-11-29 | 2023-12-19 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-04-18 | 2024-03-25 | In-Service | N/A | 2023-06-15 | In-Service
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E | 2018-2019 | 2023 | 2023 | 2023-10-31 | 2023-04-05 | 2023-03-28 | 2023-05-01 | 2023-06-13 | 2023-07-27 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | In-Service | N/A | 2022-04-19 | In-Service
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023 | 2026 | 2026-12-31 | 2026-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | N/A | N/A | N/A | In-Service | N/A | N/A | Q3-2024: Tulucay-Napa #2 60 kV Line Capacity Increase project approved in 2020: this project would upgrade line terminals in Tulucay and Basalt subs. PG&E discovered that with records update, it was found the substation equipment already met ampacity requirement. So this project is no longer needed.
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023 | 2026 | 2022-08-31 | 2022-07-29 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | In-Service | N/A | 2021-07-26 | In-Service
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017 | 2024 | 2024-12-27 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-05-31 | 2024-04-30 | 2024-03-31 | In-Service | NOC: AL 6047-E | 2022-06-01 | In-Service
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020 | 2022 | 2022-03-01 | 2022-12-14 | 2022-12-14 | 2024-02-23 | 2023-12-19 | 2023-11-27 | 2023-11-28 | 2023-12-22 | 2023-12-18 | 2023-12-18 | In-Service | NOC: AL 5293-E | 2021-01-05 | In-Service
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-12-01 | 2027-12-01 | 2029-11-15 | Initiating | TBD | 2029-06-28 | Q3-2024: Project ISD delayed due to this project being rescoped in 2023-24 CAISO Transmission Plan to Atlantic High Voltage .
Banta 60 kV Bus Voltage Conversion | PG&E | 2022-2023 | 2024 | [6 empty] | N/A | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2028-03-30 | In-Flight | N/A | 2024-11-27 | Q3-2024: Project ISD delayed due to delays in receiving long lead materials such as Circuit breakers and Switchgears as originally planned.
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025 | 2027 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2026-04-01 | 2026-04-01 | 2028-04-13 | In-Flight | TBD | 2026-10-06 | Q3-2024: Project ISD delayed due to schedule/construction sequencing date adjustments. Project Kick off was on 5/29/24
Borden-Storey 230 kV 1 and 2 Line Reconductoring | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-31 | 2029-05-01 | 2029-05-01 | 2030-05-01 | Initiating | TBD | 2027-10-01 | Q3-2024: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014 | 2023 | 2023-12-29 | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2025-07-11 | 2025-07-11 | 2025-06-13 | In-Flight | N/A | 2019-07-09 | Q3-2024: Schedule/construction sequencing date adjustments.
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022 | 2028 | 2028-12-01 | 2028-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-02-01 | 2028-02-01 | Initiating | TBD | 2027-01-01 | Q3-2024: No date changes at this time.
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012 | 2027 | 2027-02-01 | 2027-02-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-07-01 | 2029-07-01 | 2029-07-01 | Initiating | TBD | 2027-01-01 | Q3-2024: No date changes at this time.
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022 | 2029 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | In Flight | N/A | 2027-08-05 | Q3-2024: No date changes at this time.
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025 | 2025 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-27 | In-Flight | N/A | 2024-10-04 | Q3-2024: Schedule/construction sequencing date adjustments.
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-18 | In-Flight | TBD | 2026-06-12 | Q3-2024: Schedule/construction sequencing date adjustments.
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | Initiating | TBD | 2026-10-01 | Q3-2024: No date changes at this time.
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-01 | 2028-06-01 | In-Flight | TBD | 2031-01-08 | Q3-2024: No date changes at this time.
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022 | 2025 | 2025-10-02 | 2025-03-31 | 2024-12-24 | 2026-02-26 | 2026-02-26 | 2026-03-25 | 2025-11-12 | 2026-10-05 | 2026-06-19 | 2027-01-25 | In-Flight | N/A | 2026-01-02 | Q3-2024: Project ISD delayed due to re-scoping due to realign with new IT and automation standards.
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019 | 2024 | 2024-10-02 | 2025-03-31 | 2025-02-14 | 2025-05-15 | 2025-08-11 | 2025-07-18 | 2025-11-19 | 2026-10-20 | 2026-10-20 | 2027-12-31 | In-Flight | N/A | 2026-02-02 | Q3-2024: Project ISD delayed due to re-scoping due to Cottonwood BK1 emergency project and realign with new IT and automation standards.
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022 | 2027 | 2027-11-10 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | In-Flight | N/A | 2026-05-13 | Q3-2024: No date changes at this time.
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-31 | 2026-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2027-06-30 | Initiating | TBD | 2027-03-01 | Q3-2024: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
Estrella Substation Project | PG&E | 2013-2014 | 2019 | 2026 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | 2029-07-16 | 2029-11-01 | 2029-07-05 | 2029-07-03 | In-Flight | PTC: A.17-01-023 | 2025-03-03 | Q3-2024: Schedule/construction sequencing date adjustments.
Garberville Area Reinforcement | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-01 | 2030-12-31 | 2030-12-31 | 2029-11-21 | In-Flight | TBD | 2028-11-22 | Q3-2024: Improved ISD due to schedule/construction sequencing date adjustments.
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025 | 2025 | 2025-03-28 | 2024-06-03 | 2024-04-30 | 2024-04-30 | 2024-07-12 | 2024-08-30 | 2024-12-04 | 2024-09-30 | 2025-01-01 | 2025-01-25 | In-Flight | N/A | 2023-04-03 | Q3-2024: Schedule/construction sequencing date adjustments.
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022 | 2028 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2030-04-12 | In-Flight | TBD | 2026-09-09 | Q3-2024: Project ISD delayed due to transformer LLM.
Henrietta 230/115 kV Bank 3 Replacement | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-31 | 2027-06-01 | 2027-06-01 | 2028-07-21 | In-Flight | TBD | 2026-07-17 | Q3-2024: Project ISD delayed due to schedule/construction sequencing date adjustments. Project Kick off was on 4/29/24.
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021 | 2026 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | In Flight | NOC - TBD on Filing Date | 2025-07-24 | Q3-2024: No date changes at this time.
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023 | 2027 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-06-26 | Initiating | TBD | 2029-04-27 | Q3-2024: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022 | 2026 | 2026-05-01 | 2026-05-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-10-12 | In-Flight | N/A | 2026-04-09 | Q3-2024: Schedule/construction sequencing date adjustments.
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016 | 2027 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2029-08-10 | 2029-08-10 | 2030-12-31 | In flight | NOC - TBD on Filing Date | 2027-01-08 | Q3-2024: ISD recalibrated in PG&E's work portfolio.
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021 | 2027 | 2027-12-31 | 2027-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-10-01 | Q3-2024: No date changes at this time.
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017 | 2027 | 2027-06-21 | 2028-12-29 | 2029-01-01 | 2029-01-01 | 2029-01-01 | 2029-01-11 | 2029-01-11 | 2029-06-08 | 2029-12-25 | 2029-12-10 | In-Flight | CPCN: A.23-09-001 Filed & Under Review | 2028-06-07 | Q3-2024: Schedule/construction sequencing date adjustments.
Lone Tree–Cayetano–Newark Corridor Series Compensation | PG&E | 2022-2023 | 2027 | [6 empty] | N/A | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-11-01 | Q3-2024: No date changes at this time.
Los Banos 230 kV Circuit Breakers Replacement | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-31 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Initiating | TBD | 2026-07-01 | Q3-2024: No date changes at this time.
Los Banos 70 kV Area Reinforcement | PG&E | 2022-2023 | 2029 | [6 empty] | N/A | 2029-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2026-10-01 | Q3-2024: No date changes at this time.
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024 | 2027 | 2027-06-28 | 2026-01-14 | 2026-06-19 | 2026-10-19 | 2025-01-15 | 2025-01-31 | 2025-02-20 | 2025-01-06 | 2025-06-20 | 2025-06-20 | In-Flight | TBD | 2025-03-03 | Q3-2024: No date changes at this time.
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-05-31 | 2029-02-02 | 2029-10-09 | In-Flight | TBD | 2028-12-11 | Q3-2024: Project ISD delayed due to schedule/construction sequencing date adjustments. Project Kick off was on 7/1/24.
Maple Creek Reactive Support | PG&E | 2009 | 2011 | 2026 | 2026-07-01 | 2026-07-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-10-01 | 2027-10-01 | Initiating | TBD | 2026-01-01 | Q3-2024: No date changes at this time.
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021 | 2024 | 2024-05-24 | 2024-05-10 | 2024-05-24 | 2025-11-14 | 2025-11-13 | 2025-11-13 | 2026-04-23 | 2027-02-12 | 2028-10-13 | 2029-12-18 | In Flight | CPCN: A.17-12-021 | 2027-05-14 | Q3-2024: Egbert ISD delayed due to relaibility hardening priorities. Status of Egbert shown as In flight and not On Hold because this project is not On Hold in the 2023-24 CAISO Transmission Plan.
Mesa 230/115kV Spare Transformer | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2029-05-01 | 2028-04-01 | 2028-04-01 | 2029-04-01 | Initiating | TBD | 2028-01-15 | Q3-2024: Delayed as project schedule is tied to long transformer lead time. Project has not kicked off yet.
Metcalf 230 / 115 kV Transformers Circuit Breaker Addition | PG&E | 2022-2023 | 2026 | [6 empty] | N/A | 2025-09-30 | 2027-06-01 | 2027-06-01 | 2026-09-01 | In-Flight | TBD | 2026-05-06 | Q3-2024: ISD recalibrated in PG&E's work portfolio.
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008 | 2029 | 2029-04-01 | 2029-04-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-03-01 | 2027-03-01 | Initiating | TBD | 2026-01-01 | Q3-2024: No date changes at this time.
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019 | 2024 | 2024-06-06 | 2025-07-03 | 2026-06-23 | 2026-06-23 | 2027-04-07 | 2027-04-07 | 2027-04-07 | 2027-04-29 | 2027-04-29 | 2028-12-31 | In Flight | NOC: AL 5026-E | 2018-11-01 | Q3-2024: Project ISD delayed due to dependence on Midway Sec D Bus Upgrade.
Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019 | 2024 | 2024-06-06 | 2027-06-03 | 2027-09-01 | 2027-11-30 | 2028-02-25 | 2028-05-23 | 2028-08-21 | 2027-10-28 | 2028-01-24 | 2030-05-28 | In-Flight | NOC: AL 5924-E | 2026-03-31 | Q3-2024: Project now in-flight. ISD updated based on project schedule/construction sequencing date adjustments.
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013 | 2025 | 2025-05-01 | 2025-05-01 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-08-29 | 2025-08-29 | 2027-10-08 | 2030-08-22 | In Flight | N/A | 2021-04-07 | Q3-2024: ISD recalibrated in PG&E's work portfolio.
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018 | 2027 | 2027-10-20 | 2028-02-16 | 2028-05-16 | 2028-08-14 | 2028-11-09 | 2029-02-05 | 2029-04-06 | 2029-08-01 | 2029-10-26 | 2030-07-16 | In flight | NOC - TBD on Filing Date | 2027-02-11 | Q3-2024: ISD recalibrated in PG&E's work portfolio.
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016 | 2024 | 2024-08-06 | 2024-07-17 | 2024-05-08 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-01 | 2025-08-07 | 2025-08-07 | 2025-09-23 | In-Flight | N/A | 2021-08-17 | Q3-2024: Schedule/construction sequencing date adjustments.
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024 | 2027 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-01-01 | Q3-2024: No date changes at this time.
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013 | 2025 | 2023-09-22 | 2023-11-06 | 2024-03-07 | 2024-03-20 | 2024-06-20 | 2024-10-25 | 2024-10-16 | 2026-03-25 | 2026-03-25 | 2024-11-24 | In-Flight | N/A | 2024-09-20 | Q3-2024: ISD recalibrated in PG&E's work portfolio.
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023 |  |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | On-Hold (CAISO) | TBD | TBD | Q3-2024: Project on CAISO Hold.
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021 | 2026 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2027-09-29 | 2027-09-29 | 2027-09-29 | 2029-01-30 | 2029-02-27 | 2028-12-28 | In-Flight | TBD | 2026-12-09 | Q3-2024: Schedule/construction sequencing date adjustments.
Mosher Transmission Project | PG&E | 2013-2014 | 2017 | 2027 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | In Flight | NOC - TBD on Filing Date | 2027-01-20 | Q3-2024: No date changes at this time.
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2028-04-01 | 2028-04-01 | 2028-09-01 | Initiating | TBD | 2026-10-01 | Q3-2024: Project is ON HOLD per CAISO request as this project is being reassessed.
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-31 | 2027-12-31 | 2027-12-01 | In-Flight | TBD | 2026-08-21 | Q3-2024: Schedule/construction sequencing date adjustments.
New Manning 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-01 | In-Flight | TBD | 2026-04-01 | Q3-2024: Schedule/construction sequencing date adjustments.
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-01 | 2026-12-01 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2026-09-01 | Q3-2024: No date changes at this time.
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019 | 2022 | 2022-11-01 | 2023-04-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-06-01 | 2025-06-01 | 2025-07-01 | In-Flight | TBD | 2028-03-22 | Q3-2024: Schedule/construction sequencing date adjustments.
North East Kern 115 kV Line Reconductoring | PG&E | 2022-2023 | 2032 |  | 2029-02-05: N/A; 2029-04-06: 2032-12-31; 2029-08-01: 2033-12-31; 2029-10-26: 2033-12-31; 2030-07-16: 2032-12-31 | Initiating | TBD | 2026-12-01 | Q3-2024: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015 | 2030 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2028-02-01 | 2028-02-01 | 2029-02-01 | Initiating | TBD | 2028-01-01 | Q3-2024: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 |  | 2023 | 2023-03-04 | 2023-05-19 | 2023-07-18 | 2023-11-21 | 2023-10-30 | 2025-04-01 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-07-29 | In-Flight | N/A | 2021-11-16 | Q3-2024: Schedule/construction sequencing date adjustments.
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2027-01-29 | In Flight | NOC - Expected 2024 Q4 | 2026-01-23 | Q3-2024: No date changes at this time.
Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project | PG&E | 2022-2023 | 2032 |  | 2029-02-05: N/A; 2029-04-06: 2032-12-31; 2029-08-01: 2028-04-28; 2029-10-26: 2028-06-01; 2030-07-16: 2028-04-28 | In-Flight | TBD | 2026-01-07 | Q3-2024: Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project is being implemented under New Manning 500 kV substation. Schedule/construction sequencing date adjustments.
Pittsburg 115 kV Bus Reactor project | PG&E | 2022-2023 | 2032 |  | 2029-02-05: N/A; 2029-04-06: 2032-12-01; 2029-08-01: 2028-05-12; 2029-10-26: 2028-05-12; 2030-07-16: 2028-05-12 | In-Flight | TBD | 2026-11-05 | Q3-2024: Pittsburg 115 kV Bus Reactor project is being implemented under New Collinsville 500 kV substation. No Date changes at this time.
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011 | 2025 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2026-06-17 | 2026-06-17 | 2026-09-04 | 2026-06-15 | 2028-05-09 | In-Flight | N/A | 2027-10-04 | Q3-2024: Project ISD delaye due to long lead material delivery, schedule/construction sequencing date adjustments.
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019 | 2024 | 2024-12-01 | 2024-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-06-01 | 2025-06-01 | 2026-12-22 | In-Flight | TBD | 2026-06-16 | Q3-2024: Project ISD delayed as PG&E is re-evaluating the need of the project.
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-02-02 | 2028-08-16 | In-Flight | TBD | 2025-07-17 | Q3-2024: Project ISD delayed due to schedule/construction sequencing date adjustments. Project recently kicked off
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-01-01 | Q3-2024: No date changes at this time.
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021 | 2025 | 2025-11-19 | 2026-08-18 | 2026-08-18 | 2030-05-23 | 2031-11-19 | 2029-03-30 | 2028-11-07 | 2028-05-23 | 2029-03-06 | 2029-08-27 | In-Flight | NOC - TBD on Filing Date | 2028-04-03 | Q3-2024: Project ISD delayed due to schedule/construction sequencing date adjustments.
Redwood City 115kV System Reinforcement | PG&E | 2022-2023 | 2030 |  | 2029-02-05: N/A; 2029-04-06: 2030-12-01; 2029-08-01: 2029-12-01; 2029-10-26: 2029-12-01; 2030-07-16: 2028-07-05 | Initiating | TBD | 2028-04-21 | Q3-2024: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009 | 2024 | 2024-04-30 | 2024-06-30 | 2024-04-30 | 2025-04-17 | 2025-12-31 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2026-04-06 | 2025-05-21 | In-Flight | N/A | 2022-07-05 | Q3-2024: Improved ISD due to schedule/construction sequencing
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016 | 2024 | 2024-10-11 | 2024-10-31 | 2024-08-26 | 2024-12-09 | 2025-05-30 | 2025-06-04 | 2025-06-04 | 2025-06-19 | 2025-09-01 | 2026-05-14 | In-Flight | N/A | 2025-09-18 | Q3-2024: Project ISD delayed due to construction sequencing date adjustments and recalibration in PG&E's work portfolio.
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | 2024 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | 2024-11-21 | 2024-12-31 | 2024-12-31 | TBD | In-Flight | N/A | 2023-02-15 | Q3-2024: Project ISD subject to alignment with LS Power.
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024 | 2025 | 2025-12-31 | 2025-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-12-01 | 2027-12-01 | TBD | Initiating | TBD | TBD | Rescoped in 2023-24 CAISO Transmission Plan to Salinas Area Reinforcement, ISD TBD.
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-11-30 | 2028-04-01 | 2028-04-01 | 2028-04-01 | In-Flight | 851 - TBD on Filing Date | 2025-06-03 | Q3-2024: No date changes at this time.
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-04-30 | 2028-05-01 | 2028-05-01 | 2028-05-01 | In-Flight | NOC - Expected 2024 Q4 | 2025-02-07 | Q3-2024: No date changes at this time.
Santa Rosa 115 kV lines Reconductoring project | PG&E | 2022-2023 | 2028 |  | 2029-02-05: N/A; 2029-04-06: 2028-12-01; 2029-08-01: 2028-12-01; 2029-10-26: 2028-12-01; 2030-07-16: 2029-10-31 | Initiating | TBD | 2029-04-16 | Q3-2024: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023 | 2023 |  | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-12-23 | 2025-12-23 | 2026-03-03 | In-Flight | TBD | 2025-06-27 | Q3-2024: Schedule/construction sequencing date adjustments.
South Bay Area Limiting Element Upgrade | PG&E | 2022-2023 | 2027 |  | 2029-02-05: N/A; 2029-04-06: 2027-12-31; 2029-08-01: 2026-03-01; 2029-10-26: 2026-03-01; 2030-07-16: 2025-05-01 | In-Flight | TBD | 2024-06-01 | Q3-2024: ISD recalibrated in PG&E's work portfolio. On 6/4/24, PG&E completed upgrading 115KV Metcalf-El Patio Line #1 and Line #2 drops at Metcalf Substation.
South of Mesa Upgrade | PG&E | 2018-2019 | 2023 | 2026 | 2026-09-03 | 2026-05-26 | 2026-05-26 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-15 | 2027-04-15 | 2031-03-10 | In flight | NOC - TBD on Filing Date | 2029-10-03 | Q3-2024: ISD recalibrated in PG&E's work portfolio.
South of San Mateo Capacity Increase | PG&E | 2007 | 2009 | 2027 | 2027-03-01 | 2027-03-01 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2028-12-01 | 2028-12-01 | 2027-10-29 | Initiating | TBD | 2027-10-04 | Q3-2024: ISD recalibrated in PG&E's work portfolio. Project has not kicked off yet.
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-01-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-06-01 | 2028-06-01 | 2026-09-28 | In-Flight | TBD | 2026-04-13 | Q3-2024: ISD recalibrated in PG&E's work portfolio to accelerate this project.
Tesla 115 kV Bus Reconfiguration | PG&E | 2022-2023 | 2030 |  | 2029-02-05: N/A; 2029-04-06: 2030-12-01; 2029-08-01: 2028-06-01; 2029-10-26: 2028-06-01; 2030-07-16: 2028-06-01 | Initiating | TBD | 2026-07-01 | Q3-2024: No date changes at this time.
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020 | 2026 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-16 | 2027-08-16 | 2028-02-09 | 2028-02-09 | 2028-12-28 | In-Flight | N/A | 2024-05-13 | Q3-2024: Program consists of 7 individually managed projects. Project ISD delayed due to input error. Project manager accidentally inputted Feb 2028 when it should have been Dec 2028.
Tulucay-Napa #2 60 kV line Reconductoring project | PG&E | 2022-2023 | 2028 |  | 2029-02-05: N/A; 2029-04-06: 2028-12-01; 2029-08-01: 2026-12-31; 2029-10-26: 2026-12-31; 2030-07-16: 2026-12-01 | In-Flight | TBD | 2026-10-01 | Q3-2024: Schedule/construction sequencing date adjustments.
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022 | 2026 | 2026-12-01 | 2026-12-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-03-01 | 2027-03-01 | 2027-09-20 | In-Flight | TBD | 2027-05-05 | Q3-2024: Project ISD delayed due to schedule/construction sequencing date adjustments. Project kicked off 5/23/24.
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023 | 2026 | 2026-07-10 | 2026-08-21 | 2025-08-18 | 2025-12-25 | 2025-12-30 | 2026-02-06 | 2026-02-06 | 2026-04-29 | 2027-04-12 | 2027-04-30 | In-Flight | PTC: A.24-06-008 Filed & Under Review (Plainfield) NOC - Expected 2024 Q4 (Woodland-Davis) | 2025-07-30 | Q3-2024: Schedule/construction sequencing date adjustments.
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019 | 2027 | 2027-04-01 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-05-08 | 2025-10-20 | 2025-10-20 | 2026-07-17 | 2026-07-17 | 2026-07-17 | In Flight | N/A | 2025-12-25 | Q3-2024: No date changes at this time.
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025 | 2025 |  | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2026-08-31 | In-Flight | TBD | 2026-06-16 | Q3-2024: Limiting elements will be removed as part of Metcalf 230kV & 115kV MPACs project.
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014 | 2025 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | 2026-05-29 | 2026-07-31 | 2027-05-06 | 2027-04-23 | In-Flight | PTC: A.18-06-004 | 2024-05-21 | Q3-2024: Schedule/construction sequencing date adjustments.
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-05-31 | 2029-02-02 | 2027-12-06 | In-Flight | NOC - Expected 2024 Q4 | 2027-11-04 | Q3-2024: Improved ISD due to schedule/construction sequencing date adjustments. Project recently kicked off
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020 |  |  | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | 2034-03-28 | 2029-05-04 | 2033-12-31 | 2032-12-01 | In-Flight | PTC - Expected 2025 Q1 | 2027-12-31 | Q3-2024: Project now in-flight. Improved ISD due to project schedule/construction sequencing date adjustments.
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | In Flight | N/A | 2025-02-17 | Q3-2024: No date changes at this time.
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026 | 2026 | 2026-05-01 | 2026-05-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-05-01 | 2027-05-01 | Initiating | TBD | 2026-10-01 | Q3-2024: No date changes at this time.

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-10-01 | Licensing | 2009-09-01 | 2026-10-01 | Alberhill dates contingent on licensing
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 | N/A | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | Engineering | Exempt | 2024-10-07 | Material delay caused shift in construction start
Antelope-Whirlwind Line Upgrade | SCE | 2022-2023 | 2025 | N/A | New | New | New | New | New | New | Pending | Pending | 2025-12-31 | 2025-12-01 | Preliminary Engineering | Pending | 2025-09-01 | Project approved by CAISO in May 2023
Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | Pending | 2026-06-01 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-06-01 | Design | Exempt | 2025-05-29 | No change in the expected ISD between October 2023 TDF and January 2024 TDF
Colorado River-Red Bluff 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-02-01 | Initiation | Pending | 2025-10-01 | Project approved by CAISO in May 2023
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2027-06-01 | Final Engineering | Exempt | 2024-10-01 | Project sequencing and increase in scope has pushed the initial ISD out two years to 2027.
Devers-Red Bluff 500 kV 1 and 2 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 1930-03-01 | Initiation | Pending | 2029-11-01 | Supply chain challenges have increased the lead time for 500 kV circuit breakers, which limits SCE ability to complete this project by the initially expected ISD.
Devers-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-04-01 | Initiation | Pending | 2026-10-01 | Project approved by CAISO in May 2023
Inyo 230 kV Shunt Reactor | SCE | 2023-2024 | 2027 | N/A | New | New | New | New | New | New | Pending | N/A | N/A | 2027-12-31 | Initiation | Pending | Pending | The project Inyo 230 kV Shunt Reactor was submitted in the 2023-2024 TPP and approved by the CAISO. It supersedes the project New Control 115 kV Shunt Reactor.
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | N/A | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | 2024-05-31 | 2024-05-01 | 2024-06-01 | 2024-06-01 | 2025-06-01 | Construction | Exempt | 2024-03-01 | SCE has informed the CAISO that the ISD will be 6/1/25.
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2012-2013 | 2016 | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2024-12-01 | Construction | 2018-05-01 | 2020-12-01 | Unable to achieve the required capacitor balancing during testing and commissioning.
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2016-2017 | 2018-12-31 | 2023-06-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2026-01-01 | 2027-01-31 | 2027-01-01 | Construction | Exempt | Construction started | Construction of the LADWP portion of the project is scheduled from November 2026 to February 2027.
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-30 | 2025-12-01 | 2026-12-30 | 2029-12-01 | Design | Exempt | 2028-10-01 | Project sequencing and outage constraints has slipped the construction start to 2028.
Lugo-Mohave series capacitor upgrade | SCE | 2013-2014 | 2016 | 2022-06-01 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2025-04-01 | Construction | 2018-05-01 | 2020-12-01 | Longer than expected duration during the testing and commissioning of the series capacitor
Lugo-Victor-Kramer Upgrade (1/3) Add 3rd Lugo 500/230 kV Transformer | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | Preliminary Engineering | Pending | 2027-01-01 | Project approved by CAISO in May 2023 (Lugo–Victor–Kramer 230 kV Upgrade project)
Lugo-Victor-Kramer Upgrade (2/3) Reconductor Lugo–Victor 230 kV No. 1, 2, 3 & 4 lines using HTLS | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | Preliminary Engineering | Pending | 2025-10-01 | Project approved by CAISO in May 2023 (Lugo–Victor–Kramer 230 kV Upgrade project)
Lugo-Victor-Kramer Upgrade (3/3) Rebuild/build Kramer–Victor 115 kV lines to 230 kV and Loop the old segment of Kramer–Victor 115 kV into Roadway | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | Pending | 2033-06-30 | 1933-06-01 | Initiation | Pending | 1931-01-01 | Project approved by CAISO in May 2023 (Lugo–Victor–Kramer 230 kV Upgrade project)
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | TBD | 2029-10-01 | Initiation | 2015-04-01 | 2025-04-01 | Project continues to be on hold due to Riverside Council efforts to pursue funding for fully underground transmission lines and CPUC decision on City of Norco's Petition For Modification (PFM).
Mira Loma 500 kV CB Upgrade Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2028-12-01 | 2028-08-14 | 2028-12-01 | Design | Exempt | 2028-05-18 | Material Lead times have increased to 5 years pushing project completion to 2028.
Mira Loma-Mesa Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | Preliminary Engineering | Pending | 2024-03-01 | Project approved by CAISO in May 2023
New CoolwaterA 115/230 kV Bank | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2027-12-10 | 2027-12-10 | 2027-12-01 | Preliminary Engineering | Exempt | 2027-01-01 | Project approved by CAISO in May 2023
New Serrano 4AA Bank & 230kV GIS Rebuild | SCE | 2022-2023 | 2027 | N/A | New | New | New | New | New | New | Pending | Pending | 2027-12-30 | 2027-12-01 | Preliminary Engineering | Exempt | 2027-03-01 | Project approved by CAISO in May 2023
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2019-2020 | 2023-06-01 | 2023-05-01 | 2023-06-23 | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-25 | 2027-10-31 | 2027-10-31 | 2027-10-01 | Construction | Exempt | 2022-10-22 | Joint SCE/LADWP project. ISD for SCE’s portion of the project is June 2024. ISD for LADWP portion of the project at Sylmar Substation is October 2027.
San Bernardino-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 1931-04-01 | Initiation | Pending | 2029-10-01 | Project approved by CAISO in May 2023
San Bernardino-Vista 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2029-12-01 | Initiation | Pending | 2029-03-01 | Project approved by CAISO in May 2023
Serrano-Alberhill-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-12-01 | Initiation | Pending | 2027-03-01 | Project approved by CAISO in May 2023
Serrano–Del Amo–Mesa 500 kV Transmission Reinforcement | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | 2033-12-31 | 2033-12-31 | 1933-12-01 | Initiation | 2026-01-15 | 2031-01-01 | Project approved by CAISO in May 2023
Sylmar Transformer Replacement | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | Initiation | Pending | Pending | Project approved by CAISO in May 2023. Joint SCE/LADWP project.
Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 44531 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2024-02-28 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-09-01 | Construction | N/A | Construction started
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | Pending | 2025-04-01 | 2025-04-01 | 2025-04-30 | 2025-04-30 | 2025-04-30 | Pending | Preliminary Engineering | N/A | TBD | Dates modified due to material lead time. Materials like CB has the most long lead time and is Critical for Construction.
Vista-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 2031-12-01 | Initiation | Pending | Pending
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Adrian Franco, can you confirm dates and status for this project?
Note on S13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roni Mejia, @Justina Jinzo, we need to remove this comment or confirm if construction start of 2026 refers to LADWP portion of the project. @Siyuan Wang , can you please confirm? Reply: Hayy confirmed and the note has been updated accordingly. Reply: perfect. Reply: We won’t know for sure until DWP outage coordinator have a conversation with our operation people to see if a summer outage is possible. Their PM is currently trying to coordinate that meeting.

## SDGaE
Project | PTO | Transmission Plan Approved | In-Service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2023-05-01 |  | 2023-12-01 | 2024-05-28 | 2024-05-28 | 2024-11-05 | 2024-11-05 | 2025-08-07 | 2024-02-01 | 2023-12-23 | 2023-12-07 |  | Close-out | 2012-05-18 | 2018-06-29
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-04-01 | 2022-05-01 | 2022-05-02 | 2022-05-31 | 2022-05-15 | 2022-05-15 | 2022-05-15 | In-Service | In-Service |  |  |  | Close-out | Exempt | 2022-02-04
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2021-10-01 | 2022-11-01 | 2022-12-01 | 2022-12-09 | 2022-12-27 | 2022-11-18 | 2022-11-18 | In-Service | In-Service |  |  |  | Close-out | 2017-06-28 | 2021-01-19
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-05-01 | 2023-02-01 | 2022-09-01 | 2022-12-14 | 2022-12-27 | 2023-02-08 | 2023-02-08 | In-Service | In-Service |  |  |  | Close-out | 2017-11-15 | 2022-01-03
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-06-01 |  | 2022-06-01 | 2022-12-14 | 2022-12-13 | Completed | Completed | In-Service | In-Service |  |  |  | Close-out | 2016-08-17 | 2020-06-10
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-12-01 |  | 2023-05-01 | 2021-11-01 | 2021-10-22 | Completed | Completed | In-Service | In-Service |  |  |  | Close-out | Exempt | 2021-05-17
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2022-11-01 |  | 2023-06-27 | 2023-08-25 | 2023-10-24 | Completed | Completed | In-Service | In-Service |  |  |  | Close-out | Exempt | 2021-07-26
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 2016 | 2023-04-01 | 2023-02-01 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2023-02-13 | 2023-02-13 | 2026-02-24 | 2026-08-05 | 2026-08-01 | 2026-12-16 | 2027-05-12 | Design | 2016-04-25 | 2025-08-07
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2026-06-01 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-06-08 | 2026-06-08 | 2026-07-29 | 2026-08-10 | 2026-10-12 | 2026-12-21 | 2027-05-11 | Design | 2025-05-23 | 2026-07-08
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-11-01 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2026-11-10 | 2026-11-10 | 2026-12-09 | 2028-03-23 | 2028-03-16 | 2028-07-01 | 2028-05-03 | Design | Exempt | 2027-05-13
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2027-06-01 | 2024-06-01 | 2024-05-02 | 2024-12-23 | 2024-12-23 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-26 | 2024-07-01 | 2024-08-23 | 2024-10-30 | Permitting | Exempt | 2024-01-15
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2029-02-01 |  |  | 2024-08-15 | 2029-02-27 | 2029-02-27 | 2029-04-30 | 2029-09-28 | 2029-12-04 | 1930-02-26 | 2029-07-27 | Planning | TBD | 2028-10-27
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2024-12-01 |  |  | 2022-08-24 | 2024-12-17 | 2024-12-17 | 2024-10-18 | 2024-08-07 | 2024-08-07 | 2024-08-20 | 2024-10-30 | Design | Exempt | 2024-06-11
Valley Center System Improvement | SDG&E | 2023-2024 | 2028 | [11 empty] | 2028 | Planning | TBD | TBD | Newly approved in 2023-2024 TPP
Short Circuit Mitigation for Imperial Valley 230 kV Circuit Breakers Project | SDG&E | 2023-2024 | 2035 | [11 empty] | 2035 | Planning | TBD | TBD | Newly approved in 2023-2024 TPP
Short Circuit Mitigation for Miguel 230 kV Circuit Breakers Project | SDG&E | 2023-2024 | 2035 | [11 empty] | 2035 | Planning | TBD | TBD | Newly approved in 2023-2024 TPP
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-11-01 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-11-14 | 2027-11-14 | 2027-11-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | Design | 2026-07-24 | 2027-03-08
3 Ohm Series Reactor on Sycamore-Penasquitos 230 kV line | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Miguel-Sycamore Canyon (TL23021) 230 kV line Loop-in to Suncrest | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Reconductor TL680C San Marcos -Melrose Tap | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | Planning | TBD | TBD | Approved in 2022-2023 TPP
SG and OT Redundant Bus Differential Relay | SDG&E | 2022-2023 | 2024 |  | 2024 | [6 empty] | TBD | 2024 | 2024 | 2024 | Planning | TBD | TBD | Approved in 2022-2023 TPP
Upgrade TL13820 Sycamore-Chicarita 138 kV | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | Planning | TBD | TBD | Approved in 2022-2023 TPP

## VEA_GLW
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Current In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 1905-07-13 | 2021-09-01 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service | In service | In service |  |  |  |  | N/A | 2021 | In Service
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 |  | 2023-06-23 | 2023-09-23 | 2023-12-23 | 2023-12-23 | Q1/Q2-2024 | Q4/2024 | In Flight | N/A | Sept-21 | VEA is waiting on a Telecom Site Survey from AT&T to determine routes and equipment to get a connection to VEA Campus.
GLW/VEA area upgrades - revised scope | VEA/GLW | 2021-2022 (revised scope 2022-2023) | TBD |  | N/A | TBD | TBD | TBD | TBD | TBD | 2027-12-31 | 2027-12-31 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | Permitting, engineering and design | N/A | 2026-01-01 | Project's targeted In-Service date is Dec-27. Trout Canyon-Sloan Canyon 500kV is being prioritized. In addition, the ISD for the overall project is planned to be expedited by 6 months. However, the expidited date is subject to change based on the federal permitting process with BLM.
Beatty 230 kV Project | VEA/GLW | 2022-2023 | 2027-12-31 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | Permitting, engineering and design | N/A | 2026-01-01 | Project's targeted In-Service date is Dec-27; project is on schedule.

## DCRT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-24 | 2024-04-01 | 2024-04-24 | 2024-04-24 | 2024-05-24 | 2024-06-07 | In-Service | Approved | 2022-10-22 | Energized 6/7/2024

## LSPower
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service April 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support (Orchard Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2025-01-01 | 2025-01-01 | 2025-01-25 | Construction | 2021-02-19 | 2023-04-01 | Construction in progress
Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TBD | TBD | Construction | 2022-04-06 | 2024-03-25 | Construction in progress
Collinsville 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Permitting | Q3 2024 | 2026 | CPCN filed
Manning 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Permitting | 2024-06-28 | 2026 | CPCN filed
Metcalf - San José B HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-04-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | Permitting | 2024-04-29 | 2026 | CPCN filed
Newark - NRS HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-05-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Permitting | 2024-05-17 | 2026 | CPCN filed
Collinsville 230kV Reactor Project | LS Power | 2023-2024 | 2028 | [10 empty] | 2028-06-01 | Permitting | Q4 2024 | TBD

## CitizensEnergy
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Expected In-Service Jan 2024 TDF | Expected In-Service July 2024 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | Completed |  | 2023-07-21