## PGaE
Project | PTO | Transmission Plan Approved | In-service Year at Approval in Transmission Plan | Expected In-Service Year (2020-2021 Transmission Plan) | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service Jul 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Current In-Service Jul 2023 TDF (Current) | Project Status | Expected CPUC Filing | Expected Const start | Notes
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015 | 2022 | 2022-11-01 | 2023-03-15 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 | 2022-09-22 | In-Service
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013 | 2025 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | In-Service | N/A | 2018-10-16 | In-Service
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 |  | 2023 |  | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | In-Service | N/A | 2021-08-03 | In-Service
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2022 | 2022-07-06 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | In-Service | N/A | 2021-07-01 | In-Service
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019 | 2023 | 2023-01-13 | 2023-01-16 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 | 2022-09-22 | In-Service
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E | 2018-2019 | 2023 | 2023 | 2023-10-31 | 2023-04-05 | 2023-03-28 | 2023-05-01 | 2023-06-13 | 2023-07-27 | 2023-06-14 | In-Service | N/A | 2022-04-19 | In-Service
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023 | 2026 | 2022-08-31 | 2022-07-29 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-11 | 2022-08-11 | In-Service | N/A | 2021-07-26 | In-Service
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | Initiating | TBD | 2025-02-01 | Q3-2023: No date changes at this time
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025 | 2027 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-12-01 | Q3-2023: No date changes at this time
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014 | 2023 | 2023-12-29 | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-13 | 2024-12-13 | 2024-12-13 | In-Flight | N/A | 2019-07-09 | Q3-2023: No date changes at this time
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022 | 2028 | 2028-12-01 | 2028-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | Initiating | TBD | 2025-01-31 | Q3-2023: No date changes at this time
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012 | 2027 | 2027-02-01 | 2027-02-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q3-2023: No date changes at this time
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022 | 2029 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-26 | 2029-06-26 | In Flight | N/A | 2027-07-30 | Q3-2023: No date changes at this time
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025 | 2025 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | 2025-05-22 | In-Flight | TBD | 2024-04-24 | Q3-2023: No date changes at this time
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2026-06-01 | Q3-2023: No date changes at this time
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-12-01 | Q3-2023: No date changes at this time
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | Initiating | TBD | 2025-10-01 | Q3-2023: No date changes at this time
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022 | 2025 | 2025-10-02 | 2025-03-31 | 2024-12-24 | 2026-02-26 | 2026-02-26 | 2026-03-25 | 2025-11-12 | In-Flight | N/A | 2025-06-30 | Q3-2023: Improved ISD due to schedule/construction sequencing date adjustments
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019 | 2024 | 2024-10-02 | 2025-03-31 | 2025-02-14 | 2025-05-15 | 2025-08-11 | 2025-07-18 | 2025-11-19 | In-Flight | N/A | 2025-07-03 | Q3-2023: Delay due to schedule/construction sequencing date adjustments
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022 | 2027 | 2027-11-10 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | In-Flight | N/A | 2026-05-13 | Q3-2023: No date changes at this time
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-31 | 2026-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Initiating | TBD | 2024-12-01 | Q3-2023: No date changes at this time
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015 | 2022 | 2022-12-23 | 2023-03-10 | 2023-05-31 | 2023-05-31 | 2023-12-29 | 2023-12-29 | 2023-12-29 | In-Flight | NOC: AL 5872-E | 2021-06-01 | Q3-2023: No date changes at this time
Estrella Substation Project | PG&E | 2013-2014 | 2019 | 2026 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | 2029-07-16 | In-Flight | PTC: A.17-01-023 | 2024-10-24 | Q3-2023: No date changes at this time
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025 | 2025 | 2025-03-28 | 2024-06-03 | 2024-04-30 | 2024-04-30 | 2024-07-12 | 2024-08-30 | 2024-12-04 | In-Flight | N/A | 2023-04-03 | Q3-2023: Delay due to schedule/construction sequencing date adjustments.
Giffen Line Reconductoring Project | PG&E | 2018-2019 |  | 2023 | 2023-01-13 | 2023-01-19 | 2023-01-11 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2023-12-29 | In-Flight | NOC: AL 6600-E | 2023-11-02 | Q3-2023: No date changes at this time
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018 | 2022 | 2022-12-21 | 2022-12-12 | 2022-10-19 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-16 | In-Flight | N/A | 2020-04-30 | Q3-2023: No date changes at this time
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022 | 2028 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | In-Flight | TBD | 2027-02-15 | Q3-2023: No date changes at this time
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021 | 2026 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | In Flight | NOC - TBD on Filing Date | 2025-07-24 | Q3-2023: No date changes at this time
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023 | 2027 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2026-12-01 | Q3-2023: No date changes at this time
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022 | 2026 | 2026-05-01 | 2026-05-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2024-10-01 | Q3-2023: No date changes at this time
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2027 | 2027-06-28 | 2025-11-12 | 2026-04-09 | 2026-08-07 | 2026-10-02 | 2023-11-22 | 2023-12-19 | In-Flight | TBD | 2023-09-19 | Q3-2023: No date changes at this time
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016 | 2027 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | In Flight | NOC - TBD on Filing Date | 2025-01-06 | Q3-2023: No date changes at this time
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021 | 2027 | 2027-12-31 | 2027-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q3-2023: No date changes at this time
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017 | 2027 | 2027-06-21 | 2028-12-29 | 2029-01-01 | 2029-01-01 | 2029-01-01 | 2029-01-11 | 2029-01-11 | In-Flight | CPCN Expected Q3 2023 | 2027-08-09 | Q3-2023: No date changes at this time
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024 | 2027 | 2027-06-28 | 2026-01-14 | 2026-06-19 | 2026-10-19 | 2025-01-15 | 2025-01-31 | 2025-02-20 | In-Flight | TBD | 2025-01-08 | Q3-2023: No date changes at this time
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | Initiating | TBD | 2025-05-01 | Q3-2023: No date changes at this time
Maple Creek Reactive Support | PG&E | 2009 | 2011 | 2026 | 2026-07-01 | 2026-07-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-12-01 | Q3-2023: No date changes at this time
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021 | 2024 | 2024-05-24 | 2024-05-10 | 2024-05-24 | 2025-11-14 | 2025-11-13 | 2025-11-13 | 2026-04-23 | In-Flight | CPCN: A.17-12-021 | 2024-02-07 | Q3-2023: Delay due to reprioritization.
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008 | 2029 | 2029-04-01 | 2029-04-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-12-01 | Q3-2023: No date changes at this time
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019 | 2024 | 2024-06-06 | 2025-07-03 | 2026-06-23 | 2026-06-23 | 2027-04-07 | 2027-04-07 | 2027-04-07 | In Flight | NOC: AL 5026-E | 2018-11-01 | Q3-2023: This project relies on the Midway 230kV Section D Bus Upgrade project (T.0001650) to be in-serviced to provide a new terminal position for the new 230kV line.
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013 | 2025 | 2025-05-01 | 2025-05-01 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-08-29 | In Flight | N/A | 2021-04-07 | Q3-2023: Delay due to prioritization
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018 | 2027 | 2027-10-20 | 2028-02-16 | 2028-05-16 | 2028-08-14 | 2028-11-09 | 2029-02-05 | 2029-04-06 | In Flight | NOC - TBD on Filing Date | 2026-07-22 | Q3-2023: No date changes at this time
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016 | 2024 | 2024-08-06 | 2024-07-17 | 2024-05-08 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-01 | In-Flight | N/A | 2018-06-18 | Q3-2023: No date changes at this time
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024 | 2027 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q3-2023: No date changes at this time
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013 | 2025 | 2023-09-22 | 2023-11-06 | 2024-03-07 | 2024-03-20 | 2024-06-20 | 2024-10-25 | 2024-10-16 | In-Flight | TBD | 2024-07-31 | Q3-2023: No date changes at this time
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023 |  |  |  | TBD | TBD | TBD | TBD | TBD | On-Hold (CAISO) | TBD | TBD | Q3-2023: Project on CAISO Hold
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021 | 2026 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2027-09-29 | 2027-09-29 | 2027-09-29 | In Flight | NOC: AL 5200-E | 2025-07-29 | Q3-2023: No date changes at this time
Mosher Transmission Project | PG&E | 2013-2014 | 2017 | 2027 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | In Flight | NOC - TBD on Filing Date | 2027-01-20 | Q3-2023: No date changes at this time
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2025-06-01 | Q3-2023: No date changes at this time
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2026-06-01 | Q3-2023: No date changes at this time
New Manning 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-02-01 | Q3-2023: No date changes at this time
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-01 | 2026-12-01 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | Initiating | TBD | 2025-12-01 | Q3-2023: No date changes at this time
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019 | 2022 | 2022-11-01 | 2023-04-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | Initiating | TBD | 2024-01-30 | Q3-2023: No date changes at this time
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019 |  |  | 2029-12-04 | 2029-12-04 | 2029-12-04 | 2029-08-28 | 2032-10-21 | 2032-10-21 | Cancelled | CPCN - TBD on Filing Date | 2026-07-15 | Q3-2023: Cancelled per CAISO 2023 TPP
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015 | 2030 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2030-01-31 | Initiating | TBD | 2028-01-01 | Q3-2023: No date changes at this time
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 |  | 2023 | 2023-03-04 | 2023-05-19 | 2023-07-18 | 2023-11-21 | 2023-10-30 | 2025-04-01 | 2025-04-30 | In-Flight | N/A | 2021-11-16 | Q3-2023: Moraga Bank 3 SW replacement operational 6/30/22. No date changes at this time
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | In Flight | NOC - Q4 2024 | 2026-01-23 | Q3-2023: No date changes at this time
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021 | 2023 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2022-12-30 | 2024-05-31 | 2024-03-27 | 2024-03-27 | In-Flight | NOC: AL 5390-E | 2022-01-17 | Q3-2023: No date changes at this time
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011 | 2025 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2026-06-17 | 2026-06-17 | In-Flight | N/A | 2025-02-12 | Q3-2023: No date changes at this time
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019 | 2024 | 2024-12-01 | 2024-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Initiating | TBD | 2025-10-01 | Q3-2023: No date changes at this time
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q3-2023: No date changes at this time
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | Initiating | TBD | 2028-12-01 | Q3-2023: No date changes at this time
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021 | 2025 | 2025-11-19 | 2026-08-18 | 2026-08-18 | 2030-05-23 | 2031-11-19 | 2029-03-30 | 2028-11-07 | In-Flight | NOC - TBD on Filing Date | 2025-07-07 | Q3-2023: Improved ISD due to schedule/construction sequencing date adjustments.
Reedley 70 kV Reinforcement (Renamed to Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017 | 2025 | 2025-12-25 | 2025-08-14 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | In Flight | N/A | 2024-02-28 | Q3-2023: Rescoped to Dinuba 70 kV Energy Storage. No date changes at this time
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009 | 2024 | 2024-04-30 | 2024-06-30 | 2024-04-30 | 2025-04-17 | 2025-12-31 | 2025-12-12 | 2025-12-12 | In-Flight | N/A | 2022-07-05 | Q3-2023: No date changes at this time
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016 | 2024 | 2024-10-11 | 2024-10-31 | 2024-08-26 | 2024-12-09 | 2025-05-30 | 2025-06-04 | 2025-06-04 | In-Flight | N/A | 2024-08-15 | Q3-2023: No date changes at this time
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | 2024 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | 2024-11-21 | In-Flight | NOC - TBD on Filing Date | 2023-02-15 | Q3-2023: No date changes at this time
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024 | 2025 | 2025-12-31 | 2025-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2025-12-01 | Q3-2023: No date changes at this time
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-11-30 | In-Flight | TBD | 2025-07-31 | Q3-2023: Improved ISD due to schedule/construction sequencing date adjustments.
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-04-30 | In-Flight | TBD | 2025-06-11 | Q3-2023: Improved ISD due to schedule/construction sequencing date adjustments.
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023 | 2023 |  | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | Initiating | TBD | 2023-10-01 | Q3-2023: No date changes at this time
South of Mesa Upgrade | PG&E | 2018-2019 | 2023 | 2026 | 2026-09-03 | 2026-05-26 | 2026-05-26 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | In Flight | NOC - TBD on Filing Date | 2025-10-03 | Q3-2023: No date changes at this time
South of San Mateo Capacity Increase | PG&E | 2007 | 2009 | 2027 | 2027-03-01 | 2027-03-01 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | Initiating | TBD | 2026-03-01 | Q3-2023: No date changes at this time
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-01-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2025-10-01 | Q3-2023: No date changes at this time
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA_230KV BUS REACTORS C – D | PG&E | 2018-2019 | 2023 | 2023 | 2023-10-31 | 2023-10-27 | 2023-09-28 | 2023-11-29 | 2023-12-19 | 2024-03-29 | 2024-03-29 | In-Flight | N/A | 2023-06-15 | Q3-2023: No date changes at this time
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020 | 2026 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-16 | 2027-08-16 | In-Flight | N/A | 2022-06-30 | Q3-2023: Program consists of 7 individually managed projects. No date changes at this time
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023 | 2026 | 2026-12-31 | 2026-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Initiating | TBD | 2024-12-01 | Q3-2023: No date changes at this time
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022 | 2026 | 2026-12-01 | 2026-12-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | Initiating | TBD | 2025-10-01 | Q3-2023: No date changes at this time
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023 | 2026 | 2026-07-10 | 2026-08-21 | 2025-08-18 | 2025-12-25 | 2025-12-30 | 2026-02-06 | 2026-02-06 | In-Flight | PTC - Q4 2023 | 2025-09-22 | Q3-2023: No date changes at this time
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019 | 2027 | 2027-04-01 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-05-08 | 2025-10-20 | 2025-10-20 | In Flight | N/A | 2025-03-28 | Q3-2023: No date changes at this time
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025 | 2025 |  | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | Initiating | TBD | 2024-10-01 | Q3-2023: No date changes at this time
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014 | 2025 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | 2026-05-29 | In-Flight | PTC: A.18-06-004 | 2024-02-01 | Q3-2023: Delay due to prioritization. This project is expected to be funded in 2024.
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017 | 2024 | 2024-12-27 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | In-Flight | NOC: AL 6047-E | 2022-06-01 | Q3-2023: No date changes at this time
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | Initiating | TBD | 2025-05-01 | Q3-2023: No date changes at this time
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020 |  |  | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | 2034-03-28 | In Flight | CPCN - TBD on Filing Date | 2030-03-25 | Q3-2023: Project to resume in 2024 per 2022-23 CAISO TPP
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | In Flight | N/A | 2025-02-17 | Q3-2023: No date changes at this time
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020 | 2022 | 2022-03-01 | 2022-12-14 | 2022-12-14 | 2024-02-23 | 2023-12-19 | 2023-11-27 | 2023-11-28 | In-Flight | NOC: AL 5293-E | 2021-01-05 | Q3-2023: No date changes at this time
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026 | 2026 | 2026-05-01 | 2026-05-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q3-2023: No date changes at this time
Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019 | 2024 | 2024-06-06 | 2027-06-03 | 2027-09-01 | 2027-11-30 | 2028-02-25 | 2028-05-23 | 2028-08-21 | In Flight | NOC: AL 5924-E | 2024-11-01 | Q3-2023: No date changes at this time
Equipment Upgrade at CCSF Owned Warnerville 230 kV Substation | PG&E | 2022-2023 | 2024 | [6 empty] | N/A | 2024-12-31 | Initiating | TBD | 2023-12-01 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Banta 60 kV Bus Voltage Conversion | PG&E | 2022-2023 | 2024 | [6 empty] | N/A | 2024-12-31 | Initiating | TBD | 2023-12-01 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Metcalf 230 / 115 kV Transformers Circuit Breaker Addition | PG&E | 2022-2023 | 2026 | [6 empty] | N/A | 2025-09-30 | In-Flight | TBD | 2025-01-01 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Lone Tree–Cayetano–Newark Corridor Series Compensation | PG&E | 2022-2023 | 2027 | [6 empty] | N/A | 2027-12-31 | Initiating | TBD | 2026-08-18 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
South Bay Area Limiting Element Upgrade | PG&E | 2022-2023 | 2027 | [6 empty] | N/A | 2027-12-31 | Initiating | TBD | 2026-08-18 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Tulucay-Napa #2 60 kV line Reconductoring project | PG&E | 2022-2023 | 2028 | [6 empty] | N/A | 2028-12-01 | Initiating | TBD | 2027-07-20 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Santa Rosa 115 kV lines Reconductoring project | PG&E | 2022-2023 | 2028 | [6 empty] | N/A | 2028-12-01 | Initiating | TBD | 2027-07-20 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Mesa 230/115kV Spare Transformer | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2029-05-01 | Initiating | TBD | 2027-12-18 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Los Banos 70 kV Area Reinforcement | PG&E | 2022-2023 | 2029 | [6 empty] | N/A | 2029-12-31 | Initiating | TBD | 2028-08-18 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Tesla 115 kV Bus Reconfiguration | PG&E | 2022-2023 | 2030 | [6 empty] | N/A | 2030-12-01 | Initiating | TBD | 2029-07-19 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Redwood City 115kV System Reinforcement | PG&E | 2022-2023 | 2030 | [6 empty] | N/A | 2030-12-01 | Initiating | TBD | 2029-07-19 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Pittsburg 115 kV Bus Reactor project | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-01 | Initiating | TBD | 2031-07-20 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Garberville Area Reinforcement | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-01 | Initiating | TBD | 2031-07-20 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Borden-Storey 230 kV 1 and 2 Line Reconductoring | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-31 | Initiating | TBD | 2031-08-19 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
North East Kern 115 kV Line Reconductoring | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-31 | Initiating | TBD | 2031-08-19 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Henrietta 230/115 kV Bank 3 Replacement | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-31 | Initiating | TBD | 2031-08-19 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Los Banos 230 kV Circuit Breakers Replacement | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-31 | Initiating | TBD | 2031-08-19 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan
Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project | PG&E | 2022-2023 | 2032 | [6 empty] | N/A | 2032-12-31 | Initiating | TBD | 2031-08-19 | Q3-2023: approved in 2022-2023 CAISO Transmission Plan

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | 2029-06-01 | 2029-06-01 | Licensing | 2009-09-01 | 2026-06-01 | Alberhill dates contingent on licensing
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 | N/A | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Engineering | N/A | 2024-04-01
Antelope-Whirlwind Line Upgrade | SCE | 2022-2023 | 2025 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | Pending | 2026-06-01 | 2026-06-30 | Design | N/A | 2025-05-29
Colorado River-Red Bluff 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | Design | N/A | 2025-05-12
Devers-Red Bluff 500 kV 1 and 2 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Devers-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | N/A | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | 2024-05-31 | 2024-05-01 | Design | Pending | 2023-11-01
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2013 | 2016 | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | Construction | 2018-05-01 | 2020-12-01
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2017 | 2018-12-31 | 2023-06-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | 2025-01-01 | 2025-01-25 | Construction | Exempt | Construction started | Joint SCE/LADWP project. SCE completed raising its towers and LADWP's are in progress. Substation upgrades (breakers and terminal equipment) require synchronizing outages with LADWP.
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-30 | Design | Exempt | 2024-10-01
Lugo-Mohave series capacitor upgrade | SCE | 2013 | 2016 | 2022-06-01 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | Construction | 2018-05-01 | 2020-12-01
Lugo-Victor-Kramer Upgrade (1/3) Add 3rd Lugo 500/230 kV Transformer | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Lugo-Victor-Kramer Upgrade (2/3) Reconductor Lugo–Victor 230 kV No. 1, 2, 3 & 4 lines using HTLS | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Lugo-Victor-Kramer Upgrade (3/3) Rebuild/build Kramer–Victor 115 kV lines to 230 kV and Loop the old segment of Kramer–Victor 115 kV into Roadway | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | 2028-12-01 | 2028-12-01 | Design | 2015-04-01 | 2024-09-25 | Project continues on hold. Expected construction start of September 2024 based on Riverside Coucil Approval (Estimated approval Oct 2023)
Mira Loma 500 kV CB Upgrade Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending
Mira Loma-Mesa Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
New Control 115 kV Shunt Reactor | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
New CoolwaterA 115/230 kV Bank | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
New Serrano 4AA Bank & 230kV GIS Rebuild | SCE | 2022-2023 | 2027 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2020 | 2023-06-01 | 2023-05-01 | 2023-06-23 | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-25 | Construction | Exempt | 2022-10-22 | Joint SCE/LADWP project. ISD for SCE’s portion of the project remains June 2024. Expected ISD of June 2025 includes LADWP's portion of the project.
San Bernardino-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
San Bernardino-Vista 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Serrano-Alberhill-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Serrano–Del Amo–Mesa 500 kV Transmission Reinforcement | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Sylmar Transformer Replacement | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Tie line Phasor Measurement Units | SCE | 2017-2018 | 44166 | 44531 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2024-02-28 | 2024-02-05 | Construction | N/A | Construction started | The in-service dates range from July 2023 to February 2024
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | Pending | 2025-04-01 | 2025-04-01 | 2025-04-30 | Design | N/A | 2024-06-17
Vista-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023

## SDGaE
Project | PTO | Transmission Plan Approved | In-Service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-12-01 |  | 2023-05-01 | 2021-11-01 | 2021-10-22 |  |  |  |  | Close-out | Exempt | 2021-05-17
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-06-01 |  | 2022-06-01 | 2022-12-14 | 2022-12-13 | Completed | Completed | In-Service | In-Service | Close-out | 2016-08-17 | 2020-06-10
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2022-11-01 |  | 2023-06-27 | 2023-08-25 | 2023-10-24 | Completed | Completed | In-Service | In-Service | Close-out | Exempt | 2021-07-26
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-04-01 | 2022-05-01 | 2022-05-02 | 2022-05-31 | 2022-05-15 | 2022-05-15 | 2022-05-15 | In-Service | In-Service | Close-out | Exempt | 2022-02-04
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2021-10-01 | 2022-11-01 | 2022-12-01 | 2022-12-09 | 2022-12-27 | 2022-11-18 | 2022-11-18 | In-Service | In-Service | Close-out | 2017-06-28 | 2021-01-19
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-05-01 | 2023-02-01 | 2022-09-01 | 2022-12-14 | 2022-12-27 | 2023-02-08 | 2023-02-08 | In-Service | In-Service | Close-out | 2017-11-15 | 2022-01-03
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2023-05-01 |  | 2023-12-01 | 2024-05-28 | 2024-05-28 | 2024-11-05 | 2024-11-05 | 2025-08-07 | 2024-02-01 | Construction | 2012-05-18 | 2018-06-29
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2027-06-01 | 2024-06-01 | 2024-05-02 | 2024-12-23 | 2024-12-23 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-26 | Design | Exempt | 2024-02-23
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2024-12-01 |  |  | 2022-08-24 | 2024-12-17 | 2024-12-17 | 2024-10-18 | 2024-08-07 | Design | Exempt | 2024-05-14
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 1905-07-08 | 2023-04-01 | 2023-02-01 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2023-02-13 | 2023-02-13 | 2026-02-24 | 2026-08-05 | Design | 2016-04-25 | 2025-06-18
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2026-06-01 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-06-08 | 2026-06-08 | 2026-07-29 | 2026-08-10 | Design | 2025-05-23 | 2026-05-04
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-11-01 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2026-11-10 | 2026-11-10 | 2026-12-09 | 2028-03-23 | Design | Exempt | 2027-03-16
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-11-01 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-11-14 | 2027-11-14 | 2027-11-14 | 2027-10-14 | Planning | 2026-07-24 | 2027-03-08
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2029-02-01 |  |  | 2024-08-15 | 2029-02-27 | 2029-02-27 | 2029-04-30 | 2029-09-28 | Planning | TBD | 2029-01-03
Miguel-Sycamore Canyon (TL23021) 230 kV line Loop-in to Suncrest | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
SG and OT Redundant Bus Differential Relay | SDG&E | 2022-2023 | 2024 |  | 2024 | [6 empty] | TBD | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Reconductor TL680C San Marcos -Melrose Tap | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
3 Ohm Series Reactor on Sycamore-Penasquitos 230 kV line | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Upgrade TL13820 Sycamore-Chicarita 138 kV | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD | Planning | TBD | TBD | Newly approved in 2022-2023 TPP

## VEA_GLW
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Current In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 1905-07-13 | 2021-09-01 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service | In service | In service |  | N/A | 2021 | In Service
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 |  | 2023-06-23 | 2023-09-23 | 2023-12-23 | In Flight | N/A | Sept-21
GLW/VEA area upgrades - revised scope | VEA/GLW | 2021-2022 (revised scope 2022-2023) | TBD |  | N/A | TBD | TBD | TBD | TBD | TBD | 2027-12-31 | Permitting, engineering and design | N/A | 2026-01-01 | The revised scope of the GLW/VEA area upgrades was approved in the 2022-2023 TPP.
Beatty 230 kV Project | VEA/GLW | 2022-2023 | 2027-12-31 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | Permitting, engineering and design | N/A | 2026-01-01

## DCRT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-24 | Inflight | Approved

## LSPower
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service April 2023 TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support (Orchard Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | Construction | 2021-02-19 | 2023-04-01
Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | Final Design | 2022-04-06 | Q4 2023 | Construction pending CPUC approval
Collinsville 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | Permitting | Q1 2024 | 2026
Manning 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | Permitting | Q1 2024 | 2026
Metcalf - San José B HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-04-01 | 2028-05-01 | Permitting | Q1 2024 | 2026
Newark - NRS HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-05-01 | 2028-04-01 | Permitting | Q1 2024 | 2026

## CitizensEnergy
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Previous TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | In-Flight |  | 2023-07-21