## PGaE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Apr 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013 | Q1-2021 | Q1-2021 | In-Service | N/A | Q4-2018 | (blank)
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | Q3-2021 | Q3-2021 | In-Service | N/A | Q4-2021 | (blank)
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 |  | Q2-2022 | Q2-2022 | In-Service | N/A | Q3-2021 | (blank)
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023 | Q3-2022 | Q3-2022 | In-Flight | N/A |  | (blank)
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020 | Q4-2022 | Q4-2022 | In-Flight | NOC: AL 5293-E |  | Q3: clearance moved from Q1 2022 due to Cogen Impacts then from to Q4 2022 due to system loading
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015 | Q1-2023 | Q4-2022 | In-Flight | PTC: A.17-12-010 |  | (blank)
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018 | Q4-2022 | Q4-2022 | In-Flight | N/A |  | (blank)
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019 | Q1-2023 | Q4-2022 | In-Flight | PTC: A.17-12-010 |  | (blank)
Giffen Line Reconductoring Project | PG&E | 2018-2019 |  | Q1-2023 | Q1-2023 | In-Flight | NOC: AL 6600-E | Q4-2022 | Q3: Generation impacts during clearances for 6 weeks.
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021 | Q1-2023 | Q1-2023 | In-Flight | NOC: AL 5390-E |  | Q3: Reconductoring from Oro loma to Defrancesco Tap is complete. Remaining scope Expected complete Q1-2023
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E |  |  | Q2-2023 | Q1-2023 | In-Flight | N/A | Q2-2022 | Q3: Fault duty comes into target level after all reactors are replaced
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015 | Q1-2023 | Q2-2023 | In-Flight | NOC: AL 5872E | Q2-2021 | (blank)
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA_230KV BUS REACTORS C – D | PG&E |  |  | Q4-2023 | Q3-2023 | In-Flight | N/A | Q1-2023 | Q3: Fault duty comes into target level after all reactors are replaced
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 |  | Q2-2023 | Q3-2023 | In-Flight | N/A | Q4-2021 | (blank)
Tesla 230 kV Bus Series Reactor project | PG&E | 2018-2019 | 2023 | Q4-2023 | Q3-2023 | In-Flight | N/A |  | (blank)
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013 | Q4-2023 | Q1-2024 | In-Flight | TBD | Q4-2023 | Q3: Delay due to reprioritization and execution risks (supply chain issues, resource constraints, etc).
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025 | Q2-2024 | Q2-2024 | In-Flight | N/A |  | Q3: DelayQ2-2024 Sensitive to supply chain risks and 3rd Party CEQA dependencies
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009 | Q2-2024 | Q2-2024 | In-Flight | N/A | Q3-2022 | Q3: Both XFMRs in-Service by Q2-2024
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017 | Q2-2024 | Q2-2024 | In-Flight | NOC: AL 6047-E |  | Q3: BW Line: Q2-2023; BC Line: Q2-2024
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021 | Q2-2024 | Q2-2024 | In-Flight | CPCN: A.17-12-021 |  | (blank)
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016 | Q3-2024 | Q2-2024 | In-Flight | N/A | Q2-2018 | (blank)
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016 | Q4-2024 | Q3-2024 | In-Flight | N/A | Q3-2023 | (blank)
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | Q3-2024 | Q3-2024 | In-Flight | TBD |  | (blank)
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014 | Q4-2024 | Q4-2024 | In-Flight | N/A |  | (blank)
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022 | Q1-2025 | Q4-2024 | In-Flight | N/A | Q3-2024 | Q3: Earlier ISD due to ISD used on specific order and not T.Dot
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019 | Q2-2023 | Q4-2024 | Initiating | TBD | Q1-2024 | Q3: Delay due to reprioritization, project has not been initiated yet
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023 | Q4-2024 | Q4-2024 | Initiating | TBD | Q4-2023 | (blank)
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019 | Q1-2025 | Q1-2025 | In-Flight | N/A | Q3-2024 | Q3: Construction Sequencing starting with 115kV side followed by 230kV side.
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011 | Q1-2025 | Q1-2025 | In-Flight | N/A | Q2-2024 | (blank)
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013 | Q2-2025 | Q2-2025 | In-Flight | N/A |  | (blank)
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025 | Q2-2025 | Q2-2025 | Initiating | TBD | Q4-2024 | (blank)
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025 | Q4-2025 | Q3-2025 | In-Flight | TBD |  | Q3: Reason for improvement: iterative schedule refinement as more information is gathered as the project progresses
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023 | Q3-2026 | Q3-2025 | In-Flight | TBD | Q1-2025 | Q3: Improved ISD due to reprioritization
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014 | Q1-2027 | Q3-2025 | In-Flight | PTC: A.18-06-004 | Q3-2024 | Q3: The current expected in-service date is July 2025. There was a reprioritization in 2021 that moved the expected in-service date into 2027, however, this was reversed after discussion with the CAISO.
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024 | Q4-2026 | Q4-2025 | Initiating | TBD | Q4-2024 | Q3: Improved ISD due to reprioritization
Metcalf 230 kV Substation Circuit Breaker #No 292 Upgrade | PG&E | 2021-2022 | 2025 | Q1-2025 | Q4-2025 | Initiating | TBD | Q2-2025 | Q3: Delay due to reprioritization, project has not been initiated yet
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019 | Q4-2024 | Q4-2025 | Initiating | TBD | Q4-2025 | Q3: Delay due to reprioritization, project has not been initiated yet
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023 | Q4-2026 | Q4-2025 | Initiating | TBD | Q4-2024 | Q3: Improved ISD due to reprioritization
Reedley 70 kV Reinforcement (Renamed to Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017 | Q3-2025 | Q4-2025 | In-Flight | N/A |  | (blank)
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019 | Q4-2025 | Q4-2025 | In Flight | N/A | Q1-2025 | (blank)
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026 | Q1-2026 | Q2-2026 | Initiating | TBD | Q1-2025 | Q3: Delay due to reprioritization, project not initiated yet
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | Q4-2025 | Q2-2026 | In-Flight | TBD |  | Q3: Reason for delay - Reprioritization, awaiting PM reassignment from project execution team
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024 | Q1-2026 | Q2-2026 | In-Flight | TBD |  | Q3: Reason for delay - Reprioritization, awaiting PM reassignment from project execution team
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028 | Q2-2028 | Q2-2026 | Initiating | TBD | Q2-2025 | Q3: Improved ISD due to reprioritization
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021 | Q2-2026 | Q2-2026 | In-Flight | NOC: AL 5200-E |  | (blank)
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019 | Q3-2025 | Q2-2026 | In Flight | NOC: AL 5026-E |  | Q3: The change in ISD is due to delays on the Midway Section D Bus Upgrade project that’s impacting our ISD schedule. The Midway-Kern #2 230kV depends on the Midway Section D Bus Upgrade project to provide a new open terminal position for the new 230kV line.
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022 | Q4-2026 | Q2-2026 | Initiating | TBD | Q4-2025 | Q3: Improved ISD due to reprioritization
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027 | Q2-2027 | Q2-2026 | Initiating | TBD | Q2-2025 | Q3: Improved ISD due to reprioritization
South of Mesa Upgrade | PG&E | 2018-2019 | 2023 | Q2-2026 | Q2-2026 | In Flight | NOC - Feb 2024 | Q4-2024 | (blank)
Estrella Substation Project | PG&E | 2013-2014 | 2019 | Q3-2026 | Q3-2026 | In-Flight | PTC: A.17-01-023 |  | (blank)
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021 | Q3-2026 | Q3-2026 | In-Flight | NOC - TBD on Filing Date |  | (blank)
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021 | Q4-2026 | Q4-2026 | In-Flight | NOC - TBD on Filing Date | Q2-2026 | (blank)
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024 | Q4-2026 | Q4-2026 | Initiating | TBD | Q4-2025 | (blank)
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026 | Q1-2026 | Q4-2026 | Initiating | TBD | Q2-2026 | Q3: Delay due to reprioritization, project has not been initiated yet
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | Q3-2026 | Q4-2026 | In Flight | NOC - May 2024 |  | (blank)
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022 | Q2-2026 | Q4-2026 | Initiating | TBD | Q4-2024 | Q3: Delay due to reprioritization, project has not been initiated yet
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026 | Q1-2026 | Q4-2026 | Initiating | TBD | Q2-2025 | Q3: Delay due to reprioritization, project has not been initiated yet
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024 | Q4-2025 | Q4-2026 | Initiating | TBD | Q4-2025 | Q3: Delay due to reprioritization, project has not been initiated yet
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020 | Q4-2026 | Q4-2026 | Initiating | TBD | Q1-2023 | (blank)
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027 | Q2-2027 | Q2-2027 | Initiating | TBD | Q4-2025 | (blank)
South of San Mateo Capacity Increase | PG&E | 2007 | 2009 | Q1-2027 | Q2-2027 | Initiating | TBD | Q1-2026 | Q3: Delay due to reprioritization, project not initiated yet
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016 | Q3-2027 | Q3-2027 | In Flight | NOC - TBD on Filing Date |  | (blank)
Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019 | Q2-2027 | Q3-2027 | In Flight | NOC: AL 5924-E | Q4-2024 | (blank)
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | Q3-2027 | Q3-2027 | In Flight | N/A | Q2-2025 | (blank)
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | (blank)
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023 | Q4-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | (blank)
Mosher Transmission Project | PG&E | 2013-2014 | 2017 | Q4-2027 | Q4-2027 | In Flight | NOC - April 2026 | Q1-2027 | (blank)
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027 | Q2-2027 | Q4-2027 | Initiating | TBD | Q4-2026 | Q3: Delay due to reprioritization, project has not been initiated yet
Maple Creek Reactive Support | PG&E | 2009 | 2011 | Q3-2026 | Q4-2027 | Initiating | TBD | Q4-2026 | Q3: Delay due to reprioritization, project has not been initiated yet
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008 | Q2-2029 | Q4-2027 | Initiating | N/A | Q4-2026 | Q3: Improved ISD due to reprioritization
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027 | Q1-2027 | Q4-2027 | Initiating | N/A | Q4-2025 | Q3: Delay due to reprioritization, project has not been initiated yet
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022 | Q1-2028 | Q1-2028 | In-Flight | N/A |  | (blank)
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022 | Q2-2028 | Q2-2028 | In-Flight | TBD | Q1-2027 | (blank)
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018 | Q1-2028 | Q2-2028 | In Flight | NOC - April 2026 |  | (blank)
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022 | Q4-2028 | Q2-2028 | Initiating | TBD | Q1-2025 | Q3: Improved ISD due to reprioritization
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012 | Q1-2027 | Q4-2028 | Initiating | TBD | Q4-2027 | Q3: Delay due to reprioritization, project has not been initiated yet
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021 | Q4-2027 | Q4-2028 | Initiating | TBD | Q4-2027 | Q3: Delay due to reprioritization, project has not been initiated yet
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024 | Q4-2027 | Q4-2028 | Initiating | TBD | Q4-2027 | Q3: Delay due to reprioritization, project has not been initiated yet
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028 | Q1-2028 | Q4-2028 | Initiating | TBD | Q2-2026 | Q3: Delay due to reprioritization, project has not been initiated yet
New Manning 500 kV substation | PG&E | 2021-2022 | 2028 | Q1-2028 | Q4-2028 | Initiating | TBD | Q1-2027 | Q3: Delay due to reprioritization, project has not been initiated yet
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028 | Q1-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q3: Delay due to reprioritization, project has not been initiated yet
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028 | Q1-2028 | Q4-2028 | Initiating | TBD | Q4-2027 | Q3: Delay due to reprioritization, project has not been initiated yet
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028 | Q1-2028 | Q4-2028 | Initiating | TBD | Q1-2026 | Q3: Delay due to reprioritization, project has not been initiated yet
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026 | Q2-2026 | Q4-2028 | Initiating | TBD | Q4-2027 | Q3: Delay due to reprioritization, project has not been initiated yet
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017 | Q4-2028 | Q1-2029 | In-Flight | CPCN Expected Q3 2022 |  | Q3: CEQA process presently under way
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022 | Q2-2029 | Q2-2029 | In Flight | TBD | Q3-2027 | (blank)
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020 | Q2-2029 | Q2-2029 | On-Hold (CAISO) | CPCN - TBD on Filing Date | Q3-2025 | (blank)
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019 | Q4-2029 | Q4-2029 | On-Hold (CAISO) | CPCN - TBD on Filing Date | Q1-2024 | (blank)
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028 | Q1-2028 | Q4-2029 | Initiating | TBD | Q4-2028 | Q3: Delay due to reprioritization, project has not been initiated yet
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015 | Q4-2030 | Q4-2030 | Initiating | TBD |  | (blank)
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023 |  |  | On-Hold (CAISO) | TBD |  | (blank)

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date Apr 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Laguna Bell Corridor Upgrade | SCE | 2015 | 2020-12-31 | N/A | N/A | In-Service | N/A | N/A | Currently in-service; completed as a portion of Mesa 500 kV Substation Loop-In
Moorpark-Pardee No. 4 230 kV Circuit | SCE | 2018 | 2020-12-31 | N/A | N/A | In-Service | N/A | N/A | In-service January 2022
Mesa 500 kV Substation Loop-In | SCE | 2014 | 2020-12-01 | 2022-05-31 | 2022-05-22 | In-Service | N/A | N/A | In-service May 2022
Lugo-Mohave series capacitor upgrade | SCE | 2013 | 2016 | 2023-06-01 | 2023-06-01 | Construction | 2018-05-01 | 2020-12-01
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2013 | 2016 | 2023-06-01 | 2023-06-01 | Construction | 2018-05-01 | 2020-12-01
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-04-01 | 2024-12-01 | Design | Exempt | 2024-10-01
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2017 | 2018-12-31 | 2025-01-25 | 2025-01-25 | Construction | Exempt | Construction started | Joint SCE/LADWP project. SCE completed raising its towers and LADWP's are in progress. Substation upgrades (breakers and terminal equipment) require synchronizing outages with LADWP.
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | 2025-10-01 | 2027-04-01 | Permitting | 2009-09-01 | Pending | Alberhill dates contingent on licensing
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2027-07-01 | Design | 2015-04-01 | 2023-05-01
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2020 | 2023-06-01 | 2024-06-01 | 2024-06-01 | Design | Exempt | 2022-10-22
Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 2025-12-01 | 2025-12-01 | Construction | N/A | Construction started | The in-service dates range from September 2022 to December 2025
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | 2023-12-01 | 2023-12-01 | Planning | Pending | Pending
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 | 2025-12-01 | 2025-12-01 | Planning | N/A | Pending
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | Pending | Pending | Initiation | N/A | Pending
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | Pending | Pending | Initiation | N/A | Pending
* Joint SCE/LADWP project. Date indicated only includes SCE scope

## SDGaE
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Apr 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-12-14 | 2022-12-27 | Construction | 2017-11-15 | 2022-01-03
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-12-14 | 2022-12-13 | Construction | 2016-08-17 | 2020-06-10
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2024-12-23 | 2024-12-23 | Design | 2023-08-22 | 2024-08-19
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-11-01 | 2021-10-22 | Close-out | Exempt | 2021-05-17
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2023-08-25 | 2023-10-24 | Construction | Exempt | 2021-07-26
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2024-05-28 | 2024-05-28 | Construction | 2012-05-18 | 2018-06-29
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-20 | 2027-12-20 | Design | 2026-07-24 | 2027-04-12
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2028-11-27 | 2026-05-13 | Design | 2023-09-01 | 2024-03-01
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-05-31 | 2022-05-15 | Construction | Exempt | 2022-02-04
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2022-12-09 | 2022-12-27 | Construction | 2017-06-28 | 2021-01-19
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2026-03-30 | 2026-11-25 | Design | Exempt | 2025-03-20
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 1905-07-08 | 2024-12-17 | 2025-10-24 | Design | 2016-04-25 | 2024-08-09
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 2022-06-01 | 2024-08-15 | 2024-08-15 | Planning | TBD | 2024-07-19 | Added
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 2022-06-01 | 8/15/2024 | 8/15/2024 | Planning | TBD | TBD | Added

## VEA_GLW
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date April 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 2021 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service | In service | N/A | 2021
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | June-22 | 2022-12-20 | In Flight | N/A | Sept-21
GLW/VEA area upgrades | VEA/GLW | 2021-2022 | TBD | TBD | TBD | Permitting, engineering and design | N/A | TBD

## DCRT
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date Apr 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 |  | Approved

## LSPower
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date Apr 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01
Round Mountain 500 kV Dynamic Voltage Support | LS Power | 2018-2019 | 2024 | 2024-12-01 | 2024-12-01

## CitizensEnergy
Project | PTO | Transmissino Plan Approed | In-service Date at Approval in Transmission Plan | Expected In-Service Date Apr 2022 TDF | Current Expected In-service date | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023