## PGaE
Project | PTO | Transmission Plan Approved | In-service Year at Approval in Transmission Plan | Expected In-Service Year (2020-2021 Transmission Plan) | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service Jul 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Expected In-Service Oct 2023 TDF | Project Status | Expected CPUC Filing | Expected Const start | Notes
Cooley Landing-Palo Alto and Ravenswood-Cooley Landing 115 kV Lines Rerate | PG&E | 2008 | 2015 | 2022 | 2022-11-01 | 2023-03-15 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 | 2022-09-22 | In-Service
Kasson – Kasson Junction 1 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2027 | 2027-06-28 | 2025-11-12 | 2026-04-09 | 2026-08-07 | 2026-10-02 | 2023-11-22 | 2023-12-19 | 2023-09-25 | In-Service | N/A | 2023-09-21 | In-Service
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013 | 2025 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | In-Service | N/A | 2018-10-16 | In-Service
North of Mesa Upgrade (formerly Midway-Andrew 230 kV Project) | PG&E | 2012-2013 | 2019 |  |  | 2029-12-04 | 2029-12-04 | 2029-12-04 | 2029-08-28 | 2032-10-21 | 2032-10-21 | 2029-12-04 | Cancelled | CPCN - TBD on Filing Date | 2024-01-02 | Cancelled per CAISO 2022-2023 Transmission Plan
Oakland Clean Energy Initiative (Oakland X 115kV Bus Upgrade) | PG&E | 2017-2018 |  | 2023 |  | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24 | In-Service | N/A | 2021-08-03 | In-Service
Palermo – Wyandotte 115 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2023 | 2022 | 2022-07-06 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | In-Service | N/A | 2021-07-01 | In-Service
Ravenswood – Cooley Landing 115 kV Line Reconductor | PG&E | 2017-2018 | 2019 | 2023 | 2023-01-13 | 2023-01-16 | 2022-12-30 | 2022-12-30 | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-15 | In-Service | PTC: A.17-12-010 | 2022-09-22 | In-Service
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | PG&E | 2018-2019 | 2023 | 2023 | 2023-10-31 | 2023-04-05 | 2023-03-28 | 2023-05-01 | 2023-06-13 | 2023-07-27 | 2023-06-14 | 2023-06-14 | In-Service | N/A | 2022-04-19 | In-Service
Vaca Dixon Area Reinforcement (Replace Bank 5) | PG&E | 2017-2018 | 2023 | 2026 | 2022-08-31 | 2022-07-29 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-11 | 2022-08-11 | 2022-08-11 | In-Service | N/A | 2021-07-26 | In-Service
Atlantic 230/60 kV transformer voltage regulator | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-12-01 | Initiating | TBD | 2026-03-01 | Q4-2023: Project Delayed due to Reprioritization
Banta 60 kV Bus Voltage Conversion | PG&E | 2022-2023 | 2024 | [5 empty] | (blank) | N/A | 2024-12-31 | 2027-12-01 | Initiating | TBD | 2026-03-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025 | 2027 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2026-04-01 | Initiating | TBD | 2025-10-01 | Q4-2023: Improved ISD due to Reprioritization
Borden-Storey 230 kV 1 and 2 Line Reconductoring | PG&E | 2022-2023 | 2032 | [5 empty] | (blank) | N/A | 2032-12-31 | 2029-05-01 | Initiating | TBD | 2026-10-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Cascade 115/60 kV No.2 Transformer Project | PG&E | 2010-2011 | 2014 | 2023 | 2023-12-29 | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2025-07-11 | In-Flight | N/A | 2019-07-09 | Q4-2023: Project Delayed
Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022 | 2028 | 2028-12-01 | 2028-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | Initiating | TBD | 2027-01-01 | Q4-2023: No date changes at this time.
Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012 | 2027 | 2027-02-01 | 2027-02-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-07-01 | Initiating | TBD | 2027-01-01 | Q4-2023: Project Delayed due to Reprioritization
Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022 | 2029 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-26 | 2029-06-26 | 2029-06-26 | In Flight | N/A | 2027-08-05 | Q4-2023: No date changes at this time.
Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025 | 2025 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | In-Flight | TBD | 2024-04-02 | Q4-2023: No date changes at this time.
Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2026-03-01 | Q4-2023: No date changes at this time.
Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-05-01 | Initiating | TBD | 2026-10-01 | Q4-2023: Improved ISD due to Reprioritization
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | Initiating | TBD | 2025-10-01 | Q4-2023: No date changes at this time.
Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022 | 2025 | 2025-10-02 | 2025-03-31 | 2024-12-24 | 2026-02-26 | 2026-02-26 | 2026-03-25 | 2025-11-12 | 2026-10-05 | In-Flight | N/A | 2025-02-19 | Q4-2023: Project Delayed
Cottonwood 230/115 kV Transformers 1 and 4 Replacement Project | PG&E | 2017-2018 | 2019 | 2024 | 2024-10-02 | 2025-03-31 | 2025-02-14 | 2025-05-15 | 2025-08-11 | 2025-07-18 | 2025-11-19 | 2026-10-20 | In-Flight | N/A | 2025-02-19 | Q4-2023: Project Delayed
Dinuba Energy Storage (Rescoped from Reedley 70 kV Area Reinforcement Projects) | PG&E | 2017-2018 | 2017 | 2025 | 2025-12-25 | 2025-08-14 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | TBD | In Flight | N/A | TBD | Q4-2023: The Reedley 70 kV Area Reinforcement Project (Dinuba Energy Storage) is not officially on hold from CAISO. However, with evolved needs, CAISO is considering a potential re-scope in the current 2023-2024 cycle of TPP. PG&E submitted a proposal pending approval.
East Marysville 115/60 kV Project | PG&E | 2018-2019 | 2022 | 2027 | 2027-11-10 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | In-Flight | N/A | 2026-05-13 | Q4-2023: No date changes at this time.
East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-31 | 2026-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Initiating | TBD | 2025-04-01 | Q4-2023: No date changes at this time.
East Shore-Oakland J 115 kV Reconductoring Project (name changed from East Shore-Oakland J 115 kV Reconductoring Project & Pittsburg-San Mateo 230 kV Looping Project since only the 115 kV part was approved) | PG&E | 2011-2012 | 2015 | 2022 | 2022-12-23 | 2023-03-10 | 2023-05-31 | 2023-05-31 | 2023-12-29 | 2023-12-29 | 2023-12-29 | 2023-12-29 | In-Flight | NOC: AL 5872-E | 2021-06-01 | Q4-2023: No date changes at this time.
Equipment Upgrade at CCSF Owned Warnerville 230 kV Substation | PG&E | 2022-2023 | 2024 | [5 empty] | (blank) | N/A | 2024-12-31 | 2023-04-28 | In-Service | TBD | 2023-02-16 | Q4-2023: Scope extensions to the previously approved project Bellota-Warrenville 230kV Reinforcement (T.0000043). Approved in 2022-2023 CAISO Transmission Plan. In-Service
Estrella Substation Project | PG&E | 2013-2014 | 2019 | 2026 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | 2029-07-16 | 2029-11-01 | In-Flight | PTC: A.17-01-023 | 2024-11-27 | Q4-2023: Project Delayed
Garberville Area Reinforcement | PG&E | 2022-2023 | 2032 | [5 empty] | (blank) | N/A | 2032-12-01 | 2030-12-31 | Initiating | TBD | 2025-06-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Gates 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2025 | 2025 | 2025-03-28 | 2024-06-03 | 2024-04-30 | 2024-04-30 | 2024-07-12 | 2024-08-30 | 2024-12-04 | 2024-09-30 | In-Flight | N/A | 2023-04-03 | Q4-2023: schedule/construction sequencing date adjustments.
Giffen Line Reconductoring Project | PG&E | 2018-2019 |  | 2023 | 2023-01-13 | 2023-01-19 | 2023-01-11 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2023-12-29 | 2023-12-29 | In-Flight | NOC: AL 6600-E | 2023-11-02 | Q4-2023: No date changes at this time.
Glenn 230/60 kV Transformer No. 1 Replacement | PG&E | 2013-2014 | 2018 | 2022 | 2022-12-21 | 2022-12-12 | 2022-10-19 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-16 | 2024-05-30 | In-Flight | N/A | 2020-04-30 | Q4-2023: Project Delayed
Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022 | 2028 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | In-Flight | TBD | 2027-02-15 | Q4-2023: No date changes at this time.
Henrietta 230/115 kV Bank 3 Replacement | PG&E | 2022-2023 | 2032 | [5 empty] | (blank) | N/A | 2032-12-31 | 2027-06-01 | Initiating | TBD | 2025-10-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021 | 2026 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | In Flight | NOC - TBD on Filing Date | 2025-07-24 | Q4-2023: No date changes at this time.
Ignacio Area Upgrade | PG&E | 2017-2018 | 2023 | 2027 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2026-12-01 | Q4-2023: No date changes at this time.
Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022 | 2026 | 2026-05-01 | 2026-05-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Initiating | TBD | 2025-10-01 | Q4-2023: No date changes at this time.
Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016 | 2027 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2029-08-10 | In Flight | NOC - TBD on Filing Date | 2027-01-08 | Q4-2023: Project Delayed due to Reprioritization
Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021 | 2027 | 2027-12-31 | 2027-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-10-01 | Q4-2023: No date changes at this time.
Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017 | 2027 | 2027-06-21 | 2028-12-29 | 2029-01-01 | 2029-01-01 | 2029-01-01 | 2029-01-11 | 2029-01-11 | 2029-06-08 | In-Flight | CPCN: A.23-09-001 Filed & Under Review | 2028-04-05 | Q4-2023: Project Delayed
Lone Tree–Cayetano–Newark Corridor Series Compensation | PG&E | 2022-2023 | 2027 | [5 empty] | (blank) | N/A | 2027-12-31 | 2027-12-01 | Initiating | TBD | 2027-03-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Los Banos 230 kV Circuit Breakers Replacement | PG&E | 2022-2023 | 2032 | [5 empty] | (blank) | N/A | 2032-12-31 | 2028-04-01 | Initiating | TBD | 2026-07-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Los Banos 70 kV Area Reinforcement | PG&E | 2022-2023 | 2029 | [5 empty] | (blank) | N/A | 2029-12-31 | 2028-12-01 | Initiating | TBD | 2026-10-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Manteca #1 60 kV Line Section Reconductoring Project | PG&E | 2020-2021 | 2024 | 2027 | 2027-06-28 | 2026-01-14 | 2026-06-19 | 2026-10-19 | 2025-01-15 | 2025-01-31 | 2025-02-20 | 2025-01-06 | In-Flight | TBD | 2024-10-07 | Q4-2023: schedule/construction sequencing date adjustments.
Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-05-31 | Initiating | TBD | 2026-01-01 | Q4-2023: Project Delayed due to Reprioritization
Maple Creek Reactive Support | PG&E | 2009 | 2011 | 2026 | 2026-07-01 | 2026-07-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-01-01 | Q4-2023: No date changes at this time.
Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021 | 2024 | 2024-05-24 | 2024-05-10 | 2024-05-24 | 2025-11-14 | 2025-11-13 | 2025-11-13 | 2026-04-23 | 2027-02-12 | In-Flight | CPCN: A.17-12-021 | 2024-02-07 | Q4-2023: Project Delayed
Mesa 230/115kV Spare Transformer | PG&E | 2022-2023 | 2032 | [5 empty] | (blank) | N/A | 2029-05-01 | 2028-04-01 | Initiating | TBD | 2027-01-15 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Metcalf 230 / 115 kV Transformers Circuit Breaker Addition | PG&E | 2022-2023 | 2026 | [5 empty] | (blank) | N/A | 2025-09-30 | 2027-06-01 | Initiating | TBD | 2026-06-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade | PG&E | 2003 | 2008 | 2029 | 2029-04-01 | 2029-04-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | Initiating | TBD | 2026-01-01 | Q4-2023: Improved ISD due to Reprioritization
Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019 | 2024 | 2024-06-06 | 2025-07-03 | 2026-06-23 | 2026-06-23 | 2027-04-07 | 2027-04-07 | 2027-04-07 | 2027-04-29 | In Flight | NOC: AL 5026-E | 2018-11-01 | Q4-2023: No date changes at this time.
Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019 | 2024 | 2024-06-06 | 2027-06-03 | 2027-09-01 | 2027-11-30 | 2028-02-25 | 2028-05-23 | 2028-08-21 | 2027-10-28 | In Flight | NOC: AL 5924-E | 2024-11-01 | Q4-2023: Improved ISD due to Reprioritization
Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Midway 230kV Bus Section D Upgrade Project) | PG&E | 2010-2011 | 2013 | 2025 | 2025-05-01 | 2025-05-01 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-08-29 | 2025-08-29 | In-Flight | N/A | 2021-04-07 | Q4-2023: No date changes at this time.
Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018 | 2027 | 2027-10-20 | 2028-02-16 | 2028-05-16 | 2028-08-14 | 2028-11-09 | 2029-02-05 | 2029-04-06 | 2029-08-01 | In Flight | NOC - TBD on Filing Date | 2026-07-22 | Q4-2023: Project Delayed due to Reprioritization. Activities will resume in 2024.
Monta Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016 | 2024 | 2024-08-06 | 2024-07-17 | 2024-05-08 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-01 | 2025-08-07 | In-Flight | N/A | 2018-06-18 | Q4-2023: No date changes at this time.
Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024 | 2027 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-01-01 | Q4-2023: No date changes at this time.
Moraga-Castro Valley 230 kV Line Capacity Increase Project | PG&E | 2010-2011 | 2013 | 2025 | 2023-09-22 | 2023-11-06 | 2024-03-07 | 2024-03-20 | 2024-06-20 | 2024-10-25 | 2024-10-16 | 2026-03-25 | In-Flight | TBD | 2026-01-14 | Q4-2023: Long lead meterials scheduled to arrive in Q2 2024.
Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023 |  |  |  | TBD | TBD | TBD | TBD | TBD | TBD | On-Hold (CAISO) | TBD | TBD | Q4-2023: Project on CAISO Hold
Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2013-2014 | 2021 | 2026 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2027-09-29 | 2027-09-29 | 2027-09-29 | 2029-01-30 | In Flight | NOC: AL 5200-E | 2025-07-29 | Q4-2023: Project Delayed
Mosher Transmission Project | PG&E | 2013-2014 | 2017 | 2027 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | In Flight | NOC - TBD on Filing Date | 2027-01-20 | Q4-2023: No date changes at this time.
Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026 | 2026 |  | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2028-04-01 | Initiating | TBD | 2026-10-01 | Q4-2023: Project Delayed due to Reprioritization
New Collinsville 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-31 | In-Flight | TBD | 2026-04-07 | Q4-2023: Improved ISD
New Manning 500 kV substation | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-01 | In-Flight | TBD | 2026-06-01 | Q4-2023: Improved ISD
Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024 | 2026 | 2026-12-01 | 2026-12-01 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-01 | Initiating | TBD | 2026-03-01 | Q4-2023: No date changes at this time.
Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019 | 2022 | 2022-11-01 | 2023-04-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-06-01 | Initiating | TBD | 2025-03-01 | Q4-2023: Project Delayed due to Reprioritization
North East Kern 115 kV Line Reconductoring | PG&E | 2022-2023 | 2032 |  | 2028-11-09: (blank); 2029-02-05: N/A; 2029-04-06: 2032-12-31; 2029-08-01: 2033-12-31 | Initiating | TBD | 2026-12-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015 | 2030 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2028-02-01 | Initiating | TBD | 2027-01-01 | Q4-2023: Improved ISD due to Reprioritization
Oakland Clean Energy Initiative (MORAGA 115KV BUS UPGRADE & BK 3 SW) | PG&E | 2017-2018 |  | 2023 | 2023-03-04 | 2023-05-19 | 2023-07-18 | 2023-11-21 | 2023-10-30 | 2025-04-01 | 2025-04-30 | 2025-04-30 | In-Flight | N/A | 2021-11-16 | Q4-2023: No date changes at this time. In-Service date is subject to change as construction and clearances sequencing changes.
Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | 2027-01-29 | In Flight | NOC - TBD on Filing Date | 2026-01-23 | Q4-2023: No date changes at this time.
Panoche – Ora Loma 115 kV Line Reconductoring | PG&E | 2015-2016 | 2021 | 2023 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2022-12-30 | 2024-05-31 | 2024-03-27 | 2024-03-27 | 2024-03-27 | In-Flight | NOC: AL 5390-E | 2022-01-17 | Q4-2023: No date changes at this time.
Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project | PG&E | 2022-2023 | 2032 |  | 2028-11-09: (blank); 2029-02-05: N/A; 2029-04-06: 2032-12-31; 2029-08-01: 2028-04-28 | In-Flight | TBD | 2026-06-01 | Q4-2023: Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project is being implemented under New Manning 500 kV substation. Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Pittsburg 115 kV Bus Reactor project | PG&E | 2022-2023 | 2032 |  | 2028-11-09: (blank); 2029-02-05: N/A; 2029-04-06: 2032-12-01; 2029-08-01: 2028-05-12 | In-Flight | TBD | 2026-04-07 | Q4-2023: Pittsburg 115 kV Bus Reactor project is being implemented under New Collinsville 500 kV substation. Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011 | 2025 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2026-06-17 | 2026-06-17 | 2026-09-04 | In-Flight | N/A | 2025-04-01 | Q4-2023: schedule/construction sequencing date adjustments.
Ravenswood 230/115 kV transformer #1 Limiting Facility Upgrade | PG&E | 2018-2019 | 2019 | 2024 | 2024-12-01 | 2024-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-06-01 | Initiating | TBD | 2025-03-01 | Q4-2023: Improved ISD due to Reprioritization
Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-01-01 | Q4-2023: No date changes at this time.
Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2028-12-01 | Initiating | TBD | 2027-01-01 | Q4-2023: Improved ISD due to Reprioritization
Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021 | 2025 | 2025-11-19 | 2026-08-18 | 2026-08-18 | 2030-05-23 | 2031-11-19 | 2029-03-30 | 2028-11-07 | 2028-05-23 | In-Flight | NOC - TBD on Filing Date | 2025-08-15 | Q4-2023: Improved ISD
Redwood City 115kV System Reinforcement | PG&E | 2022-2023 | 2030 |  | 2028-11-09: (blank); 2029-02-05: N/A; 2029-04-06: 2030-12-01; 2029-08-01: 2029-12-01 | Initiating | TBD | 2026-12-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Rio Oso 230/115 kV Transformer Upgrades | PG&E | 2007 | 2009 | 2024 | 2024-04-30 | 2024-06-30 | 2024-04-30 | 2025-04-17 | 2025-12-31 | 2025-12-12 | 2025-12-12 | 2025-12-12 | In-Flight | N/A | 2022-07-05 | Q4-2023: No date changes at this time.
Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016 | 2024 | 2024-10-11 | 2024-10-31 | 2024-08-26 | 2024-12-09 | 2025-05-30 | 2025-06-04 | 2025-06-04 | 2025-06-19 | In-Flight | N/A | 2024-10-15 | Q4-2023: No date changes at this time.
Round Mountain 500 kV Dynamic Voltage Support | PG&E | 2018-2019 | 2024 | 2024 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | 2024-11-21 | 2024-12-31 | In-Flight | NOC - TBD on Filing Date | 2023-02-15 | Q4-2023: schedule/construction sequencing date adjustments.
Salinas-Firestone #1 and #2 60 kV Lines | PG&E | 2019-2020 | 2024 | 2025 | 2025-12-31 | 2025-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-12-01 | Initiating | TBD | 2025-12-01 | Q4-2023: Project Delayed due to Reprioritization
San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-11-30 | 2028-04-01 | In-Flight | TBD | 2026-07-14 | Q4-2023: Project Delayed
San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028 | 2028 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-04-30 | 2028-05-01 | In-Flight | TBD | 2026-07-11 | Q4-2023: schedule/construction sequencing date adjustments.
Santa Rosa 115 kV lines Reconductoring project | PG&E | 2022-2023 | 2028 |  | 2028-11-09: (blank); 2029-02-05: N/A; 2029-04-06: 2028-12-01; 2029-08-01: 2028-12-01 | Initiating | TBD | 2026-12-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023 | 2023 |  | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-12-23 | In-Flight | TBD | 2025-07-09 | Q4-2023: Project Delayed
South Bay Area Limiting Element Upgrade | PG&E | 2022-2023 | 2027 |  | 2028-11-09: (blank); 2029-02-05: N/A; 2029-04-06: 2027-12-31; 2029-08-01: 2026-03-01 | Initiating | TBD | 2025-06-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
South of Mesa Upgrade | PG&E | 2018-2019 | 2023 | 2026 | 2026-09-03 | 2026-05-26 | 2026-05-26 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-15 | In Flight | NOC - TBD on Filing Date | 2025-10-17 | Q4-2023: No date changes at this time.
South of San Mateo Capacity Increase | PG&E | 2007 | 2009 | 2027 | 2027-03-01 | 2027-03-01 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2028-12-01 | Initiating | TBD | 2027-01-01 | Q4-2023: Project Delayed due to Reprioritization
Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-01-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-06-01 | Initiating | TBD | 2027-07-01 | Q4-2023: Project Delayed due to Reprioritization
Tesla 115 kV Bus Reconfiguration | PG&E | 2022-2023 | 2030 |  | 2028-11-09: (blank); 2029-02-05: N/A; 2029-04-06: 2030-12-01; 2029-08-01: 2028-06-01 | Initiating | TBD | 2026-07-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Tesla Substation 230 kV bus section D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS C - D | PG&E | 2018-2019 | 2023 | 2023 | 2023-10-31 | 2023-10-27 | 2023-09-28 | 2023-11-29 | 2023-12-19 | 2024-03-29 | 2024-03-29 | 2024-03-29 | In-Flight | N/A | 2023-06-15 | Q4-2023: No date changes at this time.
Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020 | 2026 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-16 | 2027-08-16 | 2028-02-09 | In-Flight | N/A | 2024-02-15 | Q4-2023: Program consists of 7 individually managed projects. Project delayed.
Tulucay-Napa #2 60 kV Line Capacity Increase | PG&E | 2019-2020 | 2023 | 2026 | 2026-12-31 | 2026-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | N/A | In-Service | TBD | N/A | Q4-2023: Tulucay-Napa #2 60 kV Line Capacity Increase project approved in 2020: this project would upgrade line terminals in Tulucay and Basalt subs. PG&E discovered that with records update, it was found the substation equipment already met ampacity requirement. So this project is no longer needed.
Tulucay-Napa #2 60 kV line Reconductoring project | PG&E | 2022-2023 | 2028 |  | 2028-11-09: (blank); 2029-02-05: N/A; 2029-04-06: 2028-12-01; 2029-08-01: 2026-12-31 | Initiating | TBD | 2025-12-01 | Q4-2023: Approved in 2022-2023 CAISO Transmission Plan. Updated dates from what was provided in 2022-2023 CAISO Transmission Plan to dates upon project inclusion in PG&E's Investment Plan.
Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022 | 2026 | 2026-12-01 | 2026-12-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-03-01 | Initiating | TBD | 2026-03-01 | Q4-2023: Project Delayed due to Reprioritization
Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023 | 2026 | 2026-07-10 | 2026-08-21 | 2025-08-18 | 2025-12-25 | 2025-12-30 | 2026-02-06 | 2026-02-06 | 2026-04-29 | In-Flight | PTC - Q1 2024 | 2025-06-25 | Q4-2023: schedule/construction sequencing date adjustments.
Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019 | 2027 | 2027-04-01 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-05-08 | 2025-10-20 | 2025-10-20 | 2026-07-17 | In Flight | N/A | 2025-12-25 | Q4-2023: Project Delayed
Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025 | 2025 |  | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-06-01 | Initiating | TBD | 2025-03-01 | Q4-2023: schedule/construction sequencing date adjustments.
Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014 | 2025 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | 2026-05-29 | 2026-07-31 | In-Flight | PTC: A.18-06-004 | 2023-11-03 | Q4-2023: schedule/construction sequencing date adjustments.
Warnerville-Bellota 230 kV line reconductoring | PG&E | 2012-2013 | 2017 | 2024 | 2024-12-27 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-05-31 | In-Flight | NOC: AL 6047-E | 2022-06-01 | Q4-2023: schedule/construction sequencing date adjustments.
Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027 | 2027 |  | 2027-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-05-31 | Initiating | TBD | 2025-04-01 | Q4-2023: Project Delayed due to Reprioritization
Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020 |  |  | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | 2034-03-28 | 2029-05-04 | In Flight | CPCN - TBD on Filing Date | 2025-07-10 | Q4-2023: Improved ISD due to Reprioritization
Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015 | 2026 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | In Flight | N/A | 2025-02-17 | Q4-2023: No date changes at this time.
Wilson-Le Grand 115 kV line reconductoring | PG&E | 2012-2013 | 2020 | 2022 | 2022-03-01 | 2022-12-14 | 2022-12-14 | 2024-02-23 | 2023-12-19 | 2023-11-27 | 2023-11-28 | 2023-12-22 | In-Flight | NOC: AL 5293-E | 2021-01-05 | Q4-2023: schedule/construction sequencing date adjustments.
Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026 | 2026 | 2026-05-01 | 2026-05-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | TBD | 2027-12-01 | Q4-2023: No date changes at this time.

## SCE
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | Licensing | 2009-09-01 | 2026-06-01 | Alberhill dates contingent on licensing
Antelope 66 kV Circuit Breaker Duty Mitigation Project | SCE | 2021-2022 | 2026 | N/A | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Engineering | N/A | 2024-04-01 | No change in the expected ISD between July and October TDFs
Antelope-Whirlwind Line Upgrade | SCE | 2022-2023 | 2025 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | Pending | 2026-06-01 | 2026-06-30 | 2026-06-30 | Design | N/A | 2025-05-29 | No change in ISD between July and October TDFs
Colorado River-Red Bluff 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | Design | N/A | 2024-05-15 | No change in the expected ISD between July and October TDFs
Devers-Red Bluff 500 kV 1 and 2 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Devers-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | N/A | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | 2024-05-31 | 2024-05-01 | 2024-06-01 | Design | Pending | 2023-11-01 | 1. Outage restrictions 2. Material delays
Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2012-2013 | 2016 | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | Construction | 2018-05-01 | 2020-12-01 | Due to construction field delays, in-service date is delayed to June 2024.
Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2016-2017 | 2018-12-31 | 2023-06-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2026-01-01 | Construction | Exempt | Construction started | Joint SCE/LADWP project. ELM Project delays have delayed construction due to non availability of outage on 500 kV lines
Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-30 | 2025-12-01 | Design | Exempt | 2024-10-23 | No change in expected ISD between July and October TDFs
Lugo-Mohave series capacitor upgrade | SCE | 2013-2014 | 2016 | 2022-06-01 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | Construction | 2018-05-01 | 2020-12-01 | Due to construction field delays, in-service date is delayed to June 2024
Lugo-Victor-Kramer Upgrade (1/3) Add 3rd Lugo 500/230 kV Transformer | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Lugo-Victor-Kramer Upgrade (2/3) Reconductor Lugo–Victor 230 kV No. 1, 2, 3 & 4 lines using HTLS | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Lugo-Victor-Kramer Upgrade (3/3) Rebuild/build Kramer–Victor 115 kV lines to 230 kV and Loop the old segment of Kramer–Victor 115 kV into Roadway | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Project on hold | 2015-04-01 | 2024-06-01 | Project continues on hold. Expected construction start of September 2024 based on Riverside Coucil Approval (Estimated approval Oct 2023)
Mira Loma 500 kV CB Upgrade Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2028-12-01 | Design | Pending | Pending | Material Lead times have increased to 5 years
Mira Loma-Mesa Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
New Control 115 kV Shunt Reactor | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | On hold | Pending | Pending | Project approved by CAISO in May 2023. A new project has been submitted in the 2023-2024 TPP that, if approved, will supersede this project.
New CoolwaterA 115/230 kV Bank | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2027-12-10 | Initiation | Pending | Pending | Project approved by CAISO in May 2023
New Serrano 4AA Bank & 230kV GIS Rebuild | SCE | 2022-2023 | 2027 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2019-2020 | 2023-06-01 | 2023-05-01 | 2023-06-23 | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-25 | 2027-10-31 | Construction | Exempt | 2022-10-22 | Joint SCE/LADWP project. ISD for SCE’s portion of the project remains June 2024. SCE received projected ISD for LADWP portion of the project at Sylmar Substation.
San Bernardino-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
San Bernardino-Vista 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Serrano-Alberhill-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Serrano–Del Amo–Mesa 500 kV Transmission Reinforcement | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | 2033-12-31 | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Sylmar Transformer Replacement | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023
Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020-12-01 | 44531 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2024-02-28 | 2024-02-05 | 2024-02-05 | Construction | N/A | Construction started | The in-service dates range from July 2023 to February 2024
Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | Pending | 2025-04-01 | 2025-04-01 | 2025-04-30 | 2025-04-30 | Design | N/A | 2024-06-17 | No change in the expected ISD between July and October TDFs
Vista-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | Initiation | Pending | Pending | Project approved by CAISO in May 2023

## SDGaE
Project | PTO | Transmission Plan Approved | In-Service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service Jul 2023 TDF | Expected In-Service Oct 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Reconductor TL692: Japanese Mesa - Las Pulgas | SDG&E | 2013-2014 | 2021-06-15 | 2021-12-01 |  | 2023-05-01 | 2021-11-01 | 2021-10-22 | [5 empty] | Close-out | Exempt | 2021-05-17
Artesian 230 kV Sub & loop-in TL23051 | SDG&E | 2013-2014 | 2016-06-01 | 2022-06-01 |  | 2022-06-01 | 2022-12-14 | 2022-12-13 | Completed | Completed | In-Service | In-Service |  | Close-out | 2016-08-17 | 2020-06-10
Rose Canyon-La Jolla 69 kV T/L | SDG&E | 2013-2014 | 2018-06-01 | 2022-11-01 |  | 2023-06-27 | 2023-08-25 | 2023-10-24 | Completed | Completed | In-Service | In-Service |  | Close-out | Exempt | 2021-07-26
TL644, South Bay-Sweetwater: Reconductor | SDG&E | 2010-2011 | 2013-06-01 | 2022-04-01 | 2022-05-01 | 2022-05-02 | 2022-05-31 | 2022-05-15 | 2022-05-15 | 2022-05-15 | In-Service | In-Service |  | Close-out | Exempt | 2022-02-04
TL674A Loop-in (Del Mar-North City West) & Removal of TL666D (Del Mar-Del Mar Tap) | SDG&E | 2012-2013 | 2021-06-15 | 2021-10-01 | 2022-11-01 | 2022-12-01 | 2022-12-09 | 2022-12-27 | 2022-11-18 | 2022-11-18 | In-Service | In-Service |  | Close-out | 2017-06-28 | 2021-01-19
2nd Escondido-San Marcos 69 kV T/L | SDG&E | 2013-2014 | 2015-06-01 | 2022-05-01 | 2023-02-01 | 2022-09-01 | 2022-12-14 | 2022-12-27 | 2023-02-08 | 2023-02-08 | In-Service | In-Service |  | Close-out | 2017-11-15 | 2022-01-03
Southern Orange County Reliability Upgrade Project – Alternative 3 (Rebuild Capistrano Substation, construct a new SONGS-Capistrano 230 kV line and a new 230 kV tap line to Capistrano) | SDG&E | 2010-2011 | 2015-06-01 | 2023-05-01 |  | 2023-12-01 | 2024-05-28 | 2024-05-28 | 2024-11-05 | 2024-11-05 | 2025-08-07 | 2024-02-01 | 2023-12-23 | Construction | 2012-05-18 | 2018-06-29
Reconductor TL 605 Silvergate – Urban | SDG&E | 2015-2016 | 2018-06-01 | 2027-06-01 | 2024-06-01 | 2024-05-02 | 2024-12-23 | 2024-12-23 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-26 | 2024-07-01 | Design | Exempt | 2024-02-23
TL649D Reconductor (San Ysidro - Otay Lake Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2024-12-01 |  |  | 2022-08-24 | 2024-12-17 | 2024-12-17 | 2024-10-18 | 2024-08-07 | 2024-08-07 | Design | Exempt | 2024-05-14
TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 1905-07-08 | 2023-04-01 | 2023-02-01 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2023-02-13 | 2023-02-13 | 2026-02-24 | 2026-08-05 | 2026-08-01 | Design | 2016-04-25 | 2025-06-18 | Should ISD be Nov 2026?
TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2026-06-01 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-06-08 | 2026-06-08 | 2026-07-29 | 2026-08-10 | 2026-10-12 | Design | 2025-05-23 | 2026-05-04
TL690E, Stuart Tap-Las Pulgas 69 kV Reconductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-11-01 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2026-11-10 | 2026-11-10 | 2026-12-09 | 2028-03-23 | 2028-03-16 | Design | Exempt | 2027-03-16
Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-11-01 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-11-14 | 2027-11-14 | 2027-11-14 | 2027-10-14 | 2027-10-14 | Planning | 2026-07-24 | 2027-03-08
TL623C Reconductor (San Ysidro - Otay Tap) | SDG&E | 2017-2018 | 2022-06-01 |  | 2029-02-01 |  |  | 2024-08-15 | 2029-02-27 | 2029-02-27 | 2029-04-30 | 2029-09-28 | 2029-12-04 | Planning | TBD | 2029-01-03
Miguel-Sycamore Canyon (TL23021) 230 kV line Loop-in to Suncrest | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD |  | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD |  | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
SG and OT Redundant Bus Differential Relay | SDG&E | 2022-2023 | 2024 |  | 2024 | [6 empty] | TBD |  | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD |  | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Reconductor TL680C San Marcos -Melrose Tap | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD |  | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
3 Ohm Series Reactor on Sycamore-Penasquitos 230 kV line | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD |  | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Upgrade TL13820 Sycamore-Chicarita 138 kV | SDG&E | 2022-2023 | 2032 |  | 2032 | [6 empty] | TBD |  | Planning | TBD | TBD | Newly approved in 2022-2023 TPP
Upgrade series capacitors on HW-NG and HA-NG to 2739 MVA | SDG&E | 2022-2023 | 2032 | N/A | 1905-07-24 | [6 empty] | N/A | 2032 | Planning | TBD | TBD | Newly approved in 2022-2023 TPP

## VEA_GLW
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Current In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gamebird 230/138 kV Transformer Upgrade | VEA/GLW | 2019-2020 | 1905-07-13 | 2021-09-01 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | VEA portion: Dec-21 GLW portion: Nov-21 Transformer: Q2 22 | In service | In service | In service |  |  | N/A | 2021 | In Service
Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 |  | 2023-06-23 | 2023-09-23 | 2023-12-23 | 2023-12-23 | In Flight | N/A | Sept-21
GLW/VEA area upgrades - revised scope | VEA/GLW | 2021-2022 (revised scope 2022-2023) | TBD |  | N/A | TBD | TBD | TBD | TBD | TBD | 2027-12-31 | 2027-12-31 | Permitting, engineering and design | N/A | 2026-01-01 | The revised scope of the GLW/VEA area upgrades was approved in the 2022-2023 TPP.
Beatty 230 kV Project | VEA/GLW | 2022-2023 | 2027-12-31 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-31 | Permitting, engineering and design | N/A | 2026-01-01

## DCRT
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-24 | 2024-04-01 | 2024-04-24 | 2024-04-24 | Inflight | Approved

## LSPower
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service April 2023 TDF | Expected In-Service July 2023 TDF | Current Expected In-Service | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
Gates 500 kV Dynamic Voltage Support (Orchard Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2025-01-01 | Construction | 2021-02-19 | 2023-04-01
Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | Final Design | 2022-04-06 | Q4 2023 | Construction pending CPUC approval
Collinsville 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | Permitting | Q1 2024 | 2026
Manning 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | Permitting | Q1 2024 | 2026
Metcalf - San José B HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-04-01 | 2028-05-01 | 2028-05-01 | Permitting | Q1 2024 | 2026
Newark - NRS HVDC Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-05-01 | 2028-04-01 | 2028-04-01 | Permitting | Q1 2024 | 2026

## CitizensEnergy
Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Jan 2022 TDF | Expected In-Service Apr 2022 TDF | Expected In-Service July 2022 TDF | Expected In-Service Oct 2022 TDF | Expected In-Service Jan 2023 TDF | Expected In-Service Apr 2023 TDF | Expected In-Service July 2023 TDF | Expected In-Service Oct 2023 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | In-Flight |  | 2023-07-21