## Status Report
| This Project Status Report is required to be submitted upon request from a CAISO representative. NOTE: If the Project is approaching or within 6 months of its Initial Synchronization Date, and is not expected to be delayed, please also complete the "Prior to Synch" tab. |  |  |  |  | Last Updated: 10/7/2026
Status Report Submission Date
Project Name
Queue Number (####)
Project TP Deliverability Status
Group Project Sought TPD Under
Interconnection Customer (Entity)
Primary Customer Contact Name
| Interconnection Customer to complete Columns E, F, and G below as applicable |  | Completed?: Yes or No | Date Completed: | Comments or Notes:
NU/ IFs Construction Start | 1 | GIA Execution Has the GIA for this Project been executed? If not, you may skip the remaining questions and go to the "Upgrades Status" tab, but please provide the current estimation for the execution date in the notes. | No
Written Notice to Proceed | 2 | Written notice to proceed Has the Project provided the notification to the Participating Transmission Owner (PTO) to design, procure, and construct transmission upgrades? If due date is not achievable, describe in the notes the status of the required modification. | No
| 3 | Site Exclusivity or Site Control What Type of land is the project being developed on: Private, State, Federal, other? Has the project acquired all necessary land rights or permits? Please provide a description and details of the land rights acquired, or the status of such acquisition and expected completion timeline. | No |  |  | If this project has executed multiple PPAs, please type the sum of the total MW capacity procured under all PPAs in item #2. below.
Permitting Complete | 4 | Project Permitting Status : Project, Environmental, or Land Use Permit Status' Have all of the required Permits for the Project been requested and acquired? In the Notes, list all required permits and their current status. | No |  |  | 1. PPA POI | 2. PPA MW Capacity | 3. PPA Fuel Type / Technology
| 5 | Power Purchase Agreements (PPA) Has the Project executed a PPA? If yes, describe the PPA(s) in the notes, and define the POI, MW capacity, and fuel type/technology of the PPAs. | No
| 6 | Project Procurement Status: Does the Project have executed and approved PPAs for the off-take of the project. Please note the PPA(s), the off-taker(s), the PPA COD, and other pertinent information. | No
| 7 | Gen-tie route and Point of Change of Ownership (POCO) Have all necessary agreements been executed or land acquisitions completed with the Land Owners for the Project to reach its POCO? | No
| 8 | Initial Drawing Package Has the Initial Drawing Package been submitted to and accepted by the PTO? | No
| 9 | Final Drawing Package Has the Final Drawing Package been submitted to and accepted by the PTO? | No
9 | 10 | Load and Generator Relay Settings Have the Generator Relay Settings (PS-1 and G5-1) been submitted to and accepted by the PTO? | No
| 11 | Affected System Have all Identified Affected Systems provided approval o confirmed mitigation of issues for the Project? In the Notes, list all Affected Systems and their current statuses. NOTE: Documentation showing resolution for Identified Affected Systems must be submitted to Queue Management six months prior to Synchronization of the Project. | No
BAA Notification | 12 | New Resource Implementation (NRI) Process Has the Project (or blocks of the project) commenced the NRI process? If yes, describe in the Notes the status of the NRI Project in MPAI. | No
| 13 | In-service Date Is the Project on track for its current In-Service Date? If date is not achievable, describe in the notes the status of the required modification. | No
| 14 | Initial Synchronization Date Is the Project on track for its current Initial Synchronization Date? If date is not achievable, describe in the notes the status of the required modification. | No
| 15 | Commercial Operation Date (COD) Is the Project on track to meet the COD specified in the GIA? If not, please describe in the Notes the status of the required modification request. | No | N/A
| 16 | Modification Request Needed? Is a modification request from the Interconnection Customer/Project necessary at this time? | No | N/A
CAISO Public

## Upgrade Status
Directions: Identifiy the currently assigned upgrades and confirm the status of development:
Precursor Network Upgrades (PNU) | Network Upgrade ID (if applicable) | Est. In Service Date | Notes:
Reliability Network Upgrades (RNU)
Delivery Network Upgrades (DNU)
Distribution Upgrades
CAISO Public

## Prior to Synch
If the Project is within 6 months of its Initial Synchronization Date and does not expect to be delayed, please complete this tab. All items on both this tab and the Status Report tab must be completed (or not applicable to the Project) in order for Queue Management to approve Initial Synchronization. FYI... This form/tab, including some data on the Status Report Tab, replaces the previously known Transmission Check Sheet.
|  | Completed?: Goal = Yes to all | Date Completed: (If Applicable) | Comments or Notes:
Inverter Confirmation
1 | Project Inverters Do the inverters that were installed match the most recently approved study or modification results? In the Notes, detail what inverters have been installed. Provide the manufacturer, model/type, MW rating of each. | No
Appendix H / Attachment 7 Confirmation
2 | Step Up Transformer Does the step up transformer, have a duration equal to the lesser of the normal three-phase fault clearing time (4-9 cycles) or one-hundred fifty (150) milliseconds, plus any subsequent post-fault voltage recovery to the final steady-state post-fault voltage unless clearing the fault effectively disconnects the generator from the system? | No
3 | Disturbance Response Will the Generating Facility remain online for any voltage disturbance caused by a single-phase fault on the transmission grid, or within the Project between the Point of Interconnection and the high voltage terminals of the Project’s step up transformer, with delayed clearing, plus any subsequent post-fault voltage recovery to the final steady-state post-fault voltage unless clearing the fault effectively disconnects the generator from the system? | No
4 | Momentary Cessation Does the Project meet the momentary cessation requirements? | No
5 | Off Nominal Frequency Does the Project comply with the off nominal frequency requirements set forth in the WECC Under Frequency Load Shedding Relay Application Guide or successor requirements as they may be amended from time to time? | No
6 | Power Factor Does the Project operate within a power factor range of 0.95 leading to 0.95 lagging, measured at the Point of Interconnection as defined in the LGIA in order to maintain a specified voltage schedule? | No
7 | Monitor and Record Data For LGIA only, does the project meet the monitor and record data requirements for all frequency ride-through events, transient low voltage disturbances that initiated reactive current injection, reactive current injection or momentary cessation for transient high voltage disturbances, and inverter trips? Including that the data must be time synchronized, using a GPS clock or similar device, to a one millisecond level of resolution; all data except phase angle measuring unit data must be sampled at least every 10 milliseconds; each recording will include as a minimum 150 milliseconds of data prior to the triggering event, and 1000 milliseconds of data after the event trigger; and the Project must store this data for a minimum of 30 days. | No
8 | Phase Angle Measuring For LGIA Only, has a phase angle measuring unit or functional equivalent been installed at the entrance to the facility or at the Generating Facility’s main substation transformer? Including that the phase angle measuring unit must have a resolution of at least 30 samples per second and this data will be stored for a minimum of 30 days. | No
GO/GOP NERC/WECC Registration? <<Ryan, I adjusted the compliance section below to remove specific PRC 12 and make it more general confirmation that they meet ALL compliance obligations - now that we have new ones like PRC28-30. Anything missing here?
Compliance: For NERC and WECC Compliance, and Reliability Coordinator Obligations
9 | NERC/WECC Registration Has the Project registered as required with NERC and WECC? In the comments section, please include the Registered Entity Name, NCR number, and other identifying information. Note: ISO will notify WECC if not registered. Please contact: registration@wecc.org with questions. | No
10 | NERC PRC Compliance Does the generating facility require compliance with all NERC and WECC compliance standards? Please note any issues or concerns with meeting such compliance obligations. | No
11 | Reliability Coordinator Has the IC provided the Reliability Coordinator (RC West) notification and received approval for operations? | No
Other confirmations:
12 | Limiting Mechanism Has the limiting mechanism as described in the GIA or response to MMA been installed? If so, please provide details about the mechanism by which the Project will limit its output to the approved MW at POI. | No
13 | PMAX Is the PMAX value the same in the PGA, GIA, the App & Study RIMS project, and the NRI RIMS Project? | No
14 | Hybrid/Co-located Is the Project Co-located or Hybrid consistent with the PGA, GIA, the App & Study RIMS project, and the NRI RIMS Project? | No
15 | Financial Deficiencies Has the Project cured all financial deficiencies? -- Confirm no study cost invoices are in default. -- Confirm Project has fulfilled all financial obligations for CAISO studies (Study, Repower, MMAs, LOS, etc.) | No
CAISO Public