## Version_History
FNM Scope for FNM DB24M12
(Production 12/18/2024)
Revision History – Final Scope: 10/16/2024, Late Model Scope Change Request Deadline: 11/4/2024
Effective Date | Version | Description
2024-10-16 | 1 | Final scope by due date. The scope is considered finalized without any addendum attached.
2024-12-16 | 2 | Add additional information
California ISO – Public

## NRI
I. NRI Projects
No | PTO | Resource ID | Project Name / Description | Project Key | Capacity (MW) | POD | Additional Information
1 | SCE | CLAP_PRIMMBT1_LOAD | Silver State South Solar Project Storage CLAP | 23CLAP32189 | 7 |  | New Custom LAP resource
2 | DCRT | ATLASC_5_ACBBT6 | Atlas COMPLEX 9 BESS | 24NGR37282 | 150 | CIELLO AZUL 500 kv Bus | New Non-Generation resource
3 | DCRT | ATLASC_5_ACBBT2 | Atlas COMPLEX 7A BESS | 24NGR37283 | 180 | CIELLO AZUL 500 kv Bus | New Non-Generation resource
4 | DCRT | ATLASC_5_ACBBT3 | Atlas COMPLEX 7B BESS | 24NGR37284 | 120 | CIELLO AZUL 500 kv Bus | New Non-Generation resource
5 | DCRT | ATLASC_5_ACBBT4 | Atlas COMPLEX 8A BESS | 24NGR37285 | 210 | CIELLO AZUL 500 kv Bus | New Non-Generation resource
6 | DCRT | ATLASC_5_ACBBT5 | Atlas COMPLEX 8B BESS | 24NGR37286 | 172 | CIELLO AZUL 500 kv Bus | New Non-Generation resource
7 | DCRT | ATLASC_5_ACBBT1 | Atlas COMPLEX 4A BESS | 24NGR37287 | 150 | CIELLO AZUL 500 kv Bus | New Non-Generation resource
8 | PGAE | KOLA_2_KLBBT1 | Kola | 16AS0072 | 275 | TESLA 230 KV BUS 2C | New aggregate Non-Generation resource: Child RES_ID: KOLA_2_KLBT1A, Capacity: 200 MW Child RES_ID: KOLA_2_KLBT1B, Capacity: 75 MW
9 | PGAE | KOLA_2_KLBBT2 | Kola BESS 2 | 24NGR37637 | 125 | TESLA 230 KV BUS 2C | New Non-Generation resource
10 | PGAE | ORTGA_6_MCDBT1 | Merced BESS | 24NGR38692 | 2.93 | Mercy Springs SW Sta-Canal-Oro Loma 70kV Line @ Pole 15/15 | New Non-Generation resource
11 | SCE | TWINKL_2_ASCBTA | Aratina Solar Center 1 a BESS | 23NGR29813 | 75 | KRAMER 230 KV BUS | New aggregate Non-Generation resource: Child RES_ID: TWINKL_2_ASCBT1, Capacity: 50 MW Child RES_ID: TWINKL_2_ASCBT2, Capacity: 25 MW
12 | SCE | TWINKL_2_ASCBTB | Aratina Solar Center 1 b BESS | 23NGR29815 | 50 | KRAMER 230 KV BUS | New Non-Generation resource
13 | SCE | CWATER_1_DS1BT1 | Daggett Solar 1 BESS | 24NGR37330 | 113.5 | CWATER 115 KV | New Non-Generation resource
14 | SCE | LCKHT1_2_LSCBT1 | Lockhart Solar CL ESS 1 | 24NGR39038 | 69 | Kramer 230 KV Bus | New Non-Generation resource
15 | SCE | LCKHT1_2_LSCBT2 | Lockhart Solar CL ESS 2 | 24NGR39039 | 59.7 | Kramer 230 KV Bus | New Non-Generation resource
16 | SDGE | OTAY_6_CVEBT3 | Chula Vista Energy Center 2 BESS | 22NGR24837 | 49.7 | OTAY 69KV BUS | New Non-Generation resource
17 | SCE | WHTHIL_3_WHAWD1 | White Hills Wind Farm A | 24PSEUDO37855 | 50 | ELDORADO BUS 230 KV BUS | New Pseudo resource
18 | SCE | WHTHIL_3_WHBWD2 | White Hills Wind Farm B | 24PSEUDO38717 | 300 | ELDORADO BUS 230 KV BUS | New Pseudo resource
19 | PGAE | LUNAVL_2_LVSSR1 | Luna Valley Solar | 15AS883561 | 113.5 | Tranquility 230 KV BUS | New Solar resource
20 | PGAE | KIRKER_1_PBSSR1 | Pittsburg RV Boat Solar | 24GEN35637 | 2.9 | KIRKER 115 KV BUS | New Solar resource
21 | PGAE | LUNAVL_2_LVSSR2 | Luna Valley Solar 2 | 24GEN37297 | 2 | Tranquility 230 KV BUS | New Solar resource
22 | PGAE | LUNAVL_2_LVSSR3 | Luna Valley Solar 3 | 24GEN37481 | 84.5 | Tranquility 230 KV BUS | New Solar resource
23 | SCE | TWINKL_2_ASCSRA | Aratina Solar Center 1 | 15AS882170 | 120 | KRAMER 230 KV BUS | New aggregate Solar resource: Child RES_ID: TWINKL_2_ASCSR1, Capacity: 80 MW Child RES_ID: TWINKL_2_ASCSR2, Capacity: 40 MW
24 | SCE | TWINKL_2_ASCSRB | Aratina Solar Center 1 b PV | 23GEN29814 | 80 | KRAMER 230 KV BUS | New Solar resource
25 | PGAE | NOOSA_1_NESBT1 | Noosa Energy Storage | 24NGR36344 | 99 | RIPON 115 KV BUS | New Storage resource
26 | PGAE |  | CHEVRON RICHMOND REFINERY; STOILS_1_UNITS; Chevron Richmond IRG097 RIG server replacement | 24RIG33809 | 172.85 |  | RIG Reconfiguration
27 | SCE |  | Silver State South Solar | 24RIG38400 | 250 |  | RIG Reconfiguration
28 | SCE |  | CRIMSN_2_CRMBT1 | 24RIG38567 | 350 |  | RIG Reconfiguration
29 | SCE |  | IRG374 RIG Replacement | 24RIG39076 | 3 |  | RIG Reconfiguration
30 | SCE |  | Bottleneck Energy Storage RIG IP Update | 24RIG40231 | 80 |  | RIG Reconfiguration
31 | SDGE |  | SAMPSN_6_KELCO1 | 24RIG36253 | 19.175 |  | RIG Reconfiguration
32 | SDGE |  | EnerSmart Chula Vista 1 - 2024 RIG IP Change | 24RIG38950 | 3 |  | RIG Reconfiguration
33 | SDGE |  | EnerSmart Chula Vista 2 - 2024 RIG IP Change | 24RIG38952 | 3 |  | RIG Reconfiguration

## TRAN
II. Transmission Projects
No | PTO | RIMS ID | Project Name | Project Key
1 | PGAE | 19TRANS10265 | Forebay Wind Repower Project | ET4260
2 | PGAE | 19TRANS10266 | Santa Clara Wind Repower Project | ET4261
3 | PGAE | 20TRANS12531 | Microsoft Data Center Interconnection Project | ET4371
4 | PGAE | 20TRANS12531 | Microsoft Data Center Interconnection Project | ET4372
5 | PGAE | 21TRANS16173 | Manteca #1 60 kV Line Section ReconductoringProject | ET4623
6 | PGAE | 23TRANS33020 | Limestone Sub: Decommission Substation | ET5304
7 | SCE | 20TRANS14106 | SCE Centralized Remedial Action Scheme (CRAS) | ET5447
8 | SCE | 22TRANS22429 | Avocet Energy Storage (TOT906/Q1608) | ET5081
9 | SCE | 22TRANS22429 | Avocet Energy Storage (TOT906/Q1608) | ET5082
10 | SCE | 24TRANS37523 | Commerce BESS 250MW TOT927/Q1611 | ET5400
11 | SCE | 24TRANS37523 | Commerce BESS 250MW TOT927/Q1611 | ET5401
12 | SCE | 24TRANS37632 | Vista 66 kV Bank on Bus Project | ET5402
13 | SCE | 24TRANS37632 | Vista 66 kV Bank on Bus Project | ET5403
14 | SDGE | 22TRANS24436 | Q1669 Pome BESS Pomerado Substation | ET5143
15 | SDGE | 22TRANS24436 | Q1669 Pome BESS Pomerado Substation | ET5144

## EIM_RC
III. EIM/ RC Projects
No | Entity | Project Name | Project Key
1 | AESO_RC | Double Model the Picture Butte phase shifter in parallel. | 24EMS40415
2 | AVA_BA | - IRO-010-6.13 tab of RC Data Gathering spreadsheet has new substation coordinates | 24EMS39869
3 | AVA_BA | - ICCP mapping to AVA CIM model | 24EMS39903
4 | AVA_BA | - Note: the ratings in this submittal are SPRING = High1/High2, and WINTER = High3/High4 | 24EMS39904
5 | AZPS_BA | Update SERX Impedances | 24EMS39711
6 | AZPS_BA | Move DBN__DBAPS_230_4 line from the 324 switch to 124 switch. | 24EMS40305
7 | BANC_BA | Breaker(s)\ Disconnect(s) - Updated ICCP ID | 24EMS38948
8 | BANC_BA | Substation\Load - Updated ICCP points that either don't exist anymore or were incorrectly mapped per Luxon's email | 24EMS40044
9 | BANC_BA | Breaker(s)\ Disconnect(s) - Added multiple 230KV disconnects. Renamed OLN S4393 to S683. | 24EMS40045
10 | BCHA_RC | Substation - removed RIM | 24EMS39687
11 | BCHA_RC | Substation - removed SRY | 24EMS39688
12 | BCHA_RC | Substation\Load - removed RIM_LOAD | 24EMS39689
13 | BCHA_RC | Substation\Load - removed SRY_LOAD | 24EMS39690
14 | BCHA_RC | Transmission Line - Remove 60L43_2 | 24EMS39691
15 | BCHA_RC | Transmission Line - Remove 60L73_2 | 24EMS39692
16 | BCHA_RC | Transmission Line - Remove 5L1_8 | 24EMS39693
17 | BCHA_RC | - | 24EMS39694
18 | BCHA_RC | - | 24EMS39695
19 | BCHA_RC | Transmission Line - Remove 60L74_3 | 24EMS39696
20 | BCHA_RC | Transmission Line - Remove 60L74_5 | 24EMS39697
21 | BCHA_RC | Transmission Line - Remove 60L73_4 | 24EMS39698
22 | BCHA_RC | Transmission Line - Remove 60L44_2 | 24EMS39699
23 | BCHA_RC | Substation - Simplify SPG 12kV system; remove 12CL54, 12CL52, 12CL51, 12CL53, 12RX522, 12RX524, 12RX526, 12RX511, etc | 24EMS39700
24 | BCHA_RC | Substation - Added MNY | 24EMS39701
25 | BCHA_RC | Substation\Transformer - Added MNY_T1 | 24EMS39702
26 | BCHA_RC | Substation\Load - Added MNY_LOAD | 24EMS39703
27 | BCHA_RC | Transmission Line - Added line 2L348_3 | 24EMS39704
28 | BCHA_RC | Transmission Line - Added line 2L348_2 | 24EMS39705
29 | BCHA_RC | Transmission Line - Added line 1L364_7 | 24EMS39706
30 | BCHA_RC | Substation\Load - Updated ICCP mapping file | 24EMS39707
31 | BPAT_BA | Contingency Definition - BPA Contingency List updated with ASHE/CGS fixes. | 24EMS38946
32 | BPAT_BA | Generator - Remodeled from 4 gens to 2 gens. | 24EMS39402
33 | BPAT_BA | Breaker(s)\ Disconnect(s) - Cleaned up. | 24EMS39403
34 | BPAT_BA | Breaker(s)\ Disconnect(s) - Fixed disconect types form MOD to DSC. | 24EMS39404
35 | BPAT_BA | RAS - RAS logic input additions due to new LONGHORN 230kV lines. | 24EMS39405
36 | BPAT_BA | Contingency Definition - BPA Contingency List for "BPA Network Model File 1258.xml" model. | 24EMS39906
37 | BPAT_TOP | Transmission Line - Added View Substation | 24EMS38940
38 | BPAT_TOP | Transmission Line - Grays Harbor changes-added Y/Grays Harbor to Satsop Park and South Elma Substations. Changed Y to N and deleted Grays Harbor to Olympia-South Elma 115kV line, Satsop Park-Cosmopolis 115kV line, South Elma-Satsop Park 115Kv line. Discovery Substation=changed N to Y for TOP and added N. Wasco to TOP Customer field. | 24EMS39318
39 | BPAT_TOP | Breaker(s)\ Disconnect(s) - Added new PCB B257 and switch LBD B257. | 24EMS40434
40 | CEN_BA | Substation\Load - UPDATE CUC Substation | 24EMS39416
41 | CEN_BA | Substation\Load - UPDATE CUC Substation | 24EMS39417
42 | CEN_BA | Substation\Load - UPDATE LMA Substation | 24EMS39473
43 | CEN_BA | Substation\Load - UPDATE LMA Substation | 24EMS39474
44 | CEN_BA | Substation\Load - UPDATE LMA Substation | 24EMS39475
45 | CHPD_BA | Periodic MOD-027 Generator modeling update for Rock Island Powerhouse 1 Units B8 and B10 | 24EMS38939
46 | CHPD_BA | Substation\Load - New Jumpoff Ridge station to be looped into 3 existing CHPD lines | 24EMS39770
47 | CHPD_BA | Generator - MOD-027 testing, governor model update | 24EMS39902
48 | EPE_TOP | Substation\Load - Added Conforming Load 0873B | 24EMS40043
49 | GCPD_BA | Breaker(s)\ Disconnect(s) - GC107 is a normally open switch. This is to satisfy the CAISO process to make an update. | 24EMS39772
50 | GCPD_BA | GCPD:ANCNT_LK | 24EMS40376
51 | GRID_TOP | Substation\Load - Updated One-line for Cielo Azul Switchyard which included the addtion of Bay 4 for Centennial Flats generation facility. | 24EMS39390
52 | GRID_TOP | Transmission Line - System voltage limits updated | 24EMS39713
53 | GRID_TOP | Transmission Line - System voltage limits updated in preparation of Cielo Azul Sub to be energized in November | 24EMS39714
54 | HHWP_TOP | Transmission Line - I know that this is not an appropriate way to submit this information. It was a request during an OPWG meeting a few nonths ago to submit the FERC 881 MVAR template with 4 seasons of ratings. In attempting to do that, I realized how complicated that template is. This file is a download from the information in HANA with the new ratings that we will have in place at the time this project is released. If it is still needed, I am fully prepared to resubmit this data in the preferred template but need some guidance. | 24EMS39765
55 | HHWP_TOP | Transmission Line - Per request from Sanjeev R, this file modifies buses to show they are radial and thus should be excluded from HANA alarming. Only the lines hightlighted in yellow are modified. No other changes were made. | 24EMS39766
56 | IID_TOP | Generator - This is the template requested by the DEWG group asking for D curve data to correct flat and triangle curves. | 24EMS39317
57 | IPCO_BA | Breaker(s)\ Disconnect(s) - Contingency changes for HPVY | 24EMS39477
58 | IPCO_BA | Breaker(s)\ Disconnect(s) - Contingency changes for KPRT_MPSN | 24EMS39478
59 | IPCO_BA | Breaker(s)\ Disconnect(s) - Contingency changes for CHIP east half | 24EMS39479
60 | IPCO_BA | Breaker(s)\ Disconnect(s) - Contingency changes for CHIP west half | 24EMS39480
61 | IPCO_BA | Transmission Line - Update r, x, and bch of ACLineSegments: BOBN-CHIP_A, CHIP-DRAM_A, CHIP-RTSN1_A, HBRD-CHIP_A | 24EMS39589
62 | IPCO_BA | Generator - Update ratedS, maxQ, and minQ of SynchronousMachine: BSP1 | 24EMS39590
63 | IPCO_BA | Generator - Update maxOperatingP and minOperatingP of GeneratingUnit: BSP1 Update ratedS, maxQ, and minQ of SynchronousMachine: BSP1 | 24EMS39591
64 | IPCO_BA | Breaker(s)\ Disconnect(s) - Update name change of Breakers/Disconnects: 301A to 301Z | 24EMS39592
65 | IPCO_BA | Substation\Load - Addition of Loads: 015, 016, 017, 018 | 24EMS39593
66 | IPCO_BA | Transformer - Removal of Transformer: MOBL | 24EMS39594
67 | IPCO_BA | Transformer - Addition of Transformer: T132 | 24EMS39595
68 | IPCO_BA | Transformer - Addition of Transformer: T135 | 24EMS39596
69 | IPCO_BA | Transformer - Addition of Transformer: MBE7 | 24EMS39597
70 | IPCO_BA | Breaker(s)\ Disconnect(s) - Removal of Breakers/Disconnects: 102A, 102B, 131L | 24EMS39598
71 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 061C | 24EMS39599
72 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 011Z, 012Z, 015A, 016A, 017A, 018A, 021Z, 022Z, 101X, 131L, 132L, 132X, 132Z | 24EMS39600
73 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: JMP1 | 24EMS39601
74 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 061A, 061B, 061C, 061X, 061Y, 061Z, 062A, 062B, 062C, CUT1 | 24EMS39602
75 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 049X, 135H, 135L | 24EMS39603
76 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: JMP1, JMP2, JMPQN | 24EMS39604
77 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 231X, 231Y, 231Z, 232X, 232Y, 232Z, BUS_CUT1, BUS_CUT2, 033F | 24EMS39605
78 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 102C, 103C, 104C, 132X | 24EMS39606
79 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: CLRPT1, CLRPT3, CLRPT4 | 24EMS39607
80 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 102A, 102B, 102C | 24EMS39608
81 | IPCO_BA | - All ICCP Object IDs for IPCO_BA FNM. | 24EMS39609
82 | IPCO_BA | - CIM export of IPCO_BA FNM. | 24EMS39610
83 | LDWP_BA | Substation\Load - Update CB and Disconnect Normal Status | 24EMS39866
84 | LDWP_BA | Substation\Load - Update ICCP Mapping | 24EMS39867
85 | NEVP_TOP | Substation\Load - Updated CIM Measurement Names | 24EMS40125
86 | NEVP_TOP | Substation\Load - Updated CIM Measurement Names | 24EMS40126
87 | NEVP_TOP | Substation\Load - Updated CIM Measurement Names | 24EMS40127
88 | NEVP_TOP | Substation\Load - Updated CIM Measurement Names | 24EMS40128
89 | NEVP_TOP | Substation\Load - Updated CIM Measurement Names | 24EMS40129
90 | NEVP_TOP | Substation\Load - Updated CIM Measurement Names | 24EMS40130
91 | NEVP_TOP | Substation\Load - Updated CIM Measurement Names | 24EMS40131
92 | NWMT_TOP | Substation\Load - New substation work CHAFINWD, MILLER_C, RENOVA; misc. switch and other equip. changes | 24EMS39764
93 | PACE | Create Freezeout RAS | 24EMS37690
94 | PACE | Add COYOTEU pseudo breaker to COYOTEU_CLOVER_500 line | 24EMS40294
95 | PACW | Update Line Mapping at Outlook, Punkin Tap, and Punkin Center | 24EMS38390
96 | PACW | Update Line Mapping at Lucerne, Weed and OBERLNTP | 24EMS38503
97 | PAC_TOP | Transformer - Updated primary and secondary tap settings for 2 transformers | 24EMS38941
98 | PAC_TOP | Breaker(s)\ Disconnect(s) - Updated SCADA measurements for 2 breakers | 24EMS38942
99 | PAC_TOP | Transmission Line - Removed 1 zero impedance line segment | 24EMS38943
100 | PAC_TOP | Transmission Line - Removed 1 zero impedance line segment | 24EMS38944
101 | PAC_TOP | Transmission Line - Removed 1 zero impedance line segment | 24EMS38945
102 | PAC_TOP | Generator - Update MVAR Capability Curve for Anticline Wind | 24EMS39503
103 | PAC_TOP | Substation\Load - Convert Xfmr1 as a load point. Remove 46 kV circuit | 24EMS39504
104 | PAC_TOP | Breaker(s)\ Disconnect(s) - Add 1 switch | 24EMS39505
105 | PAC_TOP | Transmission Line - Update MVA key for branch to HARRYAL | 24EMS39506
106 | PAC_TOP | Transformer - Model high side tap positions for 500/230 kV Xfmrs. | 24EMS39507
107 | PAC_TOP | Transformer - Model high side tap positions for 500/230 kV Xfmrs. | 24EMS39508
108 | PAC_TOP | Transformer - Model high side tap positions for 500/345 kV Xfmrs. | 24EMS39509
109 | PAC_TOP | Transmission Line - Correct MVAR measurement for branch to YELLOWTA | 24EMS39510
110 | PAC_TOP | Breaker(s)\ Disconnect(s) - Add 1 switch | 24EMS39511
111 | PAC_TOP | Transmission Line - Add branch to REYNOLDPT | 24EMS39512
112 | PAC_TOP | Generator - Add new station with generation. | 24EMS39513
113 | PAC_TOP | Breaker(s)\ Disconnect(s) - Add 2 new MOABs and 4 new switches | 24EMS39514
114 | PAC_TOP | Transmission Line - Add 4 jumpers and two branches to MIDVALLY | 24EMS39515
115 | PAC_TOP | Transmission Line - Add 4 jumpers and two branches to MIDVALLY | 24EMS39516
116 | PAC_TOP | Transmission Line - Add breakers, switches, 2 branches to TERMINAL and 2 branches to 90TH.SO | 24EMS39517
117 | PAC_TOP | Substation\Load - Add station and Load | 24EMS39518
118 | PAC_TOP | Breaker(s)\ Disconnect(s) - Add one breaker, one switch, and branch to Ketchum Metering Station | 24EMS39519
119 | PAC_TOP | Substation\Load - Add load (XFMR2). Add switching devices to branches and loads | 24EMS39520
120 | PGE_BA | Transmission Line - Remove HRZ_STM_TRJ double model | 24EMS39418
121 | PGE_BA | Generator - Add TRW1 gens MVar Curves | 24EMS39419
122 | PGE_BA | Generator - Add BCW1 gens MVar Curves | 24EMS39420
123 | PGE_BA | Transmission Line - Remove STMW-STME double model lines | 24EMS39421
124 | PGE_BA | Substation\Load - Clean up Horizon-St Marys-Trojan double modeled line. Remove Keeler-St Marys double modeled line | 24EMS39422
125 | PGE_BA | Substation\Load - Clean up HRZN_KEEL #1 & #2 double modeled lines | 24EMS39423
126 | PGE_BA | Transmission Line - Clean up ESUB_WCKR_W11661 double model | 24EMS39424
127 | PGE_BA | Substation\Load - Build Seaside BESS project (SESD_2_UNIT_BESS) | 24EMS39425
128 | PGE_BA | Contingency Definition - contingency definition updates | 24EMS39426
129 | PGE_BA | - List of ICCP points mapping | 24EMS39427
130 | PGE_BA | - Model Difference report | 24EMS39428
131 | PGE_BA | - Model Updates for PGE: CIMXML model file | 24EMS39429
132 | PNM_BA | Transformer - Updated the MVA rating of the transformer from 220MVA to 440MVA | 24EMS38981
133 | PNM_BA | Transmission Line - Contingency Definition Template Added | 24EMS39085
134 | PNM_BA | Transmission Line - Contingency Definition Template Added | 24EMS39086
135 | PNM_BA | Transmission Line - Updated the line impedance values for the QLRA-ATSO transmission line. R, X and B values have been changed R = 0.00010, X = 0.00100 and B = 0.00002 | 24EMS39485
136 | PNM_BA | Transmission Line - Update - Line Branch Name Change - PROS-KIRT1 to KIRT-PROS1 | 24EMS40020
137 | PNM_BA | Transmission Line - Update - Changed Valent and Spanish peak bus under PNM area for Psuedo Tie-line | 24EMS40021
138 | PNM_BA | Breaker(s)\ Disconnect(s) - Add TAG Solar Breaker 52F3_F4_BF2_TAG | 24EMS40264
139 | PNM_BA | Breaker(s)\ Disconnect(s) - Add TAG Solar Breaker 52F1_F2_BF1_TAG | 24EMS40265
140 | PNM_BA | Breaker(s)\ Disconnect(s) - Add TAG Solar Switch 89F3_F4_BF2_TAG | 24EMS40266
141 | PNM_BA | Breaker(s)\ Disconnect(s) - Add TAG Solar Switch 89F1_F2_BF1_TAG | 24EMS40267
142 | PNM_BA | Breaker(s)\ Disconnect(s) - Add TAG Solar Switch 89M2_TAG | 24EMS40268
143 | PNM_BA | Breaker(s)\ Disconnect(s) - Add TAG Solar Switch 89M1_TAG | 24EMS40269
144 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Switch 89T2_TAG | 24EMS40270
145 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Switch 89T1_TAG | 24EMS40271
146 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Breaker 52U1_TAG | 24EMS40272
147 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Switch 89M1_TAG | 24EMS40273
148 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Switch 54365 | 24EMS40274
149 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Switch 54361 | 24EMS40275
150 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Switch 54363 | 24EMS40276
151 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Breaker 64962 | 24EMS40277
152 | PNM_BA | Breaker(s)\ Disconnect(s) - Add RioPuerc 115 Switch 64963 | 24EMS40278
153 | PNM_BA | Contingency Definition - Update Contingency for PR Pachmann RioPuerco 115 line | 24EMS40279
154 | PNM_BA | Contingency Definition - Add Contingency for RIPU-TAGS1 115 line | 24EMS40280
155 | PNM_BA | Substation\Load - Add TAG Solar Substation | 24EMS40281
156 | PNM_BA | Transformer - Add TAG_Xfms 115_13_8 | 24EMS40282
157 | PNM_BA | Transmission Line - Addition of transmission line RIPU-TAGS1 115kV between TAG Solar and RioPuerc 115 sub | 24EMS40283
158 | PNM_BA | Generator - Addition of TAG BESS, a 70 MW battery storage system, to Rio Puerco 115kV Substation. | 24EMS40284
159 | PNM_BA | Generator - Addition of TAG Solar, a 140 MW solar plant, to Rio Puerco 115kV Substation. | 24EMS40285
160 | PNM_BA | Generator - Addition of TAG Solar dyd mapping. | 24EMS40302
161 | PSEI_BA | - List of PSE ICCP Points | 24EMS39153
162 | PSEI_BA | - PSE CIM Export | 24EMS39154
163 | SCL_BA | Substation\Load - BROAD_ST SCADA Linkage Updates and Supporting docs for contingency definition changes, NO switches, ratings, and equipment naming. | 24EMS39865
164 | SNPD_TOP | Substation\Load - Updated UFLS relay models | 24EMS39277
165 | SNPD_TOP | Substation\Load - Updated 230kV limits | 24EMS39588
166 | SPP_RC | SPP Incremental Updates for DB132 | 23EMS31680
167 | SRP | Update Litihum LIM Unit to P to 250 | 24EMS39970
168 | SRP | Move DBN_DBAPS_230_4 line from DBN124 connection to DBN324 connection at APS DBN. New RDFID. | 24EMS40247
169 | SRP_BA | Transformer - Added 69/12kV XFMR | 24EMS39751
170 | SRP_BA | Transformer - Added 69/12kV XFMR | 24EMS39752
171 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS39753
172 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS39754
173 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS39755
174 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS39756
175 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS39757
176 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS39758
177 | SRP_BA | Transmission Line - Added Walker to Wortman line | 24EMS39759
178 | SRP_BA | Transmission Line - Added Abel to Boca line | 24EMS39760
179 | SRP_BA | Transmission Line - Added Konos to Pendergast line and Konos to Rovey line | 24EMS39761
180 | SRP_BA | Transmission Line - Added Charlie to Delta line and Charlie to Schrader line | 24EMS39762
181 | SRP_BA | - Data Gathering Worksheet Included w/ Submission | 24EMS39995
182 | SRP_BA | - GIS Shapefile Included w/ Submission | 24EMS39996
183 | SRP_BA | - ICCP List Included w/ Submission | 24EMS39997
184 | SRP_BA | Transformer - Added 69/12kV XFMR | 24EMS39998
185 | SRP_BA | Transformer - Added 69/12kV XFMR | 24EMS39999
186 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS40000
187 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS40001
188 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS40002
189 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS40003
190 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS40004
191 | SRP_BA | Breaker(s)\ Disconnect(s) - Added 69 kV breakers and disconnects | 24EMS40005
192 | SRP_BA | Transmission Line - Added Walker to Wortman line | 24EMS40006
193 | SRP_BA | Transmission Line - Added Abel to Boca line | 24EMS40007
194 | SRP_BA | Transmission Line - Added Konos to Pendergast line and Konos to Rovey line | 24EMS40008
195 | SRP_BA | Transmission Line - Added Charlie to Delta line and Charlie to Schrader line | 24EMS40009
196 | SRP_BA | Transmission Line - SCOTT Cut-in Between Abel and Santan - Delete SANTAN_ABEL 230kV Line, Add ABEL_SCOTT 230kV Line, Add SANTAN_SCOTT 230kV Line | 24EMS40159
197 | TEPC_TOP | Substation\Load - Addition of Port of Tucson Mobile load with switch in PATRIOT station, and small remodeling of IRV_PAT line to reflect relative position to mobile transformer | 24EMS40017
198 | TEPC_TOP | Breaker(s)\ Disconnect(s) - Correction to include previously existing breakers with meters in Irvington that weren't properly modeled. | 24EMS40018
199 | TEPC_TOP | Substation\Load - Final removal of HA_NUCOR from TEPC company, Harris Nucor Steel cut over to WALC AEPCO BA on 8/13/2024 | 24EMS40019
200 | TSGT_TOP | Contingency Definition - Rename contingency to include PNM1 preface. | 24EMS38996
201 | WALC | Update Normal Switch Statuses | 24EMS40172
202 | WALC_TOP | Substation\Load - Load on ED3 CB114 added. | 24EMS40314
203 | WALC_TOP | Transformer - Rating udpate | 24EMS40315
204 | WALC_TOP | Transmission Line - Rating udpate | 24EMS40316
205 | WALC_TOP | Breaker(s)\ Disconnect(s) - adding DSC for PPK | 24EMS40317
206 | WALC_TOP | Breaker(s)\ Disconnect(s) - adding brakers and disconcets for substation Longtin | 24EMS40318
207 | WALC_TOP | Breaker(s)\ Disconnect(s) - adding brakers and disconcets for substation lonebutt | 24EMS40319
208 | WALC_TOP | Substation\Load - Changing load name MCI_LOAD to NUCOR | 24EMS40320
209 | WALC_TOP | Breaker(s)\ Disconnect(s) - adding brakers and disconcets for substation CMOHAVE | 24EMS40321
210 | WALC_TOP | Transmission Line - Adding three 69kv transmission lines. | 24EMS40322
211 | WALC_TOP | Transformer - Adding two transformers LNG T201 and LNG T202; 230/69kv | 24EMS40323
212 | WALC_TOP | Transformer - Adding two transfromers CMOV T1 and CMOV T2; 69/24.9 kv | 24EMS40324
213 | WALC_TOP | Generator - Adding two solar generators; Sunrise Solar #1 and Sunrise Solar #2 | 24EMS40325
214 | WALC_TOP | Substation\Load - Substation CMOHAVE substation is added. Load MOHAVE PWR is added on the 24.9kv bus. Load MEC 69 is added on to the 69kv bus. | 24EMS40326
215 | WALC_TOP | Substation\Load - Load "CAMP MOHAVE" on the RIV 69 kv bus is removed. | 24EMS40330
216 | WALC_TOP | Substation\Load - Equivalent Loads labeled "LNG XMR T201" and "LNG XFM T202" are removed. | 24EMS40331