## Version_History
FNM Scope for FNM DB24M5
(Production 5/15/2024)
Revision History – Final Scope: 3/13/2024, Late Model Scope Change Request Deadline: 4/8/2024
Effective Date | Version | Description
2024-03-13 | 1 | Final scope by due date. The scope is considered finalized without any addendum attached.
2024-05-13 | 2 | Add additional information
2024-05-15 | 3 | Update EIM_RC section
California ISO – Public

## NRI
I. NRI Projects
No | PTO | Resource ID | Project Name | Project Key | Capacity (MW) | POD | Additional Information
1 | IID | VIKING_2_VCBBT1 | Vikings Co-located BESS | 23PSEUDO32729 | 150 | NELSN 230KV BUS | New Pseudo resource
2 | IID | VIKING_2_VCSSR1 | Vikings Co-located PV | 23PSEUDO32730 | 130 | NELSN 230KV BUS | New Pseudo resource
3 | PGAE | HUMBRD_1_HMBBT1 | Hummingbird Energy Storage | 18AS1897 | 75 | METCALF 115kV BUS | New Non-Generation resource
4 | PGAE | ELNIDO_1_ECRSR1 | East Cleveland Road Solar | 23GEN25873 | 3 | WILSON 115 KV BUS | New Solar resource
5 | PGAE | BURNEY_6_HCCTG1 | HAT CREEK BIOENERGY | 23GEN32056 | 3 | PIT#1 60KV BUS | New Conventional resource
6 | PGAE | ORTGA_6_LSLSB1 | Lara Solar 2 Hybrid | 23NGR33531 | 0.93 | Mercy Springs SW Sta-Canal-Oro Loma 70kV Line @ Pole 15/15 | New Non-Generation resource
7 | SCE | FILIPPI_2_QZSSRX | Quartzite Solar 8 | 15AS880888 | 300 | COLRIV 230KV | New aggregate Solar resource, Child_RES_ID: FILIPPI_2_QZSSR1, 150 MW Child_RES_ID: FILIPPI_2_QZSSR2, 150 MW
8 | SCE | FILIPPI_2_QZSBTX | Quartzite Solar 8 BESS | 22NGR20879 | 150 | COLRIV 230KV BUS | New aggregate Non-Generation resource, Child_RES_ID: FILIPPI_2_QZSBT1, 75 MW Child_RES_ID: FILIPPI_2_QZSBT2, 75 MW
9 | IID |  | Midway 3 Solar PFR RIG Reconfig | 23RIG33072 | 20 |  | RIG Reconfiguration
10 | PGAE |  | Mustang 2 Barbaro | 23RIG33248 | 50 |  | RIG Reconfiguration
11 | PGAE |  | Mustang 2 Whirlaway | 23RIG33250 | 100 |  | RIG Reconfiguration
12 | PGAE |  | Lost Hills IRG181 | 24RIG34074 | 20 |  | RIG Reconfiguration
13 | SCE |  | Orange County Energy Storage 3 frequency response | 23RIG33532 | 6 |  | RIG Reconfiguration
14 | SCE |  | Alamitos Energy Storage Frequency Response and HSL | 24RIG33684 | 100 |  | RIG Reconfiguration

## TRAN
II. Transmission Projects
No | PTO | RIMS ID | Project Name | Project Key
1 | PGAE | 22TRANS22285 | Rio Dell New Business Circuit & Substation Reinforcement | ET5070
2 | PGAE | 22TRANS22285 | Rio Dell New Business Circuit & Substation Reinforcement | ET5071
3 | SDGE | 21TRANS19642 | Q1806 Captiva Energy Storage | ET4781

## EIM_RC
III. EIM/ RC Projects
No | Entity | Project Name | Project Key
1 | AESO_RC | AESO Incremental Updates for DB128 | 23EMS31671
2 | AVA_BA | - Updated contingency definitions associated with the changes in this network model submittal | 24EMS34122
3 | AVA_BA | - IRO-010-6.13 tab of RC Data Gathering spreadsheet has new substation coordinates | 24EMS34123
4 | AVA_BA | - AVA voltage ratings submitted per new template | 24EMS34369
5 | AVA_BA | Shunt Cap\Reactor\ SVD¿s - AVA VCC and VCR parameters per new template and review. | 24EMS34537
6 | AVA_BA | Generator - Addition of AVA Clearwater Wind generation facility | 24EMS34830
7 | AVA_BA | - ICCP mapping to AVA CIM model | 24EMS34831
8 | AVA_BA | - Note: the ratings in this submittal are SUMMER = High1/High2, and SPRING = High3/High4 | 24EMS34832
9 | AVA_BA | - Note: the ratings in this submittal are SUMMER = High1/High2, and SPRING = High3/High4 | 24EMS35614
10 | AVA_TOP | Shunt Cap\Reactor\ SVD¿s - AVA VCC and VCR parameters per new template and review. | 24EMS33959
11 | AVRN_BA | Generator - Update Klondike_2_K2 Max Gen to 76 MW | 24EMS35531
12 | AZPS_BA | Shunt Cap\Reactor\ SVD¿s - Update the Base Voltage value for VCCs on the following substations: CEL, EC, FA, MDT, MU, PLK, PY, RMN, TT | 24EMS34654
13 | AZPS_BA | Contingency Definition - Updated contingency for new RAB cut-in and CIX-DLN 500kV Line | 24EMS34656
14 | AZPS_BA | Transmission Line - Updated Impedance for WMTTP-BL | 24EMS34657
15 | AZPS_BA | Transmission Line - Updated Impedance for VE-CTTIE | 24EMS34658
16 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added disconnect WW661 | 24EMS34872
17 | AZPS_BA | Breaker(s)\ Disconnect(s) - WK switching fields WK361,WK362,WK363 renamed to WK161,WK162 and WK163 | 24EMS34873
18 | AZPS_BA | Transformer - Added 69/12kV XFMR 3 A | 24EMS34874
19 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added new breakers WD342,WD562,WD442, and disconnects WD443D, WD441D, WD563, WD341D, WD641J, WD741D, WD041D, WD1541J, WD461 | 24EMS34875
20 | AZPS_BA | Transmission Line - TB-FZMCM ratings updated | 24EMS34876
21 | AZPS_BA | Transmission Line - MMRT-TB ratings updated | 24EMS34877
22 | AZPS_BA | Substation\Load - Added eqv load off of STS T10 | 24EMS34878
23 | AZPS_BA | Generator - Added new battery/solar unit | 24EMS34879
24 | AZPS_BA | Substation\Load - Added new generating station at SS4 | 24EMS34880
25 | AZPS_BA | Transmission Line - SNV-FRN ratings updated | 24EMS34881
26 | AZPS_BA | Transformer - SAR 69/12kV XMFR #19 ratings updated | 24EMS34882
27 | AZPS_BA | Breaker(s)\ Disconnect(s) - Replaced RW mod switches with disconnects for RW557, RW857,RW1051 and RW1455 | 24EMS34883
28 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added new breaker RIV362 | 24EMS34884
29 | AZPS_BA | Transmission Line - FZ-MCM ratings updated | 24EMS34885
30 | AZPS_BA | Transmission Line - FRN-MMRT ratings updated | 24EMS34886
31 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added psuedo switches based on PV status | 24EMS34887
32 | AZPS_BA | Substation\Load - Replaced BESSES with station JVX. New RDFIDs generated | 24EMS34888
33 | AZPS_BA | Breaker(s)\ Disconnect(s) - Renamed RCH1662J to RCH1662 | 24EMS34889
34 | AZPS_BA | Substation\Load - Added CLN feeder 2 | 24EMS34890
35 | AZPS_BA | Breaker(s)\ Disconnect(s) - Replaced YKK6403 with YKU6403 | 24EMS34891
36 | AZPS_BA | Breaker(s)\ Disconnect(s) - Updated normal open status for several transfer switch disconnects as per CAISO request | 24EMS34892
37 | AZPS_BA | Generator - dyd mappings | 24EMS34893
38 | AZPS_BA | Contingency Definition - Updated Contingency Definitions | 24EMS34894
39 | AZPS_BA | Breaker(s)\ Disconnect(s) - Removed GP K6555 Disconnect | 24EMS34895
40 | AZPS_BA | Transformer - Updated YMX XFMR T1 ratings | 24EMS34896
41 | AZPS_BA | Breaker(s)\ Disconnect(s) - Renamed HDW disconnects/breakers to HDW556,HDW555 and HDW557 | 24EMS34897
42 | AZPS_BA | Breaker(s)\ Disconnect(s) - Rename CRSDISC to DSN761 | 24EMS34898
43 | AZPS_BA | Breaker(s)\ Disconnect(s) - Rename CRSDISC to CRSU7280 | 24EMS34899
44 | AZPS_BA | Substation\Load - Added VS Fdr 5 load | 24EMS34900
45 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added VS542,VS543D,VS544D | 24EMS34901
46 | AZPS_BA | Breaker(s)\ Disconnect(s) - Removed disconnect MU345 | 24EMS34902
47 | AZPS_BA | Breaker(s)\ Disconnect(s) - CG-TR ratings updated | 24EMS34903
48 | AZPS_BA | Breaker(s)\ Disconnect(s) - Added WLF1242,WLF1243 and WLF1241D | 24EMS34904
49 | AZPS_BA | Breaker(s)\ Disconnect(s) - Replaced LY1143J with LY1141D | 24EMS34905
50 | AZPS_BA | Breaker(s)\ Disconnect(s) - DGSDISC renamed to DGS241 | 24EMS34906
51 | AZPS_BA | Breaker(s)\ Disconnect(s) - CU762,CU761 and CU763 renamed to CU162,CU161 and CU163 | 24EMS34907
52 | AZPS_BA | Breaker(s)\ Disconnect(s) - WMTDISC renamed to WMTQ2521 | 24EMS34908
53 | AZPS_BA | Transmission Line - Updated SUM-WM ratings | 24EMS34909
54 | AZPS_BA | Transmission Line - Updated STRTP-TT ratings | 24EMS34910
55 | AZPS_BA | Substation\Load - Removed WWTMP | 24EMS34911
56 | AZPS_BA | Breaker(s)\ Disconnect(s) - WWBSD renamed to WW2521 | 24EMS34912
57 | AZPS_BA | Transformer - AVYT 69/12kV XMFR3 impedance and rating update | 24EMS34913
58 | AZPS_BA | Breaker(s)\ Disconnect(s) - Several 12kV feeder disconnect names were updated to include a "d" suffix. I.E AD2041 to AD2041D | 24EMS34914
59 | AZPS_TOP | Shunt Cap\Reactor\ SVD¿s - Update the Base Voltage value for VCCs on the following substations: CEL, EC, FA, MDT, MU, PLK, PY, RMN, TT | 24EMS34370
60 | AZPS_TOP | Contingency Definition - Updated contingency for new RAB cut-in and CIX-DLN 500kV Line | 24EMS34372
61 | AZPS_TOP | Transmission Line - Updated Impedance for WMTTP-BL | 24EMS34373
62 | AZPS_TOP | Transmission Line - Updated Impedance for VE-CTTIE | 24EMS34374
63 | BANC_BA | Substation\Load - Update System Voltage Limits in BANC | 24EMS34915
64 | BANC_BA | Breaker(s)\ Disconnect(s) - Removed disconnects D917 and D918. | 24EMS34916
65 | BANC_BA | Breaker(s)\ Disconnect(s) - Updated connectivity for breakers S7085 and S7087. | 24EMS34917
66 | BANC_BA | Transformer - Updated impedances, ratings and ratedS for multiple transformers in SMUD area. | 24EMS34918
67 | BANC_BA | To tag the Breakers as UCON in the aliasname at the sha_wasn station | 24EMS35933
68 | BCHA_RC | Transformer - JOR T1M03 deleted | 24EMS34846
69 | BCHA_RC | Substation\Load - substation QNL deleted | 24EMS34847
70 | BCHA_RC | Substation\Load - Added a new substation LGW | 24EMS34848
71 | BCHA_RC | Substation\Load - Added a new substation PGM | 24EMS34849
72 | BCHA_RC | Substation\Load - Updated ICCP mapping file | 24EMS34850
73 | BPAT_BA | Breaker(s)\ Disconnect(s) - EWEB substation rebuild. | 24EMS34840
74 | BPAT_BA | Breaker(s)\ Disconnect(s) - | 24EMS34841
75 | BPAT_BA | Breaker(s)\ Disconnect(s) - New bay and future connection. | 24EMS34842
76 | BPAT_BA | Substation\Load - New Umatilla Electric station | 24EMS34843
77 | BPAT_BA | Substation\Load - New Umatilla Electric station | 24EMS34844
78 | BPAT_BA | Contingency Definition - BPA Contingency List | 24EMS34845
79 | BPAT_BA | Shunt Cap\Reactor\ SVD¿s - New shunt reactor R1. | 24EMS35227
80 | BPAT_BA | Transmission Line - New 500kV line "LNHR_CSGP_1500_A" | 24EMS35228
81 | BPAT_BA | Transmission Line - New 500kV line "MCNY_LNHR_1500_A" | 24EMS35229
82 | BPAT_BA | Substation\Load - New 500kV substation McNary and Coyote Springs | 24EMS35230
83 | BPAT_BA | RAS - Cattle Creek RAS update due line rating update. | 24EMS35232
84 | BPAT_BA | Shunt Cap\Reactor\ SVD¿s - New shunt reactor R1. | 24EMS35234
85 | BPAT_BA | Transmission Line - New 500kV line "LNHR_CSGP_1500_A" | 24EMS35235
86 | BPAT_BA | Transmission Line - New 500kV line "MCNY_LNHR_1500_A" | 24EMS35236
87 | BPAT_BA | Substation\Load - New 500kV substation McNary and Coyote Springs | 24EMS35237
88 | BPAT_BA | RAS - Cattle Creek RAS update due line rating update. | 24EMS35239
89 | BPAT_BA | Breaker(s)\ Disconnect(s) - Added new breaker PCB A66 for line reconfiguration at Midway. | 24EMS35812
90 | BPAT_TOP | Transmission Line - Added Cherry Grove-Heye Meyer 115kV line and Heye Meyer-119th Street 115kV line. Deleted Cherry Grove-119th Street 115kV line. Added Hooper Springs Substation. Added Benton-White Bluffs No 2 115kV line, changed the CGS Backup Bank tap to this line and deleted the Benton-451B No 1 115kV line (this is what line the CGS tap was on) and White Bluffs-451B No 1 115kV line. | 24EMS34127
91 | CEN_BA | Breaker(s)\ Disconnect(s) - UPDATE NORMAL OPEN STATUS OF SWITCHES | 24EMS34159
92 | CEN_BA | Transmission Line - UPDATE 161 kv Grid | 24EMS34976
93 | CEN_BA | Transmission Line - UPDATE 161 kv Grid | 24EMS34977
94 | CEN_BA | Transmission Line - UPDATE 161 kv Grid | 24EMS34978
95 | CEN_BA | Substation\Load - UPDATE 161 KCH Substation | 24EMS35180
96 | CEN_BA | Substation\Load - UPDATE 161 KCH Substation | 24EMS35181
97 | CEN_BA | Substation\Load - UPDATE 161 KCH Substation | 24EMS35182
98 | CHPD_BA | - CHPD identified ICCP points it was providing to the RC but the RC hadn't incorporated into the RC real-time model - this is the list of all points (including those that likely can't be implemented in the RC's model) | 24EMS34516
99 | CHPD_BA | - CHPD identified ICCP points it was providing to the RC but the RC hadn't incorporated into the RC real-time model - this is the list of points specific to the model | 24EMS34517
100 | CHPD_BA | - CHPD identified ICCP points it was providing to the RC but the RC hadn't incorporated into the RC real-time model - this is the list of points specific to the model | 24EMS34626
101 | CHPD_BA | - CHPD identified ICCP points it was providing to the RC but the RC hadn't incorporated into the RC real-time model - this is the list of points specific to the model | 24EMS34627
102 | CHPD_BA | Update ICCP and miscellaneous modeling updates from CHPD | 24EMS34681
103 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Update - Make Terry Disconnect Switch 2179 a Circuit Switcher, just like 2279. | 24EMS34938
104 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Removal - Remove Switch 2177 at Terry Substation. | 24EMS34939
105 | DOPD_TOP | Transmission Line - Update - The current model shows the South Nile-Rapids Line terminating at Rapids between Breakers 14172 and 14272. The line should terminate between Rapids Breakers 14172 and 14572. The current model shows the Rapids-Hanna Line terminating at Rapids be | 24EMS34940
106 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Update - Rapids MOD 14177 should be changed to 14577. | 24EMS34941
107 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Update - Rapids MOD 14577 should be changed to 14177. | 24EMS34942
108 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Addition - Add Breaker 14982 per the provided one-line diagram (G-01-LD1-S-01 wURBN Completed.pdf) | 24EMS34943
109 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Addition - Add MOD 14981 per the provided one-line diagram (G-01-LD1-S-01 wURBN Completed.pdf) | 24EMS34944
110 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Addition - Add MOD 14783 per the provided one-line diagram (G-01-LD1-S-01 wURBN Completed.pdf) | 24EMS34945
111 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Update - The pseudo-breakers T1_PSD, T2_PSD, T3_PSD, and T4_PSD are misnamed. T1 should become T4, T2 should become T3, T3 should become T2, and T4 should become T1. | 24EMS34946
112 | DOPD_TOP | Breaker(s)\ Disconnect(s) - Update - Move Urban Industrial Switch 181081 to the other side of the tap for T4_PSD. 181081 should be immediately adjacent to Breaker 181082. | 24EMS34947
113 | DOPD_TOP | Transmission Line - Addition of new Urban Industrial-Rapids 230-kV Line | 24EMS34952
114 | DOPD_TOP | Transmission Line - Addition of new Lincoln Rock-Urban Industrial 230-kV Line | 24EMS34953
115 | EPE_TOP | Breaker(s)\ Disconnect(s) - Addition of 0388A MOD at Amrad Substation | 24EMS34824
116 | EPE_TOP | Transformer - Addition of White Sands T1 XFMR ICCP Points | 24EMS34825
117 | EPE_TOP | Substation\Load - Additon of 115kv West Side Temp Substation | 24EMS34826
118 | EPE_TOP | Generator - Additon of 10MW Chihuahuan Desert Solar Facility | 24EMS34827
119 | HHWP_TOP | ACLineSegment - PSLF Change File with updated Line Impedances and Facility Ratings | 24EMS34124
120 | HHWP_TOP | ACLineSegment - HHWP FAC-008 Summary Tables (See S-3) | 24EMS34125
121 | HHWP_TOP | ACLineSegment - All HHWP Lines Impedance Updates & Facility Ratings Verfication - Project ID: 23EMS33222 Includes Ratings Updates for Lines #7 & #8 | 24EMS34126
122 | IID_BA | Generator - Update of PMax Value | 24EMS34691
123 | IID_TOP | RAS - Addition of new generation to Path 42 RAS, Ocotillo would be the first one to come into service tentatively April 2023 and then the remaining towards the end of 2023. | 22EMS25501
124 | IID_TOP | RAS - Addition of new generation to Path 42 RAS, Ocotillo would be the first one to come into service tentatively April 2023 and then the remaining towards the end of 2023. | 22EMS25502
125 | IID_TOP | Transmission Line - The 230kV S line from ECSS to IV sub has a new rating after project completion. Please see attachment for rating. | 24EMS33960
126 | IID_TOP | Breaker(s)\ Disconnect(s) - This is phase 1 for a new breaker addition at Ramon substation to accommodate a new capacitor bank being added. | 24EMS34487
127 | IID_TOP | Shunt Cap\Reactor\ SVD¿s - Uploading requested shunt data, but it is currently labeled as VCC's and all our shunt devices are manual, could you please move to manual static capacitors? | 24EMS34535
128 | IID_TOP | Transmission Line - We currently only use nominal ratings which are continuous and emergency ratings which are 30 min. I have updated the "thermal limits" sheet with the required data per request by RC to meet the FAC-011/FAC-014. | 24EMS34536
129 | IID_TOP | Transmission Line - Updated Facility Ratings | 24EMS35249
130 | IID_TOP | Transmission Line - The updated Path 42 RAS points to include Viking capacitor Bank and Ramon capacitor Bank. I have also included the tentative updated display to the spreadsheet. The highlighted yellow indicates modified/new points. | 24EMS35292
131 | IID_TOP | Shunt Cap\Reactor\ SVD¿s - The updated one line includes new cap bank installation required for Path 42 update. | 24EMS35391
132 | IID_TOP | Shunt Cap\Reactor\ SVD¿s - The new 230kV Ramon Cap bank PSLF attributes | 24EMS36116
133 | IID_TOP | Transformer - The new 230:92kV Bank#5 at El Centro SLD. | 24EMS36117
134 | IID_TOP | Transformer - The new 230:92kV Bank#5 at El Centro PSLF properties. | 24EMS36118
135 | IID_TOP | RAS - The new Path 42 RAS display to include capacitor banks and Viking Generation. | 24EMS36119
136 | IID_TOP | Transformer - The new 230:92kV Bank#5 ICCP points. | 24EMS36120
137 | IID_TOP | Shunt Cap\Reactor\ SVD¿s - The new 230kV capacitor bank at Ramon. These points were previously submitted to CAISO EMS Team in March. | 24EMS36121
138 | IID_TOP | Transformer - The new 230:92kV Bank#5 ICCP points. | 24EMS36122
139 | IID_TOP | Transformer - The new 230:92kV Bank#5 ICCP points. | 24EMS36123
140 | IPCO_BA | Generator - Updated American Falls Unit 1 and 3 and Shoshone Falls dynamic data models per IRO-010 item 6.25 | 24EMS34488
141 | IPCO_BA | Shunt Cap\Reactor\ SVD¿s - Update reactance and limits of C506 | 24EMS34710
142 | IPCO_BA | Transmission Line - Update name change of Transmission Line: HILL-LNDN to LNDN-HILL | 24EMS34711
143 | IPCO_BA | Breaker(s)\ Disconnect(s) - Update name change of Breakers/Disconnects: 012F to 015F, 013F to 016F | 24EMS34712
144 | IPCO_BA | Breaker(s)\ Disconnect(s) - Update name change of Breakers/Disconnects: 113T3_STR109 to 113T3, 113T2 to 113T2_STR109, 113T3_STR110 to 113T2_STR110 | 24EMS34713
145 | IPCO_BA | Generator - Update reactive capability curve for JKPT | 24EMS34714
146 | IPCO_BA | Transmission Line - Update ratings of Transmission Line: MNCO-SUGR | 24EMS34715
147 | IPCO_BA | Transmission Line - Removal of Transmission Line: FRSR-JKPT | 24EMS34716
148 | IPCO_BA | Breaker(s)\ Disconnect(s) - Removal of Breakers/Disconnects: 078T1, 061F | 24EMS34717
149 | IPCO_BA | Substation\Load - Removal of load: T061 | 24EMS34718
150 | IPCO_BA | Generator - Addition of reactive capability curve for PGCV | 24EMS34719
151 | IPCO_BA | Generator - Addition of reactive capability curve for CRSP | 24EMS34720
152 | IPCO_BA | Generator - Addition of reactive capability curve for LLCN | 24EMS34721
153 | IPCO_BA | Generator - Addition of reactive capability curve for SHKO | 24EMS34722
154 | IPCO_BA | Generator - Addition of reactive capability curve for CDRW | 24EMS34723
155 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breaker/Disconnect: TMP | 24EMS34724
156 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 011D, 011X_MBE5, 012D, 012B, 011B, 011C, 012C | 24EMS34725
157 | IPCO_BA | - All ICCP Object IDs for IPCO_BA FNM. | 24EMS34726
158 | IPCO_BA | - CIM export of IPCO_BA FNM. | 24EMS34727
159 | IPCO_BA | Shunt Cap\Reactor\ SVD¿s - Update reactance and limits of C506 | 24EMS34804
160 | IPCO_BA | Transmission Line - Update name change of Transmission Line: HILL-LNDN to LNDN-HILL | 24EMS34805
161 | IPCO_BA | Breaker(s)\ Disconnect(s) - Update name change of Breakers/Disconnects: 012F to 015F, 013F to 016F | 24EMS34806
162 | IPCO_BA | Breaker(s)\ Disconnect(s) - Update name change of Breakers/Disconnects: 113T3_STR109 to 113T3, 113T2 to 113T2_STR109, 113T3_STR110 to 113T2_STR110 | 24EMS34807
163 | IPCO_BA | Generator - Update reactive capability curve for JKPT | 24EMS34808
164 | IPCO_BA | Transmission Line - Update ratings of Transmission Line: MNCO-SUGR | 24EMS34809
165 | IPCO_BA | Transmission Line - Removal of Transmission Line: FRSR-JKPT | 24EMS34810
166 | IPCO_BA | Breaker(s)\ Disconnect(s) - Removal of Breakers/Disconnects: 078T1, 061F | 24EMS34811
167 | IPCO_BA | Substation\Load - Removal of load: T061 | 24EMS34812
168 | IPCO_BA | Generator - Addition of reactive capability curve for PGCV | 24EMS34813
169 | IPCO_BA | Generator - Addition of reactive capability curve for CRSP | 24EMS34814
170 | IPCO_BA | Generator - Addition of reactive capability curve for LLCN | 24EMS34815
171 | IPCO_BA | Generator - Addition of reactive capability curve for SHKO | 24EMS34816
172 | IPCO_BA | Generator - Addition of reactive capability curve for CDRW | 24EMS34817
173 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breaker/Disconnect: JMPR1 | 24EMS34818
174 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 061A, 061C, 131Z, 131X | 24EMS34819
175 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breaker/Disconnect: TMP | 24EMS34820
176 | IPCO_BA | Breaker(s)\ Disconnect(s) - Addition of Breakers/Disconnects: 011D, 011X_MBE5, 012D, 012B, 011B, 011C, 012C | 24EMS34821
177 | IPCO_BA | - All ICCP Object IDs for IPCO_BA FNM. | 24EMS34822
178 | IPCO_BA | - CIM export of IPCO_BA FNM. | 24EMS34823
179 | IPCO_BA | - Updated System Voltage Limits with exception rationale | 24EMS35069
180 | IPCO_BA | - Updated Shunt Equipment parameters | 24EMS35070
181 | LDWP | Scattergood RAS Update | 24EMS35700
182 | LDWP_BA | Substation\Load - ICCP - Update INT, ELN, BAR, PER | 24EMS34637
183 | LDWP_BA | Generator - Dynamic Models ELAND PV,BESS | 24EMS34638
184 | LDWP_BA | Generator - Dynamic Models for INT U3,U4 | 24EMS34639
185 | LDWP_BA | Substation\Load - Dynamic Models for INT U3,U4 and ELAND PV,BESS | 24EMS34640
186 | LDWP_BA | Substation\Load - CIM File - Update INT, ELN, BAR, PER | 24EMS34641
187 | LDWP_BA | Breaker(s)\ Disconnect(s) - Update Breaker Normal Status for HSK SYL 2 and INT GON 1 | 24EMS34954
188 | LDWP_BA | Breaker(s)\ Disconnect(s) - Update Breaker Normal Status for HSK SYL 2 and INT GON 1 | 24EMS34955
189 | NEVP_BA | Mercury-USAF TAP Impedance Update | 24EMS35944
190 | NEVP_TOP | Generator - Added ICCP for NDL_IPP_PV MVAR measurement | 24EMS34919
191 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Updated CIM measurement names for new breakers and XFMRs | 24EMS34920
192 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Updated CIM measurement names for new breakers and XFMRs | 24EMS34921
193 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Updated CIM measurement names for new breakers and XFMRs | 24EMS34922
194 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Updated CIM measurement names for new breakers and XFMRs | 24EMS34923
195 | NEVP_TOP | Generator - Updated pMAX for GMS_IPP_PV | 24EMS34924
196 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Removed and renamed ICCP at Sub | 24EMS34925
197 | NEVP_TOP | Breaker(s)\ Disconnect(s) - Removal of old Tracy equipment (24.5 kV completely removed, 60 kV bus equipment renamed, 120 kV equipment removed) | 24EMS34926
198 | NWMT | Update ratedU on transformer windings at BRDVIEW and COLSTRI$ to 550 and 241.5 on the transformer windings. Remove the tap changer controls if they are not in the NWMT CIM submission. | 24EMS35852
199 | NWMT_TOP | Transmission Line - Voltage exclusions justification | 24EMS34799
200 | NWMT_TOP | Transmission Line - All of the above. | 24EMS35013
201 | NWMT_TOP | Transmission Line - Misc. system-wide changes; YCGS, RENOVA | 24EMS35015
202 | PAC_TOP | Update Amasa-Windstar 230 kV rating to 618 MVA instead of 400 MVA. | 24EMS33958
203 | PAC_TOP | Breaker(s)\ Disconnect(s) - Updated measurements for 230kV breakers and switches. | 24EMS34238
204 | PAC_TOP | Breaker(s)\ Disconnect(s) - Added 4 breakers and measurements for 2 loads. Updated load names | 24EMS34239
205 | PAC_TOP | Transmission Line - Removed CORRAL_OCHOCO_230_E line and updated measurements for line to CATALINA. | 24EMS34240
206 | PAC_TOP | Transmission Line - Removed CORRAL_OCHOCO_230_E line and updated measurements for line to CATALINA. | 24EMS34241
207 | PAC_TOP | Generator - Added new BESS generator | 24EMS34242
208 | PAC_TOP | Transmission Line - Removed 2 switches and line to UMAPINE. Updated measurements for line to PROSPECP. | 24EMS34243
209 | PAC_TOP | Transmission Line - Removed 2 switches and line to PROSPECP. Updated measurements for line to UMAPINE. | 24EMS34244
210 | PAC_TOP | Substation\Load - Added new station | 24EMS34245
211 | PAC_TOP | Breaker(s)\ Disconnect(s) - Addition of 1 switch | 24EMS34956
212 | PAC_TOP | Transmission Line - Removal and replacement of WARRENNT line with line to BENLOMON | 24EMS34957
213 | PAC_TOP | Transmission Line - Removal and replacement of WARRENNT line with line to WARREN | 24EMS34958
214 | PAC_TOP | Substation\Load - Removal of station | 24EMS34959
215 | PAC_TOP | Breaker(s)\ Disconnect(s) - Updates to device names | 24EMS34960
216 | PAC_TOP | Transmission Line - Addition of 2 lines to TERMINAL | 24EMS34961
217 | PAC_TOP | Transmission Line - Addition of 2 lines to OQUIRRH | 24EMS34962
218 | PAC_TOP | Transmission Line - Removal of 2 switches. Updates to CLOVER line measurements | 24EMS34963
219 | PAC_TOP | Transmission Line - Removal of 2 switches. Updates to CAMPWILL line measurements | 24EMS34964
220 | PAC_TOP | Transmission Line - Removal of 3 breakers, 8 switches, and 2 lines to CLOVER and CAMPWILL | 24EMS34965
221 | PAC_TOP | Transmission Line - Updates to measurements for SHIRLEYB and AMASA lines | 24EMS34966
222 | PAC_TOP | Breaker(s)\ Disconnect(s) - Addition of 2 breakers | 24EMS34967
223 | PAC_TOP | Transmission Line - Relocation of 4 switches and 1 load to new ASHTONU and SARATOTP stations. Addition of line to new ASHTONU station. | 24EMS34968
224 | PAC_TOP | Substation\Load - New Station | 24EMS34969
225 | PAC_TOP | Substation\Load - New station | 24EMS34970
226 | PAC_TOP | Generator - Updates for reaggregation of existing wind generation. Addition of Rock River wind generation (54 MW), 9 breakers, and 20 switches. | 24EMS34971
227 | PAC_TOP | Transmission Line - Addition of 1 breaker and 1 line to BDO | 24EMS34972
228 | PAC_TOP | Transmission Line - Updated impedance for line to WARREN | 24EMS34973
229 | PAC_TOP | Transmission Line - Addition of 4 breakers, 2 switches, and 1 line to PIONEER. Updated impedance for line to BDOTP | 24EMS34974
230 | PAC_TOP | Transformer - Addition of 2 transformers, 5 breakers, 9 switches, 1 shunt reactor, and 1 shunt capacitor | 24EMS34975
231 | PGE_BA | Substation\Load - Builde the new Evergreen substation | 24EMS34692
232 | PGE_BA | Substation\Load - Sbus&Node reconfiguration and SCADA points update. | 24EMS34693
233 | PGE_BA | Substation\Load - Clean up Orenco double modeling | 24EMS34694
234 | PGE_BA | Substation\Load - Install the Battery storage in 13kV level at Coffee Creek station | 24EMS34695
235 | PGE_BA | Substation\Load - Move Mobile 8 to Dayton station | 24EMS34696
236 | PGE_BA | - PGE WebOMS English name-CIM model name mapping update | 24EMS34697
237 | PGE_BA | - List of ICCP points mapping | 24EMS34698
238 | PGE_BA | - Model Difference report | 24EMS34699
239 | PGE_BA | - Model Updates for PGE: CIMMXL model file | 24EMS34700
240 | PGE_BA | Horizon-Keeler Toplogy Correction | 24EMS35858
241 | PNM | Update SVC limits with the limits provided by PNM in the attached email. | 24EMS35074
242 | PNM | Add new PNM season | 24EMS35304
243 | PNM | RIOPUERC, WESTMES$ | 24EMS36370
244 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Breaker CS1 | 24EMS34489
245 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Breaker 52C1 | 24EMS34490
246 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Breaker 52F1-4 | 24EMS34491
247 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Switch CAP2 | 24EMS34492
248 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Switch CAP1 | 24EMS34493
249 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Switch 89C1-2 | 24EMS34494
250 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Switch 89C1-1 | 24EMS34495
251 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Switch 89-T2 | 24EMS34496
252 | PNM_BA | Breaker(s)\ Disconnect(s) - Add PEGS Breaker 52-T1 | 24EMS34497
253 | PNM_BA | Breaker(s)\ Disconnect(s) - Add PEGS Breaker 89-T1 | 24EMS34498
254 | PNM_BA | Breaker(s)\ Disconnect(s) - Add PEGS Breaker 182 | 24EMS34499
255 | PNM_BA | Breaker(s)\ Disconnect(s) - Add PEGS Switch 381 | 24EMS34500
256 | PNM_BA | Breaker(s)\ Disconnect(s) - Add PEGS Switch 185 | 24EMS34501
257 | PNM_BA | Breaker(s)\ Disconnect(s) - Add PEGS Switch 183 | 24EMS34502
258 | PNM_BA | Contingency Definition - Update Contingency for 230 PEGS Ambros line | 24EMS34503
259 | PNM_BA | Contingency Definition - Add Contingency for PEGS 230-Escalante Solar line | 24EMS34504
260 | PNM_BA | Contingency Definition - Add Escalante CAP2 | 24EMS34505
261 | PNM_BA | Shunt Cap\Reactor\ SVD¿s - Add Escalante CAP1 | 24EMS34506
262 | PNM_BA | Substation\Load - Add Escalante Solar Substation | 24EMS34507
263 | PNM_BA | Breaker(s)\ Disconnect(s) - Add Escalante Solar Breaker CS2 | 24EMS34508
264 | PNM_BA | Transformer - Add Escalante Xfmr 230_35_5 | 24EMS34509
265 | PNM_BA | Transmission Line - Addition of transmission line between Escalante Solar and PEGS 230kV sub | 24EMS34510
266 | PNM_BA | Generator - Addition of Escalante Solar, a 200 MW solar plant, to PEGS 230kV Substation. | 24EMS34511
267 | PNM_BA | Contingency Definition - Updated Line Contingency Definitions for new St Cecilia Station | 24EMS34512
268 | PNM_BA | Contingency Definition - Updated Line Contingency Definitions for new Sun Ranch Station | 24EMS34513
269 | PNM_BA | Generator - Added ICCP Object name W075$ATSO_BESS_MVAr | 24EMS35250
270 | PNM_BA | Generator - Added ICCP Object name W075$ATSO_BESS_MW | 24EMS35251
271 | PNM_BA | Generator - Added ICCP Object name W075$ATSO_PV_MVAr | 24EMS35252
272 | PNM_BA | Generator - Added ICCP Object name W075$ATSO_PV_MW | 24EMS35253
273 | PNM_BA | Transformer - Updated the St Cecilia 115kV station and removed the St Cecilia 115_12Xf transformer. | 24EMS35390
274 | PNM_BA | Substation\Load - ICCP SCADA Mapping file requested by CAISO | 24EMS35530
275 | PSCO_TOP | Correct 9812_2 default position at SMEL station | 24EMS34029
276 | PSEI_BA | - | 24EMS33759
277 | PSEI_BA | - | 24EMS33760
278 | PSEI_BA | Shunt Cap\Reactor\ SVD¿s - All PSE's shunt equipment is already reported, so the list is accurate. PSE does not utilize controllers for their operation; i.e. they are manually operated as needed. | 24EMS34486
279 | PSEI_BA | - PSE's cim model export | 24EMS35116
280 | PSEI_BA | - List of PSEI's ICCP IDs for PSE scada model | 24EMS35117
281 | SCL_BA | Shunt Cap\Reactor\ SVD¿s - Revised Shunt Equipment Data Template submission that includes additional details for the two transmission capacitors at BOTHELL. All other SCL shunt capacitors are located at the distribution voltage level and are operated manually. | 24EMS34367
282 | SMUD_TOP | Substation\Load - Update System Voltage Limits in BANC | 24EMS34937
283 | SNPD_TOP | Transmission Line - Update 115kV line ratings of Beverly Park - Swamp Creek and BPA Sno-King - Halls Lake #1 | 24EMS33858
284 | SNPD_TOP | Shoofly Install\ Removal - Install a shoo-fly to bypass Camano Substation. Note that this substation will be reconstructed as a 4-breaker ring bus. | 24EMS34154
285 | SNPD_TOP | Shoofly Install\ Removal - | 24EMS34828
286 | SNPD_TOP | Shoofly Install\ Removal - Install a shoo-fly at Lake Goodwin Substation | 24EMS34829
287 | SNPD_TOP | Substation\Load - Revise in-service date for Phase 2 | 24EMS35183
288 | SPP_RC | SPP Incremental Updates for DB128 | 23EMS31672
289 | SRP_BA | Transmission Line - Added Harquahala SRP Branches | 24EMS34834
290 | SRP_BA | Substation\Load - Babbitt | 24EMS34835
291 | SRP_BA | Generator - Added New HARQ SRP Assets (only new to SRP BA) | 24EMS34836
292 | SRP_BA | Transformer - Added 34.5/230kV and 12/230kV XFMRs | 24EMS34837
293 | SRP_BA | Transmission Line - Added 500kV Babbitt Branch | 24EMS34838
294 | SRP_BA | Breaker(s)\ Disconnect(s) - Added Parlett 230kV / 34.5kV / 12kV Portion | 24EMS34839
295 | SRP_BA | Add PARLETTE Station that was submitted on 4/17/24 to fix transformers | 24EMS35943
296 | SVP_TOP | Transmission Line - Exisitng Line rating update | 24EMS34361
297 | SVP_TOP | Transmission Line - Exisitng Line rating update | 24EMS34362
298 | SVP_TOP | Transmission Line - Exisitng Line rating update | 24EMS34363
299 | SVP_TOP | Transmission Line - Exisitng Line rating update | 24EMS34364
300 | TEP | Double model BX_TEP and COALMINE stations in WACM for TEP to WACM ownership transition. | 24EMS34680
301 | TEPC_TOP | Substation\Load - Devices have updated names for consistency to new internal naming standard. Also updated some loads to correctly reflect being nonconforming. | 24EMS34800
302 | TEPC_TOP | Shunt Cap\Reactor\ SVD¿s - Updates and corrections of reactive element ratings to reflect 2024 Summer PSLF case | 24EMS34801
303 | TEPC_TOP | Transmission Line - Updates and corrections of impedances and line MVA ratings to reflect 2024 Summer PSLF case | 24EMS34802
304 | TEPC_TOP | Substation\Load - Fixes to topology of distribution buses to crrrect internal estimation issues. | 24EMS34803
305 | TIDC_TOP | Shunt Cap\Reactor\ SVD¿s - No changes to existing Shunt equipment | 24EMS34622
306 | TPWR_BA | Update TPWR limits to use Summer and Spring limits. | 24EMS35207
307 | TSGT_TOP | Substation\Load - Add Valent substation and CB's | 24EMS34979
308 | TSGT_TOP | Breaker(s)\ Disconnect(s) - Add CB 286, 586, 482 and Disc 185, 283, 485, 581, 583, 585, 683 | 24EMS34983
309 | WALC | Station WTH_CISO Whitehills UNIT updates (CIDI#00273368) | 24EMS35809
310 | WALC | Update ratedU on transformer windings at MEAD_Z to 525 and 230. | 24EMS35853