## Cluster14
2016-05-30 | Cluster 14
2016-07-04 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Scoping Meeting* | Specify/Confirm POI* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Interconnection Financial Security & Submit Dynamic Model | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report issued | Phase II Study Results Meeting* | Phase II Study Report updates | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment (Step 2) & Downsizing Results | Annual Deliverability Retention Affidavit | 2025 Cycle TP Deliverability Affidavit & TP Deliverability Retention Affidavit | 2025 Cycle TP Deliverability Allocation & Results | 2025 Cycle IC Allocation Decision | Post 3rd Financial Security*
2016-09-05 | Dates | Start |  | 2021-04-01 |  |  |  |  | 2021-09-28 | 2022-09-15 | 2022-09-16 |  |  |  | 2022-10-01 | ~1/10/2024 | 2024-01-31 | 2024-02-01 |  | 2024-02-14 | 2024-05-31 | TBD |  | TBD | 2024-01-10 |  | 2025-09-02 | 2026-03-31
2016-10-10 |  | End | 2021-03-01 | 2021-04-15 |  | 2021-09-27 | 2021-09-27 | (per project) | 2022-09-15 | 2022-09-29 | 2022-12-14 | (per project) | (per project) | 2023-01-13 | 2024-01-31 | ~2/14/2024 | 2024-02-14 | 2024-04-30 | (per project) | 2024-05-31 | 2024-06-07 | TBD | 2024-07-01 | TBD | 2024-02-14 | 2025-09-01 | 2026-03-31 | 2026-04-07 | On or before the start of construction
2016-11-11 | Milestone Timeframe |  |  | 15 CDs |  |  |  | Within 3 BDs After Scoping Meeting | 170 CDs to Complete |  | Within 90 CDs of Issuing Phase I Study Report | Within 5 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Early December, Annually |  | Within 90 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting |  |  | Prior to Subsequent Clusters' Phase II Study, Annually |  | Annually until COD
2016-11-24 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 |  | 16.1 | 6.1.2 |  | 16.1 | 6.6, 6.7, 16.1 | 6.7, 16.1 | 6.7, 16.1 | 6.7.2.2, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7, 16.1 | 8.5, 16.1 | 8.9.2 | 8.5, 16.1 | 8.7, 16.1 | 8.7 | 8.9 thru 8.9.2, 16.1 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5, 16.1 | 11.3.1 thru 11.3.1.7, 11.5, 16.1 | 7.4, 7.5, 16.1 | 8.9.3, 16.1 | 8.9.2 | 8.9 thru 8.9.2, 16.1 | 8.9.4 thru 8.9.6, 8.9.8 | 11.3.2 thru 11.3.2.4
2016-11-25
2016-12-26 | Customer Actions |  |  |  |  | Customer Actions |  | Customer Actions |  |  |  | Customer Actions | [5 empty] | Customer Actions |  |  |  |  | Customer Actions
2017-01-02 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | 2021-06-30 | 2021-06-30 |  |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 5 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Due Date per Market Notice | Due Date per Market Notice |  | Within 7 CDs of receipt of Notification of Allocation | Before Start of Construction
2017-01-16 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security & submit an updated, valid dynamic model to the CAISO |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in Writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report |  | Inform ISO of Decision Based on Allocation Information Received |  | Post 2nd Financial Security | Review Reassessment Results | A) Return Notarized Affidavit to ISO B) Due Every Year Until COD | Return Affidavit and supporting documenation to ISO |  | Inform ISO of Decision Based on Allocation Information Received | Post 3rd Financial Security
2017-02-20 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data http://www.caiso.com/PublishedDocuments/GeneratingFacilityData-AttachmentAtoAppendix1.xlsm |  |  | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary |  |  |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | http://www.caiso.com/Documents/AffidavitTemplate-ProjectsSeekingTransmissionPlanDeliverability.docx |  |  |  |  | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  | http://www.caiso.com/Documents/Template-ProjectsPreviouslyAllocatedTransmissionPlanDeliverability.docx |  |  |  | May be milestone based - contact PTO
2017-05-29
2017-07-04 | ISO Actions |  |  |  |  | ISO Actions | [5 empty] | ISO Actions | [5 empty] | ISO Actions |  |  |  |  | ISO Actions
2017-09-04 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | Notifies if additional Information is Complete or Deficient | Notifies if IR is Complete or Deficient or Application is Not Valid | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Host meeting and address customer questions | Review all comments and, if necessary, issue addendum or revised Study Report | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | Send Affidavit Market Notice Score Projects based on Affidavit Information | Send Affidavit Market Notice with links to Affidavits Score seeking requests based on Affidavit Information | Allocate TP Deliverability to requests meeting eligibility criteria. Provide Allocation Results to Customers. | Review allocation decisions for any impacts to Second Interconnection Financial Security
2017-10-09 | ISO Response Timeframe |  | Prior to 30 CDs Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | Timely | Timely |  |  | Within 10 BDs of results meeting | Within 30 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Prior to 30 CDs Before Affidavits Due to ISO | Prior to 30 CDs before Affidavits Due to ISO |  | Timely Manner
2017-11-10 | Revised August 29, 2024
2017-11-23 | Dates - subject to change
2017-11-24 | * Date varies by project
2017-12-25
2018-01-01
2018-01-15
2018-01-19
2018-05-28
2018-07-04
2018-09-03
2018-10-08
2018-11-11
2018-11-22
2018-11-23
2018-12-25
Note on T2: Wilson, Daune: is this still happening

## Cluster13
2016-05-30 | Cluster 13
2016-07-04 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Scoping Meeting* | Specify/Confirm POI* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report issued, Customer comment option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment (Step 2) & Downsizing Results | Annual Deliverability Retention Affidavit | Tender Draft GIA* | GIA Negotiation* | Executable GIA* | Post 3rd Financial Security*
2016-09-05 | Dates | Start |  | 2020-04-01 |  |  |  |  | 2020-07-25 | 2021-01-10 |  |  |  |  | 2021-04-29 | 2021-10-15 | 2021-11-20 |  |  | 2022-01-21 | 2022-03-15 | 2022-04-06 |  |  | 2022-10-16 | (per project) | (per project) | (per project)
2016-10-10 |  | End | 2020-03-01 | 2020-04-15 | (per project) | 2020-06-30 | 2020-06-30 | (per project) | 2021-01-10 | 2021-01-22 | 2021-02-21 | 2021-02-24 | (per project) | 2021-04-22 | 2021-11-20 | 2021-12-01 | 2021-12-03 | 2021-12-20 | 2021-12-26 | 2022-03-14 | 2022-03-22 | 2022-07-31 | 2022-05-19 | 2022-08-01 | 2022-12-01 | (per project) | (per project) | (per project) | On or before the start of construction
2016-11-11 | Milestone Timeframe |  |  | 15 CDs | Within 10 BDs of Notification |  |  | Within 3 BDs After Scoping Meeting | 170 CDs to Complete |  | Within 30 CDs of Issuing Phase I Study Report | Within 3 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Early December, Annually |  | Within 30 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Early December, Annually | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs after Tendering GIA | Within 10 BDs After Negotiation Completion
2016-11-24 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 | 3.5.2.1, 3.5.2.2 | 3.5.2.2 | 6.1.2 |  | 6.6 | 6.6, 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4, 7.5 | 8.9.3 | 13.1 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2016-11-25
2016-12-26 | Customer Actions |  |  |  |  | Customer Actions |  | Customer Actions |  |  |  | Customer Actions | [5 empty] | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions
2017-01-02 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | 2020-06-30 | 2020-06-30 |  |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 3 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Due Date per Market Notice | Within 30 CDs after Receipt of Draft GIA |  |  | Before Start of Construction
2017-01-16 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in Writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report |  | Inform ISO of Decision Based on Allocation Information Received |  | Post 2nd Financial Security | Review Reassessment Results | A) Return Notarized Affidavit to ISO B) Due Every Year Until COD | Provides Comments to Draft GIA |  | Execute the GIA, Provide All Requested Information | Post 3rd Financial Security
2017-02-20 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data http://www.caiso.com/PublishedDocuments/GeneratingFacilityData-AttachmentAtoAppendix1.xlsm |  |  | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary |  |  |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | http://www.caiso.com/Documents/AffidavitTemplate-ProjectsSeekingTransmissionPlanDeliverability.docx |  |  |  |  | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  | http://www.caiso.com/Documents/Template-ProjectsPreviouslyAllocatedTransmissionPlanDeliverability.docx |  |  |  | May be milestone based - contact PTO
2017-05-29
2017-07-04 | ISO Actions |  |  |  |  | ISO Actions | [5 empty] | ISO Actions | [5 empty] | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions
2017-09-04 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | Notifies if additional Information is Complete or Deficient | Notifies if IR is Complete or Deficient or Application is Not Valid | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | Send Affidavit Market Notice Score Projects based on Affidavit Information | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2017-10-09 | ISO Response Timeframe |  | Prior to 30 CDs Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | Timely | Timely |  |  | Within 10 BDs of results meeting | Within 15 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Prior to 30 CDs Before Affidavits Due to ISO | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs After Draft GIA Tendered | Within 10 BDs After Negotiation Completion
2017-11-10 | Revised November XX, 2019
2017-11-23 | Dates - subject to change
2017-11-24 | * Date varies by project
2017-12-25
2018-01-01
2018-01-15
2018-01-19
2018-05-28
2018-07-04
2018-09-03
2018-10-08
2018-11-11
2018-11-22
2018-11-23
2018-12-25

## Cluster12
2016-05-30 | Cluster 12
2016-07-04 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Scoping Meeting* | Specify/Confirm POI* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report & AFC results issued, Customer comment option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment (Step 2) & Downsizing Results | Annual Deliverability Retention Affidavit | Tender Draft GIA* | GIA Negotiation* | Executable GIA* | Post 3rd Financial Security*
2016-09-05 | Dates | Start |  | 2019-04-01 |  |  |  |  | 2019-07-25 | 2020-01-10 |  |  |  |  | 2020-04-29 | 2020-10-15 | 2020-11-20 |  |  | 2021-01-21 | 2021-03-15 | 2021-04-06 |  |  | 2021-10-16 | (per project) | (per project) | (per project)
2016-10-10 |  | End | 2019-03-01 | 2019-04-15 | (per project) | 6/30/2019* | 2019-06-30 | (per project) | 2020-01-10 | 2020-01-24 | 2020-02-09 | 2020-02-12 | (per project) | 2020-04-09 | 2020-11-20 | 2020-12-01 | 2020-12-04 | 2020-12-20 | 2020-12-26 | 2021-03-14 | 2021-03-22 | 2021-07-31 | 2021-05-19 | 2021-08-01 | 2021-12-01 | (per project) | (per project) | (per project) | On or before the start of construction
2016-11-11 | Milestone Timeframe |  |  | 15 CDs | Within 10 BDs of Notification | (*Extension of validation deadline is pending FERC approval) |  | Within 3 BDs After Scoping Meeting | 170 CDs to Complete |  | Within 30 CDs of Issuing Phase I Study Report | Within 3 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Early December, Annually |  | Within 30 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Early December, Annually | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs after Tendering GIA | Within 10 BDs After Negotiation Completion
2016-11-24 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 | 3.5.2.1, 3.5.2.2 | 3.5.2.2 | 6.1.2 | 6.1.1 | 6.6 | 6.6, 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4, 7.5 | 8.9.3 | 13.1 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2016-11-25
2016-12-26 | Customer Actions |  |  |  |  | Customer Actions |  | Customer Actions |  |  |  | Customer Actions | [5 empty] | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions
2017-01-02 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | 2019-06-30 | 2019-06-30 |  |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 3 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Due Date per Market Notice | Within 30 CDs after Receipt of Draft GIA |  |  | Before Start of Construction
2017-01-16 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in Writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report |  | Inform ISO of Decision Based on Allocation Information Received |  | Post 2nd Financial Security | Review Reassessment Results | A) Return Notarized Affidavit to ISO B) Due Every Year Until COD | Provides Comments to Draft GIA |  | Execute the GIA, Provide All Requested Information | Post 3rd Financial Security
2017-02-20 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data |  |  | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary |  |  |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | http://www.caiso.com/Documents/AffidavitTemplate-ProjectsSeekingTransmissionPlanDeliverability.docx |  |  |  |  | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  | http://www.caiso.com/Documents/Template-ProjectsPreviouslyAllocatedTransmissionPlanDeliverability.docx |  |  |  | May be milestone based - contact PTO
2017-05-29
2017-07-04 | ISO Actions |  |  |  |  | ISO Actions | [5 empty] | ISO Actions | [5 empty] | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions
2017-09-04 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | (If Applicable) Notifies if additional Information is Complete or Deficient | (If Applicable) Notifies if IR is Complete or Deficient or Application is Not Valid | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | Send Affidavit Market Notice Score Projects based on Affidavit Information | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2017-10-09 | ISO Response Timeframe |  | Prior to 30 CDs Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | A) Within 5 BDs After Receipt of Valid IR B) Within 5 BDs of Results Meeting | Timely |  |  | Within 10 BDs of results meeting | Within 15 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Prior to 30 CDs Before Affidavits Due to ISO | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs After Draft GIA Tendered | Within 10 BDs After Negotiation Completion
2017-11-10 | Revised Feb 6, 2019
2017-11-23 | Dates - subject to change
2017-11-24 | * Date varies by project
2017-12-25
2018-01-01
2018-01-15
2018-01-19
2018-05-28
2018-07-04
2018-09-03
2018-10-08
2018-11-11
2018-11-22
2018-11-23
2018-12-25

## Cluster 11
2016-05-30 | Cluster 11
2016-07-04 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Pro Forma Study Agreement | Scoping Meeting* | Specify/Confirm POI* | Study Agreements* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report & AFC results issued, Customer comment option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment (Step 2) & Downsizing Results | Annual Deliverability Retention Affidavit | Tender Draft GIA* | GIA Negotiation* | Executable GIA* | Post 3rd Financial Security*
2016-09-05 | Dates | Start |  | 2018-04-01 | [6 empty] | 2018-07-25 | 2019-01-10 |  |  |  |  | 2019-04-29 | 2019-10-15 | 2019-11-20 |  |  | 2020-01-21 | 2020-03-15 | 2020-04-06 |  |  | 2020-10-16 | (per project) | (per project) | (per project)
2016-10-10 |  | End | 2018-03-01 | 2018-04-15 | (per project) | 2018-05-31 | 2018-05-31 | 2018-06-30 | (per project) | 2018-07-30 | 2019-01-10 | 2019-01-24 | 2019-02-09 | 2019-02-13 | (per project) | 2019-04-10 | 2019-11-20 | 2019-12-01 | 2019-12-04 | 2019-12-20 | 2019-12-26 | 2020-03-14 | 2020-03-22 | 2020-07-31 | 2020-05-18 | 2020-08-01 | 2020-12-01 | (per project) | (per project) | (per project) | On or before the start of construction
2016-11-11 | Milestone Timeframe |  |  | 15 CDs (Changed from 30 CD. New cluster window timeframe is pending conclusion of the 2017 IPE Expedited GIDAP Enhancements initiative) | Within 10 BDs of Notification | (Changed from Within 20 BDs after Window Closes. New cluster window timeframe is pending conclusion of the 2017 IPE Expedited GIDAP Enhancements initiative) | (Change from within 30 CDs After Window Closes. New cluster window timeframe is pending conclusion of the 2017 IPE Expedited GIDAP Enhancements initiative) | (Changed from Within 60 CDs after Window Closes. New cluster window timeframe is pending conclusion of the 2017 IPE Expedited GIDAP Enhancements initiative) | Within 3 BDs After Scoping Meeting | Within 30 CDs of Scoping Meeting | 170 CDs to Complete |  | Within 30 CDs of Issuing Phase I Study Report | Within 3 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Early December, Annually |  | Within 30 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Early December, Annually | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs after Tendering GIA | Within 10 BDs After Negotiation Completion
2016-11-24 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 | 3.5.2.1, 3.5.2.2 | 3.5.2.2 | 6.1.1 | 6.1.2 | 6.1.1 | 6.1.1 | 6.6 | 6.6, 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4, 7.5 | 8.9.3 | 13.1 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2016-11-25
2016-12-26 | Customer Actions |  |  |  |  | Customer Actions |  |  | Customer Actions |  |  |  |  | Customer Actions | [5 empty] | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions
2017-01-02 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | 2018-05-31 |  | 2018-06-30 |  | Within 30 CDs of Scoping Meeting |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 3 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Due Date per Market Notice | Within 30 CDs after Receipt of Draft GIA |  |  | Before Start of Construction
2017-01-16 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | Review ISO provided GISPA. | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI | Execute ISO provided GISPA |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in Writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report |  | Inform ISO of Decision Based on Allocation Information Received |  | Post 2nd Financial Security | Review Reassessment Results | A) Return Notarized Affidavit to ISO B) Due Every Year Until COD | Provides Comments to Draft GIA | Negotiate GIA with ISO & PTO | Execute the GIA, Provide All Requested Information | Post 3rd Financial Security
2017-02-20 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data |  |  |  | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | http://www.caiso.com/Documents/AffidavitTemplate-LaterQueueClusterProjectsSeekingTPDeliverability.doc |  |  |  |  | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  | http://www.caiso.com/Documents/AffidavitTemplate-LaterQueueClustersProjectsPreviouslyAllocatedTPDeliverability.doc |  |  |  | May be milestone based - contact PTO
2017-05-29
2017-07-04 | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions | [5 empty] | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions
2017-09-04 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | (If Applicable) Notifies if additional Information is Complete or Deficient | (If Applicable) Notifies if IR is Complete or Deficient or Application is Not Valid | (Pending Validity of IR) Issues Pro-Forma Generator Interconnection Study Process Agreement (GISPA) | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Provide (PTO & ISO) Signed GISPA to Customer | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | Send Affidavit Market Notice Score Projects based on Affidavit Information | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2017-10-09 | ISO Response Timeframe |  | Prior to 30 CDs Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | Within 30 CDs After Window Closes | A) Within 5 BDs After Receipt of Valid IR B) Within 5 BDs of Results Meeting | Timely | Within 10 BDs of POI Designation |  |  | Within 10 BDs of results meeting | Within 15 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Prior to 30 CDs Before Affidavits Due to ISO | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs After Draft GIA Tendered | Within 10 BDs After Negotiation Completion
2017-11-10 | Revised Jan 25, 2018
2017-11-23 | Dates - subject to change
2017-11-24 | * Date varies by project
2017-12-25
2018-01-01
2018-01-15
2018-01-19
2018-05-28
2018-07-04
2018-09-03
2018-10-08
2018-11-11
2018-11-22
2018-11-23
2018-12-25

## Cluster 10
2016-05-30 | Cluster 10
2016-07-04 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Pro Forma Study Agreement | Scoping Meeting* | Specify/Confirm POI* | Study Agreements* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report & AFC results issued, Customer comment option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment (Step 2) & Downsizing Results | Annual Deliverability Retention Affidavit | Tender Draft GIA* | GIA Negotiation* | Executable GIA* | Post 3rd Financial Security*
2016-09-05 | Dates | Start |  | 2017-04-01 | [6 empty] | 2017-07-25 | 2018-01-10 |  |  |  |  | 2018-04-29 | 2018-10-15 | 2018-11-20 |  |  | 2019-01-21 | 2019-03-15 | 2019-04-06 |  |  | 2019-10-16 | (per project) | (per project) | (per project)
2016-10-10 |  | End | 2017-03-01 | 2017-04-30 | (per project) | 2017-05-26 | 2017-05-30 | 2017-06-29 | (per project) | 2017-07-29 | 2018-01-10 | 2018-01-26 | 2018-02-09 | 2018-02-14 | (per project) | 2018-04-10 | 2018-11-20 | 2018-12-01 | 2018-12-06 | 2018-12-20 | 2018-12-26 | 2019-03-14 | 2019-03-22 | 2019-07-31 | 2019-05-19 | 2019-08-01 | 2019-12-01 | (per project) | (per project) | (per project) | On or before the start of construction
2016-11-11 | Milestone Timeframe |  |  | 30 CDs | Within 10 BDs of Notification | Within 20 BDs after Window Closes | Within 30 CDs After Window Closes | Within 60 CDs After Window Closes | Within 3 BDs After Scoping Meeting | Within 30 CDs of Scoping Meeting | 170 CDs to Complete |  | Within 30 CDs of Issuing Phase I Study Report | Within 3 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report | 205 CDs | Early December, Annually |  | Within 30 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Early December, Annually | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs after Tendering GIA | Within 10 BDs After Negotiation Completion
2016-11-24 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 | 3.5.2.2 | 3.5.2.2 | 6.1.1 | 6.1.2 | 6.1.1 | 6.1.1 | 6.6 | 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4, 7.5 | 8.9.3 | 13.1 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2016-11-25
2016-12-26 | Customer Actions |  |  |  |  | Customer Actions |  |  | Customer Actions |  |  |  |  | Customer Actions | [5 empty] | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions
2017-01-02 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | Within 20 BDs after Window Closes |  | Within 3 BDs after Scoping Meeting |  | Within 30 CDs of Scoping Meeting |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 3 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Due Date per Market Notice | Within 30 CDs after Receipt of Draft GIA |  |  | Before Start of Construction
2017-01-16 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | Review ISO provided GISPA. | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI | Execute ISO provided GISPA |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in Writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report |  | Inform ISO of Decision Based on Allocation Information Received |  | Post 2nd Financial Security | Review Reassessment Results | A) Return Notarized Affidavit to ISO B) Due Every Year Until COD | Provides Comments to Draft GIA | Negotiate GIA with ISO & PTO | Execute the GIA, Provide All Requested Information | Post 3rd Financial Security
2017-02-20 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data |  |  |  | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | Affidavit Template for Cluster 5 and Later Queue Clusters Seeking TPDeliverability |  |  |  |  | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  | Affidavit Template for Cluster 5 and Later Queue Clusters Previously Allocated Transmission Plan Deliverability |  |  |  | May be milestone based - contact PTO
2017-05-29
2017-07-04 | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions | [5 empty] | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions
2017-09-04 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | (If Applicable) Notifies if additional Information is Complete or Deficient | (If Applicable) Notifies if IR is Complete or Deficient or Application is Not Valid | (Pending Validity of IR) Issues Pro-Forma Generator Interconnection Study Process Agreement (GISPA) | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Provide (PTO & ISO) Signed GISPA to Customer | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | Send Affidavit Market Notice Score Projects based on Affidavit Information | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2017-10-09 | ISO Response Timeframe |  | Prior to 30 CDs Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | Within 30 CDs After Window Closes | A) Within 5 BDs After Receipt of Valid IR B) Within 5 BDs of Results Meeting | Timely | Within 10 BDs of POI Designation |  |  | Within 10 BDs of results meeting | Within 15 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Prior to 30 CDs Before Affidavits Due to ISO | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs After Draft GIA Tendered | Within 10 BDs After Negotiation Completion
2017-11-10 | Revised January 25, 2018
2017-11-23 | Dates - subject to change
2017-11-24 | * Date varies by project
2017-12-25
2018-01-01
2018-01-15
2018-01-19
2018-05-28
2018-07-04
2018-09-03
2018-10-08
2018-11-11
2018-11-22
2018-11-23
2018-12-25

## Cluster 9
2016-05-30 | Cluster 9
2016-07-04 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Pro Forma Study Agreement | Scoping Meeting* | Specify/Confirm POI* | Study Agreements* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report & AFC results issued, Customer comment option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment (Step 2) & Downsizing Results | Annual Deliverability Retention Affidavit | Tender Draft GIA* | GIA Negotiation* | Executable GIA* | Post 3rd Financial Security*
2016-09-05 | Dates | Start |  | 2016-04-01 | [6 empty] | 2016-07-25 | 2017-01-17 |  |  |  |  | 2017-04-29 | 2017-10-16 | 2017-11-20 |  |  | 2018-01-20 | 2018-03-15 | 2018-04-06 |  |  | 2018-10-16 | (per project) | (per project) | (per project)
2016-10-10 |  | End | 2016-03-01 | 2016-04-30 | (per project) | 2016-05-27 | 2016-05-30 | 2016-06-29 | (per project) | 2016-07-29 | 2017-01-17 | 2017-01-31 | 2017-02-16 | 2017-02-22 | (per project) | 2017-04-17 | 2017-11-20 | 2017-11-16 | 2017-12-06 | 2017-12-20 | 2017-12-26 | 2018-03-14 | 2018-03-22 | 2018-07-31 | 2018-05-19 | 2018-08-01 | 2018-11-16 | (per project) | (per project) | (per project) | On or before the start of construction
2016-11-11 | Milestone Timeframe |  |  | 30 CDs | Within 10 BDs of Notification | Within 20 BDs after Window Closes | Within 30 CDs After Window Closes | Within 60 CDs After Window Closes | Within 3 BDs After Scoping Meeting | Within 30 CDs of Scoping Meeting | 170 CDs to Complete |  | Within 30 CDs of Issuing Phase I Study Report | Within 3 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report | 205 CDs | Mid-November |  | Within 30 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Mid-November, Annually | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs after Tendering GIA | Within 10 BDs After Negotiation Completion
2016-11-24 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 | 3.5.2.2 | 3.5.2.2 | 6.1.1 | 6.1.2 | 6.1.1 | 6.1.1 | 6.6 | 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4, 7.5 | 8.9.3 | 13.1 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2016-11-25
2016-12-26 | Customer Actions |  |  |  |  | Customer Actions |  |  | Customer Actions |  |  |  |  | Customer Actions | [5 empty] | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions
2017-01-02 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | Within 20 BDs after Window Closes |  | Within 3 BDs after Scoping Meeting |  | Within 30 CDs of Scoping Meeting |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 3 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Due Date per Market Notice | Within 30 CDs after Receipt of Draft GIA |  |  | Before Start of Construction
2017-01-16 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | Review ISO provided GISPA. | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI | Execute ISO provided GISPA |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in Writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report |  | Inform ISO of Decision Based on Allocation Information Received |  | Post 2nd Financial Security | Review Reassessment Results | A) Return Notarized Affidavit to ISO B) Due Every Year Until COD | Provides Comments to Draft GIA | Negotiate GIA with ISO & PTO | Execute the GIA, Provide All Requested Information | Post 3rd Financial Security
2017-02-20 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data |  |  |  | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary | Generator Interconnection and Deliverability Allocation Procedures Cluster Process Summary |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | Affidavit Template for Cluster 5 and Later Queue Clusters Seeking TPDeliverability |  |  |  |  | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  | Affidavit Template for Cluster 5 and Later Queue Clusters Previously Allocated Transmission Plan Deliverability |  |  |  | May be milestone based - contact PTO
2017-05-29
2017-07-04 | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions | [5 empty] | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions
2017-09-04 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | (If Applicable) Notifies if additional Information is Complete or Deficient | (If Applicable) Notifies if IR is Complete or Deficient or Application is Not Valid | (Pending Validity of IR) Issues Pro-Forma Generator Interconnection Study Process Agreement (GISPA) | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Provide (PTO & ISO) Signed GISPA to Customer | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | Send Affidavit Market Notice Score Projects based on Affidavit Information | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2017-10-09 | ISO Response Timeframe |  | Prior to 30 CDs Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | Within 30 CDs After Window Closes | A) Within 5 BDs After Receipt of Valid IR B) Within 5 BDs of Results Meeting | Timely | Within 10 BDs of POI Designation |  |  | Within 10 BDs of results meeting | Within 15 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Prior to 30 CDs Before Affidavits Due to ISO | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs After Draft GIA Tendered | Within 10 BDs After Negotiation Completion
2017-11-10 | Revised Aug. 4, 2016
2017-11-23 | Dates - subject to change
2017-11-24 | * Date varies by project
2017-12-25
2018-01-01
2018-01-15
2018-01-19
2018-05-28
2018-07-04
2018-09-03
2018-10-08
2018-11-11
2018-11-22
2018-11-23
2018-12-25

## Cluster 8
2015-05-25 | Cluster 8
2015-07-03 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Pro Forma Study Agreement | Scoping Meeting* | Specify/Confirm POI* | Study Agreements* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report & AFC results issued, Customer comment option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment (Step 2) & Downsizing Results | Annual Deliverability Retention Affidavit | Tender Draft GIA* | GIA Negotiation* | Executable GIA* | Post 3rd Financial Security*
2015-09-07 | Dates | Start |  | 2015-04-01 | [6 empty] | 2015-07-30 | 2016-01-15 |  |  |  |  | 2016-04-29 | 2016-10-17 | 2016-11-20 |  |  | 2017-01-20 | 2017-03-15 | 2017-04-06 |  |  | 2017-10-17 | (per project) | (per project) | (per project)
2015-10-12 |  | End | 2015-03-01 | 2015-04-30 | (per project) | 2015-05-29 | 2015-05-30 | 2015-06-29 | (per project) | 2015-07-29 | 2016-01-15 | 2016-02-01 | 2016-02-14 | 2016-02-18 | (per project) | 2016-04-14 | 2016-11-20 | 2016-11-16 | 2016-12-06 | 2016-12-20 | 2016-12-23 | 2017-03-14 | 2017-03-22 | 2017-07-31 | 2017-05-19 | 2017-08-01 | 2017-11-16 | (per project) | (per project) | (per project) | On or before the start of construction
2015-11-11 | Milestone Timeframe |  |  | 30 CDs | Within 10 BDs of Notification | Within 20 BDs after Window Closes | Within 30 CDs After Window Closes | Within 60 CDs After Window Closes | Within 3 BDs After Scoping Meeting | Within 30 CDs of Scoping Meeting | 170 CDs to Complete |  | Within 30 CDs of Issuing Phase I Study Report | Within 3 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report | 205 CDs | Mid-November |  | Within 30 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Mid-November, Annually | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs after Tendering GIA | Within 10 BDs After Negotiation Completion
2015-11-26 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 | 3.5.2.2 | 3.5.2.2 | 6.1.1 | 6.1.2 | 6.1.1 | 6.1.1 | 6.6 | 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4, 7.5 | 8.9.3 | 13.1 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2015-11-27
2015-12-25 | Customer Actions |  |  |  |  | Customer Actions |  |  | Customer Actions |  |  |  |  | Customer Actions | [5 empty] | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions
2016-01-01 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | Within 20 BDs after Window Closes |  | Within 3 BDs after Scoping Meeting |  | Within 30 CDs of Scoping Meeting |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 3 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Due Date per Market Notice | Within 30 CDs after Receipt of Draft GIA |  |  | Before Start of Construction
2016-01-18 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | Review ISO provided GISPA. | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI | Execute ISO provided GISPA |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report |  | Inform ISO of decision based on allocation information received |  | Post 2nd Financial Security | Review Reassessment Results | A) Return Notarized Affidavit to ISO B) Due every year until COD | Provides comments to Draft GIA | Negotiate GIA with ISO & PTO | Execute the GIA, Provide All Requested Information | Post 3rd Financial Security
2016-02-15 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data |  |  |  | <FUTURE: link to Scoping Meeting Checklist/What to expect?> | <FUTURE: link to how to designate POI> | <FUTURE: link to Withdrawal Process> |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | Affidavit Template for Cluster 5 and Later Queue Clusters Seeking TPDeliverability |  |  |  |  | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  | Affidavit Template for Cluster 5 and Later Queue Clusters Previously Allocated Transmission Plan Deliverability |  |  |  | May be milestone based - contact PTO
2016-05-30
2016-07-04 | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions | [5 empty] | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions
2016-09-05 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | (If Applicable) Notifies if additional Information is Complete or Deficient | (If Applicable) Notifies if IR is Complete or Deficient or Application is Not Valid | (Pending Validity of IR) Issues Pro-Forma Generator Interconnection Study Process Agreement (GISPA) | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Provide (PTO & ISO) Signed GISPA to Customer | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | Send Affidavit Market Notice Score Projects based on Affidavit Information | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2016-10-10 | ISO Response Timeframe |  | Prior to 30 CDs Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | Within 30 CDs After Window Closes | A) Within 5 BDs After Receipt of Valid IR B) Within 5 BDs of Results Meeting | Timely | Within 10 BDs of POI Designation |  |  | Within 10 BDs of results meeting | Within 15 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Prior to 30 CDs before Affidavits Due to ISO | No Later Than Est. Time to Construct IFs and NUs plus 180 CDs | Within 120 CDs After Draft GIA Tendered | Within 10 BDs After Negotiation Completion
2016-11-11 | Revised Aug. 4, 2016
2016-11-24 | Dates - subject to change
2016-11-25 | * Date varies by project
2016-12-26
2017-01-02
2017-01-16
2017-02-20
2017-05-29
2017-07-04
2017-09-04
2017-10-09
2017-11-10
2017-11-23
2017-11-24
2017-12-25

## Cluster 7
2014-05-26 | Cluster 7
2014-07-04 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Pro Forma Study Agreement | Scoping Meeting* | Specify/Confirm POI* | Study Agreements* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report & AFC results issued, Customer comment option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | Tender Draft GIA for EO Projects* | EO GIA Negotiation | EO Executable GIA* | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment & Downsizing Results | Tender Draft GIA for FC/PCDS Projects | Annual Deliverability Retention Affidavit | FC/PCDS GIA Negotiation* | FC/PCDS Executable GIA* | Post 3rd Financial Security*
2014-09-01 | Dates | Start |  | 2014-04-01 | [6 empty] | 2014-07-01 | 2014-12-17 |  |  |  |  | 2015-04-30 | 2015-10-16 | 2015-11-21 | [5 empty] | 2016-01-20 | 2016-03-15 | 2016-04-06 |  |  |  | 2016-10-16
2014-10-13 |  | End | 2014-03-01 | 2014-04-30 | (per project) | 2014-05-29 | 2014-05-30 | 2014-06-29 | (per project) | 2014-07-29 | 2014-12-17 | 2015-01-02 | 2015-01-16 | 2015-01-22 | (per project) | 2015-03-17 | 2015-11-21 | 2015-11-15 | 2015-12-08 | 2015-12-21 | 2015-12-24 | (per project) | 2016-04-06 | (per project) | 2016-03-14 | 2016-03-22 | 2016-07-31 | 2016-05-19 | 2016-08-01 | 2016-08-31 | 2016-11-15 | 2016-11-29 | (per project) | On or before the start of construction
2014-11-11 | Milestone Timeframe |  |  | 30 CDs | Within 10 BDs of Notification | Within 20 BDs after Window Closes | Within 30 CDs After Window Closes | Within 60 CDs After Window Closes | Within 3 BDs After Scoping Meeting | Within 30 CDs of Scoping Meeting | 170 CDs to Complete |  | Within 30 CDs of Issuing Phase I Study Report | Within 3 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report | 205 CDs | Mid-November |  | Within 30 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting | Within 30 CDs after Phase II Results Meeting | Within 120 CDs after Issuing Final Phase II Study Report | Within 10 BDs of Negotiation Completion |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Within 30 CDs after Issuing Reasessment Results | Mid-November, Annually | Within 120 CDs after Issuing Reassessment Results | Within 10 BDs of Negotiation Completion
2014-11-27 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 | 3.5.2.2 | 3.5.2.2 | 6.1.1 | 6.1.2 | 6.1.1 | 6.1.1 | 6.6 | 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 13.1.1 | 13.2 | 13.2, 13.3 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4, 7.5 | 13.1 | 8.9.3 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2014-11-28
2014-12-25 | Customer Actions |  |  |  |  | Customer Actions |  |  | Customer Actions |  |  |  |  | Customer Actions | [5 empty] | Customer Actions |  |  | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions
2015-01-01 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | Within 20 BDs after Window Closes |  | Within 3 BDs after Scoping Meeting |  | Within 30 CDs of Scoping Meeting |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 3 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting | Within 30 CDs after Receipt of Draft GIA |  |  |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Within 30 CDs after Receipt of Draft GIA | Due Date per Market Notice |  |  | Before Start of Construction
2015-01-19 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | Review ISO provided GISPA. | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI | Execute ISO provided GISPA |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report | Provides comments to Draft GIA | Negotiate GIA with ISO & PTO | Execute the GIA |  | Inform ISO of decision based on allocation information received |  | Post 2nd Financial Security | Review Reassessment Results | Provides comments to Draft GIA | A) Return Notarized Affidavit to ISO B) Due every year until COD | Negotiate GIA with ISO & PTO | Execute the GIA | Post 3rd Financial Security
2015-02-16 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data |  |  |  | <FUTURE: link to Scoping Meeting Checklist/What to expect?> | <FUTURE: link to how to designate POI> | <FUTURE: link to Withdrawal Process> |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | Affidavit Template for Cluster 5 and Later Queue Clusters Seeking TPDeliverability | [7 empty] | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  |  | Affidavit Template for Cluster 5 and Later Queue Clusters Previously Allocated Transmission Plan Deliverability |  |  | May be milestone based - contact PTO
2015-05-25
2015-07-03 | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions | [5 empty] | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions
2015-09-07 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | (If Applicable) Notifies if additional Information is Complete or Deficient | (If Applicable) Notifies if IR is Complete or Deficient or Application is Not Valid | (Pending Validity of IR) Issues Pro-Forma Generator Interconnection Study Process Agreement (GISPA) | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Provide (PTO & ISO) Signed GISPA to Customer | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | PTO Tenders Draft GIA Appendices | Send Affidavit Market Notice Score Projects based on Affidavit Information | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2015-10-12 | ISO Response Timeframe |  | Prior to 30 CDs Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | Within 30 CDs After Window Closes | A) Within 5 BDs After Receipt of Valid IR B) Within 5 BDs of Results Meeting | Timely | Within 10 BDs of POI Designation |  |  | Within 10 BDs of results meeting | Within 15 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting | Within 30 CDs after Issuing Final Phase II Study Report | Within 120 CDs after Issuing Final Phase II Study Report | Within 10 BDs after completion of negotiation |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Within 30 CDs after Issuing Reassessment Results | Prior to 30 CDs before Affidavits Due to ISO | Within 120 CDs after Issuing Reassessment Results | Within 10 BDs after negotiation completion
2015-11-11 | Revised Feb. 12, 2015
2015-11-26 | Dates - subject to change
2015-11-27 | * Date varies by project
2015-12-25
2016-01-01
2016-01-18
2016-02-15
2016-05-30
2016-07-04
2016-09-05
2016-10-10
2016-11-11
2016-11-24
2016-11-25
2016-12-26
Formulas:
IC Allocation Decision = [IC Allocation Decision, row above]+7
Pro Forma Study Agreement = [IR Submittal]+30
Scoping Meeting* = [IR Submittal]+60
Study Agreements* = [Scoping Meeting*]+30
Phase I Study = [Phase I Study, row above]+169
Post Initial Financial Security = [Phase I Study]+90
Phase II Study = [Phase II Study, row above]+205
Tender Draft GIA for FC/PCDS Projects = [Annual Reassessment & Downsizing Results]+30
FC/PCDS GIA Negotiation* = [Annual Reassessment & Downsizing Results]+120

## Cluster 6
2013-05-27 | Cluster 6
2013-07-04 | Milestone |  | IR Open Window Announcement | IR Submittal | IR Validation* |  | Pro Forma Study Agreement | Scoping Meeting* | Specify/Confirm POI* | Study Agreements* | Phase I Study | Phase I Study Report issued, Customer comment option on Study Report | Phase I Study Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report & AFC Results Issued, Customer Comment Option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | Tender Draft GIA for EO Projects* | EO GIA Negotiation | EO Executable GIA* | TP Deliverability Allocation & Results (Reassessment Step 1) | IC Allocation Decision | Annual Reassessment (Step 2) & Downsizing Study | Post 2nd Financial Security | Annual Reassessment & Downsizing Results | Tender Draft GIA for FC/PCDS Projects | Annual Deliverability Retention Affidavit | FC/PCDS GIA Negotiation* | FC/PCDS Executable GIA* | Post 3rd Financial Security*
2013-09-02 | Dates | Start |  | 2013-04-01 | [6 empty] | 2013-08-01 | 2014-01-17 |  |  |  |  | 2014-04-30 | 2014-10-16 | 2014-11-21 | [5 empty] | 2015-01-20 | 2015-03-15 | 2015-04-06 |  |  |  | 2015-10-16
2013-10-14 |  | End | 2013-03-01 | 2013-04-30 | (per project) | 2013-05-29 | 2013-05-30 | 2013-06-29 | (per project) | 2013-07-29 | 2014-01-17 | 2014-02-03 | 2014-02-16 | 2014-02-20 | (per project) | 2014-04-17 | 2014-11-21 | 2014-11-15 | 2014-12-09 | 2014-12-21 | 2014-12-24 | (per project) | 2015-04-08 | (per project) | 2015-03-15 | 2015-03-22 | 2015-07-31 | 2015-05-20 | 2015-08-01 | 2015-08-31 | 2015-11-15 | 2015-11-29 | (per project) | On or before the start of construction
2013-11-11 | Milestone Timeframe |  |  | 30 CDs | Within 10 BDs of Notification | Within 20 BDs after Window Closes | Within 30 CDs After Window Closes | Within 60 CDs After Window Closes | Within 3 BDs After Scoping Meeting | Within 30 CDs of Scoping Meeting | 170 CDs to Complete |  | Within 30 CDs of Issuing Phase I Study Report | Within 3 BDs after Phase I Report Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report | 205 CDs | Mid-November |  | Within 30 CDs of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting | Within 30 CDs after Phase II Results Meeting | Within 120 CDs after Issuing Final Phase II Study Report | Within 10 BDs of Negotiation Completion |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Within 30 CDs after Issuing Reassessment Results | Mid-November, Annually | Within 120 CDs after Issuing Reassessment Results | Within 10 BDs of Negotiation Completion
2013-11-28 | Tariff Appendix DD Section Number(s) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 | 3.5.2.2 | 3.5.2.2 | 6.1.1 | 6.1.2 | 6.1.1 | 6.1.1 | 6.6 | 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 13.1.1 | 13.2 | 13.2, 13.3 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6, 8.9.8 | 7.4, 7.5 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4, 7.5 | 13.1 | 8.9.3 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2013-11-29
2013-12-25 | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions
2014-01-01 | Customer Response Timeframe |  |  |  | Within 10 BDs of Notification | Within 20 BDs after Window Closes |  | Within 3 BDs after Scoping Meeting |  | Within 30 CDs of Scoping Meeting |  | Within 10 BDs of Receipt, 3 BDs Before Phase I Results Meeting |  | Within 3 BDs after Phase I Results Meeting | Within 10 BDs after Phase I Results Meeting | Within 90 CDs After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 BDs of Receipt, 3 BDs Before Phase II Report Meeting |  | Within 3 BDs after Phase II Report Meeting | Within 30 CDs after Receipt of Draft GIA |  |  |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 CDs after Issuance of Final Phase II Study report |  | Within 30 CDs after Receipt of Draft GIA | Due Date per Market Notice |  |  | Before Start of Construction
2014-01-20 | Customer Actions |  |  | Submit: 1) IR Package 2) Study Fee/Deposit 3) Site Exclusivity/Deposit | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information | Review ISO provided GISPA. | A) Attend Scoping Meeting B) Review/Comment on Meeting MInutes | Specify/Confirm POI | Execute ISO provided GISPA |  | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Results Meeting | Option to provide initial or further comments on Phase I Study Report | Customer submits Appendix B reflecting any allowed modifications to project, including Option A/B choice (and updated IR package if necessary) | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report | Provides comments to Draft GIA | Negotiate GIA with ISO & PTO | Execute the GIA |  | Inform ISO of decision based on allocation information received |  | Post 2nd Financial Security | Review Reassessment Results | Provides comments to Draft GIA | A) Return Notarized Affidavit to ISO B) Due every year until COD | Negotiate GIA with ISO & PTO | Execute the GIA | Post 3rd Financial Security
2014-02-17 | Customer Resources |  | Market Notices | GIDAP Interconnection Request - Generating Facility Data |  |  |  | <FUTURE: link to Scoping Meeting Checklist/What to expect?> | <FUTURE: link to how to designate POI> | <FUTURE: link to Withdrawal Process> |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  | AppendixB-GeneratorInterconnectionStudyProcessAgreement | Participating transmission owner financial security instruments. |  | Affidavit Template for Cluster 5 and Later Queue Clusters Seeking TPDeliverability | [7 empty] | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  |  | Affidavit Template for Cluster 5 and Later Queue Clusters Previously Allocated Transmission Plan Deliverability |  |  | May be milestone based - contact PTO
2014-05-26
2014-07-04 | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions
2014-09-01 | ISO Actions |  | Sends Market Notice to Subscribers | Notifies Customer if IR is Complete or Deficient | (If Applicable) Notifies if additional Information is Complete or Deficient | (If Applicable) Notifies if IR is Complete or Deficient or Application is Not Valid | (Pending Validity of IR) Issues Pro-Forma Generator Interconnection Study Process Agreement (GISPA) | A) Schedule Scoping Meeting B) Provide Meeting Minutes | Review POI Changes | Provide (PTO & ISO) Signed GISPA to Customer | Performs Phase I Study | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date |  | Send Affidavit Market Notice Score Project based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers. | Reviews allocation decisions for any impacts to Second Financial Security | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project posted by each project's Posting due date | Provide Reassessment Results to Impacted Customers. Determine if executed GIA amendments are needed. | PTO Tenders Draft GIA Appendices | Send Affidavit Market Notice Score Projects based on Affidavit Information | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2014-10-13 | ISO Response Timeframe |  | Prior to 30s CD Before Cluster Application Window Opens | Within 10 BDs of Receipt | Within 5 BDs of Receipt from Customer | Within 5 BDs of Receipt | Within 30 CDs After Window Closes | A) Within 5 BDs After Receipt of Valid IR B) Within 5 BDs of Results Meeting | Timely | Within 10 BDs of POI Designation |  |  | Within 10 BDs of results meeting | Within 15 BDs after results Meeting | Timely manner |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 BDs | Within 15 BDs after Results Meeting | Within 30 CDs after Issuing Final Phase II Study Report | Within 120 CDs after Issuing Final Phase II Study Report | Within 10 BDs after completion of negotiation |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Within 30 CDs after Issuing Reassessment Results | Prior to 30 CDs before Affidavits Due to ISO | Within 120 CDs after Issuing Reassessment Results | Within 10 BDs after negotiation completion
2014-11-11 | Revised Feb. 12, 2015
2014-11-27 | Dates - subject to change
2014-11-28 | * Date varies by project
2014-12-25
2015-01-01
2015-01-19
2015-02-16
2015-05-25
2015-07-03
2015-09-07
2015-10-12
2015-11-11
2015-11-26
2015-11-27
2015-12-25
Formulas:
IC Allocation Decision = [IC Allocation Decision, row above]+7
Pro Forma Study Agreement = [IR Submittal]+30
Scoping Meeting* = [IR Submittal]+60
Study Agreements* = [Scoping Meeting*]+30
Phase I Study = [Phase I Study, row above]+169
Post Initial Financial Security = [Phase I Study]+90
Phase II Study = [Phase II Study, row above]+205
Tender Draft GIA for FC/PCDS Projects = [Annual Reassessment & Downsizing Results]+30
FC/PCDS GIA Negotiation* = [Annual Reassessment & Downsizing Results]+120

## Cluster 5
2012-07-04 | Cluster 5
2012-09-03 | Milestone |  | GIDAP Tariff Effective Date | Cluster 5 Decision (GIDAP) | Phase I Study | Affidavits |  | Phase I Study Report issued, Customer comment option on Study Report | Phase I Study Results Meeting* | Phase I Results Meeting Follow Up Comments to Study Report* | Appendix B Submittal & Selection of Options A & B* |  | Post Initial Financial Security | Phase II Study | Deliverability Initial Affidavit | Phase II Study Report issued, Customer comment option on Study Report | Phase II Study Results Meeting* | Phase II Results Meeting Follow Up Comments to Study Report* | Tender Draft GIA for EO Projects* | EO GIA Negotiation | EO Executable GIA* | TP Deliverability Allocation and Results | IC Allocation Decision | Annual Reassessment Study | Post 2nd Financial Security | Reassessment Report | Tender Draft GIA for FC/PCDS Projects | Annual Deliverability Retention Affidavit | FC/PCDS GIA Negotiation* | FC/PCDS Executable GIA* | Post 3rd Financial Security*
2012-10-08 | Dates | Start | 2012-07-25 | 2012-07-25 | 2012-07-15 |  |  | 2013-01-31 | [5 empty] | 2013-05-12 | 2013-10-16 | 2013-12-03 | [5 empty] | 2014-01-20 | 2014-03-14 | 2014-04-06 |  |  |  | 2014-10-16
2012-11-12 |  | End |  | 2012-08-06 | 2013-01-31 | 2012-12-21 | 2013-01-20 | 2013-02-14 | 2013-03-02 | 2013-03-06 | 2013-03-15 |  | 2013-05-01 | 2013-12-03 | 2013-11-15 | 2013-12-17 | 2014-01-02 | 2014-01-07 | (per project) | 2014-04-16 | (per project) | 2014-03-14 | 2014-03-21 | 2014-07-31 | 2014-06-01 | 2014-08-01 | 2014-08-31 | 2014-11-15 | 2014-11-29 | (per project) | On or before the start of construction
2012-11-22 | Milestone Timeframe |  | July 24: FERC issued order accepting GIDAP Tariff July 25: Effective date of GIDAP Tariff |  | 200 Calendar Days to complete |  |  |  | Within 30 Calendar Days of Issuing Phase I Study Report |  |  |  |  | 205 Calendar Days | Mid-November |  | Within 30 Calendar Days of Issuing Phase II Study Report | Within 3 BDs after Phase II Study Results Meeting | Within 30 CDs after Phase II Results Meeting | Within 120 CDs after Issuing Final Phase II Study Report | Within 10 BDs of Negotiation Completion |  |  | Prior to Subsequent Clusters' Phase II Study, Annually | 180 CDs after Issuance of Final Phase II Study report | Annually until COD | Within 30 CDs after Issuing Reassessment Report | Mid-November, Annually | Within 120 CDs after Issuing Reassessment Report | Within 10 BDs of Negotiation Completion
2012-11-23 | Tariff Appendix DD Section Number(s) |  |  | FERC filing Transmittal Letter | 6.6 |  |  | 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 |  | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.9.2 | 8.5 | 8.7 | 8.7 | 13.1.1 | 13.2 | 13.2, 13.3 | 8.9 thru 8.9.2 | 8.9.4 thru 8.9.6 | 7.4 | 11.3.1 thru 11.3.1.7, 11.5 | 7.4 | 13.1 | 8.9.3 | 13.2 | 13.2, 13.3 | 11.3.2 thru 11.3.2.4
2012-12-25
2013-01-01 | Customer Actions |  |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions |  |  |  | Customer Actions
2013-01-21 | Customer Response Timeframe |  |  | Within 10 Calendar Days from Issuance of FERC Approved Order |  |  | Within 30 Calendar Days of Receipt of Affidavits | Within 10 Business Days of Receipt, 3 Business Days Before Phase I Report Meeting |  | Within 3 Business Days after Phase I Report Meeting | Within 10 Business Days after Phase I Results Meeting |  | Within 90 Calendar Days After Final Phase I Study Report |  | Due Date per Market Notice | Within 10 Business Days of Receipt, 3 Business Days Before Phase II Report Meeting |  | Within 3 Business Days after Phase II Report Meeting | Within 30 CDs after Receipt of Draft GIA |  |  |  | Within 7 CDs of receipt of Notification of Allocation |  | 180 Calendar Days after Issuance of Final Phase II Study report |  | Within 30 CDs after Receipt of Draft GIA | Due Date per Market Notice |  |  | Before Start of Construction
2013-02-18 | Customer Actions |  |  | Provides decision to ISO by 8/6/2012 to Withdraw or Continue (see Section 3.5.1.1 (b) of Tariff, Tariff begins on page 122) (all IR data needs to be valid at this time) |  | Pre-C5 customers Affidavit Form Posted | Pre-C5 customers return completed Affidavits | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Report Meeting | Option to provide further comments on Phase I Study Report | Customer resubmits Appendix B reflecting any allowed modifications to project | Customer selects Option A or B in Appendix B | Post Initial Financial Security |  | Return Notarized Affidavit to ISO | Receive Phase II Study Report and Provide Comments in writing to ISO | Attend Phase II Results Meeting | Option to provide further comments on Phase II Study Report | Provides comments to Draft GIA | Negotiate GIA with ISO & PTO | Execute the GIA |  | Inform ISO of decision based on allocation information received |  | Post 2nd Financial Security | Review Reassessment Report | Provides comments to Draft GIA | A) Return Notarized Affidavit to ISO B) Due every year until COD | Negotiate GIA with ISO & PTO | Execute the GIA | Post 3rd Financial Security
2013-05-27 | Customer Resources |  | http://elibrary.ferc.gov/idmws/common/OpenNat.asp?fileID=13033536 | http://www.caiso.com/Documents/May252012GIDAPAmendmentER12-1855pdf.pdf |  | http://bpmcm.caiso.com/Pages/BPMLibrary.aspx |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  |  | http://www.caiso.com/planning/Pages/GeneratorInterconnection/GeneratorInterconnectionApplicationProcess/Default.aspx | http://www.caiso.com/planning/Pages/GeneratorInterconnection/GeneratorInterconnectionApplicationProcess/Default.aspx |  | Affidavit Template for Cluster 5 and Later Queue Clusters Seeking TPDeliverability | [7 empty] | Deliverability Allocation Customer Options Form |  | Participating transmission owner financial security instruments |  |  | Affidavit Template for Cluster 5 and Later Queue Clusters Previously Allocated Transmission Plan Deliverability |  |  | May be milestone based - contact PTO
2013-07-04
2013-09-02 | ISO Actions |  |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions |  |  |  | ISO Actions
2013-10-14 | ISO Actions |  |  |  |  | Sends Out Affidavits |  | Issues Report to Customer via E-mail on or before 01/31/2013 | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B with PTO. Notifies Customer if Material Modification Review needed. |  | ISO coordinates with PTO to determine whether each project Posted by each project's Posting due date |  | Send Affidavit Market Notice Score Projects based on Affidavit Information | A) Issue Report to Customer B) Schedule Results Meeting | Provide meeting minutes, including action items, next steps, Option A/B implications, and attendee list. | Review all comments and, if necessary, issue addendum or revised Study Report | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer | Allocate TP Deliverability to FC and PCDS projects meeting affidavit eligibility criteria. Provide Allocation Results to Customers | Reviews allocation decisions for any impacts to Second Financial Security. | Performs reassessment of active projects for next cluster's Phase II Interconnection Study base case | ISO coordinates with PTO to determine whether each project Posted by each project's Posting due date | Provide Reassessment Reports to Impacted Customers. Determine if executed GIA amendments are needed. | PTO Tenders Draft GIA Appendices | Send Affidavit Market Notice Score Project based on Affidavit Information | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2013-11-11 | ISO Response Timeframe |  |  | Cut off date for IR withdrawal is COB 8/3/2012 | Approximately 60 Calendar Days After Window Closes |  |  |  | Within 10 Business Days | Within 15 Business Days after results Meeting | Timely manner |  |  |  | Prior to 30 CDs before Affidavits Due to ISO |  | Within 10 Business Days | Within 15 Business Days after results Meeting | Within 30 CDs after Issuing Final Phase II Study Report | Within 120 CDs after Issuing Final Phase II Study Report | Within 10 BDs after completion of negotiation |  | Timely Manner |  |  | Within 1 BD of completion of Reassessment Study | Within 30 CDs after Issuing Reassessment Report | Prior to 30 CDs before Affidavits Due to ISO | Within 120 CDs after Issuing Reassessment Report | Within 10 BDs after negotiation completion
2013-11-28 | Revised Feb. 12, 2015
2013-11-29 | Dates - subject to change
2013-12-25 | * Date varies by project
2014-01-01
2014-01-20
2014-02-17
2014-05-26
2014-07-04
2014-09-01
2014-10-13
2014-11-11
2014-11-27
2014-11-28
2014-12-25
Formulas:
Cluster 5 Decision (GIDAP) = [GIDAP Tariff Effective Date]
IC Allocation Decision = [TP Deliverability Allocation and Results, row below]
IC Allocation Decision = [IC Allocation Decision, row above]+7
Phase I Study = [Phase I Study, row above]+200
Phase II Study = [Phase II Study, row above]+205
Phase II Study Results Meeting* = [Phase II Study]+30
Tender Draft GIA for FC/PCDS Projects = [Reassessment Report]+30
FC/PCDS GIA Negotiation* = [Reassessment Report]+120

## Acronyms
Acronym | Term
AFC | Annual Full Capacity
BD | Business Day (Per ISO Tariff - Excludes Federal Holidays & day after Thanksgiving)
CD | Calendar Day
COD | Commercial Operation Date
EO | Energy Only
FC | Full Capacity
GIA | Generator Interconnection Agreement
GIDAP | Generation Interconnection and Deliverabilty Allocation Procedures
GISPA | Generator Interconnection Study Process Agreement
IR | Interconnection Request
ISO | (California) Independent System Operator
PCDS | Partial Capacity Deliverability Status
POI | Point of Interconnection
PTO | Participating Transmission Owner
TP | Transmission Planning