## Impact Category
CAISO -Public
Select a Schedule Impact Category and Identify it for each project in the column labeled 'Reason for ISD Change from Original Comitted Date'. The Schedule Impact Definitions and Examples are listed below.
1 | Bundling Dependencies – Schedule impact due to bundling, scope tie-ins, or dependencies with other projects. This includes waiting on another project or benefiting from early completion, combined construction, or coordinated execution (e.g., proceeding early because Project X completed ahead of plan).
Delay example: Project cannot proceed until a dependent project is complete.
Acceleration example: Related project finishes early, enabling coordinated execution sooner.
2 | Clearances – Schedule impact related to meeting electrical or mechanical clearance requirements, including governing authority approvals (e.g., NERC, GO95/GO128, CAISO/WECC). This includes redesign, mitigation, or approval processes required to meet clearance standards.
Delay example: Redesign required to resolve clearance violations before construction can proceed.
Acceleration example: Clearance requirements are met without modification, allowing work to proceed as planned.
3 | Financing – Schedule impact driven by funding availability, approvals, cost recovery, or rate treatment timing. This includes delays in securing capital or benefits from early funding authorization.
Delay example: Capital approval is deferred to a future funding cycle.
Acceleration example: Funding is approved earlier than planned, enabling earlier project execution.
4 | ISO Action – Schedule impact resulting from CAISO actions, including approvals, re-studies, queuing outcomes, scope changes, or project prioritization decisions. This includes both delays and schedule pull-ins driven by ISO determinations.
Delay example: CAISO-required re-study extends the project schedule.
Acceleration example: CAISO approval is granted without requiring additional studies.
5 | Land Rights – Schedule impact related to land acquisition, easements, title issues, encroachments, access agreements, or eminent domain. This includes delays from negotiations or disputes and acceleration from early acquisition or agreements.
Delay example: Prolonged easement negotiations delay construction start.
Acceleration example: Land rights are secured early through negotiated agreements.
6 | Material – Schedule impact due to availability or delivery timing of project-specific materials not related to broader supply chain disruptions. This includes fabrication timing, procurement issues, or substitution with available materials.
Delay example: Late delivery of custom-fabricated equipment delays installation.
Acceleration example: Standard materials are used, allowing earlier installation.
7 | Other – Schedule impact that does not align with established categories and requires additional explanation in project documentation.
Delay example: Unique constraint not captured by standard categories delays the project.
Acceleration example: Innovative execution approach shortens the project duration.
8 | Outage – Schedule impact related to transmission or substation outage availability, constraints, or system conditions. This includes required outages for construction or energization activities.
Delay example: Required outage window is denied or postponed.
Acceleration example: An earlier or combined outage window becomes available.
9 | Permitting (CPUC/CEQA) – Schedule impact related to CPUC permitting and CEQA environmental review, including documentation, mitigation requirements, coordination, or litigation.
Delay example: Extended CEQA review or legal challenge delays approval.
Acceleration example: Permit is issued early with minimal conditions.
10 | Permitting (non-CPUC/CEQA) – Schedule impact related to federal, state, local, tribal, or special-district permits (e.g., BLM, USFS, city/county). This includes agency processing timelines and coordination requirements.
Delay example: Agency permit processing exceeds expected timelines.
Acceleration example: Required permits are issued ahead of schedule.
11 | Project Design – Schedule impact from engineering scope definition, design development, rework, constructability reviews, or changes outside the approved design.
Delay example: Late scope change requires redesign and delays construction.
Acceleration example: Reuse of previously approved designs shortens the design phase.
12 | Safety – Schedule impact related to safety incidents, compliance requirements, or work stoppages necessary to maintain safe working conditions.
Delay example: Work halted due to a safety incident investigation.
Acceleration example: Improved safety planning reduces downtime during construction.
13 | Securities – Schedule impact associated with financial instruments or structuring related to project funding and capital allocation.
Delay example: Delays in financial structuring postpone funding availability.
Acceleration example: Early completion of financing arrangements enables faster project start.
14 | Supply Chain Delays – Schedule impact driven by macro-level supply chain conditions such as global shortages, shipping congestion, or geopolitical factors affecting procurement timelines.
Delay example: Global shortages extend equipment lead times.
Acceleration example: Alternative sourcing reduces procurement duration.
15 | Unspecified – Schedule impact reported without a clearly defined or documented cause at the time of reporting.
Delay example: Milestone delay reported without explanation.
Acceleration example: Milestone achieved early without a documented reason.
16 | Vendor Quality / Delays – Schedule impact related to vendor or contractor performance, including QA/QC issues, rework, missed milestones, or strong execution performance.
Delay example: Vendor quality issues require rework and delay progress.
Acceleration example: Vendor exceeds milestone expectations and completes work early.
17 | Weather – Schedule impact related to environmental conditions such as severe weather, fire restrictions, access closures, or natural events that limit construction activities.
Delay example: Fire restrictions halt construction work.
Acceleration example: Favorable weather conditions allow extended work periods.
18 | Workforce Availability – Schedule impact related to labor availability, crew sizing, competing work demands, or specialized skill constraints.
Delay example: Crew shortages delay construction activities.
Acceleration example: Early crew mobilization improves productivity and schedule.

## PGaE
CAISO -Public
ID | Network Upgrades | Description | PTO | Study | Type of Upgrade | Category | Status | Trigger Year | Current Expected Construction Start | Expected CPUC Permit Application | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF (Current) | Agregate MW in Queue with Executed LGIA | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
19rsmt-3 | Schindler 70kV Bus Normal & Outage Overload | Upgrade Schindler 70 kV Bus to 1113 kcmil AAC | PG&E | RA-19 | Reliability | Bus Flow | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
21rsmt-1 | Henrietta Substation 70kV CBs 12 and 72 Overstress | Henrietta Sub: Replace 70kV CB 12 & 72 and switches. | PG&E | RA-21 | Reliability | SCD overstress | Not Triggered | 2021 |  |  | 2025-12-31 | 2026-06-16 | 2025-02-26 | 2026-09-14 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 2027-11-23 | 2029-03-28 | TBD |  |  | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered
21rsmt-5 | Palo Alto 115 kV circuit breakers 412 and 442 overstress | Replace Palo Alto 115 kV circuit breakers 412 and 442 with 63 kA interrupting capability | PG&E | RA-21 | Reliability | SCD overstress | Not Assigned | 2021 |  | 2029-11-29 | 2024-09-30 | 2025-03-27 | 2026-06-10 | 2027-11-08 | 2027-11-08 | 2027-11-08 | 2027-11-08 | 2029-03-29 | 2029-10-18 | 2031-10-08 | 2032-01-05 | 2032-01-05 | 2032-01-05 | 2032-07-12 | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to an Active Generation project
22rsmt-2 | Cottonwood 60 kV many CB overstress upgrade | Replace Cottonwood 60 kV circuit breakers 22, 32, 42, 52, 62, 82 | PG&E | RA-22 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C12P1-GCR01 | Moraga: Repl OCB 582 | Replace Moraga 115 kV circuit breakers 582 | PG&E | C12 | Reliability | SCD overstress | Not Assigned | [13 empty] | 2032-02-04 | TBD |  |  | 0 | (blank) | N/A | Q3 - 2026 - Dependent Queue project withdrawn. No longer assigned
C13P1-NCA02 | Cottonwood 230 kV circuit breaker 212, 242 & 282 overstress | Replace Cottonwood 230 kV circuit breaker 212, 242 & 282 | PG&E | C13 | Reliability | SCD overstress | Not Assigned | 2025 | [12 empty] | N/A | N/A |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C13P1-WGR03 | Mesa Substation 115 kV CBs 142 overstress | Replace Mesa Substation 115 kV CB 142 with 63 kA interrupting capability | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P1-GGD01 | PGAE_250_QC14P1RAS-03-gbay-tassajara–q1877ss-overload-RAS | RAS to trips Q1877 at Q1877SS Switching Station when an overload occurs in GRANT-Q1877SS or Q1877SS-EASTSHORE 115kV Lines due to outage of Q1877SS-EASTSHORE or GRANT-Q1877SS 115kV Lines, respectively, when Q1877 is in discharging mode. | PG&E | C14 | Reliability | RAS (Reliability) | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | N/A |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P1-GGR03 | Ames Distribution 115 kV circuit breaker 112 & 122 overstress | Replace Ames Distribution 115 kV circuit breakers 112 & 122 | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P1-GGR06 | Newark 115 kV bus overstress beyond 63 kA | Install series bus reactors between Newark Substation 115 kV bus secions E and F | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P1-GGR08 | Sobrante 115 kV CB 112 overstress | Replace Sobrante 115 kV circuit breaker 112 | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD |  | TBD |  |  | 0 | (blank) | N/A | Q3 - 2026 - Dependent Queue project withdrawn. No longer assigned
C14P1-NLD02 | Eagle Rock-Cortina 115 kV Line (Lower Lake Sw Sta-Highland J2-Cache J) | Reconductor 2.5 miles of Eagle Rock-Cortina 115 kV (Lower Lake SW STA-Highland J2 section) to 477 ACSS and upgrade any limiting equipment | PG&E | C14 | Deliverability | Re-conductor | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P1-NLD04 | Ukiah-Hopland-Cloverdale 115 kV Line (Cloverdale-Hopland J) and Geysers #3-Eagle Rock 115 kV Line (Geysers34-Eagle Rock) | Reconductor 14.79 miles of Ukiah-Hopland-Cloverdale 115 kV (Cloverdale-Hopland Jt) to 477 ACSS and upgrade any limiting equipment | PG&E | C14 | Deliverability | Re-conductor | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | TBD |  |  | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered
C14P1-NLD05 | Geyser #3-Cloverdale 115 kV Line (Aidlin SwSta-Cloverdale) | Reconductor 8 miles of Geyser #3-Cloverdale (MPE Tap-Cloverdale) 115 kV to 477 ACSS and upgrade any limiting equipment | PG&E | C14 | Deliverability | Re-conductor | Not Triggered |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | TBD |  |  | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered
C14P1-NLD06 | Ukiah-Hopland-Cloverdale 115 kV Line (Cloverdale-Hopland J) and Geysers #3-Eagle Rock 115 kV Line (Geysers34-Eagle Rock) | Reconductor entire Geysers #3-Eagle Rock 115 kV (1.77 miles) to 1113 AAC and upgrade any limiting equipment | PG&E | C14 | Deliverability | Re-conductor | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | TBD |  |  | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered
C14P2-FGR05 | Transient stability mitigation: Panoche-Mendota 115 kV lines RAS | RAS should trip the output of Q1940 for the loss of Panoche-Mendota 115 kV line to mitigate the oscillations and voltage criteria violations. | PG&E | C14 | Reliability | RAS (Reliability) | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | N/A |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-FGR06 | Transient Stability: Updated dynamic models required | Updated dynamic models required that exhibits acceptable performance. | PG&E | C14 | Reliability | Transient Stability | Initiating | 2025 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | TBD |  |  | 25 | (blank) | N/A | Q3 - 2026 - Not a project This is a transient stability model
C14P2-FPN02 | Los Banos 230 kV circuit breaker 252 & 262 overstress | Relocate CB 262, 242 & 252 and their line terminal to the new 230 kV BAAH bus section. 242 & 252 line terminals would be crossed if we only move one line. | PG&E | C14 | Reliability | SCD overstress | Not Assigned | 2023 |  | 2027-09-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-04-01 | 2028-04-01 | Removed |  | 2028-12-28 | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects. Project In-Service date improved due to study needs and other test results for capacity and saftey concerns
C14P2-FPN05 | Los Banos: Q1381 is assigned a 230 kV BAAH Bus Section CB 262 Overtress | Needed for CB 262 Overtress GRNU | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-GGR10 | Claremont (OAK K) 115 kV circuit breaker 122 overstress | Replace Claremont (OAK K) 115 kV circuit breaker 122 | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-GGR11 | Palermo 115 kV CB 152 overstress | Replace Palermo 115 kV CB 152 | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-GGR13 | Ravenswood 115 kV CB 132 and 142 | Replace Ravenswood 115 kV CB 132 and 142 | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  | Removed | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-GGR14 | Birds Landing Sw Sta 230 kV CB 212, 412 overload mitigation | Upgrade Birds Landing Sw Sta 230 kV bay 2 to 3000 A equipment and replacing 3 circuit breakers and associated switches/relays | PG&E | C14 | Reliability | Bus Flow | Not Triggered |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD |  | TBD |  |  | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered
C14P2-GGR15 | Pittsburg Substation 230 kV Bus Section E overload. enhance conductor rating | Seek enhanced ratings of 2964/3372A for 2-2300 kcmil AL conductor. Assumes replacement of all fittings to compression and limited reconductor work to attach new fittings. | PG&E | C14 | Reliability | Bus Flow | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-GGR16 | Pittsburg Substation 115 kV Bus Section E overload. Reconductor/Reinforce Bus. | Reconductor bus to 3-2300 kcmil. Evaluate and Reinforce Structures. | PG&E | C14 | Reliability | Bus Flow | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-GPT02 | San Jose Area HVDC 230 kV Line (Newark - NRS) | To build two HVDC lines, 1) from Newark 230 kV to NRS 230 kV and 2) Metcalf 500 kV to San Jose B 115 kV. | PG&E | LS Power | Capacity | HVDC | Not Assigned | 2022 |  | 2027-05-04 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-11-30 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2027-03-16 | 2027-05-28 | 2028-04-01 | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-GPT02 | San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | To build two HVDC lines, 1) from Newark 230 kV to NRS 230 kV and 2) Metcalf 500 kV to San Jose B 115 kV. | PG&E | LS Power | Capacity | HVDC | Not Assigned | 2022 |  | 2026-04-03 |  | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-04-30 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2027-12-30 | 2027-12-30 | 2028-05-01 | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects. Tracking to completion of the San Jose B scope and not the LS Power scope with 5/1/2028 ISD.
C14P2-KGR09 | Kern PP 70 kV circuit breaker 62 overstress | Replace Kern PP 70 kV circuit breaker 62 | PG&E | C14 | Reliability | SCD overstress | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-NLD07 | Hopland Transformer Bank #2 replacement | Replace Hopland 115/60 kV Transformer Bank #2 with 3-phase 100/110 MVA transformer with LTC | PG&E | C14 | Deliverability | Re-conductor | Not Triggered | [17 empty] | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered
C14P2-NPT03 | Rio Oso 230/115 kV Transformer Upgrades | This project will resolve current configuration issues, address reliability and capacity concerns, and alleviate high- voltage issues at Rio Oso Substation. The upgrades to Rio Oso will also position the substation for future system reinforcement projects, enhanced automation, and additional controls of PG&E’s transmission system. This proposed project will rebuild Rio Oso Substation within the existing substation fence line. The project will include a 115kV and 230kV gas-insulated switchgear (GIS) in a breaker and a half (BAAH) configuration, and replacement of the two 230/115kV transformers with larger capacity units. This proposal will allow the project team to perform most of the work without interfering with the existing equipment. | PG&E | C14 | Capacity | Bus Upgrade | Not Assigned | 2007 |  | 2021-06-01 | 2024-04-30 | 2024-06-30 | 2024-04-30 | 2025-04-17 | 2025-12-31 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2026-04-06 | 2026-04-06 | 2025-05-21 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C14P2-SGR01 | Midway Substation 500 kV circuit breaker 712 overload mitigation | Replace Midway 500 kV CB 712, switches and jumpers to achieve 4000 A normal rating | PG&E | C14 | Reliability | Bus Flow | Not Assigned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | Removed |  |  | 0 | (blank) | N/A | Q3 - 2026 - Removed. No longer assigned to Generation projects
C8P2-10 | QC8RAS-02 SPS (Deliverability Triggered RNU) | QC8SPS-02 SPS to modify the existing Hatchet Ridge SPS to trip Q1106 200 MW wind and Hatchet Ridge 102 MW wind for thermal overloads on the Q1106 SS-Cottonwood, Carberry SS-Round Mountain or Pit #3-Carberry SS 230 kV Lines. | PG&E | C8 | Deliverability | RAS (Deliverability) | Not Assigned | 2017 |  | 2029-05-24 | 2023-07-28 | 2023-07-28 | 2023-07-28 | TBD | 2027-03-31 | 2028-12-07 | 2028-12-07 | 2028-12-07 | 2028-12-07 | 2025-10-10 | 2027-03-18 | 2029-12-19 | 2029-12-19 | Removed | 0 | (blank) | N/A | Q3 - 2026 - Queue project that required this upgrade has withdrawn
C9P2-F17 | Panoche 115 kV circuit breakers 152 overstress | Replace Panoche 115 kV circuit breaker 152 and associated switches/relays | PG&E | C9 | Reliability | SCD overstress | Not Assigned |  |  | 2026-10-26 | [8 empty] | 2028-01-20 |  | TBD | Removed |  | 2028-02-22 | 0 | (blank) | N/A | Q3 - 2026 - Removed. Upgrade came back as C14P2-FPN06 132 & 152 overstress mitigation
C12P1-GCR01 | Moraga: Repl OCBs 612 & 622 | Replace Moraga 115 kV circuit breakers 612, 622 | PG&E | C12 | Reliability | SCD overstress | Not Assigned | 2022 |  | 2023-09-19 | 2026-10-01 | 2027-01-01 | 2028-11-23 | 2029-10-10 | 2028-11-23 | 2028-11-23 | 2028-11-23 | 2028-11-23 | 2024-02-18 | 2026-12-03 | 2032-02-04 | 2024-02-18 | 2024-02-18 | 2024-02-18 | 0 | (blank) | N/A | Q3 - 2026 - Dependent Queue project withdrawn. No longer assigned
C12P1-GCR01 | Moraga: EM REPL CB 642 & 712 | Replace Moraga 115 kV circuit breakers 642 and 712 | PG&E | C12 | Reliability | SCD overstress | Not Assigned | 2022 |  | 2025-11-03 | [8 empty] | 2026-04-09 |  | 2032-02-04 | 2026-05-15 | 2026-05-29 | 2026-02-22 | 0 | (blank) | (blank) | Q3 - 2026 - Dependent Queue project withdrawn. No longer assigned
20rsmt-3 | Midway 230 kV Bus Section E overload mitigation | Replace limiting conductor and/or fittings on Bus Section E to achieve 3372 A min. rating | PG&E | RA-20 | Reliability | Bus Flow | In-Service | 2021 |  |  | 2022-09-30 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 370 | (blank) | (blank) | Q3 - 2026 - In-Service
20rsmt-5 | Tesla 500 kV circuit breaker 612 overstress | Replace Tesla Substation 500 kV CB 612 and associated switches/relays | PG&E | RA-20 | Reliability | SCD overstress | In-Service | 2020 |  | 2025-10-23 | 2024-03-01 | 2024-05-28 | 2024-07-05 | 2024-08-08 | 2024-08-15 | 2024-10-28 | 2025-06-30 | 2025-02-18 | 2026-03-30 | 2025-10-31 | 2026-06-08 | 2026-06-11 | 2026-06-11 | 2026-03-31 | 810 | (blank) | (blank) | Q3 - 2026 - In-Service
20rsmt-7a | Tesla 500 kV circuit breaker 632 overstress | Replace Tesla 500 kV circuit breaker 632 with 63 kA interrupting capability | PG&E | RA-20 | Reliability | SCD overstress | In-Service | 2021 |  |  | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 1260 | (blank) | (blank) | Q3 - 2026 - In-Service
20rsmt-7b | Tesla 500 kV circuit breakers 542 and 642 overstress | Replace Tesla 500 kV circuit breakers 542 and 642 with 63 kA interrupting capability | PG&E | RA-20 | Reliability | SCD overstress | In-Service | 2020 |  | 2024-09-16 | 2024-07-31 | 2023-09-20 | 2024-04-12 | 2024-07-05 | 2024-07-12 | 2024-09-24 | 2024-11-20 | 2024-05-03 | 2025-06-30 | 2025-08-05 | 2025-03-31 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 4830 | (blank) | (blank) | Q3 - 2026 - In-Service
21rsmt-3 | Kern PP Substation 115 kV CB overstress (BAAH Conversion Phase 1 - CB282) | Kern PP Sub: Existing PG&E 115 kV BAAH conversion project will cover this replacement. | PG&E | RA-21 | Reliability | SCD overstress | In-Service | 2021 |  | 2021-07-09 | 2026-02-28 | 2023-12-05 | 2023-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-03-01 | 2024-11-08 | 2025-03-31 | 2025-03-31 | 2025-01-09 | 2025-01-09 | 2025-01-09 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
21rsmt-4 | Monta Vista 115 kV circuit breaker 1322 overstress | Replace Monta Vista 115 kV circuit breaker 1322 | PG&E | RA-21 | TPP | SCD overstress | In-Service | 2021 |  |  | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 1550 | (blank) | (blank) | Q3 - 2026 - In-Service
C11P2-FC01 | Midway 500kV CB's 722 Overstress | Midway Sub: Replace 500kV CB's 722, SW's and Relays | PG&E | C11 | Reliability | SCD overstress | In-Service | 2021 |  |  | 2025-12-31 | 2025-12-31 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 1300.1 | (blank) | N/A | Q3 - 2026 - In-Service
C11P2-FP01 | Midway 500 kV circuit breakers 732, 752, 802, 812, 832, 842 & 852 overstress | Replace Midway 500 kV circuit breakers 732, 802, 832 and 842 and associated switches/relays | PG&E | C11 | Reliability | SCD overstress | In-Service | 2021 |  |  | 2022-09-30 | 2025-12-31 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 1300.1 | (blank) | (blank) | Q3 - 2026 - In-Service
C11P2-GP01 | Moraga-Castro Valley 230 kV Line Capacity Increase Project | The project scope of work involves upgrading the limiting substation equipment (jumper conductors and wave traps) on the Moraga-Castro Valley and Castro Valley-Newark 230 kV lines to utilize their full conductor ratings. | PG&E | C11 | Deliverability | Re-conductor | In-Service | 2011 |  | 2024-08-20 | 2023-09-22 | 2023-11-06 | 2024-03-07 | 2024-03-20 | 2024-06-20 | 2024-10-25 | 2024-10-16 | 2026-03-25 | 2026-03-25 | 2024-11-24 | 2025-05-05 | 2025-04-07 | 2025-04-07 | 2025-04-07 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
C11P2-NC01 | Tesla Substation 230 kV bus section C-D and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS C - D | Increase Tesla Substation 230 kV series bus reactors between bus section C and D and D and E | PG&E | C11 | Reliability | SCD overstress | In-Service | 2019 |  | 2023-06-15 | 2023-10-31 | 2023-10-27 | 2023-09-28 | 2023-11-29 | 2023-12-19 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-04-18 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 1012.3 | (blank) | (blank) | Q3 - 2026 - In-Service
C11P2-NC01 | Tesla Substation 230 kV bus section D-E and circuit breakers 372, 382 and 842 overstress (reactors) TESLA: 230KV BUS REACTORS D - E | Increase Tesla Substation 230 kV series bus reactors between bus section C and D and D and E | PG&E | C11 | TPP-Approved | SCD overstress | In-Service | 2019 |  | 2022-04-19 | 2023-10-31 | 2023-04-05 | 2023-03-28 | 2023-05-01 | 2023-06-13 | 2023-07-27 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2024-03-25 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 1012.3 | (blank) | (blank) | Q3 - 2026 - In-Service
C11P2-ND03 | North Dublin-Cayetano 230 kV Line | Reconductor North Dublin-Cayetano 230 kV Line 2.63 miles OH Line & 2.82 UG cable with new UG cable 797 MVA/2000 A | PG&E | C11 | Deliverability | Re-conductor | In-Service | 2021 |  | 2025-08-04 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-03-25 | 2025-03-25 | 2025-02-10 | 2025-03-24 | 2025-03-25 | 2025-01-20 | 2025-03-20 | 2026-05-01 | 2026-05-13 | 2026-03-26 | 2026-03-31 | 0 | Clearances | Utility | Q3 - 2026 - No change
C12P1-GPT01 | Ames Distribution 115 kV circuit breaker 132 overstress | Replace Ames Distribution 115 kV circuit breaker 132 | PG&E | C12 | Reliability | SCD overstress | In-Service | 2019 |  | 2025-03-18 | 2024-03-31 | 2024-06-14 | 2024-08-22 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2028-03-24 | 2028-03-24 | 2030-08-08 | 2026-03-23 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 600 | (blank) | (blank) | Q3 - 2026 - In-Service
C12P1-NPT01 | Gold Hill Substation 115 kV circuit breakers 142 overstress | Replace Gold Hill Substation 115 kV circuit breakers 142 and associated switches/relays | PG&E | C12 | Reliability | SCD overstress | In-Service | 2021 |  | 2024-03-27 | 2023-09-30 | 2024-01-04 | 2023-11-13 | 2025-07-02 | 2025-08-28 | 2025-01-28 | 2025-01-01 | 2025-01-01 | 2024-11-21 | 2024-12-31 | 2024-11-27 | 2025-11-14 | 2025-12-06 | 2025-12-06 | 49.9 | (blank) | (blank) | Q3 - 2026 - In-Service
C12P1-NPT01 | Gold Hill Substation 115 kV circuit breakers 172 overstress with Bank 5 | Replace Gold Hill Substation 115 kV circuit breakers 172 and associated switches/relays | PG&E | C12 | Reliability | SCD overstress | In-Service | 2021 |  | 2024-03-01 | 2023-09-30 | 2024-01-04 | 2023-11-13 | 2025-07-02 | 2025-08-28 | 2025-01-28 | 2025-01-01 | 2025-01-01 | 2024-11-21 | 2024-12-31 | 2024-11-27 | 2026-05-29 | 2026-05-29 | 2026-04-30 | 49.9 | (blank) | (blank) | Q3 - 2026 - In-Service
C12P1-NPT04 | Vaca Dixon Substation 230 kV circuit breakers 442 overstress | Replace Vaca Dixon Substation 230 kV circuit breakers 442, 452 and 462 and associated switches/relays | PG&E | C12 | Reliability | SCD overstress | In-Service | 2021 |  | 2026-03-28 | 2024-03-31 | 2024-06-27 | 2024-12-02 | 2025-03-06 | 2025-05-20 | 2025-08-14 | 2025-10-16 | 2025-10-16 | 2027-06-09 | 2026-11-05 | 2027-05-28 | 2026-04-10 | 2026-06-04 | 2026-06-25 | 850 | (blank) | (blank) | Q3 - 2026 - In-Service
C12P2-GRNU2 | Gates Substation 230 kV Bus Overstress (Reactors on Bus E and F) | Install series bus reactors between Gates Substation 230 kV bus sections E and F | PG&E | C12 | Reliability | SCD overstress | In-Service | 2022 |  |  | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2024-05-31 |  | 2026-04-30 | 2026-04-27 | 2026-04-10 | 2025-12-31 | 2025-12-11 | 2025-12-11 | 3200.01 | (blank) | (blank) | Q3 - 2026 - In-Service
C12P2-GRNU3 | Midway Substation 500 kV CB 712 overstress | Replace Midway Substation 500 kV CB 712 with 63 kA interrupting capability | PG&E | C12 | Reliability | SCD overstress | In-Service | 2021 |  |  | 2025-12-31 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 1000 | (blank) | N/A | Q3 - 2026 - In-Service
C12P2-KC01 | Midway Substation 500kV CB 722 Overload mitigation | Replace Midway 500 kV CB 722 to achieve 3600 A emergency rating | PG&E | C12 | Reliability | Bus Flow | In-Service | 2021 |  |  | 2025-12-31 | 2025-12-31 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 1125.1 | (blank) | N/A | Q3 - 2026 - In-Service
C12P2-PNU-02 | Gates 230 kV circuit breakers 352, 362 and 372 overstress mitigation (Cap Banks) | Replace Gates 230 kV circuit breakers 352, 362 and 372 with 63 kA interrupting capability | PG&E | C12 | Reliability | SCD overstress | In-Service | 2022 |  | 2022-10-24 | 2023-04-30 | 2023-03-31 | 2023-03-31 | 2023-04-06 | 2023-04-06 | 2023-05-23 | 2023-07-14 | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-12 | 1836.4 | (blank) | (blank) | Q3 - 2026 - In-Service
C13P1-FPT02 | Warnerville-Bellota 230 kV line reconductoring | The project proposes to reinforce 45 circuit miles of the 230 kV transmission lines between Bellota, Cottle, and Warnerville substations with 1113 kcmil steel-supported aluminum conductors with emergency capability of 1890 Amps. The project includes the installation of a new Optical Ground Wire (OPGW) that will replace the existing aging third-party owned OPGW. The project will upgrade the Bellota, Cottle, and Warnerville terminals and upgrade the line fault protection to current safety standards. The project includes replacing a manual bypass switch and installing an additional shield wire. Key construction elements are as follows: • Replace 148 steel electric transmission lattice towers with 148 new tubular steel poles (TSP’s) • Replace 1 manual bypass switch • Replace 22.5 miles of the Bellota-Warnerville 230 kV circuit • Replace 19.9 miles of the Bellota-Cottle 230 kV circuit • Replace 2.5 miles of the Cottle-Melones 230 kV circuit • Replace 0.1 mile of the Warnerville-Wilson 230 kV circuit • Replace 22.5 miles of OPGW with new OPGW • Install 22.5 miles of shield wire • Upgrade transmission line terminals at Bellota, Cottle, and Warnerville substations | PG&E | C13 | Deliverability | Re-conductor | In-Service | 2013 | 2019-12-31 | 2023-10-23 | 2024-12-27 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-05-31 | 2024-04-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 435 | (blank) | (blank) | Q3 - 2026 - In-Service
C13P1-GPN04 | Metcalf Substation 230 kV capacitor circuit breakers Interim Solution | Metcalf Substation 230 kV capacitor circuit breakers Interim Solution | PG&E | C13 | Reliability | SCD overstress | In-Service | 2018 |  | 2022-10-10 | 2025-05-31 | 2022-09-28 | 2022-12-01 | 2022-12-07 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 500 | (blank) | (blank) | Q3 - 2026 - In-Service
C13P2-GGR01 | Tesla 500 kV circuit breakers 622 overstress | Replace Tesla 500 kV circuit breaker 622 with 63 kA interrupting capability. Only went to 50 kA | PG&E | C13 | Reliability | SCD overstress | In-Service | 2021 | [7 empty] | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 400 | (blank) | (blank) | Q3 - 2026 - In-Service
C13P2-SGR01 | Midway Substation 500 kV switches 721 & 723 overload. | Replace Midway 500 kV Switch 721 & 723 to achieve 4000 A normal rating | PG&E | C13 | Reliability | Bus Flow | In-Service | 2022 |  | 2024-10-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 1550.01 | (blank) | (blank) | Q3 - 2026 - In-Service
C13P2-SPN01 | Midway Substation 500 kV Control Building | Existing PG&E project to replace the 500 kV Control Building at Midway (Needed for Midway RAS) | PG&E | C13 | Reliability | RAS (Reliability) | In-Service | 2024 |  | 2022-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-03-15 | 1850 | (blank) | (blank) | Q3 - 2026 - In-Service
C14P1-KGR11 | Midway 500 kV CB 742, 912, 942 Overstress: Rerate Midway 500 kV CB 742, 822, 912, 942 | Rerate Midway 500 kV CB 742, 822, 912, 942 | PG&E | C14 | Reliability | SCD overstress | In-Service | 2024 |  | 2025-07-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | 2031-03-31 | 2025-10-09 | 2025-10-09 | 1500 | (blank) | (blank) | Q3 - 2026 - In-Service
C14P2-FGR04 | Los Banos 500 kV circuit breakers 822, 832 overstress | Replace Los Banos 500 kV circuit breakers 822, 832 & 842 | PG&E | C14 | Reliability | SCD overstress | In-Service | 2024 |  | 2025-10-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 2030-03-31 | 2027-03-31 | 2026-09-01 | 2026-05-09 | 2600 | (blank) | (blank) | Q3 - 2026 - In-Service (breakers were uprated)
C14P2-NPT04 | Vierra 115 kV Looping Project | Loop the Tesla-Stockton Co-Gen Junction 115kV Line into Vierra Substation, convert the Vierra 115kV bus into a 4-bay breaker-and-a-half (BAAH) bus configuration, add a Howland Road Co-Gen Radial Feed, install a 115kV Sustainable Modular Protection (SMP) / Modular Protection Automation and Controls (MPAC), and install battery buildings. | PG&E | C14 | Capacity | New Station | In-Service | 2011 |  | 2025-06-02 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | 2026-05-29 | 2026-07-31 | 2027-05-06 | 2027-05-06 | 2027-05-04 | 2027-05-04 | 2026-04-30 | 2026-05-20 | 550 | (blank) | (blank) | Q3 - 2026 - In-Service
C8P1-34 | Re-conductor Padre Flat SS-Panoche #1 230 kV Line | Re-conductor 32.59 mi Q779/Padre Flat SS-Panoche #1 230 kV Line with 795 ACSS | PG&E | C8 | Deliverability | Re-conductor | In-Service | 2017 | 2023-02-10 | 2023-09-21 | 2024-05-31 | 2024-05-21 | 2024-05-20 | 2024-05-20 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-09 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
C8P1-35 | Re-conductor Los Banos-Quinto SS 230 kV Line | Re-conductor 6.11 mi Quinto Sw Sta-Los Banos 230 kV Line with super bundled 795 ACSS | PG&E | C8 | Deliverability | Re-conductor | In-Service | 2017 |  | 2022-03-03 | 2022-05-31 | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-04-28 | 2023-05-10 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 0 | Bundling Dependencies | Utility | Q3 - 2026 - In-Service
C8P2-3 | QC8RAS-08 RAS (Deliverability Triggered RNU) | QC8RAS-08 RAS to trip Generation offline for outage AND overload of either Gates 500/230 kV Transformer Bank 11 or 12 | PG&E | C8 | Deliverability | RAS (Deliverability) | In-Service | 2017 |  |  | 2023-01-12 | 2023-01-12 | 2023-12-31 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-09-30 | 2024-10-16 | 2024-10-16 | 2024-10-16 | 2024-10-16 | 2345 | (blank) | (blank) | Q3 - 2026 - In-Service
C8P2-6 | Re-conductor Los Banos-Q779 SS #1 230 kV Line | Re-conductor 4.5 mi Los Banos-Padre Flat SS #1 230 kV Line with 1113 ACSS and upgrade equipment to 1900 A. | PG&E | C8 | Deliverability | Re-conductor | In-Service | 2017 |  | 2022-10-10 | 2023-03-01 | 2023-02-28 | 2023-02-28 | 2022-12-14 | 2022-12-24 | 2022-12-24 | 2022-12-24 | 2022-12-24 | 2022-12-24 | 2022-12-24 | 2022-12-24 | 2022-12-24 | 2022-12-24 | 2022-12-24 | 35 | (blank) | (blank) | Q3 - 2026 - In-Service
C9P1-F11 | Re-conductor Dos Amigos PP-Panoche #3 230 kV Line | Re-conductor 23.63 mi Dos Amigos PP-Panoche #3 230 kV Line with 795 ACSS | PG&E | C9 | Deliverability | Re-conductor | In-Service | 2017 |  | 2025-02-18 | 2025-05-14 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-05-01 | 2026-05-01 | 2026-05-15 | 2026-05-15 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-04-15 | 1020 | (blank) | (blank) | Q3 - 2026 - In-Service
C9P2-F13-F15 | Gates 230kV Bus Section E and CB 312, 322, 2102, 2202 overload mitigation (BAAH) | Gates Substation 230 kV circuit breakers 312, 322, 2102, 2202 overload – convert bus section E to BAAH and move Panoche-Gates #1 and #2 230 kV lines and Q1117/Q1120/Q1139/Q1242/Q1243 into bus section E | PG&E | C9 | Reliability | Bus Flow | In-Service | 2019 |  | 2021-08-06 | 2023-03-31 | 2023-03-14 | 2023-05-31 | 2023-03-14 | 2023-05-23 | 2023-05-31 | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2041.3 | (blank) | (blank) | Q3 - 2026 - In-Service
C9P2-N09 | Re-conductor Stockton A-Weber #3 60 kV Line (Stockton A-Hazelton Jct) | Re-conductor 0.9 mi of Stockton A-Weber #3 60 kV Line from Stockton A to Hazelton Jct Pole 000/026 with 715 AAC. | PG&E | C9 | Reliability | Re-conductor | In-Service | 2018 |  | 2022-01-14 | 2022-03-31 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
POS-Q1553-NU2 | Metcalf 230kV MPAC Installation | PG&E Project: 230kV MPAC Installation | PG&E | C12 | Reliability | RAS (Reliability) | In-Service |  |  | 2021-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2024-02-17 | 350 | (blank) | (blank) | Q3 - 2026 - In-Service
21rsmt-SCD-23 | El Cerrito G 115kV CB 112, 142, 132 Overstress | Replace Overstressed Circuit Breakers | PG&E | RA-21 | Reliability | SCD overstress | Not Assigned | 2011 |  | 2024-01-12 | N/A | 2024-07-18 | 2024-07-17 | 2025-11-14 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-05-01 | 2025-05-01 | 2025-05-07 | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
22rsmt-3 | Metcalf 230 kV Substation Circuit Breaker #No 292 Upgrade | Upgrade Metcalf Circuit Breaker #292 due to overstress issues | PG&E | RA-22 | TPP-Approved | SCD overstress | Not Assigned | 2022 |  |  |  | 2025-01-01 | 2025-12-01 | 2022-09-27 | 2022-09-27 | 2022-09-27 | 2022-09-27 | 2022-09-27 |  | 2022-09-29 | 2022-09-29 | 2022-09-29 | 2022-09-29 | 2022-09-29 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
C11P2-NP01 | Contra Costa 230kV SW's 601, 603 overload. Replaced by Line relocation project | Contra Costa PP: Replace 230kV SW's 601 & 603 and jumpers. | PG&E | C11 | Reliability | Bus Flow | Replaced | 2021 |  | 2024-09-30 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-05-02 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-22 | 2025-09-09 | 2026-01-21 | 2026-02-27 | 2026-02-24 | 0 | (blank) | N/A | Q3 - 2026 - In-Service
C11P2-NP02 | Contra Costa 230kV Bus Sections D, E and F and circuit breaker 820 overload. Replaced by Line relocation project | Contra Costa PP: Reconductor Bus Sections D, E and F. Replace circuit breaker 820. | PG&E | C11 | Reliability | Bus Flow | Replaced | 2021 |  | 2024-09-30 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-05-02 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-22 | 2025-09-09 | 2026-01-21 | 2026-02-27 | 2026-02-24 | 480 | (blank) | N/A | Q3 - 2026 - In-Service
C11P2-NP02 | Contra Costa PP 230 kV Line Terminals Reconfiguration Project (C11P2-NP02, C11P2-NP01) | Swap the Lone Tree line and Birds Landing Sw Sta. line between Sec 2D and Sec 2E and Move the Wind Master (Delta) line to section 2E. Replaces the need for: Contra Costa 230kV Bus Sections D, E and F and circuit breaker 820 overload Contra Costa 230kV SW's 601, 603 overload | PG&E | C11 | Reliability | Bus Flow | Replaced | 2022 |  | 2024-09-30 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-22 | 2025-09-09 | 2026-01-21 | 2026-02-27 | 2026-02-24 | 480 | (blank) | (blank) | Q3 - 2026 - In-Service
C12P1-NPN02 | Lodi Substation 60 kV circuit breakers 12 and 22 overstress | (blank) | PG&E | C12 | TPP | SCD overstress | Not Assigned | 2011 |  | 2020-08-04 | 2022-03-28 | 2022-12-29 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
C12P1-NPT03 | Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | Replace Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 and associated switches/relays | PG&E | C12 | Reliability | SCD overstress | Not Assigned | 2020 |  | 2021-06-01 | 2024-12-31 | 2024-12-31 | 2023-11-10 | 2024-05-01 | 2024-12-31 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-30 | 2025-05-21 | 2025-05-21 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
C12P2-GRNU1 | Cooley Landing 60 kV Substation Circuit Breaker No #62 Upgrade: aka Cooley Landing 60 kV circuit breaker 62 overstress mitigation | Cooley Landing 60 kV circuit breaker 62 overstress mitigation: Replace Cooley Landing 60 kV circuit breaker 62 with 40 kA interrupting capability | PG&E | C12 | Capacity | Breakers | Not Assigned | 2022 |  | 2025-03-21 | N/A | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
C8P2-15 | Cottonwood Substation 230 kV Circuit Breaker 542 Overstress | Cottonwood Substation 230 kV CB Overstress: Replace CB 522 & 542 (rated @ 34.5KA, overstress close-in fault is 35,179A or 2%, 679A). | PG&E | C8 | Reliability | SCD overstress | Not Assigned | 2018 |  | 2025-06-09 | 2023-07-28 | 2023-08-15 | 2023-08-15 | 2024-09-30 | 2024-09-30 | 2024-09-04 | 2025-12-31 | 2025-12-01 | 2025-02-17 | 2025-12-31 | 2025-12-31 | 2026-02-25 | 2025-07-15 | 2025-07-15 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service
C8P2-15 | Cottonwood Substation 230 kV Circuit Breaker 522 Overstress | Cottonwood Substation 230 kV CB Overstress: Replace CB 522 & 542 (rated @ 34.5KA, overstress close-in fault is 35,179A or 2%, 679A). | PG&E | C8 | Reliability | SCD overstress | Not Assigned | 2018 |  | 2025-06-09 | 2023-07-28 | 2023-08-15 | 2023-08-15 | 2024-09-30 | 2024-09-30 | 2024-09-04 | 2025-12-31 | 2025-12-01 | 2025-02-17 | 2025-12-31 | 2025-12-31 | 2026-02-25 | 2025-07-15 | 2025-11-13 | 0 | (blank) | (blank) | Q3 - 2026 - In-Service. Correcting the operative date from July to November 2025.
C14P2-GGR12 | Pittsburg 230 kV bus overstress. Bus D-E 230kV Buss Reactors | Install bus reactors between 230 kV sections D & E | PG&E | C14 | Reliability | SCD overstress | On-Hold | 2024 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | 2030-04-11 | 2030-04-11 | 2030-04-11 | 2300 | (blank) | N/A | Q3 - 2026 - PG&E is evaluating alternatives to this mitigation before project initiation. New In-service date To be determined.
20rsmt-4 | Metcalf 115kV breakers Overstress (almost all breakers), install bus reactors on 230kV banks due to existing space constraints on the 115kV Bus | Install 4-3 ohm reactors at low side of Metcalf 115 kV 230kV Transformers | PG&E | RA-20 | Reliability | SCD overstress | In-Flight | 2020 |  | 2028-02-02 | 2025-02-28 | 2025-08-22 | 2025-09-03 | 2025-11-04 | 2026-01-29 | 2026-02-05 | 2026-07-10 | 2027-04-09 | 2027-03-04 | 2029-12-31 | 2027-04-19 | 2027-10-05 | 2027-02-26 | 2028-07-11 | 1320 | Financing | Utility | Q3 - 2026 - Engineering was paused to determine if project was still needed but has since resumed. Scope of project was breaker replacements and was rervised to installing reactors only. Long Lead times still a critical path
20rsmt-6 | 20RSMTRAS-02 (Reliability) to open Bitterwater Sw Sta-Wheeler Ridge #2 230 kV Line for loss of Midway-Bitterwater 230 kV line and overload on the Midway-Wheeler Ridge #1 230 kV line. | 20RSMTRAS-02 RAS to open Bitterwater Sw Sta-Wheeler Ridge #2 230 kV Line for loss of Midway-Bitterwater 230 kV line and overload on the Midway-Wheeler Ridge #1 230 kV line. | PG&E | RA-20 | Reliability | RAS (Reliability) | In-Flight | 2020 |  | 2027-12-02 | 2023-12-31 | 2023-12-29 | 2023-12-29 | 2023-10-31 | 2023-12-31 | 2024-11-14 | 2024-11-14 | 2025-05-08 | 2025-07-03 | 2026-07-02 | 2027-07-13 | 2027-07-13 | 2027-07-13 | 2028-02-24 | 100 | Bundling Dependencies | Utility | Q3 - 2026 - Remaining install scope to install relay in new 230kV MPAC building and transfer existing connection from Old Bldg to new 230kV MPAC. Construction tentatively planned for Q4 2027 start, with ISD in Q1 2028.
21rsmt-3 | Kern PP Substation 115 kV CB overstress (BAAH Conversion Phase 3 - CB262) | Kern PP Sub: Existing PG&E 115 kV BAAH conversion project will cover this replacement. | PG&E | RA-21 | Reliability | SCD overstress | In-Flight | 2021 |  | 2026-04-27 | 2026-02-28 | 2024-10-16 | 2024-10-16 | 2026-12-07 | 2026-12-07 | 2026-12-07 | 2026-12-07 | 2026-12-01 | 2026-12-04 | 2025-03-31 | 2026-12-31 | 2027-04-30 | 2027-04-30 | 2027-03-26 | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered by andAcrive Generation Project. Minor In-Service Date changes.
21rsmt-3 | Kern PP Substation 115 kV CB overstress (BAAH Conversion Phase 4 - CB182) | Kern PP Sub: Existing PG&E 115 kV BAAH conversion project will cover this replacement. | PG&E | RA-21 | Reliability | SCD overstress | In-Flight | 2021 |  | 2027-07-09 | 2026-02-28 | 2023-02-01 | 2023-04-11 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2028-02-01 | 2027-12-13 | 2025-03-31 | 2026-02-28 | 2028-03-03 | 2028-03-03 | 2028-04-28 | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered by andAcrive Generation Project. Minor In-Service Date changes.
22rsmt-1 | Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project | Replace 115 kV circuit breakers 132, 152, 102 and 162, install a new MPAC building for the 115 kV bus section, convert 230 kV Bus Section D to BAAH and replace overstressed breakers in Bus E to 63 kA at Panoche substation - CB102 Added to the is project | PG&E | RA-22 | Capacity | Bus Upgrade | In-Flight | 2023 |  | 2026-10-26 | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-28 | 2028-06-01 | 2028-06-01 | 2028-03-31 | 2028-04-26 | 2028-06-01 | 2028-02-28 | 125 | Clearances | Utility | Q3 - 2026 - Minor In-Service Date changes to align with overall project.
22rsmt-4 | New 230 kV switching station to loop Dos Amigos – Panoche # 3 230 kV | Build a new 2 bay 230 kV BAAH switching station to loop in the Dos Amigos – Panoche # 3 230 kV Line requiring access road, land and land rights acquisition and permitting, remote end protection upgrades, and OPGW/fiber telecommunication work | PG&E | RA-22 | Deliverability | New Station | In-Flight | 2022 | 2028-02-15 | 2030-03-28 | N/A | N/A | N/A | 2028-12-31 | 2028-12-31 | 2028-12-31 | 2028-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2030-03-04 | 2030-04-05 | 2030-04-05 | 2030-05-15 | 1095 | Land Rights | Utility | Q3 - 2026 - Project evaluated feasibility designs for three different Switching Station parcels. Land Acquisition process initiating. Minor In-Service date changes.
24RSMT-GPN01 | Tesla 230 kV & 500 kV Bus Overstress mitigation | Tesla 230 kV & 500 kV Bus Overstress mitigation: Extend 230 kV and 500 kV buses into new sections, add one (1) 500/230 kV XFMR and new control buildings. Design for future SCD Mitigation and additional elements. | PG&E | RA-24 | Reliability | SCD overstress | In-Flight | 2024 |  | 2029-04-24 | [8 empty] | 2031-04-10 |  | N/A | 2031-10-11 | 2031-04-18 | 2031-04-10 | 3950 | Project Design | Utility | Q3 - 2026 - Seismic impact to expansion area, evaluating options. In-Service date impacts are not conclusive.
24RSMT-NLD-01 | Reconductor Konocti-Eagle Rock 60 kV Line: 7.49 Miles Eagle Rock to ER T-4/23 | Reconductor Konocti-Eagle Rock 60 kV Line with 715.5-37 AAC and upgrade any limiting equipment | PG&E | RA-24 | Deliverability | Re-conductor | Not Triggered | 2025 | 2028-01-27 | 2029-10-29 | [8 empty] | 2030-05-31 |  |  | 2030-05-01 | 2030-05-31 | 2030-05-31 | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered
C11P2-KT01 | Wheeler Ridge Junction Substation | Construct and own the new Wheeler Ridge Junction project substation (to be named Casa Loma) including two new 230/115 kV transformers and three 230 kV line terminations. Upgrade existing Wheeler Ridge-Adobe Switching Station and Adobe Switching Station-Lamont 115 kV lines to 230 kV operations. Upgrade existing Kern-Tevis-Stockdale-Lamont and Kern-Tevis-Stockdale 115 kV lines to 230 kV. Rebuild existing idle line that connects Kern-Tevis-Stockdale to Magunden Substation. Reconductor Stockdale 230 kV tap #1 and #2 lines. | PG&E | C11 | Deliverability | New Station | In-Flight | 2014 |  | 2030-06-17 | N/A | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | 2034-03-28 | 2029-05-04 | 2033-12-31 | 2033-12-31 | 1933-07-11 | 2033-01-28 | 2034-05-19 | 2034-05-01 | 70 | ISO Action | Utility | Q3 - 2026 - No change
C11P2-ND01 | Re-conductor Fulton-Hopland 60 kV Line (Fitch Mountain Tap-Geysers Jct) (24 mile section) | Re-conductor Fulton-Hopland 60 kV Line (Fitch Mountain Tap 009/005A-Geysers Jct 016/004) ~7 mi total length with 715 AAC | PG&E | C11 | Deliverability | Re-conductor | In-Flight | 2018 | 2025-03-10 | 2025-10-20 | 2026-03-31 | 2027-12-31 | 2027-12-31 | 2025-11-03 | 2026-02-13 | 2026-05-25 | 2026-06-05 | 2026-04-02 | 2026-03-23 | 2027-02-02 | 2027-02-02 | 2027-02-01 | 2027-02-02 | 2027-03-31 | 230 | Clearances | Utility | Q3 - 2026 - Minor In-Service Date changes.
C11P2-NR01 | Cottonwood Substation 230 kV circuit breakers 242 overstress | Replace Cottonwood Substation 230 kV circuit breakers 222, 232, 242 and associated switches/relays | PG&E | C11 | Reliability | SCD overstress | Not Assigned | 2022 |  | 2027-03-09 | 2024-02-28 | 2024-04-02 | 2024-05-24 | 2025-08-28 | 2025-08-28 | 2025-03-07 | 2025-05-22 | 2027-01-25 | 2026-06-18 | 2027-08-25 | 2026-07-01 | 2026-12-31 | 2026-08-13 | 2026-12-24 | 0 | (blank) | (blank) | Q3 - 2026 - Slight In-Service date change.
C11P2-NR01 | Cottonwood Substation 230 kV circuit breakers 222, 232 overstress | Replace Cottonwood Substation 230 kV circuit breakers 222, 232, 242 and associated switches/relays | PG&E | C11 | Reliability | SCD overstress | Not Assigned | 2022 |  | 2028-04-03 | 2024-02-28 | 2024-04-02 | 2024-05-24 | 2025-08-28 | 2025-08-28 | 2025-03-07 | 2025-05-22 | 2027-01-25 | 2026-06-18 | 2027-08-25 | 2026-07-01 | 2026-12-31 | 2026-08-13 | 2029-04-10 | 0 | Financing | Utility | Q3 - 2026 - No longer assigned to an active Generation project. The breakers are sequenced with a larger project to Install new MPAC, Bank Replacements, and to replace CB 222, 232, 272, 292 at Cottonwood
C12P1-NPT04 | Vaca Dixon Substation 230 kV circuit breakers 452 overstress | Replace Vaca Dixon Substation 230 kV circuit breakers 442, 452 and 462 and associated switches/relays | PG&E | C12 | Reliability | SCD overstress | In-Flight | 2021 |  | 2026-11-13 | 2024-03-31 | 2024-06-27 | 2024-12-02 | 2025-03-06 | 2025-05-20 | 2025-08-14 | 2025-10-16 | 2025-10-16 | 2027-06-09 | 2026-11-05 | 2027-05-28 | 2026-11-06 | 2027-01-08 | 2027-01-08 | 850 | Bundling Dependencies | Utility | Q3 - 2026 - No change
C12P1-NPT04 | Vaca Dixon Substation 230 kV circuit breakers 462 overstress | Replace Vaca Dixon Substation 230 kV circuit breakers 442, 452 and 462 and associated switches/relays | PG&E | C12 | Reliability | SCD overstress | In-Flight | 2021 |  | 2026-06-26 | 2024-03-31 | 2024-06-27 | 2024-12-02 | 2025-03-06 | 2025-05-20 | 2025-08-14 | 2025-10-16 | 2025-10-16 | 2027-06-09 | 2026-11-05 | 2027-05-28 | 2026-07-24 | 2026-10-02 | 2026-10-02 | 850 | (blank) | N/A | Q3 - 2026 - No change
C12P2-LDNU1 | Ripon-Manteca 115 kV Line Reconductor | Reconductor Ripon-Manteca 115 kV line 1.51 mi section of 2/0 CU and 0.92 mi 4/0 ACSR (2.43 mi total) | PG&E | C12 | Deliverability | Re-conductor | In-Flight | 2021 | 2026-07-29 | 2026-10-13 | 2027-12-31 | 2027-12-16 | 2027-12-16 | 2027-12-16 | 2027-12-16 | 2028-09-11 | 2027-04-19 | 2027-05-10 | 2027-05-10 | 2027-10-31 | 2028-04-25 | 2028-07-26 | 2027-03-04 | 2027-06-03 | 99 | Bundling Dependencies | Utility | Q3 - 2026 - Construction Sequencing changes to In-Service Date
C12P2-LDNU2 | Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor (overlaps 2C project) | Reconductor Stanislaus-Melones Sw Sta-Manteca #1 115 kV line 25.23 miles section of various conductors from 018/115-043/277. This order completes Ckt1 from #030/195 to 043/277 12.67 miles | PG&E | C12 | Deliverability | Re-conductor | In-Flight | 2021 | 2027-02-12 | 2027-08-13 | 2027-12-31 | 2027-12-16 | 2027-12-16 | 2027-12-16 | 2027-12-16 | 2028-09-11 | 2028-02-29 | 2028-09-05 | 2028-09-05 | 2029-05-07 | 2029-06-04 | 2030-03-07 | 2028-03-31 | 2028-07-25 | 99 | Bundling Dependencies | Utility | Q3 - 2026 - Construction Sequencing changes to In-Service Date
C12P2-LDNU3 | Bellota-Riverbank-Melones Sw Sta 115 kV Line 115 kV Line Reconductor | Reconductor a total of 17 miles of Bellota-Riverbank-Melones SW STA 115 kV Line with 477 ACSS | PG&E | C12 | Deliverability | Re-conductor | In-Flight | 2021 | 2025-11-03 | 2026-04-14 | 2027-12-31 | 2027-12-16 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2028-09-11 | 2028-04-12 | 2028-08-18 | 2028-08-18 | 2028-11-08 | 2029-01-17 | 2027-08-26 | 2027-01-15 | 2027-02-16 | 99 | Bundling Dependencies | Utility | Q3 - 2026 - Slight In-Service date change.
C12P2-LDNU4 | Stanislaus-Melones SW STA-Riverbank Jct Sw Sta 115 kV Line Reconductor (STAN-MELONES TAP LINES: REPL CU COND P3 7.5 miles - double circuit), LDNU only needs 1 circuit | Reconductor Stanislaus-Melones Sw Sta-Riverbank Jct Sw Sta 115 kV Line 7.53 miles section of various conductors from 000/001-007/043 - scope taken over by the more comprehensive STAN-MELONES TAP LINES: REPL CU COND P3 project. | PG&E | C12 | Deliverability | Re-conductor | In-Flight | 2021 |  | 2026-05-01 | 2027-12-31 | 2027-12-16 | 2027-12-16 | 2027-12-16 | 2027-12-16 | 2028-09-11 | 2028-05-29 | 2028-06-08 | 2028-12-28 | 2028-07-21 | 2029-01-19 | 2028-08-02 | 2028-12-29 | 2028-12-28 | 99 | Bundling Dependencies | Utility | Q3 - 2026 - No change
C13P1-FLO01 | Helm-Crescent Sw Sta 70 kV Line Reconductor (4.7 miles rated ampacity 1400amp) | Reconductor a total of 4.77 miles of Helm-Crescent Sw Sta 70 kV Line with 1113 AAC and upgrade any limiting equipment to enable full conductor rating ~1400 A | PG&E | C13 | Deliverability | Re-conductor | In-Flight | 2024 | 2027-03-05 | 2027-10-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 2028-03-31 | 2027-10-12 | 2027-12-31 | 70 | Bundling Dependencies | Utility | Q3 - 2026 - Right of way acquisitions driving schedule delays. Currently at 60% design.
C13P1-FPT03 | Oro Loma 70 kV Area Reinforcement | The Oro Loma 70 kV Area Reinforcement project will reconductor 2.4 miles of the Los Banos - Livingston Jct – Canal 70 kV Line, from Los Banos sub to Santa Nella substation and 10.8 miles of the Mercy Springs SW STA – Canal – Oro Loma 70 kV Line, from Mercy Springs SW STA to Canal Substation. Transmission Planning is recommending a conductor that should be capable of handling at least 1126 Amps during summer normal and emergency conditions. Associated substation terminal equipment will be upgraded as needed to meet the ratings of the new line conductor. | PG&E | C13 | Capacity | Re-conductor | In-Flight | 2011 |  | 2028-02-04 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2028-08-28 | 2028-05-08 | 2028-06-02 | 2028-05-23 | 75 | Financing | Utility | Q3 - 2026 - Minor In-Service Date changes.
C13P1-FPT03b | MERCY SPRINGS SW STA_CONNECT 70KV LINE | MERCY SPRINGS SW STA_CONNECT 70KV LINE | PG&E | C13 | Capacity | Re-conductor | In-Flight | 2011 |  | 2030-05-09 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2028-08-28 | 2028-05-08 | 2028-06-02 | 2031-01-29 | 75 | Financing | Utility | Q3 - 2026 - This project depends on the completion of the new Dos-Amigos-Paoche Swithcing Station project before it can commence construction.
C13P1-GPN04 | Metcalf Substation 230 kV capacitor circuit breakers 654, 664, 674 and 684 overstress. | Replace Metcalf Substation 230 kV capacitor circuit breakers 654, 664, 674 and 684 | PG&E | C13 | Reliability | SCD overstress | In-Flight | 2018 |  | 2026-10-30 | 2025-05-31 | 2025-05-29 | 2025-05-21 | 2026-02-17 | 2025-05-13 | 2026-02-26 | 2025-09-23 | 2027-05-01 | 2029-05-30 | 2027-08-25 | 2028-01-28 | 2026-01-06 | 2026-12-21 | 2027-02-22 | 500 | Bundling Dependencies | Utility | Q3 - 2026 - Relies on the 230kV MPAC and cap bank breaker project to complete in order to move forward with this project's work.
C13P1-KGR01 | QC13P2RAS-04 Modify existing Midway 500/230 kV transformer overload SPS | Midway 500/230 kV transformer overload SPS to include transformer outage detection and transformer overload detection for Bank 11, 12, and 13 | PG&E | C13 | Reliability | RAS (Reliability) | In-Flight | 2024 |  | 2027-12-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-10-12 | 2030-10-12 | 2028-03-31 | 2029-02-28 | 2029-03-19 | 700 | Bundling Dependencies | Utility | Q3 - 2026 - Seeking necessary approvals for RAS from affected parties. Delays to approvals can delay the design process of this project.
C13P1-KGR05 | Midway Substation 230 kV bus and 27 circuit breakers overstress - Revsed to Install (2) Bus Reactors. Install 2 x 16 ohm series bus reactors between Midway Substation 230 kV bus sections D and E (16 ohm parallel/8 ohm net) | Install 2 x 16 ohm series bus reactors between Midway Substation 230 kV bus sections D and E (16 ohm parallel/8 ohm net) | PG&E | C13 | Reliability | SCD overstress | In-Flight | 2024 |  | 2029-12-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-10-12 | 2030-10-12 | 2031-03-31 | 2031-03-31 | 2031-03-31 | 1800 | (blank) | N/A | Q3 - 2026 - Coordinating project scope, including cluster study and equipment requirement details for project kickoff.
C13P1-KPN02 | Midway 230 kV Bus D BAAH Conversion: (Needed to install reactors between Bus Sections D & E) | Convert Midway Substation 230 kV to BAAH in order to install bus reactors & RAS | PG&E | C13 | Reliability | SCD overstress | In-Flight | 2016 |  | 2027-04-09 | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-05-08 | 2027-12-27 | 2030-02-28 | 2028-01-21 | 2030-08-22 | 2027-11-04 | 2027-11-04 | 2027-11-17 | 1900 | Bundling Dependencies | Utility | Q3 - 2026 - No change. Tracking to Phase 5 when breaker installs are complete. Tline re-arrangement dates follow.
C13P1-KPN03 | Midway 230 kV Bus D BAAH Conversion: (Needed for Midway 500/230 kV Transformer overload RAS) | Midway 230 kV Bus D BAAH Conversion: Convert Midway Substation 230 kV to BAAH needed for Midway 500/230 kV Transformer overload RAS | PG&E | C13 | Reliability | SCD overstress | In-Flight | 2025 |  | 2027-12-22 | [8 empty] | 2029-02-06 |  |  | 2030-02-01 | 2029-02-07 | 2029-02-07 | 300 | Bundling Dependencies | Utility | Q3 - 2026 - No change
C14P1-GGR07 | Newark 230 kV cap bank circuit breakers 974 & 984 overstress | (blank) | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2025 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-03-31 | 2028-04-12 | 1430 | (blank) | N/A | Q3 - 2026 - Schedule in early development. Project entering scoping and early design.
C14P1-GGR07 | NEWARK: REPL CAP BREAKER 994 EMER | (blank) | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2025 |  | 2021-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-03-31 | 2028-04-12 | 1430 | (blank) | N/A | Q3 - 2026 - This project is being coordination along side and SVP MPAC building project. Schedule in early development. Project entering scoping and early design.
C14P1-GGR09 | Tesla 230 kV Bus Overstress (2 CB with Line relocations) | Relocate a Tesla - Tracy #2 230kV line to Bus Sect. C - into BAAH bay position where Newark #2 line resides today. Newark #2 will shift to a new BAAH bay. Includes costs for (9) 230kV T-Line structures (4,000 feet of new line), BAAH bay w/2 CB's. | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2024 |  | 2029-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | 2031-04-11 | 2031-04-18 | 2031-04-10 | 3950 | Project Design | Utility | Q3 - 2026 - Seismic impact to expansion area, evaluating options. In-Service date impacts are not conclusive.
C14P1-NGR02 | Cottonwood 230 kV circuit breaker 272 & 292 overstress | Replace Cottonwood 230 kV circuit breaker 272 & 292 | PG&E | C14 | Reliability | SCD overstress | Not Assigned | 2025 |  | 2028-04-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD |  | 2029-03-14 | 2029-08-10 | 2029-04-10 | 0 | (blank) | N/A | Q3 - 2026 - Queue project that required this upgrade has withdrawn
C14P2-FGR04 | Los Banos 500 kV circuit breakers 842 overstress | Replace Los Banos 500 kV circuit breakers 822, 832 & 842 | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2024 |  | 2027-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 2030-03-31 | 2027-03-31 | 2026-09-01 | 2027-09-21 | 2600 | (blank) | N/A | Q3 - 2026 - CB has already been ordered and is on track to issue for construction this year.
C14P2-FPN03 | Los Banos 230 kV circuit breakers 212 & 222 overstress | Replace Los Banos 230 kV circuit breakers 212 & 222 | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2023 |  | 2027-09-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-04-01 | 2028-04-01 | 2027-08-06 | 2027-09-30 | 2028-12-28 | 1900 | (blank) | N/A | Q3 - 2026 - This CB uprate project is bundled with a larger Los Banos project to replace multiple breakers.
C14P2-FPN06 | Panoche 115 kV circuit breakers 152 overstress | Replace Panoche 115 kV circuit breakers 152 and associated switches | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2022 |  | 2026-10-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-03-31 | 2028-04-26 | 2028-05-01 | 2028-02-28 | 125 | Clearances | Utility | Q3 - 2026 - Minor In-Service Date changes to align with overall project.
C14P2-FPN07 | Panoche 230 kV bus overstress above 40 kA design and circuit breakers 212, 232, 242 ,252, 262, 272, 282, 292, 302, 312, 332, 412 & 422 overstress mitigation | Convert Panoche 230 kV Bus D to BAAH & Replace Bus E Overstressed CBs | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2022 |  | 2026-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-04-28 | 2028-01-21 | 2028-02-18 | 2028-04-27 | 2028-02-28 | 2725 | Bundling Dependencies | Utility | Q3 - 2026 - Minor In-Service Date changes to align with overall project.
C14P2-GGR17 | Midway 230 kV reactor replacement: Replace existing 9 ohm Midway 500/230 kV reactors with 13 ohm reactors | Replace existing 9 ohm Midway 500/230 kV reactors with 13 ohm reactors, | PG&E | C14 | Reliability | Reactor Upgrade | In-Flight | 2025 |  | 2029-02-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | 2029-03-31 | 2029-03-30 | 2029-09-07 | 300 | Bundling Dependencies | Utility | Q3 - 2026 - Construction Sequencing changes to In-Service Date.Project is dependent on other Midway project sequencing..
C14P2-GPN01 | Pittsburg 115 kV bus overstress. Bus D-E 115kV Buss Reactors | Install bus reactors between 115 kV sections D & E | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2023 |  | 2027-04-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-05-12 | 2028-05-30 | 2028-05-26 | 2028-05-26 | 2028-05-30 | 1000 | Bundling Dependencies | Utility | Q3 - 2026 - No change
C14P2-GPT03 | Vasona-Metcalf 230 kV Line Limiting Elements Removal Project: (Part of Vasona Sub CB212 relay upgrade which will remove the Wavetrap) | The scope of this project is to remove the limiting elements for Vasona-Metcalf 230 kV line at Vasona and Metcalf Substations to achieve the line conductor rating | PG&E | C14 | Capacity | Line Upgrade | Not Assigned | 2022 |  | 2026-01-20 | N/A | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2026-07-27 | 2026-06-02 | 2027-05-03 | 2027-06-10 | 0 | (blank) | (blank) | Q3 - 2026 - Minor In-Service Date changes.
C14P2-GPT04 | Ravenswood 115 kV CB 152, 312, 322 overstress | Replace Ravenswood 115 kV CB 152, 312, 322 | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2025 |  | 2032-07-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | TBD | N/A | 2029-03-31 | 2033-01-24 | 750 | Bundling Dependencies | Utility | Q3 - 2026 - Project is part of BAAH conversion at Ravenswood Substation.
C14P2-NFT01 | Estrella Substation Project | Construct and own the new Estrella 230/70/21 kV Substation and associated transmission line work as defined by the CAISO’s Transmission Plan. Construct 230 kV and 70 kV transmission lines to connect the Morro Bay-Gates 230 kV and San Miguel-Paso Robles 70 kV lines via Estrella Substation. Reconductor the southernmost portion of the San Miguel-Paso Robles 70 kV line between Estrella and Paso Robles Substations. | PG&E | C14 | Capacity | New Station | In-Flight | 2023 |  | 2027-10-19 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | 2029-07-16 | 2029-11-01 | 2029-07-05 | 2029-07-05 | 2029-03-30 | 2029-03-30 | 2029-03-30 | 2029-03-29 | 300 | Permitting | Utility | Q3 - 2026 - No change
C14P2-NFT02 | New Manning 500 kV substation | The scope of this project includes a new 500/230 kV substation (Manning), looping in the Midway – Los Banos and Gates – Los Banos 500 kV lines into the new substaiton, two 500/230 kV transformers, looping in the Panoche – Tranquility 230 kV lines into the new substation and reconductor the Mannign – Tranquility 230 kV lines, and a new double circuit 230 kV line from Manning to Tranquility substation. | PG&E | LS Power | Capacity | New Station | In-Flight | 2023 | 2025-09-24 | 2026-12-02 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-31 | 2028-06-01 | 2028-04-13 | 2028-06-01 | 2028-04-01 | 1735 | Project Design | Utility | Q3 - 2026 - No change
C14P2-NFT03 | Wilson 115 kV Area Reinforcement | Install new 115 kV and 230 kV Breaker-and-a-half (BAAH) Bus Arrangements, two Modular Protection and Automation Control (MPAC) Buildings, and two new 230/115 kV Transformers. | PG&E | C14 | Deliverability | Re-conductor | Not Assigned | 2023 |  | 2028-07-26 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2029-08-16 | 2029-12-21 | 2030-05-31 | 2031-02-26 | 0 | Financing | Utility | Q3 - 2026 - Associated with other Wilson Upgrades Impacting a Generation Project. Scope changes under way. Engineering ongoing. In-Service date subject to change as the project completes construction sequencing after Design complete.
C14P2-NFT04 | Borden-Storey 230 kV 1 and 2 Line Reconductoring | Reconductoring the Borden – Storey section(s) of the Wilson – Storey #1 and #2 230 kV lines | PG&E | C14 | Deliverability | Re-conductor | In-Flight | 2023 | 2027-05-20 | 2029-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2029-05-01 | 2029-05-01 | 2029-05-01 |  | 2029-05-08 | 2030-01-14 | 2030-05-01 | 660 | Project Design | Utility | Q3 - 2026 - Borden Storey four-month in-service date shift driven by conductor and cable design studies needed to support material selection and engineering decisions, while still remaining within the original CAISO commitment window.
C14P2-NPT01 | Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | The scope of this project is to replace the Cortina 230/115/60 kV Bank #1 with one 230/115 kV and one 115/60 kV transformer banks | PG&E | C14 | Capacity | Transformer | Not Triggered | 2022 |  | 2025-11-12 | N/A | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-01 | 2028-06-01 | 2027-09-21 | 2027-05-26 | 2028-12-29 | 2028-01-06 | 0 | (blank) | (blank) | Q3 - 2026 - Not Triggered
C14P2-NPT02 | Round Mountain 500 kV Dynamic Voltage Support | This project will support connection of the new 500kV substation between Round Mountain (RM) and Table Mountain (TM) Substations to the PG&E system. The new 500kV substation, installed by the third party (LS Power), is needed for Northern Area Voltage Support. Dynamic Voltage Support (+/- 500MVAR) is required to address both high and low voltages in this area. This project will connect both RM to TM 500kV lines to the new substation. In addition, this project will modify Round Mountain 500kV Series Capacitor Banks 3&4 Reactance to 5.28 ohm, and Table Mountain 500kV Series Capacitor Banks 1&2 Reactance to 36.32 ohm. | PG&E | LS Power | Capacity | HVDC | Not Assigned | 2019 |  | 2023-02-15 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | 2024-11-21 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-06-16 | 2026-10-17 | 2026-12-18 | 2026-07-01 | 0 | (blank) | (blank) | Q3 - 2026 - No longer assigned to an active Generation project. Round Mountain & Table Mountain Series Capacitors to be operational in July 2027. This work can/will be completed post-energization of Fern Road.
C8P2-1 | Re-conductor Borden-Gregg #1 230 kV Line | Re-conductor 6.25 mi Borden-Gregg #1 230 kV Line with 1113 ACSS and upgrade equipment to 2000 A minimum (this is the existing Borden-Gregg 230 kV Line) | PG&E | C8 | Deliverability | Re-conductor | In-Flight | 2017 | 2024-10-11 | 2026-12-10 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2027-01-08 | 2027-01-08 | 2027-01-08 | 2027-05-12 | 2028-03-03 | 695 | Land Rights | Utility | Q3 - 2026 - Project has faced land rights challenges and supply-side material delays. Construction rescheduled to start in 2027 after confirming steel poles not available on time for Q4 2026.
C9P1-F12 | Re-conductor Borden-Gregg #2 230 kV Line | Re-conductor 6.25 mi Borden-Gregg #2 230 kV Line with 1113 ACSS | PG&E | C9 | Deliverability | Re-conductor | In-Flight | 2017 | 2024-10-11 | 2026-12-10 | 2025-05-31 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2027-05-12 | 2027-05-12 | 2027-05-12 | 2027-05-12 | 2028-02-24 | 695 | Land Rights | Utility | Q3 - 2026 - Project has faced land rights challenges and supply-side material delays. Construction rescheduled to start in 2027 after confirming steel poles not available on time for Q4 2026.
C9P2-N02 | Re-conductor Fulton-Hopland 60 kV Line (Geysers Jct-Cloverdale Jct-Hopland) (7 mile section) | Re-conductor 24.21 mi Fulton-Hopland 60 kV Line (Geysers Jct 016/003A-Cloverdale Jct 026/002-Hopland) with 715 AAC and upgrade any limiting equipment | PG&E | C9 | Deliverability | Re-conductor | In-Flight | 2019 | 2025-03-11 | 2026-10-16 | 2027-05-31 | 2027-03-31 | 2027-12-31 | 2025-11-03 | 2026-02-13 | 2026-05-25 | 2026-06-05 | 2026-04-02 | 2026-03-23 | 2027-03-31 | 2027-03-31 | 2027-03-30 | 2027-03-31 | 2027-01-08 | 230 | Clearances | Utility | Q3 - 2026 - Minor In-Service Date changes.
POS-Q1587-NU1 | Arco 230kV New CB 2422 & 2432 & Bay + Cntrl Bldg & Relays | Arco 230kV New CB 2422 & 2432 & Bay + Cntrl Bldg & Relays | PG&E | C15 | Reliability | RAS (Reliability) | In-Flight | 2022 |  | 2028-06-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2028-09-22 | 100 | (blank) | N/A | Q3 - 2026 - Triggering Queue In-Service date shifting to Q3 2028
POS-Q1872-NU1 | PITTSBURG PP: INSTALL 115KV BUS D MPAC | (blank) | (blank) | C14 | (blank) | (blank) | In-Flight | 2025 |  | 2024-10-24 | [8 empty] | 2028-03-17 |  | 2028-03-17 | NF |  | 2028-03-30 | 325 | Bundling Dependencies | Utility | Q3 - 2026 - The project is in construction and planned in Service date is Q2, 2030
POS-Q1922-NU1 | Tesla MPAC | New 230kV MPAC building relocates 230kV equipment from existing Control Building | PG&E | C14 | Capacity | MPAC | In-Flight | 2018 |  | 2026-05-12 | N/A | N/A | N/A | 2024-10-09 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-03-24 | 2026-06-09 | 2028-01-11 | 2028-05-15 | 2028-01-13 | 2027-02-19 | 500 | (blank) | N/A | Q3 - 2026 - Project in construction
POS-Q1932-NU1 | Wilson Sub: Convert 115 kV DBSB to BAAH | Wilson Sub: Convert 115 kV DBSB to BAAH | PG&E | C14 | Reliability | SCD overstress | In-Flight | 2023 |  | 2028-07-26 | [8 empty] | 2031-02-26 |  | 2029-12-21 | 2029-12-21 | 2030-05-31 | 2031-02-26 | 200 | Financing | Utility | Q3 - 2026 - Engineering ongoing. In-Service date subject to change as the project completes construction sequencing after Design complete.
POS-Q1959-NU2 | Morro Bay Sub: Control Building Replacement | New 230kV MPAC building relocates 230kV equipment from existing Control Building | PG&E | C14 | Capacity | MPAC | In-Flight | 2014 |  |  | N/A | N/A | N/A | 2027-03-09 | 2027-05-06 | 2027-05-06 | 2028-05-30 | 2029-05-25 | 2029-05-25 | 2024-03-01 | 2024-03-01 | TBD | 2032-03-31 |  | 300 | Bundling Dependencies | N/A | Q3 - 2026 - PG&E is evaluating options that could remove this project from impacts to Generation Interconnection

## SCE
CAISO - Public
ID | Network Upgrades | Description | PTO | Study | Type of Upgrade | Category | Status | Current Expected Const Consturction Start | Expected CPUC Permit Application | Trigger Year | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF (Current) | Agregate MW in Queue with Executed LGIA | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
New: CAISO to provide ID (Devers 220 kV SCD Mitigation) | Devers 220 kV SCD Mitigation | Replace one (1) circuit breaker at Devers 220 kV substation with a circuit breaker with fault interrupting capability of 63kA and a tested X/R of 35 or higher. | SCE | QC13 | RNU | SCD | Plan/Analyze | Pending | N/A | 2021-11-01 | [11 empty] | New | TBD |  |  |  |  | Scope change to operating procedure, to be removed from future NU TDF (Jan)
New: CAISO to provide ID (Devers 220 kV SCD Mitigation: 80kA Upgrade) | Devers 220 kV SCD Mitigation: 80kA Upgrade | Upgrade Devers 220 Switchrack to 80 kA | SCE | QC14 | RNU | SCD | Plan/Analyze | Pending | N/A | 2024-01-30 | [11 empty] | New | 2030-11-28 |  |  |  |  | Now approved in 2025-2026 Transmission plan (Devers 230 kV SCD Upgrade), to be removed from future NU TDF (Jan)
New: CAISO to provide ID (Mira Loma B 220 kV SCD Mitigation: 80kA Upgrade) | Mira Loma B 220 kV SCD Mitigation: 80kA Upgrade | Upgrade Mira Loma B 220 Switchrack to 80 kA | SCE | QC14 | RNU | SCD | Initiation | Pending | N/A | 2024-01-30 | [11 empty] | New | 2029-10-31 |  |  |  |  | Now approved in 2025-2026 Transmission plan (Etiwanda and Mira Loma 230 kV SCD Upgrade), to be removed from future NU TDF (Jan)
New: CAISO to provide ID (Pardee 220 kV SCD Mitigation) | Pardee 220 kV SCD Mitigation | De-loop the Pardee 220 kV bus from the Pastoria-Warne-Pardee and Pardee-Santa Clara 220 kV lines to create the Pastoria-Warne-Santa Clara 220 kV line. Modify the Big Creek/Pastoria CRAS to account for the new transmission line topology. | SCE | QC13 | RNU | SCD | Plan/Analyze | Pending | N/A | 2021-11-22 | [11 empty] | New | TBD |  |  |  |  | Scope change to operating procedure, to be removed from future NU TDF (Jan)
New: CAISO to provide ID (Serrano 500 kV SCD Mitigation) | Serrano 500 kV SCD Mitigation | Replace nine (9) 500 kV GIS circuit breakers at Serrano 500 kV Substation with 63 kA-rated equivalents | SCE | QC14 | RNU | SCD | Initiation | Pending | N/A | 2024-10-30 | [11 empty] | New | 2033-08-29 |  |  |  |  | July 2026: To be removed from NU workbook, project included in TPP workbook.
SCE-TCP2-EOP-R4 | Lugo - Victorville RAS | Trip generation for Eldorado area 500kV line outages. | SCE | TC Phase II | RNU | RAS/CRAS | Closeout | 2025-01-01 | N/A | 40787 | 44166 | 45047 | 45047 | 45047 | 45261 | 45261 | 2024-04-30 | 2024-06-30 | 2024-12-31 | 2025-06-30 | 2025-05-01 | 2025-12-30 | 2026-03-31 | 2026-03-31 | 1320 | No Change | N/A | July 2026: Project completed and it should be removed from future TDF's.
SCE-C11P2-N-L1 | Pardee – Pastoria – Warne 220 kV T/L rating increase | Upgrade terminal equipment and fix ground clearance for Pardee – Pastoria- Warne 230kV line | SCE | C11 Phase II | LDNU | Capacity Increase | Closeout | 2023-06-01 | N/A | 44013 | 44849 | 45170 | 45078 | 45078 | 45383 | 45078 | 2023-10-30 | 2024-03-29 | 2024-03-29 | 2025-12-01 | 2025-12-01 | 2025-09-26 | 2025-09-26 |  | 340 |  |  | Commercially operational
SCE-C10P2-E-R3 | West of Colorado River CRAS Inland/Devers Extension - monitoring infrastructure | Infrastructure to convert the formally referred to as the New Devers RAS and the Inland RAS to centralized RAS platform | SCE | C10 Phase II | RNU | RAS/CRAS | Closeout | 2022-03-01 | N/A | 43435 | 44470 | Aug-25 | 44986 | 44986 | 45078 | 45192 | 45192 | 2024-03-01 | 2024-03-01 | 2024-04-01 | Completed | Closeout | In Service |  | 4855 |  |  | Project completed and it will be removed from future TDF's.
SCE-C9P2-N-R1 | Whirlwind AA Bank CRAS Monitoring Infrastructure | Implement Whirlwind AA Bank CRAS - monitoring infrastructure | SCE | 2018 Reassessment | GRNU | RAS/CRAS | Closeout | 2023-07-05 | N/A | 44013 | 44866 | 44958 | 44958 | 44958 | 45078 | 45078 | 2024-03-30 | 2024-06-01 | 2024-12-31 | 2024-12-31 | 2025-06-01 | 2025-06-01 | 2025-03-01 | 2025-03-01 | 692 | No Change | N/A | July 2026: Project completed and it should be removed from future TDF's.
SCE-C9C10-N | Windhub AA Bank cRAS - monitoring infrastructure | Windhub AA Bank cRAS - monitoring infrastructure | SCE | 2021 Reassessment | GRNU | RAS/CRAS | Closeout | 2022-04-01 | N/A | 44409 | 44866 | 44958 | 44958 | 44958 | 44986 | 45046 | 2023-12-31 | 2023-09-01 | 2024-12-31 | 2024-02-01 | Completed | 2022-04-01 | In Service |  | 1800 |  |  | Project completed and it will be removed from future TDF's.
New: CAISO to provide ID (Calcite CRAS) | Calcite CRAS | Monitoring infrastructure to include multiple outages as part of the new Calcite CRAS | SCE | QC14 | RNU | RAS/CRAS | Design | Pending | N/A | 2028-11-01 | [12 empty] | N/A | 2029-03-31 | 355 | Other | N/A | July 2026: Newly added, to be included in future TDFs.
PIN6902 | Calcite Substation | New four position 220 kV switchrack | SCE | Serial LGIP | GRNU | New Substation | Design | 2028-01-01 | 2025-04-01 | 44165 | 2024-01-31 |  |  | New | TBD | TBD | 2027-03-01 | 2027-03-01 | 2027-12-31 | 2027-11-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | 2029-03-01 | 255 | Permitting (Non-CPUC/CEQA) | Agency-County
SCE-C11P2-EOP-R1 | Lugo - Victorville CRAS - monitoring infrastructure | Infrastructure to convert the Lugo - Victorville RAS to centralized RAS platform | SCE | C11 Phase II | GRNU | RAS/CRAS | Design | 2025-09-25 | N/A | 43770 | 2024-06-01 | Jun-25 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-30 | 2025-06-01 | 2026-06-30 | 2027-12-30 | 2028-06-01 | 2028-06-30 | 2028-06-30 | 2028-06-30 | 1520 | No Change | N/A
SCE-C12P2-N-R3 | Moorpark CRAS: monitoring infrastructure | New Moorpark CRAS | SCE | C12 Phase II | GRNU | RAS/CRAS | Design | 2028-06-01 | N/A | 44378 | 45474 | 45474 | 45474 | 45474 | 45474 | Pending | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2027-12-01 | 2028-06-01 | 2028-12-31 | 2028-12-31 | 2028-12-31 | 715 | No Change | N/A
SCE-C9P2-NOL-R1 | New North of Lugo RAS - Backbone Portion | New North of Lugo RAS combining HDPP RAS and Calcite RAS | SCE | C9 Phase II | RNU | RAS/CRAS | Design | 2029-01-01 | N/A | 43040 | 2024-06-01 | 2024-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2030-06-30 | 1930-06-01 | 2030-06-30 | 2031-06-30 | 2031-06-30 | 350 | No Change | N/A
New: CAISO to provide ID (Pardee 220 kV SCD Mitigation: 80kA Upgrade) | Pardee 220 kV SCD Mitigation | Upgrade Pardee 220 Switchrack to 80 kA | SCE | QC14 | RNU | SCD | Design | 2029-01-01 | N/A | 2024-01-30 | [11 empty] | New | 2033-05-15 | 2033-05-15 | 2950 | No Change | N/A
SCE-C72021-EOP | Participate and modify the planned Lugo-Victorville CRAS - SCE portion | Participate and modify the planned Lugo-Victorville CRAS - SCE portion | SCE | 2021 Reassessment | RNU | RAS/CRAS | Design | N/A | N/A | 44409 | 2025-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2026-06-30 | 2027-12-30 | 2028-06-01 | 2028-06-30 | 2028-06-30 | 2028-06-30 | 300 | No Change | N/A
PIN8483-RNU | South of Vincent CRAS | Add lines south of Vincent to the Tehachapi CRAS | SCE | C13 Phase II | RNU | RAS/CRAS | Design | 2026-08-01 | N/A | 2021-12-31 | 2026-04-30 |  |  | New | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2027-12-15 | 2027-12-15 | 2026-05-01 | 2026-05-01 | 2027-11-03 | 2027-12-31 | 2027-12-31 | 1300 | No Change | N/A
SCE-C12P2-N-R2 | Tehachapi CRAS: monitoring infrastructure addition | Add N-1 to RAS | SCE | C12 Phase II | GRNU | RAS/CRAS | Execution | 2026-09-01 | N/A | 44228 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2025-04-01 | 2025-04-01 | 2025-11-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-11-24 | 2027-06-30 | 3200 | Bundling Dependency | Utility
New: CAISO to provide ID (Vincent 500 kV SCD Mitigation) | Vincent 500 kV SCD Mitigation | De-loop Antelope-Vincent No.1 and Lugo-Vincent No.2 500 kV lines | SCE | QC14 | RNU | SCD | Design | 2027-09-01 | N/A | 2024-01-30 | [11 empty] | New | 2027-01-29 | 2028-06-30 | 8200 | Bundling Dependency | Utility
SCE-C11P2-E-R1 | WOCR CRAS Inland/Devers Extension Additional Monitoring (QC11) at Wildlife Sub | WOCR CRAS Inland/Devers Extension Additional Monitoring (QC11) at Wildlife Sub | SCE | C11 Phase II | RNU | RAS/CRAS | Design | 2029-10-01 | N/A | 43891 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-10-01 | 2027-10-01 | 2027-10-01 | 2027-10-01 | 2027-10-01 | 2029-10-01 | 2029-10-01 | 2029-10-01 | 2029-10-01 | 2029-10-01 | 150 | No Change | N/A
SCE-C10P2-E-R3 | WOCR CRAS Inland/Devers Extension Monitoring (QC10) at Alberhill Sub | WOCR CRAS Inland/Devers Extension Monitoring (QC10) at Alberhill Sub | SCE | C10 Phase II | RNU | RAS/CRAS | Design | Pending | N/A | 43435 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2027-04-01 | TBD | TBD | TBD | 2029-06-01 | 2029-06-01 | Pending | On hold | On hold | On Hold | On Hold | 1617 | No Change | N/A

## SDGaE
CAISO - Public
ID | Network Upgrades | Description | PTO | Study | Type of Upgrade | Category | Status | Current Expected Const Consturction Start | Expected CPUC Permit Application | Trigger Year | Original Estimated In-service Date | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF (Current) | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
SDGE-EXISTING-RNU-01 | Imperial Valley Existing/Modified RAS' | Imperial Valley Existing/Modified RAS' | SDGE |  | PNU |  | Operational
SDGE-EXISTING-RNU-7.1 | Existing Miguel BK 80 / 81 | Existing Miguel BK 80 / 81 | SDGE |  | PNU |  | Operational
SDGE-EXISTING-RNU-02 | Existing Otay Mesa RASs | Existing Otay Mesa RASs | SDGE |  | PNU |  | Operational
SDGE-EXISTING-RNU-04 | Existing ECO/BUE anti-islanding scheme for radial generators | Existing ECO/BUE anti-islanding scheme for radial generators | SDGE |  | PNU |  | Operational
SDGE-C11-PHII-RNU-02 | Participate in the proposed RAS to protect TL13810A/TL13810B/TL13810C Friars - Penasquitos - Doublett Tap 138kV Lines (formerly known as Participate in the proposed RAS to protect TL13827 Mission – Friars 138kV line) | Participate in the proposed RAS to protect TL13810A/TL13810B/TL13810C Friars - Penasquitos - Doublett Tap 138kV Lines (formerly known as Participate in the proposed RAS to protect TL13827 Mission – Friars 138kV line) | SDGE | C11 Phase II | PNU | Reliability | Operational |  | N/A | N/A | 2024-06-22 | 2024-06-22 | 2024-06-22 | 2024-06-22 | 2024-07-22 | 2024-06-22 | 2024-07-22 | 2024-06-22 | 2024-06-22 | In-Service | In-Service | In-Service | [5 empty] | Placed in service on 6/18/22
SDGE-C08-PHII-RNU-03.1 | TL680 OLS | Overload Scheme to protect TL680C. Previously named as Modify TL684 RAS. | SDGE | C8 Phase II | GRNU | Deliverability | Operational |  | N/A | 1905-07-15 | 2024-06-23 | 2024-06-23 | 2024-06-23 | 2024-06-23 | 2024-06-23 | 2024-06-23 | 2024-04-23 | In-Service | In-Service | In-Service | In-Service | In-Service | [5 empty] | Placed in service on 3/30/23
SDGE-C07-PHI-RNU-01 | Participate in the proposed RAS to protect TL23006/TL23010/TL23002 San Luis Rey – San Onofre 230kV lines | Participate in the proposed RAS to protect TL23006/TL23010/TL23002 San Luis Rey – San Onofre 230kV lines | SDGE | C7 Phase I | PNU | Reliability | Operational |  | N/A | 1905-07-15 | 2024-06-23 | 2024-06-23 | 2024-06-23 | 2024-06-23 |  | 2024-06-23 | 2024-06-23 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-08-23 | [5 empty] | Placed in service 8/20/23
SDGE-C08-PHII-RNU-04 | Participate in the proposed RAS to protect TL23003 & TL23011 Encina to San Luis Rey 230 kV lines (Proposed grouping RAS to protect Encina/Pen/San Luis Rey 230kV Lines) | Proposed RAS to Protect TL23003 Encina - San Luis Rey 230 kV line | SDGE | C8 Phase II | PNU | [6 empty] | 2024-06-23 | 2024-06-23 | 2024-06-23
SDGE-PRE-AMEND-RNU-01.2 | Proposed RAS to Protect TL23011B Encina Tap - Encina 230 kV line | Proposed RAS to Protect TL23011B Encina Tap - Encina 230 kV line | SDGE |  | CANU-GR | [6 empty] | 2024-06-23 | 2024-06-23 | 2024-06-23
SDGE-C14-PHII-RNU-81 | update relay settings for Q1532 - ECO 138 kV #1 line | update relay settings for Q1532 - ECO 138 kV #1 line | SDGE | C14 Phase II | GRNU | Deliverability | Design | 2025-04-25 | N/A | 2024 | 2027-05-17 | [9 empty] | 2028-05-01 | 2026-04-15 | 2026-03-18 | Removed |  |  |  | This Network Upgrade was removed in the 2024 Reassessment Report

## GLW-VEA
CAISO - Public
ID | Network Upgrades | Description | PTO | Study | Type of Upgrade | Category | Status | Current Expected Const Consturction Start | Expected CPUC Permit Application | Trigger Year | Original Estimated In-service Date | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF (Current) | Agregate MW in Queue with Executed LGIA | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
VEA-C6P2-EOP-R5 | VEA Vista RAS | VEA Vista RAS: Install a new RAS to protect Jackass Flats - Mercury Switch 138 kV line under contingency conditions | VEA | C6 Phase II | RNU | Thermal | Cancelled | N/A | N/A | N/A | N/A | 2022-09-30 | 2022-11-22 | [7 empty] | N/A | N/A | Completed | Completed |  |  |  |  | Project was replaced by upgrading the Jackass Flats - Mercury Switch 138kV line. This project is completed.
VEA-C8P2-VEA-R2 | Innovation RAS | Install a new Innovation RAS | GLW | C8 Phase II | RNU |  |  |  |  | N/A | 2022-09-30 | 2022-09-30 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2023-07-01 | 2023-07-01 | 2023-05-23 | Complete | Complete | Complete | Complete | Completed | Completed |  | 1547 |  |  | Project completed.
VEA-C9P2-EOP-R3 | Innovation RAS (VEA-GLW portion) | New Innovation RAS (include Desert View RAS from QC8) to trip generation under N-1 | GLW | C9 Phase II | RNU |  |  |  |  | N/A | 2022-09-30 | 2022-09-30 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2023-07-01 | 2023-07-01 | 2023-05-23 | Complete | Complete | Complete | Complete | Completed | Completed |  | 1547 |  |  | Project completed.
VEA-C9P2-EOP-R4 | Sloan Canyon RAS (fka Bob RAS - VEA-GLW portion) | New Sloan Canyon RAS to trip generation under N-1 and N-2 | GLW | C9 Phase II | RNU |  |  |  |  | N/A | 2022-09-30 | 2022-09-30 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2023-07-01 | 2023-07-01 | 2023-05-23 | Complete | Complete | Complete | Complete | Completed | Completed |  | 1547 |  |  | Project completed.
GLW-2021-EOP-L1 | Trout Canyon - Sloan Canyon 230kV line upgrade | Trout Canyon - Sloan Canyon 230kV line upgrade | GLW | 2021 Reassessment | LDNU |  | Inflight | 2026-07-26 | N/A | N/A | TBD | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | N/A | 2027-12-31 | 2027-12-31 | 2026-12-31 | 2026-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | N/A | No Change | N/A | BLM permit received, construction activities underway