Attachment A - Plan for Stakeholder Engagement – 5- Year Market Initiatives Roadmap

The CAISO is will begin a stakeholder process in April to determine what market initiatives contained in the 5-Year Market Initiatives Roadmap will have high priority for the CAISO to begin addressing in 2008 and early 2009.  The CAISO will follow the formalized prioritization and ranking process that was developed in conjunction with stakeholders and incorporate stakeholder input in order to determine the list of high priority market enhancements.

The proposed plan for this stakeholder engagement is as follows:

March 28 - Publish Revised Market Initiatives Roadmap

April 8 - Stakeholder Conference Call

April 11 - Stakeholder Comments Due on content and correctness of Roadmap

April 15 - Publish Second Revision of Roadmap based on stakeholder comments

April 18 – Stakeholder comments due defining high priority enhancements

Week of April 14 - CAISO Internal High Level Ranking of Market Initiatives

April 24 - Publish Results of High Level Ranking

April 30 - Stakeholder Meeting

May 7 - Stakeholder Comments Due on Results of High Level Ranking

May 19 – May 30 - CAISO Internal Detailed Ranking Activities

May 29 - Publish Straw Proposal for High Priority Enhancements

June 5 - Stakeholder Conference Call

June 12- Stakeholder Comments Due on Straw Proposal

June 19 - Publish Draft Final Proposal

July 16-17 Briefing at July Board of Governors

Please submit comments on this proposed schedule to Margaret Miller at mmiller@caiso.com.