## Current Timeline
Policy Initiatives Timeline
This document provides a simple, at-a-glance, snapshot of all active policy initiatives and where they are in the stakeholder process. Updated weekly.
Note: Includes the Annual Policy Initiative Catalog & Roadmap Process but does not include any other recurring processes or miscellaneous meeting topics.
Updated: 4/24/2025 | [28 empty] | Pre-proposal development |  |  |  |  | Proposal development |  |  |  |  | Decision |  |  |  | Implementation |  |  | l | Comments Due |  |  | u | Meeting
2025
|  | Q4 | [11 empty] | Q1 | [11 empty] | Q1 | [11 empty] | Q2 | [11 empty] | Q3 | [11 empty] | Q4
Classification | Initiative | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
|  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
[27 empty] | u | [5 empty] | l |  |  |  |  | u |  |  | l
CAISO Board | Annual Policy Initiative Catalog & Roadmap Process 2025 | January Wk 1: Kickoff; February Wk 1: Catalog Submissions; March Wk 1: Prioritization Process - Survey survey submissions; May Wk 1: Prioritization Process - Survey Results; June Wk 1: Policy Initiatives Catalog Published
[29 empty] | u |  | l |  |  |  |  | u |  | l |  | Final Proposal |  |  | ISO Board of Governors
CAISO Board | Subscriber PTO Market Scheduling Options | January Wk 1: Issue Paper; January Wk 3: Straw Proposal; March Wk 2: Draft Final Proposal
Congestion revenue rights enhancements | bar: January Wk 1 to June Wk 4
[26 empty] | Foundations |  |  |  | Analysis |  |  |  | Policy Scope + Problem Statements
[31 empty] | u |  | l | u | u |  |  | u |  |  |  | l | u |  | l
| Demand and Distributed Energy Market Integration | February Wk 1: Working Groups
Joint Authority | bar: January Wk 1 to April Wk 4
| Day-Ahead Sufficiency | January Wk 1: Draft Final Proposal
Joint Authority | Day-Ahead Market Enhancements
Joint Authority | Extended Day-Ahead Market (EDAM) | bar: March Wk 1 to June Wk 1
[34 empty] | Issue Paper |  |  |  |  | Straw Proposal |  |  |  | Draft Final Proposal
Joint Authority | Price Formation Enhancements | bar: January Wk 1 to March Wk 4
Joint Authority | Price Formation Enhancements | January Wk 1: Phase 2: Working Groups
Topic 1: Scarcity Pricing | bar: January Wk 1 to March Wk 4
Topic 2: BAA-level MPM | bar: January Wk 1 to March Wk 4
Topic 3: Fast-start Pricing | bar: January Wk 1 to March Wk 4
| Storage Design and Modeling | January Wk 1: Working Groups; May Wk 1: u; May Wk 3: l; May Wk 4: u; June Wk 2: l; June Wk 4: u; July Wk 2: l
Topics 1: Bid Cost Recovery (BCR), Outage Management, Uplift, and Default Energy Bid (DEB) | bar: January Wk 1 to July Wk 3
Topic 2: State-of-Charge (SOC) Management | bar: January Wk 1 to July Wk 3
Topic 3: Distribution-level & Paired Resources | bar: January Wk 1 to July Wk 3
Joint Authority | West-wide Governance Pathways | bar: January Wk 1 to April Wk 4
CAISO Board | Interconnection Process Enhancements 2023 Track 3 | bar: January Wk 1 to April Wk 3
CAISO Board | Interconnection Process Enhancements 2023 Track 3 | January Wk 1: Draft final proposal; February Wk 2: Final Proposal; March Wk 1: ISO Board of Governors; April Wk 1: Draft Tariff Language
GHG Coordination | bar: January Wk 1 to May Wk 1
| Gas Resource Management | February Wk 1: Issue Paper
GHG Coordination | bar: January Wk 1 to April Wk 4
GHG Coordination | bar: January Wk 1 to April Wk 4
Topic 1: WEIM/EDAM GHG design | bar: January Wk 1 to April Wk 4
| Topic 2: Non-priced approaches for GHG reduction | January Wk 1: Issue Paper
Topic 3: Additional GHG-related metrics | bar: January Wk 1 to April Wk 4
Resource Adequacy Modeling & Program Design | bar: January Wk 1 to March Wk 4
| Resource Adequacy Modeling & Program Design | January Wk 1: Straw proposals
Track 1: Modeling, Defaults, and Accreditation | bar: January Wk 1 to March Wk 4
Track 2: Outage & substitution and availability and incentive mechanisms | bar: January Wk 1 to March Wk 4
Track 3a: Backstop reform and long-term EDAM RSE solutions | bar: January Wk 1 to March Wk 4
Track 3b: RA status visibility | bar: January Wk 1 to March Wk 4
Policy Development Phase Completed | bar: March Wk 2 to April Wk 1
Billing, Payment, and Credit Enhancements
Joint Authority | Storage bid cost recovery and default energy bids enhancements
CAISO Board | EDAM ISO BAA Participation Rules
Joint Authority | Inter-SC Trades in Regional Markets
Joint Authority | Inter-SC Trades in Regional Markets
CAISO Board | Interconnection Process Enhancements 2023 Track 2
Transmission Service & Market Scheduling Priorities Phase 2
Generation Deliverability Methodology Review
FERC Order 881 - Managing Transmission Line Ratings Phase 2

## Recurring Processes (WIP) (hidden)
|  | Q4 2023 | [11 empty] | 2024
|  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
|  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
Transmission Development Forum | Meetings
2023-2024 20 Year Transmission Outlook | Meetings
2022-2023 Transmission Planning Process | Study Plan
Assessments
Results
2023-2024 Transmission Planning Process | Study Plan
Assessments
Results
2024-2025 Transmission Planning Process | Study Plan
Assessments
Results
2025 Local Capacity Requirement | Study Plan
Assessments
Results
2025 Flexible Capacity Needs Assessment | Study Plan
Assessments
Results
PTO Per Unit Cost Guides | Study Plan
Assessments
Results

## Archive
| 2023 | [23 empty] | 2024
| July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
| Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
Annual Policy Initiative Catalog and Roadmap Process | January Wk 1: Workshops; March Wk 1: Prioritization workshop & RIF roundtable
[29 empty] | Discretionary initiative submissions | [7 empty] | Draft annual catalog |  |  |  | Final annual catalog
Billing, Payment and Credit Enhancements | July Wk 1: Implementation - Development; November Wk 1: ISO Board of Governors
DAME | July Wk 1: Implementation - Development
Day-Ahead Sufficiency | December Wk 1: Issue Paper; February Wk 1: Straw Proposal; April Wk 1: Draft Final Proposal; June Wk 1: ISO Board of Governors
EDAM | September Wk 1: Implementation - Development
Implementation - Agreement
EDAM ISO BAA Track A1 | July Wk 1: Track A1 Draft Final Proposal; August Wk 1: Track A1 Final Proposal; November Wk 1: Tariff filing
[5 empty] | Track A1 tariff development | [11 empty] | Implementation - Development
FERC Order 881 - Managing Transmission Line Ratings Phase 2 | July Wk 4: Working Groups; October Wk 1: Implementation - Development
Gas Resource Management | July Wk 4: Working Groups; October Wk 1: Working Groups
Generation Deliverability Methodology Review | November Wk 1: Draft Final Proposal
Final Proposal
GHG Coordination | August Wk 3: Working Groups
IPE 2023 | August Wk 4: Straw Proposal; October Wk 1: Straw Proposal
Revised Straw Proposal
Draft Final Proposal
Final Proposal
Tariff filing
ISO Board of Governors
Price Formation Enhancements | August Wk 1: Working Groups
Resource Adequacy Modeling & Program Design | October Wk 1: Working Groups
RDRR Minimum On Time | December Wk 1: Issue Paper/Draft Final Proposal; January Wk 1: Final Proposal; February Wk 1: Joint BOG/WEIM GB
Rules of Conduct Enhancements | September Wk 1: Track 2 Straw Proposal; October Wk 1: Tariff development (track 1); January Wk 1: FERC Filing (track 1)
TSMPS Phase 2 | July Wk 1: Tariff filing (track 1); March Wk 1: Tariff filing (track 2)
Tariff development (track 2)
Implementation - Development (track 1)
WEIM Base Schedule Submission Deadline | July Wk 1: Joint Governance Meeting
ASSOC | January Wk 1: Straw Proposal