## Cluster 15
2016-05-30 | Cluster 15
2016-07-04 | Process |  | IR Open Window Announcement | Resource Interconnection Standards Fair | Cluster Application Window |  | Customer Engagement Window |  |  |  | Cluster Study | Cluster Study Report Issued | Cluster Study Report Meeting | 5% Commercial Readiness Dep; Continued Site Ctrl; Shared Gen-tie | Annual Reassessment/ Cluster Restudy | Reassessment/Cluster Restudy Report Issued | Reassessment/Cluster Restudy Report Meeting | Issue Interconnetion Facilities Study Agmt incl Appendix B Technical Data | Return Agmt, Apdx B; 10% Commercial Readiness Deposit | Interconnection Facilities Study | Draft Interconnection Facilities Study Report Issued & Comment Period | Final Interconnection Facilities Study Report | Interconnection Facilities Study Report Meeting | TP Deliverability Affidavits | Annual Deliverability Retention Affidavit | Tender Draft GIA2 | GIA Negotiation2 | Executable GIA2 | Generator Interconnection Agreement Deposit2
| Process Timeframe |  |  |  | 10/1/2024-12/1/2024 |  | 1/1/2025-5/1/2025 |  |  |  | 6/1/2025-12/26/2025 |  |  |  | 12/27/2025-6/8/2026 |  |  | 6/16/2026-2/3/2027
| Subprocess |  |  |  |  | Completeness Check | Cluster Study Criteria Evaluation | Technical Validation | Auction & Scoring Results | Scoping Meeting Per Study Area & Cluster Study Criteria |  |  |  | Deficiency Cure Period through 12/26/2025 | [7 empty] | May be extended by 15 BD
2016-09-05 | Dates | Start |  | 2024-09-17 | 2024-10-01 | 2024-10-01 | 2025-01-01 | 1/1/20251 | 2025-02-12 | 2025-04-17 | 2025-06-01 | 2025-11-12 | 2025-11-13 | 2025-11-27 | 2025-12-27 | 2026-05-25 | 2026-05-26 | 2026-06-16 | 2026-07-15 | 2026-07-15 | 2026-11-13 | 2026-12-13 | 2027-01-05 |  |  | 2026-11-07 | 2027-02-02 | 2027-04-02 | TBD
2016-10-10 |  | End | 2024-09-03 |  | 2024-12-01 | 2024-12-09 | 2025-02-12 | 5/1/2025 | 2025-03-05 | 5/1/2025 | 2025-11-12 |  | 2025-11-26 | 2025-12-16 | 2026-05-25 |  | 2026-06-08 |  |  | 2026-11-12 | 2026-12-12 | 2027-01-04 | 2027-02-03 | 3/15/2027 tentative | 3/15/2027 tentative | 2027-02-02 | 2027-04-02 | 2027-04-12
2016-11-11 | Milestone Timeframe |  |  |  | 60 CD |  |  |  |  | 10 BD | 164 CD |  | Within 10 BD of Issuing Cluster Study Report | Within 20 CD of the Cluster Study Report Meeting | Within 150 CD of Cluster Study Report Meeting |  | Within 10 BD of Issuing Reassessment/Cluster Restudy Study Report | Issue Agreement within 5 BD of Restudy Report Meeting | Within 30 CD after receipt of Interconnection Facilities Study Agreement | 120 CD | 30CD | Within 15 BD of comments received | Within 30 CD of issuing Final Interconnection Facilities Study Report | [5 empty] | Upon submitting executed GIA or within 10 BD after request for unexecuted filing of GIA
2016-11-24 | Tariff Appendix KK Section Number(s) |  |  |  | 3.5.1 | 3.5.1, 3.5.2 | 3.5.4, 4.1, 4.2, 4.3, 4.4 | DD 17.1 a) | 4.1.2 | 6.1.2 | 6.6 DD 17.1(d) | 6.6, 6.7 | 6.7 | 3.5.1.5, 7.4.1(1), 10.1, 10.2, 11.1 thru 11.2.7 | 3.6.1.2, 7.4, 7.5 | 7.4.1 | 7.4.1 | 8.1.1 | 8.1.1 | 8.5 | 8.5 | 8.5 | 8.7 | 8.9 | 8.9.3 | 13 | 13 | 13 | 13.3
2016-11-25
2016-12-26 | Customer Actions | [7 empty] | 2025-02-12: Customer Actions |  |  |  | Customer Actions
2017-01-02 | Customer Response Timeframe |  |  | 10 BD before RISF |  | Within 10 BD of Notification |  | Within 10 BD of Notification | 2025-02-12: Within 14 CD of Notification; 2025-11-27: Within 20 CD After Cluster Study Report; 2026-06-16: Within 30 CD of Receipt; 2026-11-13: Within 30 CD of Receipt | Due Date per Market Notice | Due Date per Market Notice |  |  |  | Simultaneous or within 10 BD
2017-01-16 | Customer Actions |  | Suscribe to the Daily Breifing | Submit questions, attend RISF | Submit: Complete IR Package including: Application Fee, and Study and Commercial Readiness Deposit | *(If Applicable)* Submit clarifying information |  | *(If Applicable)* Submit corrected technical information | *(If Applicable)* Submit auction bid by 2/26/2024 | Attend Scoping meeting; registration and NDA required for all participants |  | Receive Cluster Study report | Attend Cluster Study Report meeting | Post 5% Commercial Readiness Deposit; demonstrate continued Site Control |  | Review Ressessment/Cluster Study report | Attend Reassessment/Cluster Study report meeting | Submit appendix B reflecting any allowed modifications,(and updated IR package if necessary), demonstrate 100% Site Control | Post 10% Commercial Readiness Deposit |  | Review draft Interconnection Facilities Study report and submit written comments or notification of no comments to CAISO | Receive final Interconnection facilities report | Attend Interconnection Facilities Study report meeting | Return TPD affidavit to ISO | Return TPD affidavit to ISO Due every year until COD |  | Negotiate GIA | Execute GIA | Post 20% GIA Deposit
2017-02-20 | Customer Resources |  | https://www.caiso.com/daily-briefing https://www.caiso.com/subscriptions/subscription-general | Save the Date - Resource Interconnection Standards Fair on 9/17/24 ¦ California ISO (caiso.com) | https://www.caiso.com/generation-transmission/generation/generator-interconnection/interconnection-request-study |  |  |  | 2025-11-27: https://www.caiso.com/generation-transmission/generation/generator-interconnection/interconnection-request-study; 2026-07-15: https://www.caiso.com/generation-transmission/generation/generator-interconnection/interconnection-request-study | [5 empty] | https://www.caiso.com/generation-transmission/generation/generator-interconnection/interconnection-request-study
2017-05-29
2017-07-04 | ISO Actions | [7 empty] | 2025-02-12: ISO Actions |  |  |  | ISO Actions
2017-09-04 | ISO Actions |  | Send Market Notice to Subscribers | Present overview of the interconnection study process highlighting certain steps | Notify IC all application components received | Notify complete application or necessary clarifying information | Score application based on submittal | Notify Application is Valid or Refund of Deposits | Notify Auction Winners or Refund of Deposits | Schedule Scoping Meeting | Perform Cluster Study | Issue Report to Interconnection Customers | Provide action items and next steps | Coordinate with PTO to confirm posting amounts were received by due date | Evaluate impacts on previously identified network upgrades | Issue Report to Interconnection Customers | Provide action items and next steps | Validate Site Control, Appendix B data and CR Deposit with PTO. Notify Customer if MMA Review needed. | Coordinate with PTO posting amounts were received by due date | Perform Interconnection Facilities Study | Issue draft reports to Interconnection Customers | Issue reports to Interconnection Customers | Provide action items and next steps |  | Send Affidavit Market Notice Score Projects based on Affidavit Information | PTO Tenders Draft GIA Appendices | ISO & PTO negotiate GIA with customer | ISO Provides Final Executable GIA to PTO and Customer
2017-10-09 | ISO Response Timeframe |  | 30 CD prior to application window opening | 60 CD prior to application window opening | Within 5 BD of receipt | Within 5 BD of receipt |  |  | 2025-02-12: Within 5 BDs of receipt; 2025-11-13: Within 10 BDs of results meeting; 2026-06-16: Timely manner |  | Prior to 30 CDs before affidavits due to ISO
2017-11-10 | Revised 4/15/2025
2017-11-23 | Dates - Controlled by CAISO tariff
2017-11-24 | 1Validation officially begins in GRIP 2/12/2025; Cluster study crieteria determination complete 2/11/2025
2017-12-25 | 2Date varies by project
2018-01-15 | CAISO Public
2018-01-19
2018-05-28
2018-07-04
2018-09-03
2018-10-08
2018-11-11
2018-11-22
2018-11-23
2018-12-25
Note on L7: Daune Wilson: The CAISO is aware now that more time will be needed.

## Acronyms
Acronym | Term
BD | Business Day (Per ISO Tariff - Excludes Federal Holidays & day after Thanksgiving)
CD | Calendar Day
COD | Commercial Operation Date
GIA | Generator Interconnection Agreement
IR | Interconnection Request
ISO | California Independent System Operator Corporation
POI | Point of Interconnection
PTO | Participating Transmission Owner